# Annex III

# STATUS OF IMPLEMENTATION OF PRELIMINARY ACTION PLAN

| ACTION | WHOM | WHEN | STATUS |
| --- | --- | --- | --- |
| Agree project leader and national focal points | Meeting | First meeting | Done |
| Identify and agree Real Time Monitoring Centre/terms of reference | UKMO/NCEP | Feb 2000 | Done |
| Identify and agree Data Assembly Centre/terms of reference | NCDC/DWD/UKMO | Feb 2000 | Done |
| Implement agreed SHIP code change | WMO/CBS | 6 months | Not approved by CBS |
| Implement agreed IMMT format change | WMO/JCOMM | April 2000 | Reviewed and agreed at meeting |
| Develop and implement required electronic and paper log changes | KNMI/USA, participants, WMO | 6 months (dep. on 4 and 5) | After meeting |
| Develop, agree, distribute draft project promotional material | P. Taylor, V. Zegowitz, WMO with participants | Mar 2000 | Reviewed at meeting. To be finalized late 2000 |
| Finalize project plan | WMO, Project Leader | Feb 2000 | Done |
| Design/agree ship survey/ship inspection report form | SOC, BOM, NWS, Project Leader, with participants | Mar 2000 | Reviewed at meeting. To be finalized late 2000 |
| Design Metadata catalogue (No. 47) supplement | WMO, DAC, JCOMM | Aug 2000 | Reviewed and agreed at meeting |
| Design ship award, project name and project logo | V. Zegowitz, Project Leader, WMO, participants | July 2000 | Reviewed at meeting. To be finalized late 2000 |
| Undertake preliminary ship identification | Participants | Before next meeting | Done at meeting |
| Convene second project meeting | WMO, Project Leader, DAC to host | Sep/ Oct 2000 | Done |