# VOSCLIM PROJECT ACTION PLAN – SECOND YEAR

| ACTION | WHOM | WHEN | STATUS |
| --- | --- | --- | --- |
| Modify electronic message/logbook software (e.g. TurboWIN) for new IMMT | KNMI, NOAA, JMA, other relevant participants | Jan. 2001 |  |
| Agree data transfer format RTMC-DAC | RTMC, DAC | Dec 2000 |  |
| Provide SOC with algorithms for computation of derived parameters in ship reports | Participants | Dec 2000 |  |
| Modify paper logbooks for new IMMT, including instructions for completion provided by SOC | SOC, relevant participants | Jan 2001 |  |
| Submit revised IMMT to JCOMM-I | WMO | June 2001 |  |
| Finalize project logo, prepare plaque | V. Zegowitz | Nov. 2000 |  |
| Finalize promotional booklet | P. Taylor, V. Zegowitz | Dec. 2000 |  |
| Prepare E, F, S versions of booklet | WMO | Jan. 2001 |  |
| Print booklet | Canada | March 2001 |  |
| Finalize survey report form and instructions, prepare electronic version and circulate for review | Australia | Dec. 2000 |  |
| Prepare electronic form in F, R, S and distribute to participants and DAC | WMO | Feb. 2001 |  |
| Submit standard survey form to JCOMM and eventually distribute to all VOS operators | WMO | June 2001 and after |  |
| Finalize real time monitoring limits | Met Office and SOC | Nov. 2000 |  |
| Finalize ship inspection report form and instructions (paper and electronic) and circulate for review | Australia | Dec. 2000 |  |
| Prepare inspection form in F, S, R and distribute to participants and DAC | WMO | Feb. 2001 |  |
| Decide web site URL and provide to participants | DAC | Nov. 2000 |  |
| Prepare skeleton web site (including simulated data and metadata) and invite review by participants | DAC | Jan 2001 |  |
| Populate web site and initiate operations | DAC | April 2001 |  |
| Design newsletter format and list of contents and circulate to participants | WMO, Project Leader, P. Taylor, S. North | Dec. 2000 |  |
| Prepare first newsletter and transmit to DAC | WMO, participants | July 2001 |  |
| Prepare consolidated list of potential ships, plus line map and circulate to participants, DAC, RTMC | E. Kent | Dec. 2000 |  |
| Begin ship recruitment and submit survey forms to DAC | Participants | Apr 2001 |  |
| Third project meeting (Geneva) | Project Leader, WMO, participants | Nov. 2001 |  |