## Slide 1
5th Meeting of the JCOMM Expert Team on Marine Climatology, 22-25 June 2015
NOAA Satellite and Information Service | National Centers for Environmental Information
Eric Freeman STG, Inc. - NOAA’s National Centers for Environmental Information
Status of the review of WMO No. 558 and 471 - Workplan

## Slide 2
No. | Ref. | Action item | by | Deadline | Status
1 | Teleconf. 20141211/W Action 1 | to provide proposal of a draft outline of Manual (558) and Guide (471) for discussion and feedback at the ‘East’ teleconference. New version should include links to GFCS and non in situ data sources (e.g. reanalysis data) and shared with ETMSS (Neal Moodie). | E. Freeman | 16 Dec. 2014 | Done
2 | Teleconf. 20141211/W Action 2 | to investigate and provide latest Word versions of the marine climatology chapters of WMO No. 558 and 471 | Secr. | 20 Dec. 2014 | Done
3 | Teleconf. 20141211/W Action 3 | to provide an update of new contacts/email addresses of TT-MCDS to Gudrun | Secr. | 19 Dec. 2014 | Done
4 | Teleconf. 20141211/W Action 4 | to provide suggestions of changes/additions to TT- MCDS membership to Gudrun | Teleconf. Participants | 19 Dec. 2014 | Done
5 | Teleconf. 20141211/W Action 5 | to email non-teleconference attendees to confirm interest in remaining within the TT- MCDS | L. Gates | 19 Dec. 2014 | Done
6 | Teleconf. 20141217/E Action 1 | To invite ETSI Chair at ETMC-5 | Secr. | ASAP | Done
7 | Teleconf. 20141217/E Action 2 | to review the draft outline, and propose changes to E. Freeman (cc Secretariat | Teleconf. participants | ASAP | Done
8 | Teleconf. 20141217/E Action 3 | to seek volunteers for providing input for specific sections according to the agreed outline | E. Freeman | Jan. 2015 | Done
9 | Teleconf. 20141217/E Action 4 | to organize teleconference to propose options regarding areas of responsibility, and future role of existing RMs | E. Freeman | Jan. 2015 | Done
10 | Teleconf. 20141217/E Action 5 | Once options are available, to write to existing RMs, and seek their feedback on their future roles in the MCDS | Secr. | Feb. 2015 | Done (as part of ETMC- 5 preparatory documentation)
11 | Teleconf. 20141217/E Action 6 | to formalize the nomination of the new TT-MCDS co- Chairs | E. Freeman | Jan. 2015 | 
12 | Teleconf. 20141217/E Action 7 | to request DMCG Chair to make a proposal to the JCOMM Co-Presidents regarding ETMC Chair | Secr. | ASAP | Done
13 | Teleconf. 20141217/E Action 8 | to approach the UK in order to have a nomination for ETMC in replacement of N. Scott. | Secr. | ASAP | Done

## Slide 3
No. | Ref. | Action item | by | Deadline | Status
14 | Teleconf. 20141217/E Action 9 | to provide the CMOC/China workplan to the ETMC, and then the ETMC to review the workplan and provide further guidance. | S. Woodruff, ETMC | Mar. 2015 | Workplan provided to ETMC-5
15 | Teleconf. 20141217/E Action 10 | to promote discussions between the Hong Kong Observatory and NMDIS regarding whether CMOC/China could contribute to the rescue of marine meteorological data of Hong Kong, China. | H.Y. Mok, S.H. Lin | Feb. 2015 | 
16 | Teleconf. 201401 Action 1 | To send copies of the current versions of the marine climatology chapters of WMO No. 558, and 471 and other existing materials to the specific items leads. | Secretariat | ASAP | Done
17 | Teleconf. 201401 Action 2 | To discuss with the Secretariat, and propose a workplan for the period February to June 2015, and leading to zero drafts by ETMC-5. | Eric Freeman (assisted by Secr.) | 7 Feb. | Done
18 | Teleconf. 201401 Action 3 | to discuss with the Secretariat and refine the current outlines of the marine climatology chapters of WMO No. 558, and 471 so that they also include details and guidance on what needs to be written. | Eric Freeman (assisted by Secr.) | 7 Feb. | Done
19 | n/a | To create templates of the new versions of 558 and 471 on the basis of the new outlines & guidelines, and provided them to Eric Freeman | Secretariat. | 15 Feb. | Done
20 | Teleconf. 201401 Action 4 | To organize another East/West teleconference to discuss methodology for updating the publications. | Eric Freeman | 16 Feb. | Done
21 | Teleconf. 201401 Action 5 | Eric Freeman as overall lead, to coordinate with the identified items/sections leads, provide guidance materials and templates, and seek their input (deadline for providing their input: 30 April 2015) | Eric Freeman (assisted by Secr.) | 20 Feb. 2015 to 15 June 2015 | Done
22 | n/a | To review the current versions of WMO No. 558 and 471 publications, and identify the elements, which will have to be kept and were not yet considered within the new proposed outline (i.e. that may have been forgotten) | Scott Woodruff | 28 Feb. 2015 | 
23 | Teleconf. | Specific items/sections leads | Items/section | 20 Feb. | Initiated

## Slide 4
No. | Ref. | Action item | by | Deadline | Status
23 | Teleconfrerence 201401 Action 6 | Specific items/Section Leads to start coordinating and collecting input from the identified contributors, and to write those items/sections as needed (deadline to provide input 15 April 2015). | leads | 2015 | Done
24 | Teleconf. 201401 Action 7 | Specific text contributors to provide their input to the Items/Sections leads | Text contributors | 15 April 2015 | Done
25 | n/a | Items/Sections leads to provide their input to Eric Freeman | Items/section leads | 30 April 2015 | Done
26 | Teleconf. 201401 Action 5 | To consolidate the marine climatology chapters of WMO No. 558, and 471, in the view to provide a zero draft by ETMC-5. | Eric Freeman, Secretariat | 15 May 2015 | Done
27 | n/a | Draft versions sent to TT- MCDS for their review (deadline 31 May 2015) | Eric Freeman | 15 May 2015 | Done
28 | n/a | TT MCDS to review draft | TT-MCDS | 31 May 2015 | In progress
29 | n/a | To consolidate comments from TT-MCDS | Eric Freeman, Secretariat | 7 June 2015 | 
30 | n/a | ETMC-5 to review draft and agree on future workplan | ETMC-5 | 22-25 June 2015 | 

## Slide 5
NCEI Climate Facebook: http://www.facebook.com/NOAANCEIclimate NCEI Ocean & Geophysics Facebook: http://www.facebook.com/NOAANCEIoceangeo NCEI Climate Twitter (@NOAANCEIclimate): http://www.twitter.com/NOAANCEIclimate
NCEI Ocean & Geophysics Twitter (@NOAANCEIocngeo): http://www.twitter.com/NOAANCEIocngeo
www.ncei.noaa.gov
www.climate.gov
NOAA’s
National Centers for Environmental Information
Contact: Eric.Freeman@noaa.gov