COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (opag)

ON PUBLIC WEATHER SERVICES (pws) expert team on pws in support of

disaster prevention and mitigation (ET/DPM)

Team Deliverables

Status as of 27 January 2011

(Kuala Lumpur, Malaysia, 25-29 May 2009)

| Deliverable 1:Enhancement of WWIS |
| --- |
|  | Actions: | Responsible | Due Date: | Status: |
| 1. | Enhance the appearance and navigation of WWIS | Language hosts and Secretariat |  | Done |
| 2. | Improve coverage |  |  | Done |
| 3. | GIS-enabled feature |  |  | Done |
| 4. | Pushe functionality for WWIS |  |  | Done |
| 5. | Add suggestion box | NOTE: all work kindly completed by HKO |  | Done Deliverable completed |
| Deliverable 2:Register of warning authorities |
|  | Actions: | Responsible | Due Date: | Status: |
| 1. | Write to Members, seeking input | Secretariat | End June 2009 | Done |
| 2. | Provide a sample register entry | Chair | End July 2009 | Done |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  | Deliverable completed |
| Deliverable 3:PWS/TCP seimnar on TC warning formulation and communication |
|  | Actions: | Responsible | Due Date: | Status: |
| 1. | Coordinate with Typhoon Committee and CMA on the organization of a PWS/TC seminar in Nanjing or Hongkong | Chair | End 2009 | Not done, keep under review |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| Deliverable 4:Workshop on PWS in support of DPM in connection with the opening of Meteoworld Pavilion |
|  | Actions: | Responsible | Due Date: | Status: |
| 1. | Clarify the role of the ET in this event | Chen Zhenlin and Secretariat | June 2009 | A workshop on DPM and Service Delivery was organized in May 2010 in Shanghai by SMB/CMA and Secretariat was requested to identify lectureres but this was done at the very last minute before the event and lectureres were from amongst those invited by CMA to the opening of the Pavilion Deliverable completed |
| Deliverable 5 : Update “Guidelines on Integrating Severe Weather Warnings into Disaster Risk Management (PWS-13) |
|  | Actions: | Responsible | Due Date: | Status: |
| 1. | Review PWS-13 and prepare Table of Contents for the new guidelines | Elliott Jacks and Jim Davidson | Sept 2009 | Done |
| 2. | ET to review and work on the content | All | Dec 2009 | Done |
| 3. | Propose techniques for easy reference using electronic media | Elliott Jack and Jim Davidson | Mid-2010 | Can the summary extracts and links be put on WMO blog?(If it exists) |
| 4. | Extract success stories and lessons learnt for posting on PWS website | ET and Secretariat | Mid-2010 | Not done |
| 5. | Publish the new guidelines entitled “ Guidelines on Early Warning Systems and Application of Nowcasting in Warning Operations” | Secretariat | End August 2010 | Guidelines were published in January 2011 and distributed to all NMHSs and PWS teams in hard copy and also posted on PWS website as of 28 January 2011 Deliverable completed |
| Deliverable 6: Update “Guidelines on cross-border exchange of warnings” re-titled “Guidelines on International and Cross-border Collaboration in the Warning Process” |
|  | Actions: | Responsible | Due Date: | Status: |
| 1. | Review PWS-9 and prepare Table of Content | Charles Dupuy and Chen Zhenlin | Sep 2009 | Done |
| 2. | ET review and work on the ontent | All | End 2009 | Done |
| 3. | Use same technique as for PWS-13 | Charles and Zhenlin | Mid-2010 | Can the summary extracts and links be put on WMO blog?(If it exists) |
| 4. | Extract success stories and lessons learnt for posting on the PWS Website | Secretariat |  |  |
| 5. | Publish the guielines | Secretariat | Mid-June 2011 | Guidelines published mid-June 2011 and distributed to all NMHSs and PWS ETs in hard copy and will also be posted on the PWS website Deliverable completed |
| Deliverable 7:List of contact points for sourcing training experts in PWS |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Define an inventory of expertise needed | Vlasta Tutis and Jim Davidson | End 2009 | Done. The list was reviewed by Chair and a more compact version produced |
| 2. | Send letter to PRs with the list of expertise to identify suitable experts | Secretariat | End-March 2010 | This action will be done after all PWS ETs have prepared the list of expertise and will be compiled by ICT/PWS into a single list . CBS requested that PWS OPAG produce a list of competencies required for delivering PWS tasks. This list will be sent in one single letter to PRs with the request for identification of experts for all areas of PWS. Deliverable ready for ET/DPM but pending for other ETs. |