| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (OPAG) ON PUBLIC WEATHER SERVICES (PWS) MEETING OF THE CBS/OPAG-PWS IMPLEMENTATION/COORDINATION TEAM ON PWS (CBS/OPAG-PWS ICT/PWS) AND TT- IMPACT DUBLIN, REPUBLIC OF IRELAND 7-11 DECEMBER 2015 |  | CBS/OPAG-PWS/ICT-PWS & TTI/Doc. 5 (01.12.2015) _______ ENGLISH ONLY |
| --- | --- | --- |

ICT/PWS Team Deliverables and Action sheets for the intersessional period 2014/2016

(Submitted by G. Fleming, Chair, OPAG/PWS)

##### Summary and purpose of document

This document contains the current status of deliverables, as decided by the meeting of the ICT (Melbourne, Australia, 2-6 June 2014).

##### Action Proposed

The Meeting is invited to note the information contained in this document.

__________________

COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMME AREA GROUP ON PUBLIC WEATHER

SERVICES (pws) IMPLEMENTATION/COORDINATION TEAM (CBS/OPAG-PWS ICT/PWS)

ICT/PWS Team Deliverables and Action sheets for the intersessional period 2014/2016 – Updated Dec 2015

|  | Deliverable 1 (TOR a): Noting the publication of the “WMO Strategy for Service Delivery and its Implementation Plan”, ensure that actions relevant to PWS are carried out |
| --- | --- |
|  | Action(s): | Responsible Member(s): | Due Date: | Status 2014: | Status 2016: |
| 1. | Initiating the discussion on the re-alignment of the OPAG with the elements of Service Delivery | All ICT Members | 6 June 2014 | Done | Done |
| 2. | Review and finalize draft TORs to reflect the re-alignment in 1 above | All ICT/PWS Members | Forthcoming ET Meetings |  | To be Done |
| 3. | Present the draft TORs to CBS-16 | OPAG Chair and Secretariat | 2016 |  | To be Done |
|  | Deliverable 2 (TOR c): Establish contact with relevant people in other CBS OPAGs, Commissions, etc., as required |
|  | Action(s): | Responsible Member(s): | Due Date: | Status 2014: | Status 2016: |
| 1. | Contact Chairpersons of OPACE III/IV to explore possible collaboration | Chairperson | June 2012 | Closed | Closed |
| 2. | Contact representatives of CHy to explore possible collaboration | Chairperson | June 2012 | Closed | Closed |
|  | Deliverable 3 (TORs c and d): Facilitate the development of one or a number of “one-stop-shops” for the provision of advice and assistance to the Humanitarian Response Community |
|  | Action(s): | Responsible Member(s): | Due Date: | Status 2014: | Status 2016: |
| 1. | Finalize the Report of the ICTT and circulate as required | Chairperson/TT | End-2012 | Completed | Completed |
| 2. | Prepare an inventory of data and products that are currently available and can be used by Humanitarian Response agencies | Chairperson/TT and WMO Secretariat | End-2012 | Undertaken through the work of the new CBS TT | Completed ?? |
| 3. | Compile a listing of PWS-based resources relevant to point 1 above and communicate this to Secretariat DPFS, to include basic warnings, basic public forecasts, SWIC, WWIS, etc. | WMO Secretariat | End-2012 | Completed | Completed |
| 4. | Investigate the use of the delivery structure of WMO (RSMCs, RCCs, etc.) and the network of National PWS Focal Points as a resource in the context of national operations of Humanitarian Response agencies | Chairperson/TT and WMO Secretariat | End-2012 | PWS will organize the work of interpretation of climate outlooks of major global centre(s) for the use by Humanitarian agencies. The TT will have a meeting in July 2014 and this item will be on the agenda. | Ongoing / underway ?? |
|  | Deliverable 4 (TOR e): Promote the concept of NMHSs as the Single Official Voice at times of severe/high-impact weather |
|  | Action(s): | Responsible Member(s): | Due Date: | Status 2014: | Status 2016: |
| 1. | Make use of the new “WMO Register of Alerting Authorities” to promote and embed the SOV concept | Chairperson/OPAG and WMO Secretariat | Ongoing | Ongoing | Ongoing |
| 2. | Designate an Expert Advisor to assist with the implementation of CAP at NMHSs and to promote registration of Members in the “WMO Register of Alerting Authorities” | ICT Members/ WMO Secretariat | May 2012 | Completed | Completed |
| 3. | Ensure inclusion of this principle in all relevant PWS documents | WMO Secretariat | Ongoing | Ongoing | Ongoing |
|  | Deliverable 5 (TOR f): Detailed feedback from recipients of targetted PWS activities, such as SWFDP, Learning-Through-Doing (LTD) Projects, training, etc. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status 2014: | Status 2016: |
| 1. | Organize the collection and analysis of feedback from training participants and PRs | WMO Secretariat | Ongoing | Ongoing | Ongoing |
| 2. | Collate information flowing back from the feedback mechanisms built into the SWFDP and publish on the PWS Website | Co-Chairperson/OPAG and WMO Secretariat | Ongoing | Ongoing | Ongoing |
| 3. | Organize the reception of bi-annual reports from Members participating in LTD Projects (through Focal Points where possible) and publish on the PWS Website | WMO Secretariat | Ongoing | Completed | Completed |
|  | Deliverable 6 (TOR g): Develop a Competency Framework for PWS Forecasting and Activities. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status 2014: | Status 2016: |
| 1. | Draft a Competency Framework relevant to PWS Forecasters and circulate to all ICT Members, ETR Representatives, etc. | Chairperson | May 2012 | Completed | Completed |
| 2. | Review draft and provide feedback to WMO Secretariat/ Chairperson | All ICT Members | July 2012 | Completed | Completed |
| 3. | Finalize PWS Competency Framework for CBS-Ext.(2014) | WMO Secretariat/ Chairperson | September 2014 | Completed | Completed |
|  | Deliverable 7 (TOR h): Develop materials on the Social and Economic Benefits of NMHSs as decided by the RA VI (Europe) Task Team and the World Bank Project. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status 2014: | Status 2016: |
| 1. | Compile and carry out comparative analysis of the impact of the services provided by NMHSs through socio-economic benefits studies | RA VI TT on socio-economic benefits/ World Bank | Mid- to end-2012 | Ongoing development through the joint WMO/World Bank publication | Completed |
| 2. | Improve methodologies in SEB studies through concurrent field testing and training as part of specific demonstration/pilot projects as well as on-going NMHSs’ investment programmes | World Bank/ WMO Secretariat | End-2012 through 2013 | Ongoing development through the joint WMO/World Bank publication | Completed |
| 3. | Disseminate an authoritative joint WMO-World Bank guidance document | WMO Secreatiat/ World Bank | December 2014 | Will be disseminated upon publication | Completed |
|  | Deliverable 8 (TOR i): Future activities as a follow-up to WENS |
|  | Action(s): | Responsible Member(s): | Due Date: | Status 2014: | Status 2016: |
| 1. | Finalize “Concept Note” developed in Shanghai in November 2011 regarding the follow-up activities to WENS | Dr Tang Xu | End-2012 | Completed | Completed |
| 2. | Implement follow-up activities as defined in the “Concept Note” | Persons as defined in the “Concept Note” | Mid-2013 | Closed | Closed |
| 3. | Prepare publications, etc., as outlined in Section 12 of the WENS Final Report | Shanghai Meteorological Service (SMS) | End-2012 | Closed | Closed |
|  | Deliverable 9 (TOR i): Guidelines for Meteorological Support to Olympic Games. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status 2014: | Status 2016: |
| 1. | Review current draft and bring it up-to-date, include the Beijing and Vancouver Games, then provide to IOC and other sporting organizations as appropriate, and publish on PWS Webpage | Chairperson ET/SPI/ WMO Secretariat | September 2014 | Chair ET/SPII to follow-up | ??? |
|  | Deliverable 10 (TOR j): Strengthen the involvement of the NMHSs’ PWS Focal Points with the work of the OPAG and of the PWS Programme |
|  | Action(s): | Responsible Member(s): | Due Date: | Status 2014: | Status 2016: |
| 1. | Update the list of National PWS Focal Points periodically | WMO Secretariat | Ongoing | Ongoing | Ongoing |
| 2. | Request PRs to appoint National PWS Focal Points in Member countries where none are, as yet, identified | WMO Secretariat | Ongoing | Ongoing | Ongoing |
| 3. | Carry out a regular survey of the work of the National PWS Focal Points in relation to PWS functions and publish the results | WMO Secretariat | Ongoing | Ongoing | Ongoing |
| 4. | Keep National PWS Focal Points fully involved and informed in the activities of the PWS Programme and of the OPAG | WMO Secretariat | Ongoing | Ongoing | Ongoing |
|  | Deliverable 11 (TOR j): Market and promote the availability and use of PWS material among the NMHS/PWS Community |
|  | Action(s): | Responsible Member(s): | Due Date: | Status 2014: | Status 2016: |
| 1. | Periodically review statistics on the hits and usage of PWS pages on the WMO Website | WMO Secretariat | Ongoing | Ongoing | Ongoing |
| 2. | Continue to implement strategies for increasing the ease of access to PWS pages through Google and other search engines | WMO Secretariat | Ongoing | Done | Ongoing |