| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (OPAG) ON PUBLIC WEATHER SERVICES (PWS) MEETING OF THE CBS/OPAG-PWS IMPLEMENTATION/COORDINATION TEAM ON PWS (CBS/OPAG-PWS ICT/PWS) AND TT- IMPACT DUBLIN, REPUBLIC OF IRELAND 7-11 DECEMBER 2015 |  | CBS/OPAG-PWS/ICT-PWS & TTI/Doc. 7 (01.12.2015) _______ ENGLISH ONLY |
| --- | --- | --- |

EXPERT TEAM ON COMMUNICATION, OUTREACH AND PUBLIC EDUCATION ASPECTS OF PWS

DELIVERABLES

(Submitted by J. Gill, Chair, ET/COPE)

##### Summary and purpose of document

This document contains the current status of deliverables, as decided by the meeting of the ET/COPE (Nanjing, China).

##### Action Proposed

The Meeting is invited to note the information contained in this document.

__________________

“MEETING OF THE COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMME AREA GROUP ON PUBLIC WEATHER

SERVICES EXPERT TEAM ON COMMUNICATION, OUTREACH AND PUBLIC EDUCATION ASPECTS OF PWS”

(CBS/OPAG-PWS ET/COPE)

(Nanjing, China 28 October - 1 November 2013)

(Updated as of 20 January 2015)

Team Deliverables

| Deliverable 1: Development of an on-line toolkit to assist NMHSs develop communication strategies for engaging with external stakeholders |
| --- |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Draft material contained in toolkit | Jon Gill | 30 April 2014 (29 Oct. 2014) | Draft developed |
| 2. | Review draft material | All | 30 June 2014 (30 Nov. 2014) |  |
| 3. | ‘Road test’ toolkit among the team as a first step and modify according to results | All | 31 August 2014 (31 January 2015) |  |
| 4. | Launch toolkit | Secretariat | 30 November 2014 (Beginning Q3 2015) |  |
| Deliverable 2: Develop NMHS survey on the usage of different media for PWS delivery |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Prepare draft of survey | Ramon Ooosterkamp | 31 January 2014 | Done |
| 2. | Review draft survey | All | 31 March 2014 | Done |
| 3. | Publish survey and send to NMHSs for completion | Secretariat | 30 April 2014 | Survey sent to NMHSs Deadline extended to mid September allow more returns |
| 4. | Analyse results of survey and prepare report | Ramon Oosterkamp | Q4 2014 | The survey results were analyzed by Ramon who also prepared the report on the outcome of the survey. |
| 5. | Publish the results of the survey | Secretariat | End March 2015 | The report will be developed into a document with graphics and circulated to the PWS Focal Points (who filled in the questionnaire) as well as placed on the PWS Website and shared with the Communication and Public Affairs Programme as well as used in PWS training workshops. |
| Deliverable 3: Develop guidance material for senior NMHS managers on working with senior Government decision-makers, with a focus on communicating the socio-economic benefits of NMHSs |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Request WMO ECWG-SOP to develop guidance material | Ivan Čačić | February 2014 | This deliveralbe has been rolled into the WMO-World Bank book and will not be done by this Team |
| 2. | Request Regional Associations, with the assistance of the Secretariat, to issue guidance material to Members | Ivan Čačić | 15 June 2014 | Closed |
| Deliverable 4; Develop online eLearning training modules on for NMHS staff, including senior managers, on priority areas of PWS communication, including on working with the media, handling difficult interviews and communicating forecast uncertainty |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Develop online eLearning module on media training and handling difficult interviews | Melanie Harrowsmith and Mao Hengqing | March 2015 | Mel is developing the the training materials (guidance sheets and videos)to be delivered by March 2015 |
| 2. | Develop online eLearning module on communicating forecast uncertainty | Melanie Harrowsmith and Mao Hengqing | March 2015 | Mel is developing the the training materials (guidance sheets and videos)to be delivered by March 2015 |
| Deliverable 5: Develop Summary Guide for NMHSs on the use of Twitter during real-time events |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Draft Summary Guide | Melanie Harrowsmith | 30 November 2013 | Draft prepared by Mel |
| 2. | Review Summary Guide | All | 31 December 2013 (20 October 2014) (January 2015) | Reviewed by John Circulated to other ET members for comments |
| 3. | Publish Summary Guide, circulate to WMO Members and publish on WMO PWSP Website | Secretariat | 30 April 2014 |  |
| Deliverable 6: Develop Summary Guide for NMHSs on PWS public education activities, with a focus on schools and youth |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Draft Summary Guide | Panagiotis Giannopoulos and Mao Hengqing | 31 January 2014 | Panos to provide update please and to inform if he can follow up on this deliverable4 an |
| 2. | Review Summary Guide | All | 28 February 2014 |  |
| 3. | Publish Summary Guide, circulate to WMO Members and publish on WMO PWSP Website | Secretariat | 30 June 2014 |  |

_____________