| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (OPAG) ON PUBLIC WEATHER SERVICES (PWS) MEETING OF THE CBS/OPAG-PWS ET/SPII AND ET/IMPACT) BEIJING, CHINA, 30 OCTOBER – 2 NOVEMBER |  | CBS/OPAG-PWS/ET-SPII/ET-IMPACT/Doc. 10.2 23.10.2017) _______ ENGLISH ONLY |
| --- | --- | --- |

REVIEW OF THE DELIVERABLES OF THE EXPERT TEAM ON IMPACT-BASED FORECASTING AND WARNING SERVICES (ET/IMPACT)

(Submitted by WMO Secretariat)

##### Summary and purpose of document

This document contains the current status of deliverables, as approved by CBS-MG-17

##### Action Proposed

The meeting is invited to note information contained in this document and propose changes as necessary

__________

Public Weather Service DELIVERY (PWSD) EXPERT TEAM ON IMPACT-BASED FORECASTING AND WARNING SERVICES (ET/IMPACT)

Team Deliverables and Action sheets for the intersessional period 2016/2018

| Deliverable 1 (TOR a): Building on the WMO Guidelines on Multi-hazard Impact-Based Forecast and Warning Services (WMO No. 1150), develop an implementation strategy which describes next actionable steps and evolution |
| --- |
|  | Action(s): | Responsible Member(s): | Due Date: |
| 1. | Organise a stakeholder workshop to plan and design the implementation plan | ET Chair and Co-Chair Secretariat | Q3 2017 |
| 2. | Publish the guidance material deriving from that workshop at 1. above. | ET Chair and Co-Chair Secretariat | Q4 2017 |
| Deliverable 2 (TOR b): Develop and maintain an expert resource to facilitate activities and projects in the area of Impact-Based Forecasting, including representatives from the social sciences. |
|  | Action(s): | Responsible Member(s): | Due Date: |
| 1. | Compile a listing of available personnel with expertise in areas relevant to Impact-Based Forecasting, with particular emphasis on those with expertise in the collection and evaluation of impact data. | All ET Members Secretariat | Q2 2018 |
| Deliverable 3 (TOR c): Actively promote Impact-Based Forecasting by identifying a network of champions within NMHSs, sharing best practices through symposia, journal papers and communication outlets. |
|  | Action(s): | Responsible Member(s): | Due Date: |
| 1. | Compile a listing of personnel within NMHSs who have expertise and/or interest in the promotion of Impact-Based Forecasting. in areas relevant to Impact-Based Forecasting, with particular emphasis on those with expertise in the collection and evaluation of impact data. | All ET Members | Ongoing |
| 2. | Use all possible opportuities to contribute to relevant scientific meetings, gatherings of NMHS personnel, publications etc to promote and explain the concept of Impact-Based Forecasting | All ET Members | Ongoing |
| Deliverable 4 (TOR d): Provide NMHSs with guidance on how to standardize Impact-Based Forecasting messaging protocols and formats (e.g. colour-coding, language, icons etc.). |
|  | Action(s): | Responsible Member(s): | Due Date: |
| 1. | Draft to be developed for inclusion into the implementation plan | ET Chair | Q3 2017 |
| Deliverable 5 (TOR e): Working with external users and stakeholders, technical commissions, regional associations, relevant OPAGs and Programmes of WMO, establish user requirements for service improvements through science and technological innovation and implementation. |
|  | Action(s): | Responsible Member(s): | Due Date: |
| 1. | Establish initial contacts with relevant TCs, NMHSs and WMO Programmes to make sure requirements are collected and taken into consideration (HiWeather, forecasting) | All ET Members Secretariat | Q4 2017 |
| Deliverable 6 (TOR f): Evolve current methodologies for verification and evaluation to incorporate a focus on Socio-Economic Benefits. |
|  | Action(s): | Responsible Member(s): | Due Date: |
| 1. | Engage with expertise from the Social Science and Economic communities to develop appropriate metrics for the verification and evaluation of Impact-Based Forecast and Warning Services. | All ET Members Secretariat | Q3 2018 |
| Deliverable 7 (TOR g): Identify skills and relevant training needs for NMHSs and external users associated with wider implementation of multi-hazard impact-based forecast and warning services. |
|  | Action(s): | Responsible Member(s): | Due Date: |
| 1. | Review of the PWS Competency Framework to identify gaps in the area of IBF | OPAG Coordinator on Competency Framework Secretariat | Q2 2017 |
| 2. | Identify existing training materials supporting the development of competencies | OPAG Coordinator on Competency Framework Secretariat | Q2 2017 |
| 3. | At the Stakeholder Workshop (see Deliverable 1) review all material on competency and training | OPAG Coordinator on Competency Framework Secretariat | Q3 2017 |