| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (OPAG) ON PUBLIC WEATHER SERVICES (PWS) JOINT MEETING OF THE CBS/OPAG-PWS TT/IMPACT AND ET/DPM SHANGHAI, CHINA, 27 JUNE-1 JULY 2016 |  | CBS/OPAG-PWS/TT-IMPACT & ET-DPM/Doc. 4.2 (13.IV.2013) _______ ENGLISH ONLY |
| --- | --- | --- |

REVIEW OF THE DELIVERABLES FROM THE

2013 MEETING OF THE ET (FLIC EN FLAC, MAURITIUS)

(Submitted by WMO Secretariat)

##### Summary and purpose of document

This document contains the current status of deliverables, as decided by the meeting of the ET/DPM (Flic en Flac, Mauritius, 2013).

##### Action Proposed

The meeting is invited to note information contained in this document.

__________

“MEETING OF THE Commission for Basic Systems Open Programme Area Group on Public

Weather Services (PWS) Expert Team on Meeting User Needs in Reducing the Impact of

Hydrometeorological Hazards (CBS/OPAG-PWS ET/DPM)”

(FLIC EN FLAC, MaURITIUS, 16-20 SEPTEMBER 2013)

(Updated as 18 APRIL 2016)

Team Deliverables

| Deliverable 1: Finalize document enitled, “WMO Guide for National Meteorological and Hydrometeorological Services (NMHSs) on the Provision of Impact-Based Products and Services” |
| --- |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Review outline developed at meeting and identify gaps within existing document entitled “WMO Guide for National Meteorological and Hydrometeorological Services (NMHSs) on the Provision of Impact-Based Products and Services” . Provide assessment to the Chair. | Jennifer and Paul | 31 October 2013 | Done |
| 2. | Based on the Assessment, request team members to write specific sections as needed. This should include devopment of Glossary. Agreement reached on assignments. | Eli | 15 November 2013 | Done |
| 3. | Team members complete writing assignments and sent to Chair. | All Team Members | 15 March 2014 | Done |
| 4. | Chair completes amalgamation of submitted sections into complete draft document and sends to team for final review and comments. | Eli | 15 April 2014 | Done |
| 5. | Team members submit final comments; Chair integrates into final document and submits to Secretariat | All Team Members | 31 May 2014 | Done |
| 6. | Secretariat submits draft document to CBS | Secretariat | 15 June 2014 | Draft approved by CBS in 2014, printed and distributed to Members |
| 7. | Chair organizes periodic conference call to assess progress with document. | All Team Members | 31 December 2013 and approximately quarterly thereafter |  |
| Deliverable 2: Training requirements document for early warning systems and impact-based forecasting |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Based on final document, develop training requirements document to address needs associated with early warning systems and impact-based forecasting. | Vlasta, John, Prem lead with participation from all members | 31 December 2014 | Not done. Need to develop into a new deliverable |
| 2. | Circulate competency document to all team members for information. | Secretariat | 30 November 2013 | Competencies approved by CBS and Cg-17 Done |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |

__________