| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (OPAG) ON PUBLIC WEATHER SERVICES (PWS) MEETING OF THE CBS/OPAG-PWS EXPERT TEAM ON COMMUNICATION, OUTREACH AND PUBLIC EDUCATION ASPECTS OF PWS DELIVERY (ET/COPE) WMO RTC, NANJING, CHINA 28 OCTOBER – 1 NOVEMBER 2013 |  | CBS/OPAG-PWS/ET-COPE/Doc. 4.2 (26.VII.2013) _______ ENGLISH ONLY |
| --- | --- | --- |

REVIEW OF THE DELIVERABLES FROM THE

2011 MEETING OF THE ET (MOMBASA, KENYA)

(Submitted by Ms Haleh Kootval, WMO Secretariat)

##### Summary and purpose of document

This document contains the current status of deliverables, as decided by the meeting of the ET (Mombasa, Kenya, 2011).

##### Action Proposed

The meeting is invited to note information contained in this document.

__________

“MEETING OF THE COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMME AREA GROUP ON PUBLIC WEATHER

SERVICES EXPERT TEAM ON COMMUNICATION, OUTREACH AND PUBLIC EDUCATION ASPECTS OF PWS”

(CBS/OPAG-PWS ET/COPE)

(MOMBASA, KENYA, 5-9 DECEMBER 2011)

Team Deliverables

(Updated 8 July 2013)

| Deliverable 1: Completion of Guidelines on communicating the socio-economic benefits of PWS (Related to ToR) |
| --- |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | All members to gather examples of communicating SEB | Jon Gill and Ivan Čačić | End of January 2012 |  |
| 2. | Prepare draft Guidelines | Jon Gill and Ivan Čačić | End of March 2012 |  |
| 3. | Review of draft by the Expert Team | All Members | End of April 2012 |  |
| 4. | Publish Guidelines and circulate to all NMHSs, Expert Team Members, PWS Focal Points, INTAD members and post to the WMO Website | Haleh Kootval | TBD | No progress |
| Deliverable 2: Completion of Guidelines on the use of social media by NMHSs (Related to ToR) |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Feedback from members on first draft | Jon Gill and Peter Kreft | End of December 2011 |  |
| 2. | Collect examples to be included | Jon Gill and Peter Kreft | End of December 2011 |  |
| 3. | Publish Guidelines and circulate to all NMHSs, Expert Team Members, PWS Focal Points, INTAD members and post to the WMO Website | Haleh Kootval | TBD | Guidelines prepared and published as PWS-24, WMO-No. 1086 |
| Deliverable 3: Develop a list of experts to assist with training and development activities on communication, outreach and public education aspects of PWS delivery (Related to ToR) |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Identify and publish names of experts, following completion of list of competencies of PWS forecasters as provided by all ETs | Haleh Kootval | Upon submission of competencies by ET/SPI | Competencies for all areas of PWS including media and broadcasting have been drafted and reviewed by CBS. The latest draft has been forwarded to ETR office for review by EC Panel of ETR prior to submission to CBS-Ext session for approval. |
| Deliverable 4: Preparation of Summary Guides on: (i) using social media by NMHSs; (ii) communicating socio-economic benefits of PWS (Related to ToR); (iii) conducting PWS outreach activities |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Draft each Summary Guides: Social media Communicating SEB Conducting outreach | Jon Gill and Peter Kreft Jon Gill and Ivan Čačić Joseph Cheruiyot Ego, José Rubiera Torres and Yao Xiuping | End of June 2012 (all Guides) |  |
| 2. | Publish guidelines and circulate to all NMHSs, Expert Team Members, PWS Focal Points, INTAD members and post to the WMO Website | Haleh Kootval | TBD | No progress |
| Deliverable 5: Preparation of Guidelines to assist NMHSs to develop a corporate external communication strategy (Related to ToR) |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Develop outline of Guidelines | Peter Kreft and Jon Gill | August 2012 |  |
| 2. | Prepare first draft of Guidelines | Peter Kreft and Jon Gill (with input from all) | December 2012 |  |
| 3. | Review and finalise | Peter Kreft and Jon Gill (input from all Members) | March 2013 |  |
| 4. | Publish guidelines and circulate to all NMHSs, ET members, PWS Focal Points, INTAD members and post to the WMO website | Haleh Kootval | TBD | No progress |
| Deliverable 6: Develop template for a Memorandum of Understanding (MoU) between an NMHS and a media organisation (Related to ToR) |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Finalise template by adding instructive example MoU | Jon Gill (examples from Yao Xiuping and Ivan Čačić) | March 2012 |  |
| 2. | Send with cover letter to Permanent Representatives, and inform PWS Focal Points, etc. | Haleh Kootval | TBD | The document has been published as WMO-No, 1099, PWS-26, placed on the PWS Websites and all NMHSs informed. |
| Deliverable 7: Determine opportunities for collaboration on communication, outreach and public education aspects of: (i) WIGOS (through the ICG on WIGOS); (ii) climate services (through CCl and the GFCS Office) |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Brief ICG-WIGOS on discussions by Team on project communication | Ivan Čačić | At ICG-WIGOS meeting | Team to be informed |
| 2. | Contribute assistance to WIGOS on project communication as appropriate | Ivan Čačić (with input from all Members) | TBD | Team to be informed |
| 3. | Liaise with GFCS Office on possible collaboration on communication aspects of services | Ivan Čačić and Haleh Kootval | As opportunities arise | PWSP as a lead for the preparation of the Implementation Plan for “The WMO Strategy for Service Delivery” has discussed the User Interface Platform of GFCS |
| 4. | Liaise with Commission for Climatology (CCl) on possible collaboration on communication aspects of services | Ivan Čačić and Haleh Kootval | As opportunities arise | No specific action |
| Deliverable 8: Liaise with other PWS Expert Teams, CBS OPAGs and Regional Associations to identify opportunities for collaboration and sharing of information on areas of mutual interest (Related to ToR) |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Liaise with Regional Associations (RAs) | Ivan Čačić | As opportunities arise | Team to be informed |
| 2. | Liaise with other PWS Expert Teams | Jon Gill | As opportunities arise | Team to be informed |
| 3. | Liaise with CBS OPAGs | Jon Gill | As opportunities arise | Team to be informed |
| Deliverable 9: Develop an on-line survey for NMHSs, to be completed by their PWS Focal Points, that measures the usage of different media for PWS delivery |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Develop survey | Peter Kreft, Yao Xiuping and José Rubiera Torres | June 2012 | Survey developed by Peter |
| 2. | Place survey on-line and check by Team Leads | Haleh Kootval | July 2012 | Survey sent to Secretariat but needs follow up by Peter (or Ramon) to initiate its functionong |
| 3. | Write to NMHSs/PWS Focal Points to complete survey | Haleh Kootval | September 2012 |  |
| 4. | Prepare short report based on survey results and circulate to PWS community | Haleh Kootval | November 2012 | To be discussed by the Team |
| Deliverable 10: Seek opportunities to organise training courses for senior and executive NMHS managers on working with media, e.g., in association with study tours, meetings of senior and executive managers, RA Sessions, etc. |
|  | Action(s): | Lead(s) Responsible: | Due Date: | Status: |
| 1. | Seek opportunities as they arise | Yao Xiuping (CMA study tours) All Members | As opportunities arise | Team to be informed |

_____________