| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (OPAG) ON PUBLIC WEATHER SERVICES (PWS) MEETING OF THE CBS/OPAG-PWS EXPERT TEAM ON SERVICES AND PRODUCTS IMPROVEMENT (ET/SPI) BOHEMIA, NEW YORK, USA 13-17 AUGUST 2012 |  | CBS/OPAG-PWS/ET-SPI/Doc. 4.2 (29.V.2012) _______ ENGLISH ONLY |
| --- | --- | --- |

REVIEW OF THE DELIVERABLES FROM THE 2010

MEETING OF THE ET (HONG KONG, CHINA)

Deliverables Action Sheet Status

(Submitted by the WMO Secretariat)

##### Summary and purpose of document

This document presents the status of the deliverables agreed by the ET/SPI at its meeting in Hong Kong, China, in 2010.

##### Action Proposed

The Meeting is invited to review the document and discuss the follow up actions needed with respect to each deliverable.

_____________

WMO Public Weather Services Expert Team on

Services and Products Improvement (ET/SPI)

Team Deliverables

Hong Kong, China, 24-28 May 2010

| Deliverable 1: Contact selected NMHSs and organizations to request inventory of probabilistic training material for forecasters to deliver and communicate uncertainty and probabilistic weather products to public/media and to request for sharing of such material. |
| --- |
|  | Actions: | Responsible Members: | Deadline: | Status: |
| 1. | ET/SPI members to contribute relevant material from their respective services. | All team members provide input to E. Lai | 15 July 2010 | Shaka: Introductory tranining on the interepretation of Numerical Weather Prediction (NWP) (Kenya). Axel: Five (5) articles on communication of uncertainty. Alasdair: only extremely rudimentary public education info at the moment. Haleh: Material from Kent Johnson of Environment Canada received via Haleh (also available online @ NCAR MetEd COMET). Edwin: 1) Uncertainty communication – issues and good practice. 2.) Weather Risk Management educational programme at Penn State University. Will: UK MO Professional Development programme: Probability Forecasting. (NOTE: Contribution by all of articles and links even though not all from NMHSs) |
| 2. | Obtain publication and guideline material from China. | E. Lai | 15 July 2010 | China will try to provide inputs. |
| 3. | Provide relevant material based on UK MO Professional Development Programme on Probability Forecasting. | W. Lang | 15 July 2010 | Status: Done Can not directly contribute any of the actual material from the Probability Forecasting course itself, due to commercial nature of the course being provided by the Met Office College. A list of course objectives has been provided. |
| 4. | Check EUMETCAL on probabilistic forecast training material. | A. Thomalla | 15 July 2010 | Contacted and still waiting for a reply. EUMETCAL training material will be similar to COMET or use the COMET training courses. |
| 5. | Check with WMO ETR, including COMET. | H. Kootval | 15 July 2010 | Status: Done Material from Kent Johnson of Environment Canada received via Haleh (also available online @ NCAR MetEd COMET). |
| 6. | Collation and summary of results to WMO/PWS. | E. Lai | 15 August 2010 | Finalized by Edwin (see Annex I) |
| 7. | Notify SWFDP of the availability of training resources. | J. Guiney | 1 September 2010 |  |
|  | NOTES: The Team collected probabilistic forecasting training material from several NHMSs including: Bureau of Meteorology (BoM), Deutscher Wetterdienst (DWD), Meteorological Service of Canada (MSC), Hong Kong Observatory (HKO), Kenya Meteorological Department (KMD), the Swedish Meteorological and Hydrological Institute (SMHI) and the UK Met Office. The Team documented relevant training materials from academia and university-government consortiums (UCAR/NCAR) e.g., COMET. EUMETCAL offers no training materials on communicating forecast uncertainty. In late 2010, EUMETNET Science & Technology Advisory Board recommended that training on communicating forecast uncertainty be a high priority. Status: Completed. |

| Deliverable 2: Develop training material based on WMO/TD-No. 1422 “Guidelines on Communicating Forecast Uncertainty”. |
| --- |
|  | Actions: | Responsible Members: | Deadline: | Status: |
| 1. | Identify resource person(s) to develop WMO/TD-No. 1422 into a set of training material. | All to provide input to J. Guiney | 1 July 2010 | Once all contributions received for Del. 1, John can complete the list of potential resource persons to develop set of training materials. (NOTE: John can use the updated collection to identify the experts.) |
| 2. | Set up resource page and links. | J. Guiney / H.Kootval | TBD | Haleh to post the existing collection on the PWS Website as a resource page. |
|  | NOTES: A resource page has been set up on the PWS Website with the information collected from Deliverable 1. The remaining action is to identify resource person(s) to develop the WMO/TD-No. 1422 into a set of training materials. Discussion: Material has been collected but not used for any specific purpose such as training or informing, except on the PWS Website. Team needs to discuss how to apply the material, and identify the next steps, perhaps as the continuation of this deliverable. Status: Incomplete. |
| Deliverable 3: Develop a pilot project following the “Learning-Through-Doing” concept involving no more than three developing countries to improve service delivery process through the following steps (TOR (d)): |
|  | Actions: | Responsible Members: | Deadline: | Status: |
| 1. | Identify NMHSs to participate in the project. | A. Mwadali |  | The new SWFDP project for Lake Victoria, focusing on agriculture and fisheries, as well as the public, will be used as a LTD Project to carry out the steps indicated in this deliverable. Haleh will keep this in view at the first technical planning meeting for the project in Oct. 2010. Status: Done |
| 2. | Identify key user groups of meteorological products and services. | All |  | Public, farmers and fishers |
| 3. | Work with the users to identify their requirements of services and products. | All |  | Ongoing through the project |
| 4. | Implement the agreed process. | All |  | Ongoing through the project implementation and training provided to the project participants |
| 5. | Work with stakeholders/users that have benefited from the services/products to advocate for resource support from governments and development partners to strengthen essential components and infrastructure to continue providing better service. | All | TBD |  |
| 6. | Report progress or results to OPAG/PWS through ET/SPI. | J. Guiney | TBD |  |
|  | NOTES: The SWFDP in Eastern Africa was identified as the Learning-Through-Doing (LTD) Pilot Project. Participating NMHSs: Burundi, Ethiopia, Kenya, Rwanda, Uganda and the United Republic of Tanzania. The SWFDP Steering Group met at WMO Headquarters from 28 February to 2 March 2012 to review the progress of the SWFDP pilots. The Steering Group noted that SWFDP – Eastern Africa is still in the early stages of its implementation. The ET/SPI will pursue opportunity to collaborate on SWFDP – Eastern Africa. Status: Incomplete |
| Deliverable 4: In close collaboration with ET/COPE, develop a supplement to WMO/TD-No. 1422 to describe best practices for user-oriented forecast products. |
|  | Actions: | Responsible Members: | Deadlines: | Status: |
| 1. | Make Swedish study available to the Team. | A. Thomalla | 1 July 2010 | Done |
| 2. | Initiate discussions with ET/COPE on terms of collaboration. | A. Thomalla | 1 July 2010 | Contacted ET/COPE several times per e-mail, so far no reply |
| 3. | Implement the results of these discussions. | All | TBD |  |
|  | NOTES: The Team identified study from Sweden on how to use ensemble predictions for operational flood forecasting as part of the European Union Project PREVIEW. Study conclusion noted that effective training and communication are clearly necessary to overcome the substantial institutional and communicative challenges to applying Ensemble Prediction Systems (EPS). Following the ET/SPI meeting in May 2010, a copy of the study was made available to the Team for further review. The Team still needs to pursue collaboration with ET/COPE to complete this deliverable. Status: Incomplete. |
| Deliverable 5: Provide guidance for NMHSs on developing user surveys and interpreting their results, through providing a collection of existing tried-and-tested surveys. |
|  | Actions: | Responsible Members: | Deadlines: | Status: |
| 1. | Collect examples of existing user surveys and accompanying interpretation. | All | August 2010 | Done |
| 2. | WMO Secretariat to draft letter to be sent to all members, and invite responses to comment on usefulness of the surveys. | H. Kootval | September 2010 | Done Letter has been drafted and will be sent out with samples of questions from all surveys and the summary guide (see below) and will be sent to all PRs, PWS experts and focal points |
| 3. | WMO Secretariat to draft one-page summary of the attributes of a good survey (Lazo paper). | H. Kootval | TBD | Done |
| 4. | Report progress or results to CBS via PWS/OPAG. | H. Kootval | November 2010 |  |
|  | NOTES: Team collected examples of surveys from nine NHMSs which have been posted on the WMO PWS Website at: http://www.wmo.int/pages/prog/amp/pwsp/surveys.htm . The WMO Secretariat/PWS Programme sent a letter, along with samples of questions from all surveys and the summary guide, to all PRs, and NMHS identified PWS experts/focal points. Status: Completed. |
| Deliverable 6: Contribute to the PWS verification and evaluation aspects of SWFDP. |
|  | Actions: | Responsible Members: | Due Date: | Status: |
| 1. | Identify appropriate experts to participate in a planned METEOALARM verification Workshop. | A. Thomalla | Jul. 2010 | Workshop was cancelled due to lack of resources |
| 2. | In liaison with DPFS, provide results of the METEOALARM Workshop to upcoming SWFDP events. | A. Thomalla | Mar. 2011 | See above |
| 3. | Establish status of WWRP/JWGFVR survey on weather warnings verification, and offer to participate as appropriate. | A. Thomalla | Jul. 2010 |  |
|  | NOTES: This deliverable is still under development. Identified activities include: Identify appropriate experts to participate in a METEOALARM verification workshop (originally planned for late 2010); In liaison with DPFS, provide results of the METEOALARM Workshop to upcoming SWFDP events; Establish status of WMO World Weather Research Programme (WWRP) Joint Working Group on Forecast Verification Research (JWGFVR) survey on weather warnings verification, and offer to participate as appropriate. Discussion: objective verification is the responsibility of DPFS. Evaluation of usefulness and overall satisfaction with forecasts is a relevant task for PWS. Status: Incomplete. |
| Deliverable 7: Develop and provide WWIS standard verificiation reports. |
|  | Actions: | Responsible Members: | Due Date: | Status: |
| 1. | DWD to investigate and report to the Team on feasibility of producing multi-country standard WWIS verification reports for all six WMO regions. | A. Thomalla | Dec. 2010 | Verification experts stated that a multi country report would not be very useful as it mixes up the different verification results. In order to improve forercast capabilities of NMHSs, national reports would be the best way forward. We are still in discussions whether national reports could be delivered by DWD. |
|  | NOTES: The Team is in the process of determining the feasibility of producing multi-country standard WWIS verification reports for all six WMO regions. Status: Incomplete |
| Deliverable 8: Contingent on the Deliverable 7, HKO will communicate this information to the WWIS Coordinators. |
|  | Actions: | Responsible Members: | Deadline: | Status: |
| 1. | HKO will communicate feasibility of producing multi-country standard WWIS verification reports for all six WMO regions to the WWIS Coordinators. Status: Incomplete. | E. Lai | TBD |  |
| Deliverable 9: Identify, develop and maintain a list of ET/SPI subject matter experts willing to contribute to PWS training activities. |
|  | Actions: | Responsible Members: | Deadline:: | Status: |
| 1. | Refine the definition of the five skills areas listed above. | All | March 2011 |  |
| 2. | Identify and agree at least one expert willing to contribute to PWS training activities. | All | July 2011 |  |
| 3. | Maintain list above experts. | H. Kootval | July 2011 |  |
|  | NOTES: The Team discussed the wide range of services and products PWS would consider for improvement and noted that it would be difficult to identify experts without first identifying the areas of expertise required. The Team agreed to develop criteria of required expertise based on 4 broad thematic areas: Building partnerships with users of information; Building a communication strategy to improve on the presentation of services and products; Building capacity in computing and data management (networks, systems, new forecasting techniques); and, Developing skills to adapt forecasts to suit various individual user groups. The Team identified five (5) basic skills areas applicable to addressing PWS aspects of the above issues: Verification; Quality Management; Application of probabilistic forecasting for PWS; Service Delivery; and, Emerging Technology/Applications. Discussions: This item has expanded to cover all areas of competencies required by a PWS Forecaster, which was discussed at length at the ICT meeting in April 2012. The Team will need to further refine the definition of these five (5) PWS skill areas, and to identify the key competency areas which will be combined with those already identified by the other Expert Teams and which will be presented to CBS-15 in september. Status: Incomplete. |
| Deliverable 10: Take the lead in the implementation of the “WMO Strategy for Service Delivery” by taking the following initial steps: |
|  | Actions: | Responsible Members: | Deadline: | Status: |
| 1. | Identify the basic models of service delivery across NMHSs. | H. Kootval/W.Lang | August 2010 | Done |
| 2. | Publish guidelines for using QMS to improve service delivery, applicable to each of these models. | W. Lang | June 2011 | Materials gathered by Will but not published as guidelines (see below) |
| 3. | Provide to the Team examples of service delivery metrics used in NMHSs, along with suggestions of how to develop them. | W. Lang | June 2011 | Materials gathered by Will (see below) |
|  | NOTES: PWS Programme hired a consultant to work this issue based on discussions at EC-62, June 2010. The final “WMO Strategy for Service Delivery” was approved by WMO Cg-VXI in June 2011. The Team (Will Lang) drafted the outline of a guideline document addressing items 2 and 3. (see Annex 2). Most of the information from this document has been incorporated into the “WMO Strategy for Service Delivery”. In view of this the Team may consdier this Deliverable complete. The Team may still be required to identify actions to help with implementing of the Implementation Plan for the “WMO Strategy for Service Delivery”, but these could be different actions. Status: Complete |

_____________