| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (OPAG) ON PUBLIC WEATHER SERVICES (PWS) MEETING OF THE CBS/OPAG-PWS IMPLEMENTATION/COORDINATION TEAM ON PWS (CBS/OPAG-PWS ICT/PWS) MELBOURNE, AUSTRALIA, 2-6 JUNE 2014 |  | CBS/OPAG-PWS/ICT-PWS/Doc. 6 (06.V.2014) _______ ENGLISH ONLY |
| --- | --- | --- |

REVIEW OF THE DELIVERABLES FROM THE 2012

MEETING OF THE ICT (MONTREAL, CANADA)

(Submitted by Ms Haleh Kootval, WMO Secretariat)

##### Summary and purpose of document

This document contains the current status of deliverables, as decided by the meeting of the ICT (Montreal, Canada, 23-27 April 2012).

##### Action Proposed

The Meeting is invited to note the information contained in this document.

__________

COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMME AREA GROUP ON PUBLIC WEATHER

SERVICES (pws) IMPLEMENTATION/COORDINATION TEAM (CBS/OPAG-PWS ICT/PWS)

ICT/PWS Team Deliverables and Action sheets for the intersessional period 2012/2014

(Updated as of: 6 May 2014)

| Deliverable 1 (TOR a): When the draft Service Delivery Implementation Plan is complete, study the Plan and ensure that the consequential actions relevant to PWS are carried out. |
| --- |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Circulate the draft of the Service Delivery IP to the ICT Members | WMO Secretariat | When ready | Done |
| 2. | ICT Members to review the draft and provide feedback | All ICT Members | Within one month | Done |
| 3. | Present the reviewed draft to CBS | WMO Secretariat | September 2012 | Done The IP was approved by EC-65 in 2012 and published in March 2014 |
| Deliverable 2 (TOR c): Establish contact with relevant people in other CBS OPAGs, Commissions, etc., as required. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Contact Chairpersons of OPACE III/IV to explore possible collaboration | Chairperson | June 2012 | Gerald to update. |
| 2. | Contact representatives of CHy to explore possible collaboration | Chairperson | June 2012 | Gerald to update |
| Deliverable 3 (TORs c and d): Facilitate the development of one or a number of “one-stop-shops” for the provision of advice and assistance to the Humanitarian Response Community. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Finalize the Report of the ICTT and circulate as required | Chairperson/ICTT | End-2012 | CBS-15 (2012) established a CBS (DPFS-PWS) Task Team on the provision of operational assistance to the Humaintarian organizations. The work of the previous TT has been rolled into this CBS TT. |
| 2. | Prepare an inventory of data and products that are currently available and can be used by Humanitarian Response agencies | Chairperson/ICTT and WMO Secretariat | End-2012 | Undertaken through the work of the new CBS TT |
| 3. | Compile a listing of PWS-based resources relevant to point 1 above and communicate this to Secretariat DPFS, to include basic warnings, basic public forecasts, SWIC, WWIS, etc. | WMO Secretariat | End-2012 | DPFS is aware of the PWS-based resources |
| 4. | Investigate the use of the delivery structure of WMO (RSMCs, RCCs, etc.) and the network of Nnational Focal Points as a resource in the context of national operations of Humanitarian Response agencies | Chairperson/ICTT and WMO Secretariat | End-2012 | PWS will organize in the work of the interpreting the climate outlooks of major global centre(s) for the use by Humanitariamn agencies. The TT will have a (real or virtual) meeting and this item will be on the agenda. Jennifer to update the ICT. |
| Deliverable 4 (TOR e): Promote the concept of NMHSs as the Single Official Voice at times of severe/high-impact weather. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Make use of the new “WMO Register of Alerting Authorities” to promote and embed the SOV concept | Chairperson/OPAG and WMO Secretariat | Ongoing | So far 133 editors have been designated following Secretariat letters to PRs |
| 2. | Designate an Expert Advisor to assist with the implementation of CAP at NMHSs and to promote registration of Members in the “WMO Register of Alerting Authorities” | ICT Members/ WMO Secretariat | May 2012 | An expert has been designated and a number of CAP jump-start workshops organized for developing countries |
| 3. | Ensure inclusion of this principle in all relevant PWS documents | WMO Secretariat | Ongoing | Being done |
| Deliverable 5 (TOR f): Detailed feedback from recipients of targetted PWS activities, such as SWFDP, Learning-Through-Doing (LTD) Projects, training, etc. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Organize the collection and analysis of feedback from training participants and PRs. | WMO Secretariat | Ongoing | Feedback is usually collected after training events are completed |
| 2. | Collate information flowing back from the feedback mechanisms built into the SWFDP and publish on the PWS Website | Co-Chairperson/OPAG and WMO Secretariat | Ongoing | Feedback is collected from participating countries in SWFDP and will be placed on the PWS website |
| 3. | Organize the reception of bi-annual reports from Members participating in LTD Projects (through Focal Points where possible) and publish on the PWS Website | WMO Secretariat | Ongoing | The one major LTD project has been implemented in Madagascar. A report will be published on the website. |
| Deliverable 6 (TOR g): Develop a Competency Framework for PWS Forecasting and Activities. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Draft a Competency Framework relevant to PWS Forecasters and circulate to all ICT Members, ETR Representatives, etc. | Chairperson | May 2012 | Done |
| 2. | Review draft and provide feedback to WMO Secretariat/ Chairperson | All ICT Members | July 2012 | Done |
| 3. | Finalize PWS Competency Framework for CBS-XV | WMO Secretariat/ Chairperson | August 2012 | Done. The draft Framework will be tabled at CBS-Ext.(14) for approval |
| Deliverable 7 (TOR h): Develop materials on the Social and Economic Benefits of NMHSs as decided by the RA VI (Europe) Task Team and the World Bank Project. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Compile and carry out comparative analysis of the impact of the services provided by NMHSs through socio-economic benefits studies. | RA VI TT on socio-economic benefits/ World Bank | Mid- to end-2012 | This work has been expanded into a major project of writing a joint WMO-World Bank book on the assessing benefits of socio-economic benefits of met/hydro services |
| 2. | Improve methodologies in SEB studies through concurrent field testing and training as part of specific demonstration/pilot projects as well as on-going NMHSs’ investment programmes | World Bank/ WMO Secretariat | End-2012 through 2013 | The book is being written and is envisioned to be ready for publication by end of 2014 |
| 3. | Disseminate through an authoritative joint WMO-World Bank guidance document | WMO Secreatiat/ World Bank | Dependent on 2 above | Will be disseminated upon publication |
| 4. | Contribute to CBS-TECO on benefit-cost studies insofar as possible | All ICT Members | September 2012 | A special session on economic benefits was held during CBS-15 TECO |
| Deliverable 8 (TOR i): Future activities as a follow-up to WENS. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Finalize “Concept Note” developed in Shanghai in November 2011 regarding the follow-up activities to WENS | Dr Tang Xu | End-2012 | A final report on WENS was published in August 2013 |
| 2. | Implement follow-up activities as defined in the “Concept Note” | Persons as defined in the “Concept Note” | Mid-2013 | A major outcome of WENS was the integration of the PWS Platform with the Shanghai Emergency Warning Centre |
| 3. | Prepare publications, etc., as outlined in Section 12 of the WENS Final Report | Shanghai Meteorological Service (SMS) | End-2012 | The new arrangements for the Shanghai PWS Platform and the Shanghai Emergency Warning Centre are published in the World Bank book “ Weather and Climate Resilience” |
| Deliverable 9 (TOR i): Guidelines for Meteorological Support to Olympic Games. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Review current draft and bring it up-to-date, include the Beijing and Vancouver Games, then provide to IOC and other sporting organizations as appropriate, and publish on PWS Webpage | Chairperson ET/SPI/ WMO Secretariat | September 2012 | While more material has been collected under this activity, no decision has been reached on its publication. Chair ET/SPII to advise |
| Deliverable 10 (TOR j): Strengthen the involvement of the NMHSs’ PWS Focal Points with the work of the OPAG and of the PWS Programme. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Update the list of National PWS Focal Points periodically | WMO Secretariat | Ongoing | Done |
| 2. | Request PRs to appoint National PWS Focal Points in Member countries where none are, as yet, identified | WMO Secretariat | Ongoing | Done |
| 3. | Carry out a regular survey of the work of the National PWS Focal Points in relation to PWS functions and publish the results | WMO Secretariat | Ongoing | While Focal Points do report on request on their activities, no survey has been done on this item |
| 4. | Keep National PWS Focal Points fully involved and informed in the activities of the PWS Programme and of the OPAG | WMO Secretariat | Ongoing | Done through quarterly reports |
| Deliverable 11 (TOR j): Market and promote the availability and use of PWS material among the NMHS/PWS Community. |
|  | Action(s): | Responsible Member(s): | Due Date: | Status: |
| 1. | Periodically review statistics on the hits and usage of PWS pages on the WMO Website | WMO Secretariat | Ongoing | Done. 140 hits on the PWS Guidelines up to July 2013 |
| 2. | Continue to implement strategies for increasing the ease of access to PWS pages through Google and other search engines | WMO Secretariat | Ongoing | PWS material is easily accessible now through Google search |

__________