| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (OPAG) ON PUBLIC WEATHER SERVICES (PWS) MEETING OF THE CBS/OPAG-PWS IMPLEMENTATION / COORDINATION TEAM ON PWS MONTREAL, CANADA, 23-27 APRIL 2012 |  | CBS/OPAG-PWS/ICT-PWS/Doc. 6/REV. 2 (28.II.2012) _______ ENGLISH ONLY |
| --- | --- | --- |

Deliverables from the 2010 Meeting of the ICT

(Shanghai, China)

(Submitted by the WMO Secretariat)

##### Summary and purpose of document

This document presents the list of deliverables resulting from the meeting of the ICT in Shanghai in 2010 and the status of the deliverables as of date.

##### Action Proposed

The Meeting is invited to consider the list and the actions taken so far and decide on how to proceed with the deliverables still pending.  To guide the Meeting, the CBS Operating Plan is also included in the document.

Annexes:	I.	ICT/PWS Team Deliverables 2010-2012

- Template for ICT Deliverables 2012-2014

- CBS Operating Plan

- Public Weather Services National Focal Points Database (see external link)

- Weather, Climate, and Water Monitoring and Prediction for the Olympic Games – A Guideline for Public Weather Services Olympic Game Support, Draft, Version 3 (see external link)

- Quarterly Brief for WMO Public Weather Services (PWS) Focal Points 
(1 October – 31 December 2011); PWS-QB 01-2012

Reference(s):	A.	Fourteenth Session of the Commission for Basic Systems (CBS-XIV, Dubrovnik, Croatia, 2009)

B.	Meeting of the Commission for Basic Systems Open Programme Area Group on Public Weather Services (PWS) Implementation / Coordination Team on PWS (Shanghai, China, September 2010)

_____________

COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (opag)

ON PUBLIC WEATHER SERVICES (pws) IMPLEMENTATION COORDINATION TEAM (ICT/PWS)

Team Deliverables 2010/2012

(Shanghai, China, 20-24 September 2010)

| Deliverable 1: Conduct a joint seminar with the IABM on the optimum use of new media for the effective communication of weather information. |
| --- |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Organise and conduct a seminar. Publish results and outcomes. | Chair/OPAG | Prior to CBS 2012; TBD | Chair/OPAG to provide update |
| 2. | GF to raise this at the IABM meeting in October; research options for location, timing, meeting support, etc. | Chair/OPAG |  | Chair/OPAG to provide update |
| Deliverable 2: Prepare a synthesis document on the various components of the PWS Programme activities related to the Shanghai 2010 World EXPO with a distillation of lessons learned for future reference. |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Synthesis document to be prepared following the discussions at the ICT-2010 meeting. | WENS coordinators and the Secretariat | November 2010 | Dr Tang-Xu to provide update (ref: Final Review Meeting WENS, Shanghai Nov 2011) |
| 2. | Lessons learnt from WENS. | WENS coordinators | 2011 | Workshop was organized for 4 countries in Shanghai in Nov 2011. Other actions proposed in the report of the Final Review Meeting. |
| Deliverable 3: Strengthen the involvement of the NMHS PWS Focal Points with the work of the OPAG and the PWS Programme. |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Update the list of National Focal Points periodically. | Secretariat | Ongoing | To date 86 Members have nominated FPs. (Annex III) |
| 2. | Request PRs to appoint FPs in Member countries where none are as yet identified. | Secretariat | Ongoing | Letters of reminder have been sent out |
| 3. | Carry out a regular survey of FPs and publish results. | Secretariat | Ongoing |  |
| 4. | Keep FPs fully involved and informed in the activities of the PWSP and the OPAG. | Secretariat | Ongoing | Quarterly reports on activities of PWSP are sent to FPs and feedback is requested. |
| Deliverable 4: Detailed feedback from recepients of targetted PWS activities, such as SWFDP, Learning-through-Doing projects, training etc |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Organise the collection and analysis of feedback from training participants and PRs. | Secretariat | Ongoing | This is done following training workshops. Some responses collected but not all participants respond. |
| 2. | Collate information flowing back from the feedback mechanisms built into the SWFDP, and publish on PWS Website. | Co-Chair/OPAG; Secretariat | Ongoing | Feedbck is collated from SWFDP quarterly reports. The full sets of feeback reports to date will be published on the PWS Website by end March 2012. |
| 3. | Organise the reception of bi-annual reports from Members participating in LTD projects (through FPs where possible) and publish on PWS Website. | Secretariat | Ongoing | This is being done. |
| Deliverable 5: List of PWS experts who can contribute to training etc |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Develop and refine the existing drafts of PWS Expertise and Competencies relevant to the work areas of the various Expert Teams. | ET Chairs | ET/DPM, ET/COPE End October 2010 ET/SPI End-year 2010 | Work completed by ET/DPM and ET/COPE. To be done by ET/SPI.. |
| 2. | Collate and harmonise the three lists of PWS Expertise and Competencies areas into one over-arching list, adding in any other PWS Expertise areas that are identified in feedback from training courses, etc. | Secretariat | End-February 2011 | The full set of competency/expertis areas will be developed into a document in consultation with the ETR Ofice and will be presented to CBS for for approval. |
| 3. | Based on the list developed in 2 above, write to PRs and ask them to nominate Experts who would be available and willing to participate in PWS work. | Secretariat | April 2011 | To be done |
| 4. | Develop a list of Experts with appropriate expertise and competencies as defined through the processes above. |  |  | To be done |
| Deliverable 6: Collate existing studies and research in the area of socio-economic applications of weather, water and climate services. Publish Guidance on the operational use of economic assessment techniques. |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Carry out a literature review of existing relevant studies and prepare a synthesis document which summarises the published knowledge. | Option A – Hire a consultant (Talk to John Z). Option B – work with SERA/WWRP group (Brian Mills) Secretariat | TBD | This work is being done by PWSP and the Regional Office for Europe as a joint WMO-World Bank Project. (Annex IV) |
| 2. | Publish Guidance document based on the above work. | Secretariat / Chair/OPAG | CBS 2012 | Joint WMO-WB guidance material will be published upon completion of the work as indicated in Annex IV. |
| Deliverable 7: Guidelines for Meteorological support to Olympic Games. |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Review draft and scope the remaining work. | Michel Jean | Completed |  |
| 2. | Update and complete the existing draft document. | Michel Jean | End-2010 | Mr Jean to update the meeting (Annex V, draft V.3.1)) |
| 3. | Publish the completed document on the PWS webpages and provide print copies to the IOC and other sporting organisations, NMHSs and other relevant bodies. | Secretariat | April 2011 | Not done |
| Deliverable 8: Market and promote availability and use of PWS material among NMHS/PWS community. |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Prepare an electronic “brochure” with links to the various PWS Websites and circulate to the PRs and FPs. | Secretariat | April 2011 | To clarify if “variousn PWS websites” refers to eg, SWIC, WWIS etc? Note: improvements in PWS Webiste and request the ICT to comment on the new format and content |
| 2. | Encourage the FPs to promote and spread knowledge about the “How-To” guides within their own NMHSs. | Secretariat | Ongoing | Being done in quarterly letters to FPs |
| 3. | Investigate availability of statistics of hits on and usage of PWS pages on WMO Website. | Secretariat | End-2010 | The meeting will be informed of the progress made |
| 4. | Discuss, with WMO Webmaster, strategies for increasing the ease of access to PWS pages through Google and other search engines. Action Column: Action taken: Tips, as provided by WMO Webmaster, for easy search by Google include: -Keeping the site regularly updated; -Purchasing an additional and parallel domain name for example www.wmopws.org to automatically point to wmo.int/pws; -using downloadable content on the site; -Keeping the site as clean as possible with html and coding; -Creating a site map and linking to it from every page; -Using backlinks. (Links pointing to your website from another website e.g. external partners websites) -joining forums as a great way to achieve links to your website; -Outbound links: On every page place one outbound link to a high ranking site; and, -Using ezine ads (or newsletters). Creating an ezine is probably the most beneficial step to take, to increasing web presence. | Secretariat | End-2010 | Done: Please see the 'Action' column |
| 5. | Make available WMO-No. 834 in soft copy on the PWS pages of the WMO Website. | Secretariat | End-2010 | The meeting will be informed of the progress made |
| Deliverable 9: Promote the concept of NMHSs as the Single Official Voice at times of severe weather. |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Investigate the use of WMD and any other relevant occasions to promote this concept. | Chair/OPAG and Secretariat | February 2010 |  |
| 2. | Make use of the new WMO Register of Alerting Authorities to promote and embed the SOV concept. | Chair/OPAG and Secretariat | Ongoing | Letters to PRs inviting them to nominate editors of the Register contained this. |
| 3. | Ensure inclusion of this principle in all relevant PWS documents. | Secretariat | Ongoing | Being done |
| 4. | Use the potential partnership with Google to highlight this in all future relevant WMO documentation. | Chair/OPAG and Secretariat | Ongoing | This subject is not active at the moment but will be kept in view. |
| Deliverable 10: Facilitate the development of one or a number of "one-stop-shops" for the provision of meteorological advice and assistance to the Humanitarian Response community. |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Prepare an inventory of data and products that are currently available and can be used by Humanitarian Agencies. | Chair/ICTT and Secretariat | October 2010 | Mr Jean to update |
| 2. | Compile a listing of PWS-based resources relevant to point 1 above and communicate this to Secretariat DPFS, to include basic warnings, basic public forecasts, SWIC, WWIS, etc. | Secretariat | End-2010 | Depends on action 1, above. |
| 3. | Investigate the use of the delivery structure of WMO (RSMCs, RCCs, etc.) and the network of (national) PWS Focal Points as a resource in the context of national operations of Humanitarian Agencies. | Chair/ICTT and Secretariat | TBD | PWS FPs are being trained to interact with the disaster management and civil protection organizations. Other humanitarian agencies? |
| Deliverable 11: Investigate the opportunites to develop and assist with improving media and communication skills for PRs and other senior NMHS managers. |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Investigate with DRA and CPA the possibilities of using Regional Association meetings to deliver training courses aimed at senior NMHS personnel. | Secretariat | February 2010 | ICT will be informed at the Session |
| 2. | Explore options with IABM for resourcing the training of communications in this context. | Chair/OPAG and Secretariat | October 2010 | To follow action 1. |
| Delivery 12: Delivery of the report of the ICT. |
| 1 | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Finalise report of the ICT meeting in September 2010; circulate to all members and publish on the PWS Website. | Chair/OPAG and Secretariat | End-October 2010 |  |

_____________

COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (opag)

ON PUBLIC WEATHER SERVICES (pws) IMPLEMENTATION / COORDINATION TEAM (ICT/PWS)

Team Deliverables

(Montreal, Canada, 23-27 April 2012)

| Deliverable 1: |
| --- |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| Deliverable 2: |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| Deliverable 3: |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |

| Deliverable 4: |
| --- |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| Deliverable 5: |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| Deliverable 6: |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| Deliverable 7: |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |

| Deliverable 8: |
| --- |
|  | Actions: | Responsible Member(s):: | Due Date: | Status: |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| Deliverable 9: |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| Deliverable 10: |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |

_____________

| CBS Operating Plan – PWS Section |
| --- |
| No. | Activities | Deliverables | Progr. | ER(s) | KO | KPI | KPT 2015 | Cost by year [in K CHF] | Total Costs | Source of Funding |
|  |  |  |  |  |  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |
| 1 | Establish an Expert Team on Service Delivery with particular focus on implementation of the WMO Strategy for Service Delivery | Publish Guidance on the means to improve Service Delivery by NMHSs; develop strategies to optimize the implementation of this Guidance | PWS | 1 | 1.1 | 1.1 |  | 60 | 60 | 60 | 60 | 360 | In-kind (expert resources) |
| 2 | Complete the WENS project through reviewing progress made and sharing the results | Hold a series of training workshops to identify best practice flowing from the WENS project and to apply this elsewhere | PWS | 1 | 1.1 | 1.1 |  | 24 | 24 | 24 | 24 | 96 | In-kind (expert resources) |
| 3 | Improve the communications and networking capabilities of top-level NMHS managers | Workshops and training courses aimed at senior NMHS personnel | PWS | 1 | 1.1 | 1.1 |  | 42 | 42 | 42 | 42 | 168 | In-kind (expert resources) |
| 4 | Strengthen NMHS engagement with user communities through Learning Through Doing projects and in particular through the SWFDP | Engagement with SWFDP; development with stand-alone PWS Learning Through Doing projects (in conjunction with Regional Associations) | PWS | 1 | 1.1 | 1.1 |  | 48 | 48 | 48 | 48 | 192 | In-kind (expert resources) |
| 5 | Strengthen the cooperation with the Climate community, in particular through contributing to the development of a Global Framework for Climate Services | Joint meetings and workshops organized with CCl other members of the Climate community. Extension of Guidance, especially in the areas of presentation, communication and user engagement, to the climate time-scales | PWS | 1 | 1.1 | 1.1 |  | 51 | 51 | 51 | 51 | 204 | In-kind (expert resources) |

| 6 | Build the knowledge on quantifiable assessment, and deepen appreciation of the social and economic impact of meteorological services | Promote studies and research in the area of socio-economic applications of weather, water and climate services. Publish Guidance on the operational use of economic assessment techniques | PWS | 1, 7 | 1.1 | 1.1 |  | 42 | 42 | 42 | 42 | 168 | In-kind (expert resources) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7 | Examine how new and emerging means of using communications technology, including social media, might be best utilized for the delivery of meteorological services | Conduct workshops and develop Guidance material on the optimum exploitation of new and emerging uses of Information and Communications Technologies | PWS | 1 | 1.1 | 1.1 |  | 30 | 30 | 30 | 30 | 120 | In-kind (expert resources) |
| 8 | Consider the technological challenges and roadblocks in delivering weather information to users seamlessly | Provide advice and guidance on optimum formats and compatibilities (GIS etc) for the integration of weather information with widely-used decision support systems. | PWS | 1 | 1.1 | 1.1 |  | 18 | 18 | 18 | 18 | 72 | In-kind (expert resources) |
| 9 | Continuing to build the Public Education function of NMHSs, especially in regard to impacts of severe weather | Provision of guidance material on recommended advice to be issued in conjunction with Severe Weather Warnings. Workshops and training activities | PWS | 1 | 1.1 | 1.1 |  | 42 | 42 | 42 | 42 | 168 | In-kind (expert resources) |
| 10 | Work with the Humanitarian Response community to develop a better understanding of their particular needs, and develop products and services to meet those needs | Facilitate the development of one or a number of "one-stop-shops" for the provision of meteorological advice and assistance to the Humanitarian Response community | DRR | 2 | 2.1 | 2.1 |  | 42 | 42 | 42 | 42 | 168 | In-kind (expert resources) |

| 11 | Develop methodologies for the proper assessment and documentation of meteorological hazards | Make studies of, and develop prototype guidelines for monitoring, archiving, mapping and statistical analysis methodologies for a selection of meteorological hazards | DRR | 2 | 2.1 | 2.1 |  | 42 | 42 | 42 | 42 | 168 | In-kind (expert resources) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | 393 | 393 | 393 | 393 | 1,884 |  |

_____________

WMO Socio-Economic Benefits-Related Activities

- The following activities have been undertaken and working mechanisms established in the area of socio-economic benefit assessment and studies,  including:

- A technical document entitled, “National Meteorological and Hydrological Services, Their Partners and User Communities – Follow up to the Madrid Action Plan – for Improved Social and Economic Benefits of Weather, Climate and Water Services” (PWS-19, WMO/TD No. 1510), was prepared and published in 2010;

- Regional Association (RA) VI (Europe) set up a “Task Team on Socio-Economic Benefits” (TT/SEB) of Hydrometeorological Service as part of the RA VI “Working Group on Service Delivery and Partnership” (WG/SDP).  The main task of the Team is to summarize existing experience in the Region and prepare a set of guidelines and practical recommendations on methods and procedures for conducting SEB studies.  The Task Team is expected to publish the result of its work by the end of 2012. The work of the Task Team is coordinated by the WMO Regional Office for Europe (ROE); and,

- The ROE and PWSP organized the “WMO RA VI Conference on Social and Economic Benefits of Weather, Climate and Water Services” (Lucerne, Switzerland, 3-4 October 2011), as part of WMO activities to implement the MAP, and to respond to the RA VI Strategic Plan for the “Enhancement of Meteorological and Hydrological Services”. The Conference, which was organized jointly with the Federal Office of Meteorology and Climatology of Switzerland (MeteoSwiss), provided a forum for discussing the results of recent studies carried out by different RA VI Members and reviewing related methodologies.  The proceedings of the Conference will be published by March 2012.

- As a next step in the follow up to MAP, and as continuation of the Task Team’s work, WMO and the World Bank plan to collaborate on a project to expand the set of guidelines on the socio-economic benefit analysis and assessment methodologies for use by NMHSs in all Regions.  The project which will be jointly managed in the Secretariat by PWSP and ROE, will draw on many existing studies and examples in this area and aim to provide guidance and affordable approaches to NMHSs on preparing systematic and robust assessment of the benefits of their services to various user communities.

- A separate but related project concerns the design and implementation of a number of pilot projects to test such methodologies in each of the WMO Regions.  It is planned to initiate this activity with a demonstration project to be carried out with a suitable Meteorological Service in RA VI.  The demonstration and pilot projects will be complemented by a training element aimed at assisting the NMHSs concerned with the choice and application of the suitable methodology for the relevant user sector.

- It should be noted that there are close linkages and synergies between the WMO activities initiated as a response to MAP, which highlight the societal benefits of the products and services of NMHSs, and the priority areas of the Organization such as the Global Framework on Climate Services (GFCS),. In addition, it is recalled that Cg-XVI approved the WMO Strategy for Service Delivery and stressed that implementation of the Strategy should be used by NMHSs to improve their relationships with users, thus increasing the relevance of NMHSs products and services to decision-making processes and ultimately demonstrating the role and position of NMHSs in the national socio-economic development processes of Members.

_____________