COMMISSION FOR BASIC SYSTEMS (CBS) OPEN PROGRAMME AREA GROUP (opag)

ON PUBLIC WEATHER SERVICES (pws) expert team on communication,

outreach and public education aspects of pws (ET/cope)

Team Deliverables

Status as of 28 January 2011

(Havana, Cuba, 16-20 November 2009)

| Deliverable 1: Prepare one page summary guides based on existing Guidelines on communication, nedia relations, education and outreach |
| --- |
|  | Actions: | Responsible | Due Date: | Status: |
| 1. | Drafts of “How-to-Guides” to be provided to the Chair | All | 31 Dec 2009 | Done |
| 2. | Chair to provide Guides to Secretariat | J. Gill | 31 January | Done |
| 3. | Translation and dispatch by the Secretariat | Secretariat | 31 March | Done |
| 4. |  |  |  |  |
| 5. |  |  | End August 2010 | Deiverable completed |
| Deliverable 2:Prepare Guidelines on communicating the social and economic benefits and impacts of PWS |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Draft to be prepared by Chair and circulate to the Team for comments | J. Gill | 31 May 2010 | Not done |
| 2. | Comments by the Team | All |  | Not done |
| 3. | Publication in time for CBS-Ext.(10) in November | Secreatariat | October 2010 | Pending on draft being finalized |
| 4. |  |  |  |  |
| 5. |  |  |  | Deliverable not completed |
| Deliverable 3:Prepare information on the use by NMHSs of emerging technologies and social media |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Draft to be prepared by Chair and circulated to the Team for comments | J. Gill | 30 June 2010 | Not done |
| 2. | Comments by the Team | All |  | Not done |
| 3. | Publication | Secretariat | 30 September 2010 | Pending on draft being finalized |
| 4. |  |  |  |  |
| 5. |  |  |  | Deliverable not completed |
| Deliverable 4:List of available experts in communications, outreach and public education to be developed |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | List of experts to be called upon to assist PWS traning activities to be developed | All | 31 Dec 2010 | Not done |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  | NOTE:CBS (2010) requested that PWS OPAG develop a list of competencies required for delivering PWS. ET/DPM has compiled such a list and once ET/COPE and ET/SPI do the same, a single list will be compiled for all PWS areas and sent to PRs to identify experts for each area. |
| Deliverable 5: Prepare a “job deiscription” of skills/personal qualities needed to work with public/user sectors |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Draft to be developed | P. Kreft | 31 Dec 2009 | Done |
| 2. |  |  |  |  |
| 5. |  |  | Nove. 2010 | Completed Deliverable completed |

_____________