Progress on implementation of WIGOS and WIS in RA II

CHEN Yongqing
Chairperson of WG-WIGOS/WIS

- Background

Cg-XVI decided to implement WIGOS and approved the Resolution 50 (Cg-XVI) – Implementation of the WMO Integrated Global Observing Systems, by which the regional associations were requested: (1) to develop their regional WIGOS implementation plans; (2) to coordinate WIGOS implementation activities with the WMO Information System in their operating plans and work programmes; and (3) to promote capacity-building and outreach activities to assist Members in the implementation of WIGOS.

Therefore, the development of a Regional WIGOS Implementation Plan for the Regional Association II (R-WIP-II) was initiated at the meeting of the Working Group on WMO Integrated Observing System and WMO Information System (WG-IOS/WIS) held in November/December， 2011 in Seoul, Republic of Korea. In the meeting, three Key services priorities in RA II that need improved observations were outlined, which are Disaster Risk Reduction supported by Nowcasting,  Climate Services (for GFCS) and Aviation Meteorology Services. Four Tasks were also suggested to be established to enhance the key services listed above. The RA II Management Group (Doha, Qatar, February/March 2012) endorsed the proposal by the WG-IOS/WIS for the establishment of the Task Team on R-WIP (TT/R-WIP). A Task Team meeting was held in Jakarta, Indonesia in September，2012 during the CBS-15 session. Task Team members, Mr Chen Yongqing(China), Dr.L.S. Lee (Hong Kong, China), Dr Jae-Gwang Won (Republic of Korea), Mr Naohisa Koide (Japan), and Dr Songkran Agsorn (Thailand) , and Dr Atkinson Roger, Mr Kuniyuki Shida from WMO Secretariat attended the meeting.  Dr L R Meena (India) attended the meeting as an observer. The meeting discussed the main projects which were suggested to be established to cover most of the areas of implementation of WIGOS in RA II, and the mechanism of the WIGOS working group. Task Team further developed and finalized the R-WIP-II which was prepared to be submitted to RA II-15 session for approval.

The Regional WIGOS Implementation Plan for the Region RA II (R-WIP-II) was submitted to the RA II-15 session which was held in Qatar from Dec.13 to 18, 2012, and was adopted as the Resolution 4.4/1 (RA II-15). RA II-15 session strengthened that the implementation of R-WIP-II be supported by all the Members of the Region, and be guided, supervised and monitored by the Management Group of RA II, with periodic reports from appropriate subsidiary bodies in charge of WIGOS.R-WIP-II will be further revised to accommodate new projects which would be submitted by Members and authorized the president to approve the revised TT/R-WIP during the intersessional period in consultation with the Management Group.

The fifteenth session of RA II reviewed the draft RA II Regional WIS Implementation Plan, and agreed that fully implementing WIS in the Region was an essential step toward the efficient implementation of WIGOS, GFCS and other priority areas. The fifteenth session of RA II agreed that the virtual WIS Implementation Project Office should continue to refine the plan, and encouraged WIS centers, in particular GISCs to provide resource toward completing the implementation plan.

EG-WIS co-coordinators drafted a work plan on developing RA-II WIS Implementation Plan in April, 2013, and a Task Team for reorganizing and finalizing the RA-II WIS-IP (the coordinator of EG-WIS) was established in May, 2013. Members came from GISCs and GISC candidates, which included Beijing, Jeddah, New Delhi, Seoul, Tehran, Tokyo and DCPC/NC Bangkok, Doha and Karachi. Based on the previous progress and outcome of developing of RAII-WIS-IP during 2011-2012,  the Task Team reorganize and compile the draft of RAII-WIS-IP in September,2013.The draft RAII-WIS-IP was completed and distributed to the WIS focal points of RA II members and the WMO secretariat for comments in September, 2013.The draft was reviewed by the Chairperson of WG-WIGOS/WIS of RA-II October, 2013.The final version of RA-II WIS-IP was submitted to the President of RA-II for approval November, 2013 and was approved by the President of RA-II in December, 2013.

- Brief introduction of R-WIP-II

R-WIP-II has used the standard template provided by WIGOS Project Office.

R-WIP-II is laid out in seven chapters that identify and describe the various activity areas to be addressed within this Region, which is corresponding to the following ten areas described in IGOS Framework Implementation Plan v.1.0,

(a)	Management of WIGOS implementation;

(b)	Collaboration with WMO and co-sponsored observing systems;

(c)	Design, planning and optimized evolution;

(d)	Integrated Observing System operation and maintenance;

(e)	Integrated Quality Management;

(f)	Standardization, system interoperability and data compatibility;

(g)	The WIGOS Operational Information Resource;

(h)	Data and metadata management, delivery and archival;

(i)	Capacity development;

(j)	Communication and outreach.

The key implementation activities that are required for the Regional WIGOS implementation within the timeframe from 2012 to 2015 are included in annex I, which identifies deliverables, timelines, responsibilities, costs and risks, and whether the activity requires regional and/or national implementation.

Most of the activities in the annex I will be implemented through seven RAII WIGOS projects under the initiative of key regional players. EG-WIGOS has responsibility for tracking execution of these activities and projects.

List of RA II WIGOS Projects

| No. | Project title | Key regional players |
| --- | --- | --- |
| I | Monitor and review the Implementation of EGOS- IP in RA II | China; Hong Kong, China |
| II | Standard and best practise Portal, including technical documents with necessary details in English from all RA II Members | Republic of Korea |
| III.1 | Observing systems integration for supporting disaster risk reduction - Integration of Surface-based Remote Sensing Data in the East Asia | China, Japan, Republic of Korea |
| III.2 | Observing systems integration for supporting disaster risk reduction - Capacity Building in Radar Techniques in the Southeast Asia | ASEAN (Thailand, Malaysia) |
| IV | Enhance the Availability and Quality Management Support for NMHSs in Surface, Climate and Upper-air Observations | Japan |
| V | Developing a Sand and Dust Storm Warning Advisory and Assessment System (SDS-WAS) in Asia Node | China, Japan, Republic of Korea |
| VI | Develop Support for NMHSs in Satellite Data, Products and Training | Japan, Republic of Korea |

RA II will be responsible for the implementation of WIGOS in the Region through its EG-WIGOS with the support from the Regional Office for Asia and the South-West Pacific and the WMO Office for West Asia.

(a)	RA II, through its Management Group, will monitor, review, guide and support the overall implementation of WIGOS in the Region, and update the Implementation Plan if and when necessary;

(b)	RA II, through the Coordinator of EG-WIGOS, will report to the ICG-WIGOS and the WIGOS Project Office on the progress in implementation of WIGOS in the Region;

(c)	The president of RA II will report to the sessions of RA II on WIGOS implementation.

- Brief introduction of R2-WIs-Ip

The RA II WIS Implementation Plan was developed on the basis of WMO regulatory material, in particular the WMO Technical Regulation, Volume I, Section A3 (WMO No. 49), the Manual on the WIS (WMO No. 1060) and the Guide to the WIS (WMO No.1061) to ensure a harmonized and synchronous implementation by all regional members as well as inter-regional project.

In particular, the R2-WIS-IP includes:

•	Functional Architecture;

•	Status of WIS in RA II;

•	Technical compliance Specification of the GISC, DCPC and NC;

•	Governance Procedures for implement of WIS centres;

•	Execution and timelines.

The purpose of the R2-WIS-IP is to provide:

a)	RA II members with overall technical guidance, assistance and support for the implementation of the WIS, which would coordinate the implementation of WIS including further improvement of GTS and optimize and achieve maximum compliance. In view of the foregoing, the RA II WIS Implementation Plan is aimed at assisting RA II Members to implement WIS functionality in their identified centres and become effective WIS users in a timely and harmonized manner. Therefore, it concentrates on the access to WIS by NMHSs as National Centres (NC). The requirements and procedures for other types of centres, like Global Information System Centres (GISC) or Data Production or Collection Centres (DCPC), are described in detail in the Manual on WIS (WMO No. 1060) and WIS Demonstration Guidelines, and therefore only briefly mentioned in this paper. However, in implementing and supporting WIS in RA II and monitoring its performance, GISCs will have to take on certain responsibilities described below. Information about the implementation of GISCs and DCPCs by RA II Members and international organizations is included in the Plan monitoring process in order to provide “one stop shop” with regard to the overall WIS implementation in RA II.

b)	Strategic approaches to effective and efficient capacity building highlight some key issues on technical implementation and designation requirement for WIS centres. The Plan also provides practical guidance and a step-by-step approach towards the WIS implementation by Members in their National Centres. A primary task for the NMHSs is ensuring compliance with the WIS requirements established by the WMO regulatory material WMO Technical Regulations, Volume I (WNO No. 49) and its Annex VII, Manual on WIS (WMO No. 1060). In order to facilitate the implementation process, the GISCs should establish close contacts with the NCs in their areas of responsibility and act as “help desks” when assistance is needed. In particular, GISCs should plan for providing assistance to build the capacity of the NCs to handle the required discovery metadata.

- Progress on implementation of R-WIP-II

The implementation of R-WIP-II will mainly rely on seven RAII WIGOS projects listed in the R-WIP-II. Six of seven project contact persons provided progress information to the co-coordinator of EG-WIGOS. No response has been received from both two contact persons of project III.2 by now, though several e-mails have been sent to them by the coordinator. The progress for each project is listed as bellow.

4.1  Project No. I- Monitor and review the Implementation of EGOS- IP in RA II

Accomplishments

The responsibility for the project was assigned to CMA Meteorological Observation Centre (MOC) by CMA. A small expert team was established by MOC. Then, a work plan was drafted, the project framework was designed, and the budget plan for the project was also developed by the expert team and has been submitted to CMA for approval.

Next steps

Responding to aim of the project,  a portal is plan to be developed by the expert team to share the progress of EGOS-IP Implementation of RA II Members, and gaps will be Identified  and prioritize actions will be listed in EGOS-IP through reviewing the progress of EGOS-IP in RA II as next steps.

4.2  Project No. II- Standard and Best Practice Portal, including Technical Documents with Necessary Details in English from all RA II Members

Accomplishments

KMA’s domestic project for the standardization of meteorological observation has been ended its 1st phase. More than 3,500 domestic sites from 27 agencies were linked as one system. 70% of the data from more than 3,500 sites are collected for the utilization in real time by 2013.

Next steps

A Portal will be developed to share the experience about standards and best practices for enhanced observational data/products utilization. KMA’s standardization project will be the first sample of experience with more than 80% data collection rate. A form will be developed to collect the standard and best practices from other members within RA II.

4.3  Project No. III.1 - Observing systems integration for supporting disaster risk reduction - Integration of Surface-based Remote Sensing Data in the East Asia

Accomplishments

Real-time exchange of radar CAPPI products and automated weather station data between Japan and Korea

The Japan Meteorological Agency (JMA) and the Korea Meteorological Administration (KMA) mutually agree to exchange radar CAPPI products and automated weather station (AWS) data in near real-time basis to use for operational purpose.  In near real-time, KMA obtains radar 2km-height pseudo CAPPI products of JMA’s weather radar stations as well as hourly data of JMA’s surface observation network, called the Automated Meteorological Data Acquisition System (AMeDAS).  JMA also obtains radar CAPPI products of  KMA’s weather radar stations as well as most data of KMA’s AWSs in near real-time.

JMA is developing a quality control system to remove noise from radar CAPPI products. JMA plans to generate a two-dimensional grid product of analyzed precipitation using quality-controlled radar CAPPI data and in-situ precipitation data of AWSs in 2014 and investigate its impact on NWP in near future.

Non-real-time exchange of raw data of Doppler radar between Japan and Korea

JMA and KMA also agree to exchange raw data of their Doppler radars in off-line basis to investigate the benefit of operational use of these data in individual NWP system.

In March 2013, JMA obtained a set of raw data for 5 days of July 2012 on the case of heavy rainfall over Kyushu Island from KMA.  It was revealed that a quality control was necessary to use such raw data in a meso-scale NWP system.

Dissemination of ground-based stations of the Global Navigation Satellite Systems on WIS/GTS

Data of ground-based stations of the Global Navigation Satellite Systems (GNSSs) are disseminated on WIS/GTS in real time so that these data are available for operational use. Table 1 shows a list of such ground-based GNSS stations in China, Korea and Japan.   At the Joint Meeting of the 12th Asia Pacific Satellite Data Exchange Meeting and 24th North America / Europe Data Exchange Meeting (22-25 October 2012, Met Office, Exeter, U.K.), CMA, JMA and KMA were requested to provide data of more ground-based GNSS stations on GTS.  It is, therefore, expected to increase the data amount in the future.

In Korea, there are several agencies that are operating several GNSS stations for their own purpose, and they have recently agreed on sharing the data for mutual benefits. More than 160 stations would be available and could be utilized by KMA in the future.  In order to exchange those data internationally, KMA will continue the domestic discussion.

Table 1 List of Ground-based GNSS Stations whose data are disseminated on WIS/GTS

| Country | Station Name | Longitude (East) | Latitude (North) |
| --- | --- | --- | --- |
| China | Wuhan(WUHN-MET) | 114.36 | 30.53 |
|  | Lhasa(LHAZ-MET) | 91.10 | 29.66 |
| Japan | Usuda(USUD-GOP) | 138.36 | 36.13 |
| Korea | Daejeon(DAEJ-MET) | 127.37 | 36.40 |

Since the technical method to assimilate zenith tropospheric delay data or total precipitable water vapor data of ground-based GNSS stations is established, the data on WIS/GTS can be used for operational purpose.

Next steps

Progress of the JMA-KMA projects will be monitored, and the benefit and difficulties of regional exchange of surface-based remote sensing observations will be identified. More members are also encouraged to exchange surface-based remote sensing observations. In this regard, each contact person will seek possibility to establish a pilot project to realize such data exchange as a trial in coming two years.

In the last year of this RA II WIGOS Project, i.e. 2016, a feasible and optimal draft design of integrated surface-based remote sensing observations will be developed based on lessons learnt from these projects.

4.4  Project No. III.2 -Observing systems integration for supporting disaster risk reduction - Capacity Building in Radar Techniques in the Southeast Asia

Information is not available now..

4.5 Project No. IV - RA II WIGOS Project to Enhance the Availability and Quality Management Support for NMHSs in Surface, Climate and Upper-air Observations

Accomplishments

WMO/JMA Survey on meteorological instruments, calibration and training in RA II was implemented, and a consolidated report, which describes status on calibration instruments for surface-based observations in RA II was completed and made available on the WMO Regional Instrument Centre (RIC) Tsukuba website.

The results of the RSMC quality monitoring have been shared among members concerned.

Experts from RIC Tsukuba visited the Bangladesh Meteorological Department (BMD) and provided practical on-the-job training on meteorological instrument aiming at establishing the operational calibration system using meteorological standards (barometer and thermometer) donated in the framework of JICA technical cooperation project.

Next steps

A survey on quality management of meteorological observation by NMHS in RA II will be carried out.

A workshop focusing on sharing and transferring skills of observation quality management is also on the schedul.

4.6 Project No. V – Developing a Sand and Dust Storm Warning Advisory and Assessment System (SDS-WAS) in Asia Node

Accomplishments

The SDS-WAS

The dust forecast model has been continuously operated throughout the year on a daily basis. The model consists of a numerical weather prediction model incorporating on-line parameterizations of all the major phases of the atmospheric dust cycle. It generates forecasts of the following minimum set of variables:

- Dust load (kg·m-2)

- Dust concentration at the surface (μg·m-3)

- Dust optical depth at 550 nm (-)

- 3-hour accumulated dry and wet deposition (kg·m-2)

Forecasts cover the period from the starting forecast time (00:00 and/or 12:00 UTC) up to a forecast time of at least 72 hours, with an output frequency of at least 3 hours. The horizontal resolution is 0.5x0.5 degrees.

A portal for dust forecast products developed

A web portal to display forecast products as well as additional information was developed and operational. The web site is http://eng.weather.gov.cn/dust/.

Next steps

Dust forecast model products verification will be carried out in the near future.

WMO EC-65 (2013) approved the Commission for Basic Systems (CBS) recommendations made at its fifteenth session in 2012 that mandatory functions and criteria for the designation of an RSMC with activity specialization in Atmospheric Sand and Dust storm Forecasts (RSMC-ASDF) are to be incorporated in the Manual on the Global Data-processing and Forecasting System (GDPFS) (WMO-No. 485). EC-65 also approved the recommendation to formally designate the SDS-WAS regional node in Barcelona, Spain, as the RSMC-ADSF for the region consisting of. Northern Africa (north of Equator), the Middle East and Europe. The sixteenth session of Commission for Atmospheric Science  (CAS-16) welcomed the initiative to designate another SDS-WAS regional node in Beijing, China, as the RSMC-ADSF for the region consisting of Asia and the Central Pacific. CMA will apply for WMO Regional Specialized Meteorological Centers with Activity Specialization on atmospheric Sand Dust Forecasts.

4.7 Project No. VI - RA II WIGOS Project to Develop Support for NMHSs in Satellite Data, Products and Training

Accomplishments

Issuance of newsletters to RA II Members.

Quarterly newsletters have been issued to share recent satellite-related information on topics such as imagery data, products and training.  The newsletters listed below, which were issued to RA II Members in November, December and March, contained brief reports on relevant relevant meetings, products progress report, news on successful launch of KOMPSAT-5 satellite and information on preparations for the Himawari-8/9 satellite series of JMA and Geo-KOMPSAT-2A of KMA.

- Vol. 4/No. 1, April 2013

- Vol. 4/No. 2, June 2013

- Vol. 4/No. 3, November 2013

- Vol. 4/No. 4, December 2013

- Vol. 5/No. 1, March 2014

All the past issues can be seen in the following WMO webpage:

https://www.wmo.int/pages/prog/sat/ra2pilotproject-intro_en.php

4th Asia/Oceania Meteorological Satellite Users’ Conference

The fourth Asia-Oceania Meteorological Satellite Users’ Conference (AOMSUC) was held in Melbourne, Australia from 9-11 October 2013.  The conference was hosted and sponsored by the Australian Bureau of Meteorology (AuBOM) and was co-sponsored by the China Meteorological Administration (CMA), the Japan Meteorological Agency (JMA), the Korean Meteorological Administration (KMA), and the World Meteorological Organization (WMO).  The conference was preceded by a two day training event at the AuBOM training facilities and brought together participants from Region II and V.

Next steps

The new generation geostationary meteorological satellites such as Himawari-8, FY-4A, GEO-KOMPSAT-2A are planning to be operated from next year, 2015. Therefore, supportive activities for preparation of satellite data users to the new generation of geostationary meteorological satellites will be carried out. The Project will support for preparation of the NMHSs in RA II especially developing countries including LDCs to the new satellites. It will involve user training, guidance to upgrade processing software and hardware, information and tools.

Issuance of quarterly newsletters will also continue. CMA will host the fifth Asia/Oceania Meteorological Satellite Users’ Conference (AOMSUC ) in Shanghai in October of 2014. More details about the conference have not decided yet and will be provided in due course.If a training event is planned at the time of the meeting like AOMSUC-3 and AOMSUC-4, the RA II WIGOS Project to develop support for NMHSs in satellite data, products and training will cooperate in it with CMA. Meanwhile, the third meeting of the Coordinating Group of the RA II WIGOS Project will be held in 2015 on the occasion of the sixth AOMSUC in Japan. A training event using new satellite data will be also planned by JMA on the occasion of the Conference.

- Progress on implementation of R2-WIs-Ip

5.1 Current status of RA II telecommunication

The Regional Meteorological Telecommunication Network (RMTN) is the communications and data management component that operates through the collection and distribution of the information critical to NMHSs operations. RMTN is also accompanied by very developed data management practices. These facilitate the orderly and efficient overall management of meteorological data and products of the World Weather Watch programme.

In the operation of WIS, the communication links enable the routine collection and dissemination of time-critical and operation-critical data and products. These, and the timely delivery of all other data and products, are the lifeblood of WMO activities. Communications links of WIS will be a core network connecting GISCs, (the GTS Main Telecommunication Network (MTN)) plus a number of communication networks connecting the various GISCs to DCPCs and NCs within each GISC’s area of responsibility. This Area Meteorological Data Networks (AMDCN) will include technologies such as the GTS, Internet and satellite broadcast systems.

The number of circuits at each speed as of Sep 2012  is given below.

It shows more than 90% circuits are running at speed ≥ 64 kbps. For effective implementation of WIS, it was recommended in the Meeting of WMO RA II Working Group on WMO Integrated Observing System and WMO Information System (WIGOS/WIS), Seoul, Republic of Korea, 30 November - 7 December 2011 that the circuits may be upgraded to 512 kbps because new sets of data like satellite and NWP products have significant contribution for operation critical activities and 512 kbps would help timely delivery of various sets of data to end users in minimal time.

However, at present only 26% of total circuits operate at speed ≥ 512 kbps. Therefore there is a need to push NMHSs for upgrade of circuits.

Moreover, certain RMTN circuits like Karachi - Tashkent and Kabul -Tashkent are not logical networks and there is no chance of their revival in coming time. It would be appropriate to remind concerned NMHSs to either revive the linkages, implement Internet links or opt for their deletion from the network list. Pictorial representation of RMTN for RA II is appended above.

5.2 WIS centres in RA II

The procedures for the designation of the GISC, DCPC and NC of WIS centres are provided in the Manual on WIS (WMO No. 1060), Part II. After successful completion of the designation procedure, the centre is included in Appendix B to the Manual, Approved WMO Information System Centres. The current status of the designation of centres by Members is available on: http://www.wmo.int/pages/prog/www/WIS/centres/index_en.php.

5.2.1 GISCs

At present, there are the seven GISCs (Beijing, Tokyo, Seoul) in RA-II which are endorsed and are operational. The other three GISCs in RA II have been successfully audited by CBS are New Delhi, Tehran and Jeddah. GISC Moscow also services RA II. All are expected to become fully operational in near future.

| Member | Centre type | GTS Function | Principal GISC | Const. Body | Endorsement CBS | Congress/EC |
| --- | --- | --- | --- | --- | --- | --- |
| China | GISC | RTH | Beijing | CBS | Endorsed by CBS | 2011/6/1 |
| India | GISC | RTH | New Delhi | CBS | Endorsed by CBS | 2011/6/1 |
| Iran, Islamic Republic of | GISC | RTH | Tehran | CBS | Endorsed by CBS | 2011/6/1 |
| Japan | GISC | RTH | Tokyo | CBS | Endorsed by CBS | 2011/6/1 |
| Republic of Korea | GISC | NMC | Seoul | CBS | Endorsed by CBS | 2011/6/1 |
| Saudi Arabia | GISC | RTH | Jeddah | CBS | Endorsed by CBS | 2011/6/1 |
| Russian Federation | GISC | WMC | Moscow | CBS | Endorsed by CBS | 2011/6/1 |

A list of links to the GISCs in RA II as follows:

• GISC Beijing : http://wisportal.cma.gov.cn/wis/

• GISC Tokyo : http://www.wis-jma.go.jp/

• GISC Seoul : http://gisc.kma.go.kr/

• GISC New Delhi : http://wis.imd.gov.in

• GISC Tehran : http://gisc.irimo.ir/

• GISC Jeddah : http://84.235.53.3:8080/MessirWIS

• GISC Moscow : http://portal.gisc-msk.wis.mecom.ru/

5.2.2 DCPCs

The table below provides information on the DCPCs that have been designated by the RA II Members with their planned functions.

| Member | Centre type | GTS Function | Principal GISC | WIMMS | Const. Body | Endorsement CBS | Congress/EC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| China | DCPC | RTH | Beijing |  | CBS | Endorsed by CBS | 2011/6/1 |
| China | DCPC | RSMC-Geographical (NMC) | Beijing |  | CBS | Endorsed by CBS | 2011/6/1 |
| China | DCPC | RSMC-Activity-ATM (NMC) | Beijing |  | CBS | Endorsed by CBS | 2011/6/1 |
| China | DCPC | RCC (Beijing NCC, - RA II) | Beijing |  | CCl | Endorsed by CBS | 2011/6/1 |
| China | DCPC | NSMC | Beijing |  | CBS | Endorsed by CBS | 2011/6/1 |
| Hong Kong, China | DCPC | WWIS | Beijing | Beijing | CBS | Endorsed by CBS | 2011/6/1 |
| India | DCPC | RTH | New Delhi | Tokyo | CBS | Under review by ET-GDDP | 2011/6/1 |
| India | DCPC | RSMC-Activity-TC | New Delhi | Tokyo | CBS | Under review by ET-GDDP | 2011/6/1 |
| Iran, Islamic Republic of | DCPC | RTH | Tehran |  | CBS | Under review by ET-GDDP | 2011/6/1 |
| Japan | DCPC | WDC-GHG | Tokyo |  | CAS | Endorsed by CBS | 2011/6/1 |
| Japan | DCPC | Satellite Centre | Tokyo |  | CBS | Endorsed by CBS | 2011/6/1 |
| Japan | DCPC | RTH | Tokyo |  | CBS | Endorsed by CBS | 2011/6/1 |
| Japan | DCPC | RSMC-Geographical | Tokyo |  | CBS | Endorsed by CBS | 2011/6/1 |
| Japan | DCPC | RSMC-Activity-TC | Tokyo |  | CBS | Endorsed by CBS | 2011/6/1 |
| Japan | DCPC | RSMC-Activity-ATM | Tokyo |  | CBS | Endorsed by CBS | 2011/6/1 |
| Japan | DCPC | RCC (Tokyo NCC, RA II) | Tokyo |  | CCl | Endorsed by CBS | 2011/6/1 |
| Japan | DCPC | GPC/LRF | Tokyo |  | CBS | Endorsed by CBS | 2011/6/1 |
| Qatar | DCPC | Marine Meteorological Centre (MMC) | Jeddah | Tokyo | JCOMM | Under review by ET-GDDP |  |
| Republic of Korea | DCPC | WAMIS | Seoul |  | CAgM | Endorsed by CBS | 2011/6/1 |
| Republic of Korea | DCPC | NMSC | Seoul |  | CBS | Endorsed by CBS | 2011/6/1 |
| Republic of Korea | DCPC | GPC / LC-LRFMME | Seoul |  | CBS | Endorsed by CBS | 2011/6/1 |
| Russian Federation | DCPC | RTH/RSMC-Geographical (Novosibirsk) | Moscow |  | CBS | Not submitted to ET-GDDP | 2011/6/1 |
| Russian Federation | DCPC | RTH/RSMC-Geographical (Khabarovsk) | Moscow |  | CBS | Not submitted to ET-GDDP | 2011/6/1 |
| Saudi Arabia | DCPC | RTH | Jeddah |  | CBS | Under review by ET-GDDP | 2011/6/1 |
| Saudi Arabia | DCPC | RSMC-Geographical (Jeddah) | Jeddah |  | CBS | Not submitted to ET-GDDP |  |
| Saudi Arabia | DCPC | RDMEC (Drought) | Jeddah |  | CHy | Not submitted to ET-GDDP |  |
| Thailand | DCPC | RTH | Tokyo |  | CBS | Not submitted to ET-GDDP |  |
| Uzbekistan | DCPC | RTH | Seoul |  | CBS | Not submitted to ET-GDDP |  |

5.2.3 NCs

The table below presents the current status of the designation of NCs in RA II with their principal GISC, WIMMS and Focal Point, which is based on the Resolution 5 of the Fifteenth session of Regional Association II (ASIA), Qatar Doha, December 2012.

| Member | NC | GTS Function | Principal GISC | WIMMS | Focal Point |
| --- | --- | --- | --- | --- | --- |
| Afghanistan | Kabul | NMC | Tehran |  | Mr Mohammad Nasim Muradi Afghan Meteorological Authority Khwaga Rawash P.O. Box 425 KABUL the Interim Administration of Afghanistan Tel: 0093 (0) 700180705 Email: raket_nasim@yahoo.com |
| Bahrain | Manama | NMC | Jeddah | Beijing | Mr Nader Ahmed Abdulla Bahrain Meteorological Service P.O. Box 586 BAHRAIN Bahrain Tel: +973 17321163 Fax: +973 17320630 Email: nader@caa.gov.bh |
| Bangladesh | Dhaka | NMC | New Delhi | Tokyo | Mr Abdul Matin Bangladesh Meteorological Department Meteorological Complex Abhawa Bhaban Agargaon 1207 DHAKA Bangladesh Tel: +880-2-8116634 Fax: +880-2-9103908 Email: info@bmd.gov.bd ; amatin2004@yahoo.com |
| Bhutan | Thimphu | NMC | New Delhi |  | Mr Chimi Wangda Council for Renewable Natural Resources Research, Ministry of Economic Affairs, Thimphu Bhutan Tel: 02 323703 Fax: 02 324 999 Email: chimwangs10@gmail.com |
| Cambodia | Phnom Penh | NMC | Tokyo | Tokyo | Ms Peou Phalla Department of Meteorology 364, Preah Monivong Blvd, Chamkarmon PHNOM PENH Cambodia Tel: +855-16-616-927 Fax: +855-23-213-490 Email: phallapeou1@gmail.com |
| China | Beijing | NMC | Beijing |  | Ms Xiang Li China Meteorological Administration 46 Zhongguancun Nandajie BEIJING 100081 China Tel: +86 10 6840 6275 Fax: +86 10 6218 6241 Email: lixiang@cma.gov.cn |
| Democratic People's Republic of Korea | Pyŏngyang | NMC | TBD |  | State Hydrometeorological Administration |
| Hong Kong, China | Hong Kong | NMC | Beijing | Beijing | Mr Lee Lap Shun Hong Kong Observatory 134A Nathan Road KOWLOON Hong Kong, China Tel: +852 2926 8416 Fax: +852 2311 9448 Email: lslee@hko.gov.hk |
| India | New Delhi | NMC | New Delhi | Tokyo | Dr L. R. Meena India Meteorological Department Mausam Bhavan Lodi Road NEW DELHI 110003 India Tel: 011 -2461 6051 Fax: 011- 2469 9216 Mobile: 91 - 98105 56531 Email: lr.meena@imd.gov.in; lrmeena@gmail.com |
| Iran, Islamic Republic of | Tehran | NMC | Tehran | Tokyo | Ms Farah Mohammadi Islamic Republic of Iran Meteorological Organization P.O. Box 13185-461 TEHRAN the Islamic Republic of Iran Tel: +989123842058 Fax: +982166070077 Mobile: +989123842058 Email: farahmohamadi@yahoo.com |
| Iraq | Baghdad | NMC | Tehran |  | Mr Sallam S. Nadhim Iraqi Meteorological Organization Almansoor P.O. Box 6078 BAGHDAD Iraq Tel: +964 7702766948 Email: sallam_omery@yahoo.com |
| Japan | Tokyo | NMC | Tokyo |  | Mr Kenji Tsunoda Japan Meteorological Agency Otemachi 1-3-4, Chiyoda-ku TOKYO 100-8122 Japan Tel: +81-3 3212 8341 Fax: +81-3 3211 8404 Email: tsunoda@met.kishou.go.jp |
| Kazakhstan | Almaty | NMC | Moscow |  | B. S RAPIKOV Kazhydromet ul. Orynbor 11/1 010000 Astana Kazakhstan Tel: +8-7172-798399 Email: rapikov_b@kazhydromet.kz; rapikov@gmail.com |
| Kuwait | Kuwait City | NMC | Jeddah | Tokyo | Mr Fahad Alnajadah Department of Meteorology P.O. Box 17 SAFAT 13001 Kuwait Tel: +965 66808266 Fax: +965 24727326 Email: f.alnajadah@met.gov.kw |
| Kyrgyzstan | Bishkek | NMC | Moscow |  | Dr Tatiana KOZHEVNIKOVA (Ms) Main Hydrometeorological Administration 1, Karasuiskaya Street GSP 720017 BISHKEK Kyrgyz Republic Tel: +(996 312) 314 605 Fax: +(996 312) 314 663 Email: usi@meteo.ktnet.kg |
| Lao People's Democratic Republic | Vientiane | NMC | Tokyo | Tokyo | Mr Singthong Pathoummady Department of Meteorology and Hydrology P.O. Box 811 VIENTIANE Lao People's Democratic Republic Tel: (+856) 21 21 5010 Fax: +856 21 223446 Mobile: (+856) 20 538 9651 Email: singthong_dmh@etllao.com; p.singthong@yahoo.com |
| Macao, China | Macau | WSO | Beijing |  | Mr Ian Vai Kei, Brian Meteorological and Geophysical Bureau Rampa do Observatório Taipa Grande Caixa postal No.93 MACAU Macao, China Tel: +853 88986260 Fax: +853 28850557 Email: brianian@smg.gov.mo |
| Maldives | Malé | NMC | New Delhi | Tokyo | Mr Ali Shareef Department of Meteorology Orchid Building Orchid Magu MALE 20-05 Maldives Tel: +960 332 6200 Fax: +960 3320021 Mobile: +960 7771828 Email: admin@meteorology.gov.mv |
| Mongolia | Ulaanbaatar | NMC | Beijing |  | Ms Davaasuren Tungalag National Agency for Meteorology, Hydrology and Environment Monitoring Khudaldaany Gudamj-5 ULAANBAATAR 46 Mongolia Tel: +976-11-328 035 Fax: +976 11 329968 Email: tungalag@icc.mn/ tungalag@yahoo.com |
| Myanmar | Yangon | NMC | Tokyo |  | Dr Hrin Nei Thiam Department of Meteorology and Hydrology Mayangon P.O. 11061 YANGON Myanmar Tel: 00 95 67 411031 Fax: 00 95 67 411449 Email: dg.dmh@mptmail.net.mm |
| Nepal | Kathmandu | NMC | Beijing |  | Mr Kamal Prakash Budhathori Department of Hydrology and Meteorology G.P.O. Box 406 Babar Mahal KATHMANDU Nepal Tel: +977 1 4255920 Fax: +977 1 4262348/ +977 1 4254890 Email: kp_budhathoki@yahoo.com |
| Oman | Muscat | NMC | Jeddah | Tokyo | Mr Ahmed H. Al Harthy Department of Meteorology P.O. Box 1, Code: 111 & P.O. Box 204, Code: 113 Muscat Oman Tel: +968-24-519360 Fax: +968-24-518360 Email: a.alharthy@met.gov.om |
| Pakistan | Karachi | NMC | Beijing | Beijing | Mr Azmat Hayat Khan Pakistan Meteorological Department Sector: H-8/2 P.O. Box 1214 ISLAMABAD Pakistan Tel: +92-51-9250598 Fax: +92-51-9250368 Email: dirndmc@gmail.com; pakmet_islamabad@yahoo.com; director@pmd.gov.pk |
| Qatar | Doha | NMC | Jeddah | Tokyo | Mr R. Monikumar Qatar Meteorology Department PostBoxNo.3000, Doha,Qatar Tel: 0097466812409 moni.kumar@caa.gov.qa monikumar.r@gmail.com |
| Qatar | Doha | Aviation Centre | Jeddah | Tokyo | Mr R. Monikumar Qatar Meteorology Department PostBoxNo.3000, Doha,Qatar Tel: 0097466812409 moni.kumar@caa.gov.qa monikumar.r@gmail.com |
| Republic of Korea | Seoul | NMC | Seoul |  | Mr Sunghoi Huh Korea Meteorological Administration 460-18, Shindaebang-dong Dongjak-gu SEOUL 156-720 Republic of Korea Tel: +82 2 2181 0416 Fax: +82 2 2181 0449 Mobile: +82-10-4559-7256 Email: shhuh@korea.kr |
| Russian Federation | Novosibirsk | WSO (Novosibirsk) | Moscow |  | Mr Alexander Karpenko Russian Federal Service for Hydrometeorology and Environmental Monitoring (Novosibirsk) Novosibirsk,Sovetskayastr,30,Russia Tel:+73832224388 Fax:+73832222555 karp@meteo-nso.ru aspd@meteo-nso.ru |
| Russian Federation | Khabarovsk | WSO (Khabarovsk) | Moscow |  | Mr Anatoly Nagorsky Russian Federal Service for Hydrometeorology and Environmental Monitoring (Khabarovsk) Khabarovsk,Leninstr,18Russia Tel:+74212233064 Fax:+74212214248 aspd@hbrv.mecom.ru |
| Saudi Arabia | Jeddah | NMC | Jeddah |  | Dr Saad Almajnooni Presidency of Meteorology and Environment P.O. Box 1358 JEDDAH 21431 Saudi Arabia Tel: +966 546467695 Fax: +966 26572931 Email: saad_J2001@hotmail.com |
| Sri Lanka | Colombo | NMC | New Delhi |  | Mr S. R. Jayasekara Department of Meteorology 383,BauddhalokaMawatha,Colombo07 Tel:+94112691443 Fax:+94112698311 siriranjith@gmail.com |
| Tajikistan | Dushanbe | NMC | Moscow |  | Mr Suhrob Olimov Main Administration of Hydrometeorology and Monitoring of the Environment DUSHANBE 734025 Tajikistan Tel: +99244625848 Mobile: +992918297570 Email: olimovsa@gmail.com |
| Thailand | Bangkok | NMC | Tokyo |  | Dr Wanchalearm Petsuwan Thai Meteorological Department 4353 Sukhumvit, Bangna 10260 BANGKOK Thailand Tel: +662 399-4596 Fax: +662 398-9861 Email: wpetsuwan@hotmail.com; gtsbkk@metnet.tmd.go.th |
| Turkmenistan | Ashgabat | NMC | TBD |  | Mr Hallyyev Batyr Jumamuradovich Administration of Hydrometeorology 28, Azadi Avenue ASHGABAT 744000 Turkmenistan Tel: +993 12 93 81 58 Fax: +993 12 93 56 86 Email: meteo@online.tm |
| United Arab Emirates | Abu Dhabi | NMC | Jeddah |  | Mr Jassim Almarzouqi National Center of Meteorology and Seismology P.O. Box 4815 ABU DHABI United Arab Emirates Tel: +971 2222 7771 Fax: +971 26661575 Email: jalmarzouqi@ncms.ae |
| Uzbekistan | Tashkent | NMC | Seoul |  | Mr Bakhtier Makhmudov Uzhydromet 72, 1st Bodomzor yuli str. TASHKENT 100052 Uzbekistan Tel: +998 711 508 635, 237 35 11 Fax: +998 712332025 Email: uzhymet@meteo.uz, mtb@meteo.uz |
| Viet Nam | Hanoi | NMC | Tokyo |  | Mr Nguyen Nam Thanh Hydrometeorological Service No. 4, Dang Thai Than Str. Hoan Kiem HANOI the Socialist Republic of Viet Nam Tel: +844 3 824 4120, +844 3 824 4187 Fax: +844 3 826 0779, +844 3 825 7740 Email: hoahtqt@gmail.com, daikhanh@kttv.gov.vn |
| Yemen | Sana'a | NMC | Jeddah |  | Mr Tareg S. Alhamady Yemen Meteorological Service Haddah Post Office P.O. Box 7145 SANA'A Republic of Yemen Tel: + 967 1 419774 ext 215 Fax: +967 1 419771 Email: fore@yms.gov.ye |

- Challenges in Implementation of WIGOS and WIS

6.1 Challenges in Implementation of WIGOS

In the R-WIP-II，the risk areas have also been identified, including lack of resources (funds, expertise), lack of understanding of benefits that WIGOS can bring to the Region, sub-regions and Members, lack of cooperation and collaboration with key partners and stakeholders, and Low commitment of Members. Each one of these factors will be a big challenge of the WIGOS implementation in Regions and Members.

The first actual challenge for implementation of WIGOS is how to promote the implementation of projects listed in R-WIP-II. The implementation of WIGOS in RA II will rely on the implementation of projects in R-WIP-II. The projects in R-WIP-II will be implemented by main players listed in the projects. Some members who bear the responsibility of projects take actions actively, and some do not. It is a big challenge for the WG-WIGOS/WIS to think out a way to promote the implementation of the projects listed in R-WIP-II.

The second actual challenge for implementation of WIGOS is how to develop a commly used technical solution to solve observation issues for differentall members. For an example, for the case of project No. III.1 (Observing systems integration for supporting disaster risk reduction - Integration of Surface-based Remote Sensing Data in the East Asia), the quality of exchanged observation data is not controlled and, therefore, users are requested to develop their own quality control system to use such observation data.  Since data characteristics are specific to Radar, it is very difficult to develop a quality control system with limited information on individual Radar.

The third actual challenge for implementation of WIGOS is the member’s meteorological data polocy. WMO is try to make meteorological data exchanged without restrictions and it is also one of important target for WIGOS. Actully, some members have set restrictions to some specific kind of data in their data policies for the national security or other purposes.. It is quite challenging to identify possible barriers related to data policy and solve them to realize regional exchange of observation data among countries.  To solve this problem, the best way would be to prove the benefit of exchanging observation data.

6.2 Challenges in Implementation of WIS

In the R2-WIS-IP，the risk areas have also been identified, including lack of staff resources for operational WIS centre, lack of DAR Metadata knowledge, and Insufficient bandwidth of communication links. To overcome the risk,

(1)  GISC and DCPC staff should be educated enough about metadata, DAR and WIS related software.  NC's staff could manage WIS related activities. RA II GISCs and GISC candidates should enhance their staff training as well as the staff of their area of responsibility. They should ensure the availability of adequate communication systems and give the necessary consultation and cooperation with all Members, to improve their functions, including the establishment of routine RA II WIS long/short-term training programs capable of giving effective communications links.

(2)  RA II should take proper measures to face DAR metadata knowledge risks on the basis of WMO requirements and plan to solve this problem through training at three different levels:

At Level 1:  Each GISC should take responsibility of training its staff and staff of area of esponsibility on regular basis.

At Level 2:  RA II should arrange DAR metadata training courses for the region staff.

At Level 3: WMO should have a leading role in tackling this risk by  customizing training courses that addresses all WIS knowledge, especially DAR metadata issue.

Each WIS centre (GISC, DCPC, NC) should establish its own training plan and encourage its staff members to actively participate in different WIS related courses.

(3) All GISCs in RA II should be invited to analyze their telecommunication links with their area of responsibility (AMDCN) in term of data volume exchange (currently and in the future) and compare it with the available bandwidth, making technical and financial plans  to smooth the  migration  from current GTS status  to WIS permanent

Annex I

RA II WIGOS IMPLEMENTATION ACTIVITIES

Depending on the implementation scale, planned activities are specified as follows:

R = Regional activity; SR = Sub-regional activity and N = National activity.

| No. | Activity | Deliverables | Timeline | Responsibility | Estimated Costs (2012-2015) K CHF | Potential Risks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Total | ARB | Shortfall |  |
| 1. Management of WIGOS Implementation in RA II |
| 1.1 R | Develop and update R-WIP-II | Regional WIGOS Implementation Plan for RA II (R-WIP-II) | Develop in 2012 and update if necessary | Drafted by TT-R-WIP-II, to be adopted by RA II-15 (Dec. 2012) and updated by RA II EG-WIGOS/MG |  | Low (on-going) |
| 1.2 R | Report progress of the RA II R-WIP-II Projects to RA II MG | Progress reports | 2013-2015 every year | Coordinators of Projects |  | Low |
| 1.3 R N | Encourage RA II Members to appoint National Focal Points and submit national reports on progress of EGOS-IP | A list of RA II EGOS-IP National Focal Points | 2013-2015 every year | RA II Members (Project No. I) |  | Mod |
| 2. Collaboration with WMO and co-sponsored observing systems |
| 2.1 SR | Examine data policy and exchange of surface-based remote sensing datasets/ products for NWP use on an offline basis | Exchange of datasets | 2013-2014 | East Asia (China, Japan, Republic of Korea) (Project No. III.1) |  | High |
| 2.2 SR | Examine data policies and exchange observational sand and dust data | Exchange of datasets | 2013 | SDS-WAS Asian Node WG (China, Japan, Republic of Korea) (Project No. V) |  | High |
| 3. Design, planning and optimized evolution of WIGOS and its regional, sub-regional and national observing components |
| 3.1 R | Review the progress of EGOS-IP in RA II based on EGOS national reports submitted by RA II Members | Prioritized actions listed in the EGOS-IP | 2015 | China, Hong Kong, China (Project No. I) |  | Mod |
| 3.2 SR | Design feasible and optimal draft design of integration of surface-based remote sensing observations based on OSE; use the results to update the RRR user requirements database and to fine tune the EGOS-IP and observing system plans. | Draft design of integration of surface-based remote sensing observation based on OSE | 2015 | East Asia (Project No. III.1) |  | High |
| 3.3 SR | Assess enhanced capacity in monitoring and forecasting of sand and dust storms by exchanged datasets; use the results to update the RRR user requirements database and to fine tune the EGOS-IP and observing system plans. | Identified benefits from exchange of sand and dust data on a near real-time basis | 2015 | SDS-WAS Asian Node WG (Project No. V) |  | High |
| 3.4 SR | Develop strategic plan on development of the Southeast Asia radar network. | Draft strategic plan on development of the Southeast Asia radar network | 2015 | Southeast Asia (ASEAN—SCMG: Thailand, Malaysia) (Project No. III.2) |  | Mod |
| 3.5 R | Identify the requirements of NMHSs of developing countries, regarding satellite imagery, data and products, use the results to update the RRR user requirements database and to fine tune the EGOS-IP | Reports on requirements of NMHSs of developing countries, regarding satellite imagery, data and products |  | Japan, Republic of Korea, other satellite operators (Project No. VI) |  | Mod |
| 4. Integrated Observing System Operation and Maintenance |
| 4.1 R | Collect and share standard and best practices documents from RA II Members | Shared best practices on integration of observational systems | 2013-2015 | Republic of Korea (Project No. II) |  | Low |
| 4.2 SR | Develop and share national reports toward operational rainfall estimation/forecasting based on radar data. | Identified technical issues and lessons learned on operation of radar systems among ASEAN countries | 2015 | Southeast Asia (ASEAN—SCMG: Thailand, Malaysia) (Project No. III.2) |  | Mod |
| 5. Integrated Quality Management |
| 5.1 R | Survey and share the status on calibration instruments for surface-based observations in RA II | Reports on status on calibration instruments for surface-based observations in RA II | 2012-13 | China, India, Japan (Project No. IV) |  | Low (on-going) |
| 5.2 R | Monitor data quality by utilizing NWP QC monitoring reports on surface observations | Improved data quality of surface observations | 2012-15 | Japan (Project No. IV) |  | Low (on-going) |
| 5.3 R | Organize intercomparison between regional standards of RICs | Traceability between RICs | 2013-15 | China, Japan (Project No. IV) |  | High |
| 5.4 R | Obtain ISO/IEC 17025 | Enhanced RIC’s capacity | 2013-15 | China, Japan (Project No. IV) |  | Mod |
| 5.5 R | Enhance support by RICs, and encourage Members to work with RICs to ensure traceability to SI | Improved data quality of surface observations | 2013-15 | China, Japan (Project No. IV) |  | Mod |
| 6. Standardization, System Interoperability and Data Compatibility |
| 6.1 R | Survey and share the status on QC/QA procedures and site management for the network of RBCN and RBSN stations | Reports on status on QC/QA procedures and site management in RA II | 2013-15 | Japan (Project No. IV) |  | Mod |
| 6.2 N | Encourage the collection of metadata on observing stations | Collection of metadata on observing stations | 2013-15 | RA II Members |  | High |
| 7. The WIGOS Operational Information Resource |
| 7.1 R | Develop a portal to share EGOS national reports | Portal to share EGOS national reports | 2013-15 | China (Project No. I) |  | Low |
| 7.2 R | Develop a standards and best practices Portal | Standards and best practices Portal | 2013-15 | Republic of Korea (Project No. II) |  | Low |
| 7.3 R | Develop QA/QC Portal | QA/QC Portal | 2013-15 | Japan (Project No. IV) |  | Mod |
| 8. Data discovery, delivery and archival |
| 8.1 R | Encourage RA II Members to be designated as NCs and DCPCs | RA II Members designated as NCs and DCPCs | 2012-15 | RA II EG on WIGOS |  | Mod |
| 8.2 R | Encourage RA II Members to share data via WIS, including from organizations other than NMHSs | New sources of data are available through WIS | 2012-15 | RA II EG on WIGOS |  | Mod |
| 9. Capacity development |
| 9.1 R | Technical Training on QA/QC procedures | Improved QA/QC at RBCN and RBSN stations | 2013-15 | China; India; Japan; Republic of Korea; Hong Kong, China; Kuwait; Russian Fedederation (Project No. IV) |  | High |
| 9.2 R | Hold training workshops on maintenance and calibration of meteorological instruments | Improved capacity in maintenance and calibration of meteorological instruments | 2013 | Japan (Project No. IV) |  | Low (being planned) |
| 9.3 R | Develop training materials on maintenance and calibration of meteorological instruments | Training materials on maintenance and calibration of meteorological instruments | 2013-15 | Japan (Project No. IV) |  | Low (being planned) |
| 9.4 R | Coordinate training activities on utilization of satellite data/products | Improved capacity in utilization of satellite data/products | 2012-15 | Japan, Republic of Korea, other satellite operators (Project No. VI) |  | Low (on-going) |
| 9.5 R | Establishing filed intercomparison campaign for observation techniques | Guidance to operate and maintain observation instruments | 2013-15 | Republic of Korea (Project No. II) |  | Low |
| 10. Communication and outreach |
| 10.1 R | Interlink RA II WIGOS portals and related Websites | Better access to RA II WIGOS-related information and products | 2013-15 | China; Hong Kong, China; India; Japan; Republic of Korea |  | low |
| 10.2 R | Develop RIC Websites | Improved access to information on RICs | 2012-15 | China, Japan (Project No. IV) |  | Low (on-going) |
| 10.3 R | Publish newsletter regularly | Improved access to information on satellite data/products | 2012-15 | Japan, Republic of Korea, other satellite operators (Project No. VI) |  | Low (on-going) |

Annex II

RA II WIGOS IMPLEMENTATION PROJECTS

Project No. I

| Project Title | RA II WIGOS Project to Monitor and Review the Implementation of EGOS-IP in RA II |
| --- | --- |
| Type | Regional Implementation Project (RA II) |
| Status | Draft Design |
| Overview | A vision for the Global Observing Systems in 2025 which provides high-level goals to guide the evolution of the global observing systems during the coming decades has been approved by EC-LXI in 2009. Accordingly, CBS-15 adopted a recommendation for the Implementation Plan for the Evolution of Global Observing Systems (EGOS-IP) to complement and respond to this Vision. The Implementation Plan outlined the key activities to be implemented during the period 2012 to 2025 aiming at maintaining and developing all WMO component observing systems. Thus, a project can be established to monitor the progress of RA II Members on the implementation of EGOS-IP, analyze gaps in the regional observing network, and therefore, prioritize actions listed in EGOS-IP. The concerned information should be shared by RA II Members and all users by establishing a portal. This project will: Encourage RA II Members to appoint National Focal Points and submit EGOS National Reports annually, Identify gaps and prioritize actions listed in EGOS-IP through reviewing the progress of EGOS-IP in RA II, Develop a Portal to share the progress of EGOS-IP Implementation of RA II Members. |
| Aim(s) | To identify gaps and prioritize actions listed in the EGOS-IP through reviewing the progress of the Evolution of Global Observing Systems (EGOS), The progress and experiences are shared by RA II members when implementing the EGOS-IP. |
| Benefits | The Portal will provide Members and users with a platform for sharing updated progress of EGOS-IP implementation in RA II |
| Key Regional Players | China and Hong Kong, China |
| Capacity development requirements | Technical assistance by CBS, Workshop(s) on gaps analysis and actions prioritizing listed in EGOS-IP. |
| Partners/Participants | All RA II Members |
| Funding Source(s) | This project will rely on existing budget allocations at the national level. Additional funding will be needed to facilitate some elements such as the cost for developing the portal software. |
| Overall Costs | (TBD) |
| Timescale | 2013–2016 |
| Expected Key Deliverables/Key responsible body | A list of RA II EGOS National Focal Points, Prioritized actions listed in the EGOS-IP, Portal to share progress EGOS IP implementation in RA II. |
| Main risk(s) | Lack of resources (funds/expertise), lack of cooperation and missing or mistaken information from Members |
| Website | Not available |
| Summary | This project will develop a Portal that will provide updated progress on EGOS-IP in RA II, identify gaps and prioritize actions listed in EGOS-IP identify regional prioritized actions to be taken. |
| Date of the update | 21 November 2012 |
| Contact Person 1 | Ms GUO Jianxia Meteorological Observation Center, China Meteorological Administration (CMA) China Tel: +86 10 68407934 Fax: +86 10 68400936 E-mail: gjxaoc@cma.gov.cn |
| Contact Person 2 | Mr LEE Lap Shun Hong Kong Observatory Hong Kong, China Tel.: +852-2926-8416 Fax: +852-2311-9448 E-mail: lslee@hko.gov.hk |

Project No. II

| Title | RA II WIGOS Project for Standard and Best Practice Portal, including Technical Documents with Necessary Details in English from all RA II Members |
| --- | --- |
| Type | Regional Implementation Project (RA II) |
| Status | Draft Design |
| Overview | This project will develop a Standard and Best Practise Portal including mechanism and procedures needed for a regular updating process. |
| Aim(s) | To develop a Standard and Best Practise Portal, To establish regional standard and best practices documentation (regional practices database) for enhanced observational data/products utilization, including data/metadata management, To specify mechanisms, procedures for regular monitoring and updating of the portal. |
| Benefits | The standard and best practices portal will enhance and improve quality and utilization of data/products. |
| Key Regional Player | Republic of Korea |
| Capacity development requirements | Technical assistance by CBS and CIMO |
| Partners/Participants | RA II Members |
| Relationship with existing project(s) | KMA WIGOS demonstration project |
| Funding Source(s) | This project will rely on existing budget allocations at the national level |
| Overall Costs | (TBD) |
| Timescale | 2013–2016 |
| Expected Key Deliverables / Key responsible body | Portal on standards and best practices with mechanisms and procedures for regular monitoring and keeping the portal up-to-dated. |
| Main risk(s) | Lack of resources (funds/expertise), lack of cooperation and missing or mistaken information from Members. |
| Website | Not available |
| Summary | This subproject will establish a RA II Portal of standards and best practices for enhanced observational data/products utilization. |
| Date of the update | 21 November 2012 |
| Contact Person 1 | Dr WON Jaegwang Korea Meteorological Administration (KMA) Republic of Korea Tel.: +82-2-2181-0694 Fax: +82-2-2181-0709 E-mail: wonjg@kma.go.kr, ecotus37@korea.kr |
| Contact Person 2 | Dr PARK Seongchan Korea Meteorological Administration (KMA) Republic of Korea Tel. +82-2-2181-0696 Fax: +82-2-2181-0709 E-mail: scpark@korea.com |

Project No. III.1

| Project Title | RA II WIGOS Project for Observing Systems Integration for Supporting Disaster Risk Reduction |
| --- | --- |
| Subproject Title | Integration of Surface-based Remote Sensing Data in the East Asia |
| Type | Regional Implementation Project (RA II) |
| Status | Draft Design |
| Overview | In order to enhance observing capabilities in severe weather monitoring and forecasting, specifically in East Asia, surface-based remote sensing datasets/ products, such as radar and GPS data, should be integrated for their better utilization. This project, as a first step, aims at developing a feasible and optimal draft design of integrated surface-based remote sensing observations toward future operational assimilation in meso-scale NWP system at the sub-regional level, as well as real-time quality-assured radar composite maps. The project will be Observing System Experiments (OSE) driven and proceed as follows: Offline Exchange of surface-based remote sensing datasets/products including radar echo intensity, Doppler velocity, AWS data, and, if available, GPS precipitable water vapour, together with supplementary information (e.g. data format, details on observations, and data quality) among participating organs. Examination of impacts of assimilation of exchanged remote sensing observation on its NWP performance. Also, sub-regional radar composite maps meeting their own operational requirements will be developed. Results and identified technical issues (e.g. data format, data policies, telecommunication for real-time data exchange, and quality of data) will be shared with and worked out cooperatively by the participating organs. Thus, requirements of data exchange for operational phase will be specified. A feasible and optimal draft design of integration of surface-based remote sensing observations will be developed based on the results of the project. To proceed with this project, existing frameworks such as CMA-JMA-KMA NWP meeting will be expanded to include this project into its agenda. |
| Aim(s) | The aim of this project is to develop a feasible and optimal draft design of integrated surface-based remote sensing observations toward operational assimilation of those data in meso-scale NWP model of the participating organs at the sub-regional level, as well as real-time quality-assured radar composite maps. |
| Benefits | Members in East Asia will benefit from this project through enhancement of their capabilities in observations for better early monitoring/warning/nowcasting/very short-range forecasting. All the other RA II Members, particularly ones in Southeast Asia which might plan a similar project in the future, will benefit from shared outcomes of this project, namely: (1) solutions to identified issues for integration of surface-based remote sensing observations at sub-regional level; as well as (2) results of impact analysis on capacities in severe weather monitoring and forecasting. |
| Key Regional Player | China, Japan and Republic of Korea |
| Capacity development requirements | Workshop(s) on better utilization (decision making & assimilation) |
| Partners/Participants | CMA, JMA, KMA |
| Relationship with existing project(s) | WMO Workshop on the Impact of Various Observing Systems on Numerical Weather Prediction. CMA-JMA-KMA joint workshop on NWP (The 1st CMA-JMA-KMA joint workshop on NWP was held in September 2011). WMO/CIMO Radar Quality Control and Quantitative Precipitation Estimation Intercomparison (RQQI). |
| Funding Source(s) | This project will rely on existing budget allocations at the national level. The project will build on existing national observational networks and information management infrastructures. Additional funding might be needed to regularly hold technical meetings among CMA, JMA, and KMA to proceed with this project. |
| Overall Costs | (TBD) |
| Timescale | 2013 – 2016 |
| Expected Key Deliverables / Key responsible body | Establishment of collaborative working mechanism toward integrated surface-based remote sensing observations in the East Asia for operational monitoring and forecasting severe weather. Solutions to identify issues to be solved for integration of surface-based remote sensing observations at sub-regional level and their solutions. Impacts on capacities of NMHSs in severe weather monitoring and forecasting through utilization of surface-based remote sensing observations. |
| Main risk(s) | Limited exchange of observational data, for instance, due to data policies of providers. Lack of sharing relevant technical documentation on exchanged data. |
| Website | Not to be established |
| Summary | This project will develop a feasible and optimal draft design of integrated surface-based remote sensing observations toward the sub-regional utilization in East Asia. |
| Date of the update | 21 November 2012 |
| Contact Person 1 | Mr Yuki Honda Office of International Affairs Japan Meteorological Agency (JMA) Japan Tel.: +81-3-3211-4966 Fax: +81-3-3211-2032 E-mail: iao-jma@met.kishou.go.jp, |
| Contact Person 2 | Dr Jaegwang WON Korea Meteorological Administration (KMA) Republic of Korea Tel.: +82-2-2181-0694 Fax: +82-2-2181-0709 E-mail: wonjg@kma.go.kr, ecotus37@korea.kr |
| Contact Person 3 | Mr LI Feng Meteorological Observation Center China Meteorological Administration (CMA) China Tel.: +86 10 68409293 Fax: +86 10 68400936 E-mail: liflif04@cma.gov.cn |

Project No. III.2

| Project Title | RA II WIGOS Project for Observing Systems Integration for Supporting Disaster Risk Reduction |
| --- | --- |
| Subproject Title | Capacity Building in Radar Techniques in the Southeast Asia |
| Type | Cross-regional Implementation Project (RAs II and V) |
| Status | Draft Design |
| Overview | Developing countries in Southeast Asia share common challenges for severe weather monitoring and forecasting. In spite of many radars having been installed in the region, they are not fully utilized due to lack of their expertises in weather radar techniques. Thus, capacity building in weather radar techniques is crucial concern for the countries. Although their levels of operational usage of radar vary, they are often facing common technical challenges. In this regard, sharing their technical issues and lessons learnt among countries in the Region and developing the regional strategy on development of the radar network in the Region will enable them to tackle those challenges collaboratively with help from the WMO community in an effective and efficient manner. This project, initiated by Thailand and Malaysia, within the framework of the ASEAN Sub-Committee on Meteorology and Geophysics (SCMG), aims at establishing a collaborative mechanism within SCMG through the following steps: Thailand and Malaysia, as leaders of this project, will develop their national reports toward operational rainfall estimation/forecasting based on radar data. In order to share their experiences and lessons learnt among the participating organs, and to identify technical problems to be solved and necessary technical supports for, the reports should include the following items in a well-structured format: (a) overview of the current radar systems, (b) organization (department, division, staff, and budget), (c) specification of radar systems, (d) maintenance of equipment, (e) data processing (QC, calibration, and composite technique), (f) radar products, (g) details of current technical problems associated with (a) to (f), (h) lessons learnt from the past experiences, (i) recent progress, (j) future development plans. The reports will be submitted to the 35th SCMG meeting (2013). The other ASEAN member countries will also develop their national reports in the same format as that of Thailand and Malaysia, and submit their reports to 36th SCMG meeting. Based on the submitted report, the meeting will develop a regional strategic plan on radar which identifies common technical issues and necessary actions to be taken. During the period of the project, all the above Members will be requested to update their national reports and submit the latest version to a SCMG meeting every year. Thailand and Malaysia are requested to encourage the other Members to develop and keep their national reports up-to-date. The regional strategic plan is also to be updated at every SCMG meeting. *Each Member will consult with the WMO or advanced RA II Members about appropriate technical missions focused on identified technical issues in the reports such as dispatch of radar experts to recipient countries, with the VCP or other funds. On completion of such a mission, the recipient Member is requested to update its national report by including details of the outcomes of the mission. *SCMG set up a new agenda item for discussion on the progress of this project. |
| Aim(s) | This project aims to develop effective early warning systems building on radar data in Southeast Asia. |
| Benefits | Capacity in monitoring and forecasting of the severe weather using radar data will be enhanced by shared experiences and lessons among the participating organs and technical missions focused on technical issues identified in national reports and the regional strategic plan. |
| Key Regional Player | ASEAN-SCMG: Thailand, Malaysia |
| Partners/ Participants | All the ASEAN Member countries (Cambodia, Brunei Darussalam, Indonesia, Lao PDR, Malaysia, Myanmar, Philippines, Singapore, Thailand, Vietnam) |
| Relationship with existing project(s) | Radar composite map in Southeast Asia, one of the on-going projects under the Meteorological Working Group of the WMO/ESCAP Typhoon Committee, Severe Weather Forecasting Demonstration Project (SWFDP) for Southeast Asia, ASEAN Sub-Committee on Meteorology and Geophysics(SCMG). |
| Funding Source(s) | This project will rely on existing budget allocations at the national level. The project will build on existing national observational networks and information management infrastructures. Additional funding will be needed for technical cooperation for those countries by dispatching appropriate experts and/or providing training workshops. |
| Overall Costs | (TBD) |
| Timescale | 2013–2016 |
| Expected Key Deliverables / Key responsible body | National reports in the Southeast Asia toward operational rainfall estimation/forecasting based on radar data, Regional strategic plan on development of the radar network. |
| Main risk(s) | 1) Failure of development of national reports by participating organs. 2) Lack of available experts. 3) Lack of funds available. |
| Website | Not to be established |
| Date of the update | 21 November 2012 |
| Contact Person 1 | Dr.Somchai Baimoung Deputy Director-General/Acting Director-General Thai Meteorological Department Thailand Tel.: +66 81 989 9025 Email: somchaib@tmd.go.th |
| Contact Person 2 | Mr A. Kamiluddin Hj Ibrahim Director, Radar Meteorology Division Malaysian Meteorological Department Malaysia Tel.: +603 7967 8154 Fax: +603 7955 0964 E-mail: kamiluddin@met.gov.my |

Project No. IV

| Project Title | RA II WIGOS Project to Enhance the Availability and Quality Management Support for NMHSs in Surface, Climate and Upper-air Observations |
| --- | --- |
| Type | Regional Implementation Project (RA II) |
| Status | Draft Design |
| Overview | The Japan Meteorological Agency (JMA)/World Meteorological Organization (WMO) Workshop on Quality Management in Surface, Climate and Upper-air Observations, held at Tokyo in July 2010 as part of activities of the Pilot Project to Enhance the Availability and Quality Management Support for NMHSs in Surface, Climate and Upper-air Observations (hereafter, Pilot Project), found out that primary factors adversely affecting data quality in RA II are calibration and maintenance of instruments mainly due to lack of traceability of measurements to international standards and calibration facilities. This project will build on outcomes of the workshop. It consists of the following two activities: (i) improvements of data quality of RBCN/RBSN stations; and (ii) enhancement of capabilities of RIC-Tsukuba and RIC-Beijing. All the outcomes of this project will be shared at a Portal to be established by the Coordinator. 1. Improvements of data quality at RBCN/RBSN stations (a) Monitoring Data Quality The Coordinator checks data quality of RA II stations and identifies and requests RA II Members to identify technical issues, based on the following results: Questionnaire on the Surface, Climate, and Upper-air Observations and Quality Management in Regional Association II (Asia) (conducted in July 2010), Questionnaire on meteorological instruments, calibration and training in Regional Association II (Asia) (conducted in January 2012), 6-monthly monitoring reports by the Lead Centre for monitoring the quality of land surface observations in Region II. Survey on status on QA/QC procedures and site managements for the network of RBCN/RBSN stations, and report the results. Based on requests from the Coordinator, the following Members will consider the possibility of technical support if funds are available, and share the summary of the technical missions with RA II Members: CMA, HKO, JMA, and KMA for Southeast Asia, IMD for South Asia, Roshydromet for Central Asia, Kuwait for Middle East. 2. Enhancement of RIC’s Services RICs plan to implement the following action items for further enhancement of their services in capacity building and calibration during the project: Organization of a training workshop to improve understanding of calibration and maintenance of meteorological instruments according to needs of RA II Members to be identified by the “Questionnaire on Meteorological Instruments, Calibration and Training in Regional Association II (Asia)”, Development of training materials on calibration and maintenance of instruments (to be prepared for publication as an Instruments and Methods of Observation Programme (IMOP) technical document), Obtaining the International Standard ISO/IEC 17025 – General requirements for the competence of testing and calibration laboratories – certification for air pressure, temperature, and humidity, Development of RIC’s Websites, Intercomparison between RIC-Tsukuba and RIC-Beijing, Reports on status on calibration instruments for surface-based observations in RA II (to be prepared for publication as an Instruments and Methods of Observation Programme (IMOP) technical document). |
| Aim(s) | This project aims at improvement of data quality at RBCN/RBSN stations and enhancement of services of RA II RICs. |
| Benefits | RA II Members, especially those with technical issues on data quality of observations, will potentially benefit from this project. |
| Role/Involvement of WMO Regional Centres in RA II | Regional Instrument Centres (RICs) Lead Centre for monitoring the quality of land surface observations |
| Key Regional Player | JMA (Coordinator), and Members of Coordination Group Technical Mission: CMA, HKO, JMA, and KMA for Southeast Asia, IMD for South Asia, Roshydromet for Central Asia, Kuwait for Middle East. |
| Capacity development requirements | Workshop on maintenance, field inspection, etc. (basic level), Workshop on traceability, measurement uncertainty, etc. (advanced level). |
| Partners/Participants | RA II Members |
| Funding Source(s) | This project will rely on existing budget allocations at the national level. Additional funding will be needed to dispatch experts to NMHSs in developing countries and/or invite their observational staff to RICs for trainings and calibrations of national standards. |
| Overall Costs | (TBD) |
| Timescale | 2013–2016 |
| Expected Key Deliverables / Key responsible body | Provision of technical support for instrument maintenance and calibration by experts from RICs. Holding a RIC’s training workshop for RA II Members. Development of training materials (to be prepared for publication as an IMOP technical document). Obtaining ISO/IEC 17025 certification. Portal Website to share outcomes of this project. Report on status on QC/QA procedures and site management in RA II. Reports on status on meteorological instruments, calibration and training in Regional Association II. |
| Main risk(s) | Lack of funding for technical missions by RICs, Insufficient communication between the Coordinator, RICs, and RA II Members on their status on maintenance and calibration of instruments to specify needs of technical supports, Lack of responses from RA II Members. |
| Website | RIC’s Website/Portal on QC/QA |
| Summary | Improvement of data quality of RA II Members through enhancement of RIC’s services and capacity |
| Date of the update | 21 November 2012 |
| Contact Person 1 | Mr Yoshihisa KIMATA Senior Coordinator for Observation Networks Administration Division, Observations Department Japan Meteorological Agency (JMA) Japan Tel.: +81 3 3211 6018 Fax: +81 3 3211 7084 Email: kimata@met.kishou.go.jp |
| Contact Person 2 | Mr He Xiaolei Meteorological Observation Center China Meteorological Administration (CMA) China Tel: +86 10 68409767 Fax: +86 10 68400936 E-mail: hxlaoc@cma.gov.cn |

Project No. V

| Project Title | RA II WIGOS Project to Develop a Sand and Dust Storm Warning Advisory and Assessment System (SDS-WAS) in Asia Node |
| --- | --- |
| Type | Regional Implementation Project (RA II) |
| Status | Draft Design |
| Overview | SDS-WAS was established in 2007 to achieve comprehensive, coordinated and sustained observations and modelling capabilities of sand and dust storms in order to improve the monitoring of sand and dust storms to increase the understanding of the dust processes and to enhance dust prediction capabilities for mitigation of risks in many affected area (aviation, health impacts, etc.). The WMO SDS-WAS Region for Asia third meeting of Regional Steering Group (RSG) was held at Tsukuba, Japan in March 2012. At the meeting, it was confirmed that observation data exchange schemes should be implemented promptly in order to enhance systematic near-real-time (NRT) monitoring of sand and dust events in each country, and the following near-term implementation plan was agreed within the SDS-WAS Asia Node activity: Each country will confirm their data policy on observation data delivery, to reach an agreement on the provision of observation data to be shared within the Node in NRT, Regional Centre (RC: China) will provide a portal website with a function for sharing the observation data and announce it to the Node members, At the beginning, experimental observation data sharing will be conducted in off-line basis (not NRT) for the sand/dust storms (SDS) seasons, For the data exchange, the ad-hoc working group will propose appropriate data format and parameters, In SDS season in the spring (from February to June) 2013, the NRT (with a goal of approximately 1-day delay) data exchange will be conducted regularly, NRT data will be used for intercomparison of sand and dust storm forecast model to improve forecast accuracy as well as for monitoring of sand and dust storms. |
| Aim(s) | This project aims at mitigation of risks in many affected areas in the Asia Node countries through enhancement of systematic NRT monitoring of sand and dust storm. |
| Benefits | The systematic NRT monitoring of sand and dust storm will provide the Asia Node countries with useful information for sand and dust storm risk mitigation. |
| Role/Involvement of WMO Regional Centres in RA II | Regional Specialized Meteorological Centre with activity specialization on Atmospheric Sand and Dust Forecast (RSMC-ASDF) (TBD) |
| Key Regional Player | China, Japan, Republic of Korea |
| Partners/Participants | Countries in SDS-WAS Asia Node (China, Japan, Kazakhstan, Republic of Korea and Mongolia) |
| Funding Source(s) | This project will rely on existing budget allocations at the national level. |
| Overall Costs | (TBD) |
| Timescale | 2013–2015 |
| Expected Key Deliverables / Key responsible body | The systematic NRT monitoring of sand and dust storm in SDS-WAS Asia Node |
| Main risk(s) | Lack of resources (funds/expertise) |
| Website | SDS-WAS Asia Node portal |
| Summary | Improvement of sand and dust storms monitoring in the SDS-WAS Asia Node |
| Date of the update | 12 November 2012 |
| Contact Person 1 | Prof. ZHANG Xiaoye Chinese Academy of Meteorological Sciences China Meteorological Administration (CMA) China Tel.: +86 10 68406601 Fax: +86 10 62175931 E-mail: xiaoye@cams.cma.gov.cn |
| Contact Person 1 | Mr Hiroshi Koide Senior Coordinator for Global Atmosphere Watch Atmospheric Environment Division Global Environment and Marine Department Japan Meteorological Agency (JMA) Japan Tel.: +81-3-3287-3439 Fax: +81-3-3211-4640 E-mail: hkoide@met.kishou.go.jp |
| Contact Person 1 | Dr Youngsin Chin Korea Meteorological Administration (KMA) Republic of Korea Tel.: +82 70 7850 6752 Fax: +82 2 831 4930 E-mail: hwangsa@korea.kr |

Project No. VI

| Project Title | RA II WIGOS Project to Develop Support for NMHSs in Satellite Data, Products and Training |
| --- | --- |
| Type | Regional Implementation Project (RA II) |
| Status | Draft Design |
| Overview | At its fourteenth session (December 2008), Regional Association II adopted a resolution to establish a pilot project for the development of support for National Meteorological and Hydrological Services (NMHSs) in the areas of satellite data, products and training. The Coordinating Group of the Pilot Project is composed of Japan (Co-coordinator); Republic of Korea (Co-coordinator); Bahrain; China; Hong Kong, China; India; Kyrgyzstan; Maldives; Oman; Pakistan; Russian Federation; Uzbekistan; Viet Nam and EUMETSAT (observer). The object of this project is to encourage NMHSs in RA II to make a kind of self-help effort to improve the flow of satellite-derived information by: Identifying the requirements of NMHSs of developing countries, regarding satellite imagery, data and products, use the results to update the RRR user requirements database and to fine tune the EGOS-IP, Facilitating the timely provision of satellite-related information by satellite operators themselves to users via the project web page, newsletters, etc., and Aligning with VLab activities to optimize assistance to NMHSs in RA II and coordinating training activities on use of satellite data/products). |
| Aim(s) | To encourage NMHSs in RA II to make a kind of self-help effort to improve the flow of satellite-derived information, To improve the knowledge and techniques to use satellite data and products. |
| Benefits | NMHSs in RA II have benefited from this project to find means to access satellite data, products and training they want, and to improve the usage of satellite-derived information. This is expected to improve NMHSs’ activities from nowcasting to climate and environment monitoring. |
| Key Regional Player | Japan, Republic of Korea and other satellite operators in RA II |
| Capacity development requirements | Assistance (or support) of WMO VLab activities and other regional training activities, Assistance of satellite operators, Liaison with EGOS-IP. |
| Partners/Participants | Members of the Coordination Group members: Japan (Co-coordinator); Republic of Korea (Co-coordinator); Bahrain; China; Hong Kong, China; India; Kyrgyzstan; Maldives; Oman; Pakistan; Russian Federation; Uzbekistan; Viet Nam, RA V (observer) and EUMETSAT (observer) All other RA II Members can be nominated as the Group members. |
| Relationship with existing project(s) | (TBD) |
| Funding Source(s) | Regular activities of this project rely on existing budget allocations at the national level. Additional funding will be needed to hold the Coordination Group meetings and training events regularly. |
| Overall Costs | (TBD) |
| Timescale | 2012–2016 |
| Expected Key Deliverables / Key responsible body | Reports on requirements of NMHSs regarding satellite imagery, data and products, Improvement on access to information on satellite data/products, Improvement on capacity in use of satellite data/products and facilitation of training datasets and toolboxes. |
| Main risk(s) | Lack of resources (funds/expertise) and lack of cooperation from Members |
| Website | The portal site of the project is operated on the WMO web server. http://www.wmo.int/pages/prog/sat/ra2pilotproject-intro_en.php |
| Summary | The project will encourage NMHSs in RA II to make a kind of self-help effort to improve the flow of satellite-érelated information. |
| Date of the update | 12 November 2012 |
| Contact Person 1 | Mr Hironobu Yokota Senior Coordinator for Meteorological Satellite Systems Satellite Program Division, Observations Department Japan Meteorological Agency (JMA) Japan Tel: +81-3201-8677 Fax: +81-3217-1036 E-mail:hyokota@met.kishou.go.jp |
| Contact Person 2 | Dr Dohyeong KIM Senior Scientist National Meteorological Satellite Center Korea Meteorological Administration Republic of Korea Tel: +82-70-7850-5705 Fax: +82-43-717-0210 E-mail: dkim@kma.go.kr |

_________

# Footnotes

Congress stressed that an effective capacity-building strategy is an essential component of the WIGOS implementation. Specialized education, training activities and improvement of necessary observing infrastructure should be reflected in the regional, sub-regional and national WIGOS implementation plans, especially for NMHSs of LDCs, LLDCs and SIDS. Hence, capacity building is not to be limited to scientific and technological concerns, but also to strategic and management consideration including human resources development, resource mobilization and communications and outreach activities.