| WORLD METEOROLOGICAL ORGANIZATION ____________________ REGIONAL ASSOCIATION V (South-West Pacific) WORKING GROUP ON INFRASTRUCTURE TASK TEAM ON WIGOS Open Workshop: RA-V Regional WIGOS Workshop JAKARTA, INDONESIA, 8-9 SEPTEMBER 2012 |  | RA-V/WG-INFR/TT-WIGOS-1/ Doc.2.3 (23.08.2012) _______ ITEM: Doc 2.3 Original: ENGLISH |
| --- | --- | --- |

THE REGIONAL WIGOS IMPLEMENTATION PLAN for RA-v

(Submitted by Russell Stringer, RA V Lead Working Group on Infrastructure and Coordinator of the Task Team on WIGOS)

SUMMARY AND PURPOSE OF DOCUMENT This document introduces the template developed by the WMO Secretariat based on the WIGOS Framework Implementation Plan adopted by EC-64. The Regional WIGOS Implementation Plan for RA-V (R-WIP-V) will be developed based on this template.

ACTION PROPOSED

Meeting participants (and other stakeholders) are invited to familiarise with the contents of the template and to form ideas on priority activities to include in Table 1 (“WIGOS Implementation Activities” for the Region).

____________

Appendix: 	Template of the Regional WIGOS Implementation Plan

DISCUSSION

THE REGIONAL WIGOS IMPLEMENTATION PLAN for RA-v

1.	Background

1.1	The template for the Regional WIGOS Implementation Plan for RA-V (R-WIP-V) was prepared by the WMO Secretariat. It is consistent with and closely derived from the WIP that was approved by EC-64 (in June 2012). An updated version of the R-WIP-V is planned to be provided on the Workshop web site during the week before the Workshop, incorporating some of the ideas submitted by stakeholders in advance of the Workshop.

1.2	All stakeholders, whether able to attend the Workshop or not, are encouraged to familiarize with the template version of R-WIP-V (as attached) and submit comments and suggestions to the Coordinator of RA-V TT-WIGOS (R.Stringer@bom.gov.au) prior to the Workshop (preferably before the end of August).

1.3	Note in particular the content of Chapter 4 and the need to insert actions into “Table 1: WIGOS Implementation Activities”. Stakeholders are encouraged to form ideas on priority activities to include in this Table.

_______________

REGIONAL WIGOS IMPLEMENTATION PLAN

WORLD METEOROLOGICAL ORGANIZATION

WMO INTEGRATED 
GLOBAL OBSERVING SYSTEM 
(WIGOS)

REGION X

(R-WIP RA X)

Version y

## CONTENTS

1.	INTRODUCTION AND BACKGROUND

1.1	Purpose of WIGOS and Scope of the WIGOS framework Implementation Plan (WIP)

1.2	WIGOS Vision and Congress Guidance for WIGOS Implementation

2.	KEY ACTIVITY AREAS FOR REGIONAL WIGOS IMPLEMENTATION

2.1	Management of WIGOS Implementation

2.2 	Collaboration with WMO and co-sponsored observing systems

2.3	Design, planning and optimized evolution of WIGOS component observing systems

2.4	Integrated Observing System Operation and Maintenance

2.5	Integrated Quality Management.

2.6	Standardization, System Interoperability and Data Compatibility

2.7	The WIGOS Operational Information Resource

2.8 	Data Discovery, Delivery and Archival

2.9 	Capacity Development

2.10 	Communication and Outreach

3.	MANAGEMENT of R-WIP

3.1	Regional Structures

3.2 	Monitoring, review and reporting mechanism

3.3 	Evaluation

4.	IMPLEMENTATION

4.1 	Activities, Deliverables, Milestones, Costs and Risks

5.	Resources

6.	Risk Assessment/Management

7.	OUTLOOK

ANNEX I	LIST OF ACRONYMS

# WIGOS FRAMEWORK IMPLEMENTATION PLAN

## 1.	INTRODUCTION AND BACKGROUND

### 1.1	Purpose of WIGOS and Scope of the RA X WIGOS Implementation Plan (R-WIP RA X)

The WMO Integrated Global Observing System (WIGOS) provides a new framework for WMO observing systems and the contributions of WMO to co-sponsored observing systems. It is important to recognize that WIGOS is not replacing the existing observing systems, but is rather an over-arching framework for the evolution of these systems which will continue to be owned and operated by a diverse array of organizations and programmes. WIGOS will focus on the integration of governance and management functions, mechanisms and activities to be accomplished by contributing observing systems, according to the resources allocated on a global, regional and national level.

The WIGOS Framework Implementation Plan (WIP) addresses the necessary activities to establish an operational WIGOS by the end of the period 2012-2015, as per the direction of WMO Congress. Yet WIGOS will continue to evolve and improve beyond 2015 through the governance and management mechanisms established by the execution of this plan.

The WIP also addresses a number of additional activities that would substantially improve the operational capabilities of WIGOS beyond the 2012-2015 implementation; however these activities are dependent on resources in addition to the regular budget. If these activities are not completed, WIGOS can still be considered operational. The resulting system will, however, be less effective in achieving its goals and benefits to Members will be reduced or delayed.

The WIP provides a basis for the development of the Regional WIGOS Framework Implementation Plans (R-WIP). The Members of a Region will adhere to the global WIP and to their regional framework (R-WIP) in the design, operation, maintenance and evolution of their national observing systems.

This plan is laid out in several chapters that identify and describe the various activity areas to be addressed within this Region. Specific regional/national activities for each area are included in Table 2 (see Section 4), which identifies deliverables, timelines, responsibilities, costs and risks, and whether the activity requires regional and/or national implementation. Similar activities are grouped under the title corresponding to the respective sub-section of Section 2.

### 1.2	WIGOS Vision and Congress Guidance for WIGOS Implementation

The Sixteenth World Meteorological Congress decided that enhanced integration of the WMO observing systems should be pursued as a strategic objective of WMO and identified this as a major expected result of the WMO Strategic Plan.

The WIGOS vision calls for an integrated, coordinated and comprehensive observing system to satisfy, in a cost-effective and sustained manner, the evolving observing requirements of Members in delivering their weather, climate, water and related environmental services. WIGOS will enhance the coordination of WMO observing systems with those of partner organizations for the benefit of society. Furthermore, WIGOS will provide a framework for enabling the integration and optimized evolution of WMO observing systems, and of WMO’s contribution to co-sponsored systems. Together with the WMO Information System (WIS), this will allow continuous and reliable access to an expanded set of environmental data and products, and associated metadata, resulting in increased knowledge and enhanced services across all WMO Programmes.

The implementation of WIGOS should build upon and add value to the existing WMO observing systems with emphasis on integration of surface- and space-based observations in an evolutionary process to satisfy requirements of WMO and WMO co-sponsored Programmes.

In implementing WIGOS, it is imperative that the current management, governance and support activities be reviewed and aligned with WMO priorities. This alignment will promote cooperation and coordination at the technical, operational and administrative levels.

The integrated satellite systems are a unique source of observational data for monitoring of weather, climate and the environment. It is important to further advance instrument intercalibration, data exchange, data management standardization, and user information and training, in order to take full advantage of space-based capabilities in the context of WIGOS.

WIGOS will be essential for the Global Framework for Climate Services (GFCS), aviation meteorological services, disaster risk reduction, and capacity development, each of which is a  WMO priority. It will also ensure a coordinated WMO contribution to the co-sponsored GCOS, GOOS, GTOS, and to the Global Earth Observation System of Systems (GEOSS).

## 2.	KEY ACTIVITY AREAS FOR REGIONAL WIGOS IMPLEMENTATION

To migrate the existing global observing systems (the Global Observing System (GOS), the Global Atmosphere Watch (GAW), the WMO Hydrological Cycle Observing System (WHYCOS) and the Global Cryosphere Watch (GCW), including surface-based and space-based components and all WMO contributions to GFCS, GCOS, GOOS, GTOS and GEOSS), particularly their regional components, into a more integrated single system that is WIGOS, focused effort is required at the regional level in the following key areas, detailed in the sub-chapters to follow:

(a)	Management of WIGOS implementation;

(b)	Collaboration with WMO and co-sponsored observing systems;

(c)	Design, planning and optimized evolution;

(d)	Integrated Observing System operation and maintenance;

(e)	Integrated Quality Management;

(f)	Standardization, system interoperability and data compatibility;

(g)	The WIGOS Operational Information Resource;

(h)	Data and metadata management, delivery and archival;

(i)	Capacity development;

(j)	Communication and outreach.

### 2.1	Management of WIGOS Implementation in RA X

WIGOS implementation is an integrating activity for all regional components of the WMO and co-sponsored observing systems: it supports all WMO Programmes and activities.

Executive Council

The WMO Executive Council will continue to monitor, guide, evaluate and support the overall implementation of WIGOS. Following the guidance by Cg-XVI, EC-LXIII established the Inter-Commission Coordination Group on WIGOS (ICG-WIGOS) with a view to providing technical guidance and assistance for the planning, implementation and further development of the WIGOS components. Progress on implementation of WIGOS will be reported to subsequent sessions of EC. The Council designated the president of CBS as chairperson of ICG-WIGOS.

Regional Association

The Regional association will play the key role in WIGOS implementation in the Region. The Regional Association, through its [insert the name of the respective regional working body], will coordinate planning and implementation of WIGOS on the regional level taking into account all WMO future priorities, such as GFCS and DRR. The [insert the name of the respective regional working body], under guidance from ICG-WIGOS, and with the support, where required, of the WIGOS Project Office in the WMO Secretariat, will be responsible for:

- The development of the Regional WIGOS Framework Implementation Plan (R-WIP);

- The integration of WIGOS regional network components; and

- The evolution of their regional networks according to the implementation plan for the evolution of global observing systems (EGOS-IP).

R-WIP will also address regional aspects of requirements, standardization, observing system interoperability, data compatibility, data management, Quality Management System (QMS) procedures including performance monitoring and data quality monitoring, and proposed improvements in observing networks/systems. An important role of the Regional Association will be to assess and continuously monitor regional requirements, identify regional gaps and identify capacity development projects within the Region to address those gaps.

The Members of the Region

Members will plan, implement, operate and maintain national networks and observing programmes based on the standards and best practices stated in the WMO Technical Regulations, the WIGOS Manual and the respective Manuals of the WIGOS component observing systems (e.g., GOS, GAW, WHyCOS and GCW). They will be encouraged to adopt a composite network approach to their networks and to include the acquisition, and onward transmission, of data from external sources, including NMHSs and other government agencies, the commercial sector and members of the public. A particular area of focus for Members of the Region under WIGOS will be increased attention to site protection and radio frequency spectrum protection.

Plans should also be developed to strengthen cooperation through partnership with different owners overseeing the WIGOS observing components within their countries. Specifically, these activities aim to enhance cooperation amongst meteorological, hydrological, marine/oceanographic and academic/ research institutions/services where they are separated at the national level.

### 2.2	Collaboration with WMO and co-sponsored observing systems

WIGOS will be an integrated, comprehensive, and coordinated system primarily comprising the surface-based and space-based observing components of the GOS, GAW, GCW, and WHYCOS, plus all WMO contributions to GCOS, GOOS and GTOS. It should be noted that in contrast to the primarily NMHS-owned observing systems upon which the WWW was built, the proposed WIGOS component observing systems are owned and operated by a diverse array of organizations, both research and operational. Therefore, the interaction between these various communities at the regional and national levels is important for the implementation of WIGOS within the Region. In particular, strengthening the interaction between research and operational observing communities is important for sustaining and evolving observing systems and practices, in line with new science and technology outcomes.

Partner Organizations

At the Regional level, coordination and cooperation will be supported by a mechanism to be defined by the Regional Association and the respective Regional bodies, such as [insert the names of the regional bodies that are active in the area of observations and monitoring], in order to resolve possible problems in data policy, product delivery and other governance issues. This interagency and inter-observing system coordination mechanism will need to be complemented and supported through similar cooperation and coordination arrangements among NMHSs and through national implementation mechanisms for GFCS, GCOS, GOOS, GTOS, and GEOSS.

The Architecture for Climate Monitoring from Space has been defined as an end-to-end system, involving the different stakeholders including operational satellite operators and R&D space agencies, the Coordination Group for Meteorological Satellites (CGMS), the Committee on Earth Observation Satellites (CEOS), the Global Climate Observing System (GCOS), the World Climate Research Programme (WCRP) and the Group on Earth Observations (GEO). Within the Regional context, the Architecture shall be part of the space-based component of WIGOS. Therefore, particular emphasis will be placed on their coordinated contribution to WIGOS within the Region, building on existing coordination mechanisms stated above.

### 2.3	Design, Planning and Optimized Evolution of WIGOS component observing systems

The WMO has agreed on the Vision for the Global Observing Systems in 2025 which provides high-level goals to guide the evolution of the global observing systems during the coming decades. To complement and respond to this Vision, an Implementation Plan for the Evolution of Global Observing Systems (EGOS-IP) has been considered by CBS-15. This EGOS-IP focuses on the long term evolution of WIGOS observing systems components, while the WIP focuses on the integration of these observing system components. Beyond 2015 these plans will provide Members of the Region with clear and focused guidelines, specifying actions that stimulate the cost-effective evolution of the observing systems to address in an integrated way the requirements of all WMO Programmes and relevant parts of co-sponsored programmes.

Concerning the surface-based sub-system of WIGOS, the current composition of mainly separate networks of observing stations comprises numerous different types of sites. With the implementation of WIGOS, these separate networks will continue to evolve but will also be given a more prominent collective identity as the WIGOS surface-based sub-system and for some purposes may be considered as a single composite system of observing (fixed or mobile) sites/platforms. The Regional Association will adopt a broader role in coordinating the implementation of relevant elements of the WIGOS surface-based sub-system, evolving from the previous concepts of mainly the Regional synoptic and climatological networks into an integrated concept of a WIGOS Regional Network.

Similarly, the space-based sub-system of WIGOS is composed of many different platforms and types of satellites. There is already partial integration due to the existence of a globally coordinated plan, which is maintained by WMO and CGMS, and which takes into account the needs of a number of application areas. However, it should be further developed and expanded to better support certain application areas that, at present, are not benefiting from the full potential of space-based observations, for example, other components of GAW and WHYCOS and new initiatives like GFCS and GCW. In addition, further integration shall be pursued in terms of inter-calibration, data and product harmonization, and composite product delivery. The Regional Association will adopt an active role in compiling the views of Members and maintaining documented requirements and priorities for data and products to be available for the Region from the WIGOS space-based sub-system.

Rolling Review of Requirements (RRR)

Coordinated strategic planning at all levels will be based on the RRR process, and will be supported by the WIGOS regulatory material. This activity will be carried out primarily at the global level under the guidance of the ICG-WIOS.

The RRR process involves regularly reviewing the observational data requirements for each of the defined WMO Application Areas and all required variables (see Table 1). The RRR process also involves reviewing the capabilities of WMO observing systems and co-sponsored systems, and the details of the networks/platforms in existence, for both space-based and surface-based systems, in delivering data on different variables. The comprehensive information collected for the globe on both requirements and capabilities is quantitatively recorded in a database accessible through the Observing Systems Capability Analysis and Review tool (OSCAR)  of the WIGOS Information Resource (WIR, see section 2.7 below). The information on surface-based networks and instrumentation details is currently recorded in Volume A, but will ultimately be available, with additional metadata through the OSCAR tool. Space-based capabilities are also recorded and made available through the OSCAR tool. OSCAR allows to perform gap analyses to identify weaknesses in existing observing programmes.

The above steps represent the analysis phase of the RRR, which is as objective as possible. Next is the prioritization and planning phase of the RRR in which experts from the various application areas interpret the gaps identified, draw conclusions, identify key issues and priorities for action. This input is composed as Statements of Guidance (SoG) from each application area. The technical commissions respond to the SoG by formulating new global observing system requirements and the regulatory and guidance publications to assist Members in addressing the new requirements. Additionally, CBS and other technical commissions draw on the SoGs to develop a Vision and an Implementation Plan for further developments of WIGOS.

Table 1: The 12 recognized WMO Application Areas

| No | Application Area | No | Application Area |
| --- | --- | --- | --- |
| 1 | Global NWP | 7 | Ocean Applications |
| 2 | High Resolution NWP | 8 | Agricultural Meteorology |
| 3 | Nowcasting & Very Short-range Forecasting | 9 | Hydrology |
| 4 | Seasonal to Inter-annual Forecasts | 10 | Climate Monitoring |
| 5 | Aeronautical Meteorology | 11 | Climate Applications |
| 6 | Atmospheric Chemistry | 12 | Space Weather |

At the Regional Level

Although the primary coordination of the RRR will lie with CBS for overall WIGOS planning, the Regional Association, through [insert the name of the respective regional working body], will follow the technical guidance of the technical commissions as represented in the EGOS-IP and other observation system implementation plans in order to evolve and implement observing systems in the Region.

The Regional Association will examine, and report back to CBS, its requirements for data, and any issues it identifies with the global WIGOS design, taking into account the particular requirements of the Region and international river basin authorities. This process will involve, in essence, (1) the use of the global data to prepare Regional data requirements, (2) use of this for detailed planning of observing system components at the Regional scale and then (3) encouragement of Members of the Region to implement these components, subject to further review at the national or sub-regional level, where appropriate.

At the National or Sub-Regional Level

The Members of the Region will contribute to the collective Regional effort to (1) assess the Regional data requirements and plan the Regional observing system components, and (2) implement and evolve observing systems following this plan, the EGOS-IP and other observation system implementation plans.

The Members of the Region will also have available the global and regional data requirements information available to use as guidance for the preparation of national requirements information which can then be used to assist with the detailed planning for evolution of national observing components of WIGOS.

In some cases, where countries are small and geographically close or already have established multilateral working relationships, there may be more merit in taking a sub-regional, as opposed to national, approach to WIGOS observing infrastructure planning. In this case, it will be necessary for the Members concerned to work in close cooperation to prepare sub-regional reviews of requirements to be used as a basis for detailed planning at that scale.

### 2.4	Integrated Observing System Operation and Maintenance

Observing system owners or custodians are responsible for operating and maintaining their systems and for complying with the regulations of the WMO and co-sponsored observing systems to which they contribute. System owners are generally NMHSs or other organizations within WMO Member countries but are sometimes other entities.

WIGOS on the Regional level involves a process for sharing of operational experiences, practices and ideas, for sharing of expertise and for pooling resources for joint activities. The benefit is to realize synergies and greater efficiencies. These interactions may be between different teams within a single organization (such as an NMHS) or between Regional organizations. These may benefit from technical guidance from relevant technical commissions and, while occurring primarily at a national level, there is a Regional role to be played.  Within Regional Association X, the following regional activities will be important:

- [Insert joint activities that provide synergies at Regional level.]

- …

### 2.5	Integrated Quality Management

The Region recognizes that meeting the quality requirements and expectations of users will be critical to the success of WIGOS. This will require an in-depth examination of current practices used by WMO observing programmes, specific mission-related requirements that are already in place, and available technological opportunities.

The WIGOS Quality Management approach is to apply the WMO QMF to the WIGOS observing components (see Technical Regulation 49, Part 4). WIGOS quality management at the Regional level will strive for compliance of all components of WIGOS with international standards, such as ISO 9001/9004 and the ISO 17025 standard where appropriate (i.e. with respect to instrument calibration and traceability of data). Compliance with international standards should be pursued in all quality assurance (QA) procedures applied by Members of the Region to all their national WIGOS observing components. In addition to the WMO QMF document, further guidance to Members will be provided by WMO via the standards and best practices described in the Regulatory Materials, such as the WIGOS Manual and Guide. Such guidance, for both mandatory and desirable practices, can be referred to for the application and implementation of quality management in national observing systems. In this context, the Region will give attention to:

(a)	The examination of current quality management practices being used in the Region;

(b)	The documentation of the quality of observations from the WIGOS Regional networks at all stages of data processing; and

(c)	Ensuring, where possible, traceability of observations to the International System of Units (SI).

CGMS, in coordination and collaboration with WMO, supports the development of quality assurance standards and formats for satellite observations, multi-satellite and multi-sensor algorithms for estimating retrieved data and products, and advanced atmospheric sounding derivation packages for use by WMO Members. To assist this effort, the Region will ensure that surface-based sites that are needed for calibration/validation of satellite data are specified.

A key aspect of Regional quality management that requires particular attention under WIGOS is the systematic and rigorous performance monitoring and evaluation (PM&E) of WIGOS capabilities, in terms of both: (a) the flow of observational data/products to models; and (b) provision of products/ information for decision-support tools and services in accordance with requirements specified by end users. Effective PM&E can improve the overall performance of WIGOS and its ability to effectively interact with its user community and to meet community needs and requirements.

Members of the Region will be responsible for ensuring compliance with the WIGOS quality management principles (such as ISO 9001, 9004, 17025).

### 2.6	Standardization, System Interoperability and Data Compatibility

The WIS has an important role in Regional WIGOS implementation, in relation to data exchange and discovery, and the provision of effective standards and practices for data management. The Therefore, the Region will coordinate WIGOS and WIS implementation activities.

Taking into account the ongoing rapid progress in technology that will continue to provide a basis for further improvements in the capability, reliability, quality and cost-effectiveness of observations, the Members of the Region will ensure that WIGOS utilizes international standards and best practices set by WMO and partner organizations and described in the WMO Regulatory Materials in the following areas:

(a) 	Instruments and methods of observation across all components including surface-based 	and space-based elements (observations and their metadata);

(b) 	WIS information exchange, as well as discovery, access and retrieval (DAR) services; and

(c) 	Data Management (Data Processing, Quality Control, Monitoring and Archival).

The Region will support all activities leading to the interoperability (including data compatibility) of WIGOS observing components through utilization and application of the same, internationally accepted standards and best practices (that is, standardization). Data compatibility will also be supported through the use of standardized data representation and formats.

Any Regional deviations from the standard practices (documented in the WMO Technical Regulations through the WIGOS Manual and other relevant Manuals) will be reported to the WIGOS Project Office.

### 2.7	The WIGOS Operational Information Resource

The WIGOS Operational Information Resource (WIR), accessible via a centralized point (web portal), will provide all WIGOS related operational information, including observational user requirements, a description of the contributing observing networks (instrument/site/platform metadata), and their capabilities, list of standards used in the WIGOS framework, data policies applicable, and information on how to access data. It will also provide general information on WIGOS benefits, and impacts to Members. It will be a tool for conducting critical reviews as part of the Rolling Review of Requirements, and can assist Members and the Regional Association in conducting observing network design studies as appropriate. It will provide guidance on how to develop capacities in developing countries according to WIGOS requirements, and will provide Members of the Region with a toolbox to be used nationally if and when required. The information collected is intended in particular to identify the gaps in the observational networks, identify areas where existing observing systems could be used, or where their scope could be expanded at limited cost to address the requirements of more application areas. The information provided on standards will support the production of more homogeneous data-sets and make the observations traceable and of known quality.

The key support tools of WIGOS are: (a) a central web portal (WIGOS Portal); (b) The WIGOS Standardization of Observations Reference Tool (SORT); and (c) the Observing System Capabilities Analysis and Review tool (OSCAR) which includes information on observational user requirements and observing systems capabilities, and allow to perform the critical review by comparing the two. [For more information on each of these support tools, please refer to the WIP.]

Understanding that sources of the individual components of the WIGOS Operational Information Resource rely on the inputs from its Members, the Region is committed to provide regular inputs to keep the information resource up-to-date.

### 2.8	Data Discovery, Delivery and Archival

Within the WIGOS framework, the WMO Information System (WIS) provides exchange of data and interpretation metadata, and management of related discovery metadata. These discovery metadata play an important role in the discovery, access and retrieval of WIGOS observations and products by the entire WMO community.

Submission, management and archival of the data themselves is generally the responsibility of observing system owners/data custodians. However, several World Data Centres and a number of regional or specialized data centres exist that collect, manage and archive basic observational data that are relevant to WMO Applications. Members of the Region are responsible for submitting their data to these regional or specialized data centres. The Regional Association will encourage its Members to abide by this commitment.

Members of the Region will adopt WIGOS and WIS standards and make their data and metadata available through WIS for delivery or for discovery, access and retrieval services. In this regard, promotion and implementation of DCPCs (Data Collection and Production Centres) as well as National Centres will be supported and encouraged by the Regional Association. Guidance will be developed and provided through the appropriate WIGOS regulatory and technical documents.

### 2.9	Capacity Development

A coordinated capacity-development effort at global, regional and national levels is of paramount importance to the developing countries in the implementation of WIGOS. This is especially the case for NMHSs of Least Developed Countries (LDCs) and Small Island Developing States (SIDSs), to enable them to develop, improve and sustain national WIGOS observing components. This needs to be complemented by capacity development efforts outside of WIGOS but in closely related areas to improve access to and effective utilization of observations, data and products, and related technologies. The WIGOS capacity development activities at the Regional level are focused on:

- Providing assistance to Members of the Region to introduce or improve institutional mandates and policies that enable effective implementation, operation and management of observing systems;

- Filling the existing gaps in the design, operation and maintenance of WIGOS observing systems, including both the infrastructure and human capacities development;

- Technological innovation, technology transfer, technical assistance and decision-support tools.

Capacity development in satellite applications for developing countries, LDCs and SIDSs are also addressed in the Implementation Plan for the Evolution of the GOS (see WMO/TD-No. 1267). The virtual lab (VL) will continue to grow and help all WMO Members realize the benefits of satellite data.

### 2.10	Communication and Outreach

The Region will establish its communication and outreach strategy through the efforts of WMO Members, Programmes, Regional Associations (RAs) and Technical Commissions (TCs), and co- sponsors. The strategy will provide details on WIGOS benefits, increased effectiveness, and efficiency, and impact on the activities of the Members of the Region, as well as on the socio-economical benefits of WIGOS data. It will take advantage of outreach programmes developed and effectively deployed so far by WMO and its partner organizations within the Region.

The WIGOS Portal will provide convenient access to relevant information on the Regional communication, outreach and capacity development, aimed at complementing, not duplicating, others’ efforts. A variety of outreach materials will be developed to educate the Members, funding agencies, policy-makers and the general public, on the importance of WIGOS to society. Materials will include posters and other educational material for elementary and high school classes, a WIGOS brochure, a semi-annual or annual newsletter, an online photo and video library, and information on the current state of the observing systems.

## 3.	REGIONAL PROJECT MANAGEMENT

The Regional Association will be responsible for the Project through [insert the name of the respective regional working body] with a support from the Regional Office(s) [insert the name of the Regional Office(s)].

### 3.1	Monitoring, review and reporting mechanism

(a)	The Regional Association, through its Management Group, will monitor, review, guide and support the overall implementation of WIGOS in the Region;

(b)	The Regional Association, through the chair of the [insert the name of the respective regional working body], will report to the ICG-WIGOS and the WIGOS Project Office on the progress in implementation of WIGOS in the Region;

(c)	The President will report at the RA’s sessions on WIGOS implementation.

### 3.2	Evaluation

The evaluation methodology will be designed against WIGOS implementation activity tables, i.e. with respect to the activities, deliverables, timeline, responsibility and budget allocations. This will include a schedule of monitoring and evaluation activities and related responsibilities. Mid-term evaluation, interim progress reports and post-implementation reviews are planned as a means of providing early feedback on progress towards success, and as a means of meeting accountability and transparency requirements for the whole implementation phase. RAs and NMHSs will provide progress reports at the request of the WIGOS Project Office.

## 4.	Implementation

### 4.1	Activities, Deliverables, Milestones, Costs and Risks

Table 1 presents the key implementation activities that are required for the Regional WIGOS implementation within the timeframe 2012-2015. The table is arranged to correspond to the activity areas presented in Section 2. In the table each implementation activity is presented along with its associated deliverables, timelines, responsibilities, costs and associated risk.

For each activity in Table 1, a detailed activity plan will be developed by the responsible entity or entities, with support of the [insert the name of the respective regional working body]. The [insert the name of the respective regional working body] has responsibility for tracking execution of these activities and this plan itself.

[To complete Table 1, it may help to examine the equivalent table in the WIP for guidance. However, in the case of this R-WIP, it is expected that the identified activities will be more specific and more focused than those contained in the WIP itself. Only detail two or three activities under each heading so as not to describe an overly ambitious plan. As far as possible, insert realistic timeframes for completing each activity, identify who is to be primarily responsible for carrying out the work, provide realistic estimates of the resources required, and where these are to come from. Finally, as far as possible, attempt to identify the key risks that may interfere with successful completion of the activity.]

Table 1	WIGOS Implementation Activities

Activities in bold are considered the most critical for WIGOS to gain operational acceptance by 2015.

Depending on the implementation scale, planned activities are specified as follows: R = Regional activity and N = National activity.

Key to activity numbers: a.b.c, where a is number of respective sub-section of section 2, b is for a regional (2) or national (3) activity, and c is a sequential number to distinguish activities from one another. ARB = Available Regular Budget. RB = Regular Budget.

| No | Activity | Deliverables | Timeline | Responsibility | Estimated Costs (2012-2015) K CHF | Potential Risks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Total | ARB | Shortfall |  |
| 1. Management of WIGOS Implementation in RA X |
|  | [Insert Regional & National Activities] |  |  |  |  |  |
| 2. Collaboration with WMO and co-sponsored observing systems |
|  | [Insert Regional & National Activities] |  |  |  |  |  |
| 3. Design, planning and optimized evolution of WIGOS and its regional, sub-regional and national observing components |
|  | [Insert Regional & National Activities] |  |  |  |  |  |
| 4. Integrated Observing System Operation and Maintenance |
|  | [Insert Regional & National Activities] |  |  |  |  |  |
| 5. Integrated Quality Management |
|  | [Insert Regional & National Activities] |  |  |  |  |  |
| 6. Standardization, System Interoperability and Data Compatibility |
|  | [Insert Regional & National Activities] |  |  |  |  |  |
| 7. The WIGOS Operational Information Resource |
|  | [Insert Regional & National Activities] |  |  |  |  |  |
| 8. Data discovery, delivery and archival |
|  | [Insert Regional & National Activities] |  |  |  |  |  |
| 9. Capacity development |
|  | [Insert Regional & National Activities] |  |  |  |  |  |
| 10. Communication and outreach |
|  | [Insert Regional & National Activities] |  |  |  |  |  |

## 5. 	Resources

[Describe here the resources that will be made available for R-WIP and that would be needed, including identification of possible sources.]

## 6.	Risk AsseSsment/ Management

The Risk Management Plan (RMP) will be developed for each implementation activity/projects, including risk mitigation. The following risk areas have been identified:

(a) [Insert risk area]

# (b) ……………….

## 7.	OUTLOOK

This document has described the key activities for the period 2012 to 2015. As determined by Cg-XVI, the goal is to have WIGOS operational by 2016. This is a challenging task. The experience gained during the WIGOS test of the concept phase clearly shows that it will be impossible to complete integration of all observing systems on global, regional and national levels in only four years. While WIGOS operations should start in 2016, there will still be a strong need to continue a significant number of implementation activities.

_________

## Annex

### LIST OF ACRONYMS

| CEOS | Committee on Earth Observation Satellites |
| --- | --- |
| CGMS | Coordination Group for Meteorological Satellites |
| CONOPS | Concept of Operations |
| DAR | Discovery, Access and Retrieval |
| DB | Database |
| DCPC | WIS Data Collection or Production Centre |
| DRR | Disaster Risk Reduction |
| ET | Expert Team (of WMO Technical Commission) |
| FAO | Food and Agriculture Organization |
| GAW | Global Atmosphere Watch |
| GCOS | Global Climate Observing System |
| GCW | Global Cryosphere Watch |
| GEO | Group on Earth Observations |
| GEOSS | Global Earth Observation System of Systems |
| GISC | WIS Global Information System Centre |
| GFCS | Global Framework for Climate Services |
| GOOS | Global Ocean Observing System |
| GTOS | Global Terrestrial Observing System |
| ICG-WIGOS | Inter-Commission Coordination Group on WIGOS |
| ICPC | Interagency Coordination and Planning Committee for Earth Observations |
| ICSU | International Council for Science |
| IOC | Intergovernmental Oceanographic Commission |
| ISO | International Standards Organization |
| ITU | International Telecommunication Union |
| LDCs | Least Developed Countries |
| MOU | Memorandum of Understanding |
| NMHS | National Meteorological and Hydrological Service |
| NOS | National Observing System |
| OSEs | Observing Systems Experiments |
| OSCAR | WIGOS Observing Systems Capabilities Analysis and Review tool |
| OSSEs | Observing System Simulation Experiments |
| QA | Quality Assurance |
| QC | Quality Control |
| QMF | Quality Management Framework |
| QMS | Quality Management System |
| RA | Regional Association |
| RCC | Regional Climate Centre |
| RIC | Regional Instrument Centre |
| RMIC | Regional Marine Instrument Centre |
| RRR | Rolling Review of Requirements |
| SIDS | Small Island Developing States |
| SoG | Statement of Guidance |
| SORT | WIGOS Standardization of Observations Reference Tool |
| SLA | Service Level Agreement |
| TC | Technical Commission |
| TOR | Terms of Reference |
| UNEP | United Nations Environment Programme |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |
| WCRP | World Climate Research Programme |
| WIGOS | WMO Integrated Global Observing System |
| WIP | WIGOS framework Implementation Plan |
| WIR | WIGOS Operational Information Resource |
| WIS | WMO Information System |
| WHYCOS | World Hydrological Cycle Observation System |
| WWW | World Weather Watch |

_____________

# Footnotes

see http://www.wmo.int/pages/about/documents/1069_en.pdf

http://www.wmo.int/pages/prog/www/OSY/gos-vision.html#egos-ip.

Available from the WMO Website at: http://www.wmo.int/pages/prog/www/OSY/gos-vision.html

Currently specified in the Manual on the Global Observing System (WMO-No. 544), elaborated in the Guide to the Global Observing System (WMO-No. 488), and described further on the WMO Website at http://www.wmo.int/pages/prog/www/OSY/GOS-RRR.html

The RRR describes data requirements, which are expressed in terms of space/time resolution, uncertainty, timeliness, etc., for each of the required observed variables, and are measures independent of observing technology.

Capabilities are derived from the individual platforms characteristics submitted by Members to WMO e.g. through WMO No. 9, Volume A, or its evolution

The following components are currently available via the WMO website: User Requirements: http://www.wmo.int/pages/prog/www/OSY/RRR-DB.html; and Space-based capabilities: http://www.wmo.int/pages/prog/sat/gos-dossier_en.php. The surface-based capabilities part is currently under development

Hydrological information only; water quality monitoring and information is currently excluded.

Interoperability is a property referring to the ability of diverse systems to work together (inter-operate)

http://www.wmo.int/wis

Interpretation metadata is the information required to interpret the data

Discovery metadata is the information describing the data-sets, generally using ISO-19115 standard, and WMO core profile in case of WIS

Congress stressed that an effective capacity-building strategy is an essential component of the WIGOS implementation. Specialized education, training activities and improvement of necessary observing infrastructure should be reflected in the regional, sub-regional and national WIGOS implementation plans, especially for NMHSs of LDCs, LLDCs and SIDS. Hence, capacity building is not to be limited to scientific and technological concerns, but also to strategic and management consideration including human resources development, resource mobilization and communications and outreach activities.