| World Meteorological Organization |  | RA II/MG-4/Doc. 6 |
| --- | --- | --- |
| REGIONAL ASSOCIATION II (ASIA) MANAGEMENT GROUP FOURTH SESSION |  | Submitted by | Secretariat |
|  |  | Date: | 22.II.2012 |
|  |  | Agenda item: | 6 |
| Doha, 29 February – 2 March 2012 |  |  | English only |

DEVELOPMENT OF THE RA II STRATEGIC OPERATING PLAN FOR 2012-2015

SUMMARY

ADDITIONAL FINANCIAL IMPLICATION: None ISSUES TO BE DISCUSSED: Approach taken for the preparation of the WIGOS and WIS components of the RA II Strategic Operating Plan (SOP) 2012-2015 DECISIONS/ACTIONS REQUIRED: The session will be invited to note the progress on the development of RA II Strategic Operating Plan (SOP) for 2012-2015 and consider the appropriate approach and timeline for finalization and adoption of the RA II SOP. REFERENCE: 1. Abridged Final Report of the Sixteenth Congress (Geneva, May-June 2011); 2. Abridged Final Report with Resolutions of the Fourteenth Session of Regional Association II (Asia); 3. WMO Strategic Plan 2012-2015 (WMO-No. 1069); 4. WMO Operating Plan 2012-2015 (October 2011 version); 5. Strategic Plan for the Enhancement of National Meteorological and Hydrological Services in RA II 2009-2011; 6. RA II/MG-4/Doc. 4 – Review of the Implementation of the Strategic Plan for the Enhancement of NMHSs in RA II CONTENT OF DOCUMENT: Appendix for inclusion in the Final Report: Appendix A - Draft text for inclusion in the General Summary of the Report of RA II MG-4 Appendix for Information: Appendix B - Background Information for discussion

DRAFT TEXT FOR INCLUSION IN THE GENERAL SUMMARY OF THE RA II MG-4

6	Strategic Planning (WMO Strategic Plan; and Development of the RA II Strategic Operating Plan 2012-2015, including regional needs and priorities) (Agenda item 6)

WMO Strategic Plan 2012-2015

6.1	The Management Group recalled that the Sixteenth World Meteorological Congress (Cg-XVI: Geneva, May/June 2011) approved the WMO Strategic Plan 2012-2015 (WMO-No. 1069), that reflects its decisions and directions that will guide decision-making by the Organization and its constituent bodies during the period 2012-2015 to ensure focused and coordinated approaches across the Organization.  Within the five Strategic Thrusts and eight Expected Results, WMO as a whole has identified the following five priority areas:

- Global Framework for Climate Services (GFCS);

- Aviation meteorological services;

- Capacity Building for the developing and least developed countries;

- Implementation of the WMO Integrated Global Observing System (WIGOS) and WMO Information System (WIS); and

- Disaster Risk Reduction (DRR).

6.2	The Group recognized that the WMO-wide Operating Plan (2012-2015) will be composed of the following four parts: (Part 1) Introduction; (Part 2) WMO Programme Activities planned and funded for Implementation in 2012-2015 (formerly considered as the Secretariat Operating Plan 2012-2015); (Part 3) the Operating Plans of eight Technical Commissions; and (Part 4) the Operating Plans of six Regional Associations.

Development of RA II Strategic Operating Plan for 2012-2015

6.3	The MG-4 recalled that the fourteenth session of RA II (Tashkent, December 2008) adopted the RA II Strategic Plan (2009-2011) and identified the highest priority areas for Region II, as follows: (a) further improvement of the GTS and implementation of WIS/WIGOS; (b) sustainable capacity building including human resources development; (c) better climate services through the enhancement and operation of the RA II RCC network; (d) establishment of a Region-wide multi-hazard early warning system; (e) upgrading of service delivery capability, in particular for aeronautical and marine meteorological services; and (f) implementation of WMO Flood Forecasting Initiative, water resources assessment and regional exchange of hydrological data and information.  The Group considered that “the further improvement of the GTS and implementation of WIS/WIGOS” is still the highest priority in the Region for 2012-2015.

6.4	Taking due note of the overall improvement of weather, climate and hydrological services by Members of RA II during the period 2009-2011 identified from the preliminary analysis of the results of the 2010-2011 survey on the basic capability of NMHSs in RA II [see RA II/MG-4/Doc. 4], and the gaps and needs of Members of RA II, the Group considered that the above priority areas for Region II, identified by XIV-RA II are still valid and to be addressed with the highest priority in the Region for 2012-2015.

6.5	In addition, the Group considered that some region-specific priorities would be:

(a) 	………….;

(b) 	………….;

(c) 	………….;

(d) 	………….;

(e)	………….

6.6	The Management Group was pleased to note the progress on the development of RA II Strategic Operating Plan (SOP) 2012-2015 by the Task Team composed of Mr X. Xu (China); Dr B.Y. Lee (Hong Kong, China); Mr L.S. Lee (Hong Kong, China); Ms M. Jabbari (Islamic Republic of Iran); Mr N. Hasegawa (Japan); Dr W.-T. Yun (Republic of Korea); and Ms M. Nazarova (Uzbekistan).  The Group further noted that the president of RA II requested the Management Group, Working Groups and the Task Team members as well as the Secretariat to further work on the formulation of Regional Key Outcomes (RKOs) and finalize the RA II SOP 2012-2015 before the fourth session of the Management Group (MG-4). It also noted that a preliminary draft RA II Operating Plan (WIGOS/WIS part – Expected Result 4) was proposed to the WG-IOS/WIS by the Secretariat, with using a Template for Operating Plans of the Technical Commissions and Regional Associations prepared by the Strategic Planning Office of WMO.

6.7	The Group reviewed the draft RA II Operating Plan (WIGOS/WIS part – Expected Result 4) revised. Recognizing the need for identifying Regional Key Outcomes, concrete activities, responsibility and timeline for the Operating Plan, the Group noted that the already identified RA II's deliverables were incorporated into the table under Regional Key Outcomes.  Some new Regional Key Outcomes (e.g., RKO 4.24 – Migration to Table Driven Code Forms (TDCF)), Deliverables and Activities are proposed in line with Cg-XVI decisions and taking into account the work plans of subgroups on IOS and WIS agreed at the meeting of WG-IOS/WIS.

6.8	The Group welcomed the progress on the development of the Expected Result 4 part of the RA II OP (2012-2015) and agreed on the approach taken for identifying Regional Key Outcomes, concrete activities, responsibility and timeline for the RA II Operating Plan.  The Group further agreed that the same approach should be extended to the development of other Expected Results 1-3 and 5-8 to complete the RA II Operating Plan.  It suggested that the further streamlining be considered to focus on realistic and feasible deliverables to be implemented in 2012-2015, and ………………….

6.9	To undertake the above task, MG-4 decided the new composition of the Task Team on Strategic Planning as follows: Mr L.S. Lee (Hong Kong, China: Chair); ………… (Country); ………… (Country); ………… (Country); ………… (Country); and ………… (Country); and requested the Task Team to work on the further development of RA II (Strategic) Operating Plan.  MG-4 agreed that the Chairpersons of Working Groups be involved in the task team’s work and requested the Secretariat to facilitate and assist the work of the Task Team.

6.10	The MG-4 further agreed on the key milestones for completion of the RA II Operating Plan, as given below:

- Development and finalization of RA II Operating Plan (ERs 1-8) (by 15-Jun-2012);

- Adoption of RA II OP 2012-2015 (at MG-5 session in June/July 2012);

- Refining of RA II OP and development and adoption of RA II SOP 2013-2015 (at XV-RA II, Dec-2012).

____________

BACKGROUND INFORMATION

WMO Strategic Plan 2012-2015

1.	Sixteenth World Meteorological Congress (Cg-XVI: Geneva, May/June 2011) approved the WMO Strategic Plan 2012-2015 (WMO-No. 1069), that reflects its decisions and directions that will guide decision-making by the Organization and its constituent bodies during the period 2012-2015 to ensure focused and coordinated approaches across the Organization. Starting with the three Global Societal Needs (GSNs), the Strategic Plan defines five Organization-wide Strategic Thrusts (STs) and eight Expected Results (ERs) as given below.

Table 1: Schematic representation of the structure of WMO Strategic Plan 2012-2015

2.	Within the five Strategic Thrusts and eight Expected Results, WMO as a whole has identified the following five priority areas that have significant contribution to the achievement of the expected results:

- Global Framework for Climate Services (GFCS);

- Aviation meteorological services;

- Capacity Building for the developing and least developed countries;

- Implementation of the WMO Integrated Global Observing System (WIGOS) and WMO Information System (WIS); and

- Disaster Risk Reduction (DRR).

3.	Cg-XVI noted that the draft WMO-wide Operating Plan (2012–2015) provided details on key outcomes, deliverables and activities, which have been used to guide resource estimates and allocations as presented in the Secretary-General’s Budget Proposal for the sixteenth financial period.  Congress requested the Secretary-General to finalize the Plan taking into account all the decisions of the Sixteenth Congress and requested the Executive Council to further improve the Operating Plan consistent with the guidance provided by Congress regarding the future strategic and operational planning.

4.	The WMO-wide Operating Plan (2012-2015) will be composed of the following four parts: (Part 1) Introduction; (Part 2) WMO Programme Activities planned and funded for Implementation in 2012-2015 (formerly considered as the Secretariat Operating Plan 2012-2015); (Part 3) the Operating Plans of eight Technical Commissions; and (Part 4) the Operating Plans of six Regional Associations.  Specific elements of the Operating Plan (OP) are:

- Expected Results and the associated Key Outcomes and Key Performance Indicators to measure the progress in the achievement of Expected Results;

- The programme Activities planned for implementation and the associated Deliverables to achieve Expected Results;

- Baselines and Performance Targets for each Key Performance Indicator to measure the progress towards achieving the Expected Results; and

- Mechanisms for monitoring and evaluating the implementation of the Strategic Plan.

A template, as given in Annex I, has been prepared by the WMO Secretariat to facilitate the work of Technical Commissions and Regional Associations to develop and finalize their Operating Plans.

Development of RA II Strategic Operating Plan for 2012-2015

Strategic Plan for the Enhancement of NMHSs in RA II (Asia) (2009-2011)

5.	A draft Strategic Plan for the Enhancement of NMHSs in RA II (2009–2011) was developed with expert services by Hong Kong, China, and in consultation with Members and with guidance by the Advisory Working Group. The fourteenth session of RA II (Tashkent, December 2008) commended the unique approach of RA II that the Strategic Plan has been developed on the basis of the survey results for the period 2005-2008, by analyzing the likely trends, developments, evolving needs and deficiencies of the Region, to identify a set of deliverables. These deliverables are action-oriented and categorized under Regional Expected Results in accordance with WMO’s set of Expected Results.  The Association adopted the RA II Strategic Plan (2009-2011) and authorized the president to make the necessary adjustments to the Regional Strategic Plan in consultation with the RA II Management Group and working groups in the light of the discussions of the Association at this session, and develop a related Action Plan in consultation with Members.

6.	XIV-RA II identified the highest priority areas for Region II, as follows:

(a) 	Further improvement of the GTS and implementation of WIS/WIGOS;

(b) 	Sustainable capacity building including human resources development;

(c) 	Better climate services through the enhancement and operation of the RA II RCC network;

(d) 	Establishment of a region-wide multi-hazard early warning system;

(e) 	Upgrading of service delivery capability, in particular for aeronautical and marine meteorological services; and

(f) 	Implementation of WMO Flood Forecasting Initiative, water resources assessment and regional exchange of hydrological data and information.

RA II Strategic Operating Plan for 2012-2015

7.	The first session of the RA II Management Group (MG-1: June 2009) agreed to prioritize the 201 deliverables when considering the Strategic Action Plan by selecting 100-120 realistic deliverables for implementation and monitoring.  The MG-1 further agreed that a task team on Strategic Plan be established to work on: identification of priorities among 201 deliverables; further development of the Action Plan by proposing concrete action for each corresponding priority deliverable; developing new survey questionnaires to monitor the implementation of the Strategic Plan and Action Plan; and finalization of the complete RA II Strategic Plan.

8.	The Task Team composed of Mr X. Xu (China); Dr B.Y. Lee (Hong Kong, China); Mr L.S. Lee (Hong Kong, China); Ms M. Jabbari (Islamic Republic of Iran); Mr N. Hasegawa (Japan); Dr W.-T. Yun (Republic of Korea); and Ms M. Nazarova (Uzbekistan) identified 110 priority deliverables under 32 Regional Expected Results, which was submitted to the second session of the Management Group (MG-2: Geneva, June 2010).

9.	The MG-2, in referring to the RA V approach to develop its Strategic Operating Plan (SOP) for 2012-2015, by mapping the deliverables under Regional Expected Results in the RA V Strategic Plan 2010-2011 into the new five Strategic Thrusts and eight Expected Results of the draft WMO Strategic Plan 2012-2015, agreed to take a similar approach for developing the RA II Strategic Action Plan for 2012-2015.  It also agreed that a proposal for the methodology and process to move towards RA II SOP 2012-2015 should be prepared and discussed during the Fifth Technical Conference.

10.	The Fifth Technical Conference (Daegu, Republic of Korea, 29 November - 3 December 2010) noted that the Task Team identified 100 priority deliverables, which were mapped into the eight Expected Results of the draft WMO Strategic Plan 2012-2015, for the RA II Action Plan.  The Conference recognized that the draft Key Performance Indicators/Targets (KPIs/KPTs) were updated, and additional Activities for deliverables were proposed, such as training courses, workshops, mission visits and exchange of know-how among Members.

11.	The Technical Conference agreed that, with reference to the WMO framework for results-based strategic planning for 2012-2015, Regional Key Outcomes (RKOs) should be formulated based on the RA II Expected Results to complete the Action Plan; and considered that the Action Plan should be called “Strategic Operating Plan (SOP)” for the period 2012-2015, in alignment with the period of the next WMO Strategic Plan (2012-2015).  As an example, the WIGOS/WIS-related part (Expected Result 4) of the latest version of RA II SOP 2012-2015 is given in Annex II.

Adjustment to the RA II SOP to align with Cg-XVI decisions

12.	The third session of the Management Group (MG-3: May 2011) extended its appreciation to the Task Team on Strategic Planning headed by Dr B.Y. Lee and Mr L.S. Lee for their significant work in the development of RA II Strategic Operating Plan (SOP), and expressed the views that the proposed activities of RA II SOP should be action-oriented, by which means the implementation progress could be monitored and problems identified, and also that there is a need for support to the Members who have difficulties in achieving set goals.  The Task Team and other RA II WG experts were invited to identify areas of region-specific problems and requirements (e.g., melting glacier in Nepal), which should be reflected in the WMO Strategic and Operating Plans.

13.	At the MG-3 session, the president requested the MG, WGs and the Task Team members as well as the Secretariat to further work on the formulation of Regional Key Outcomes (RKOs) and finalize the RA II SOP 2012-2015 before the next Management Group session (MG-4: planed for 29 February - 2 March 2012).

14.	In this respect, a preliminary draft RA II Operating Plan (WIGOS/WIS part – Expected Result 4), by using the template given in Annex I, was proposed by the Secretariat to the first meeting of the RA II WG-IOS/WIS (Seoul, Republic of Korea, 30 November - 7 December 2011) for review and further inputs.  The Chairperson and coordinators of WG-IOS/WIS and its subgroups were requested to contribute to the further development and finalization of the RA II Operating Plan.

15.	A draft RA II Operating Plan (WIGOS/WIS part - Expected Result 4), revised in light of the work plans for Subgroups on IOS and WIS is given in Annex III, for review by MG-4.  The already identified RA II's deliverables were incorporated into the table under Regional Key Outcomes.  Some new Regional Key Outcomes (e.g., RKO 4.24 – Migration to Table Driven Code Forms (TDCF)), Deliverables and Activities are proposed in line with Cg-XVI decisions.

16.	The following steps were taken to prepare the draft OP (ER 4 part):

(1)	Identified deliverables were grouped into several groups and a Regional Key Outcome was proposed for collective deliverables (or a group of deliverables);

(2)	One or two (Regional) Key Performance Indicators (KPIs) were considered for a Regional Key Outcome (RKO);

(3)	Concrete activities were proposed based on the draft SOP (summary of activities) and in light of WG-IOS/WIS discussions;

(4)	Relevant (or Responsible) Programme, Technical Commission(s) and responsibility in RA II as well as timeline were tentatively proposed;

(5)	Target column kept the original wording as in Draft SOP 2012-2015.

16.	The key milestones related to RA II Operating Plan are proposed to the next session of the Management Group (MG-4) for approval, as given below:

- Finalization of Draft OP (ER 4 part) by WG-IOS and Task Team on SOP (by 29-Feb-2012)

- Approval by MG-4 on the approach and similar work to be extended to ERs 1-8  (29-Feb-2012);

- Development and finalization of RA II Operating Plan (ERs 1-8) (by 15-Jun-2012);

- Adoption of RA II OP (at MG-5 session in June/July 2012);

- Refining of RA II OP and development and adoption of RA II SOP (at XV-RA II, Dec-2012).

___________

ANNEX I

Template for Operating Plan

(Sample of CIMO)

# ANNEX II

# Draft RA II Strategic Operating Plan 2012-2015

Strategic Thrust 2 – Advancing scientific research and application as well as development and implementation of technology

Expected Result 4 – Enhanced capabilities of Members to access, develop, implement and use integrated and interoperable surface-based and space-based systems for weather, climate and hydrological observations, as well as related environmental observations, based on world standards set by WMO

| SOP Item No. | SP Item No. | Deliverable | Key Performance Indicator/Target | Summary of activities |
| --- | --- | --- | --- | --- |
| 4.1 | 4.3 | Regular maintenance and calibration of observation instruments | Percentage of Members having a regular programme for maintenance and calibration of observation instruments, to reach 75% or above. | (a) Include item starting from the next survey among Members; (b) Implementation of the Pilot Project to Enhance the Availability and Quality Management Support for NMHSs in Surface, Climate and Upper-air Observations |
| 4.2 | 4.4 | Reliability of quality management routines and procedures of weather observations | Percentage of Members implementing reliability measures on their quality management routines and procedures of weather observations, to reach 75% or above. | (a) Include item starting from the next survey among Members; (b) Implementation of the Pilot Project to Enhance the Availability and Quality Management Support for NMHSs in Surface, Climate and Upper-air Observations |
| 4.3 | 4.5 | Real-time delivery of measured observations at remote stations | Percentage of Members implementing real-time relay of measured observations from remote stations, to reach 25% or above. | (a) Include item starting from the next survey among Members; (b) Implementation of the Pilot Project to Enhance the Availability and Quality Management Support for NMHSs in Surface, Climate and Upper-air Observations |
| 4.4 | 4.6 | Enhanced temporal and spatial coverage of weather measurements | Percentage of Members expanding their weather measurements, both temporally and spatially, to reach 25% or above. | Include item starting from the next survey among Members |
| 4.5 | 4.7 | Availability of qualified maintenance technicians in NMHSs | Percentage of Members having qualified maintenance technicians in their service, to reach 25% or above. | (a) Include item starting from the next survey among Members; (b) Implementation of the Pilot Project to Enhance the Availability and Quality Management Support for NMHSs in Surface, Climate and Upper-air Observations |
| 4.6 | 4.9 | Maintenance/enhancement of operational Regional Basic Synoptic Network (RBSN) surface stations in the Region | Number of RBSN surface stations implemented and operational, to reach 1 420 (or +0.5%) or above. [2008 level: 1413] | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how |
| 4.7 | 4.10 | Maintenance/enhancement of automatic weather stations (AWSs) in the Region | Number of AWSs implemented, to reach 4 300 (or +1.9%) or above. [2008 level: 4221] | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how |
| 4.8 | 4.11 | Maintenance/enhancement of rainfall stations in the Region | Number of rainfall stations implemented, to reach 39 000 (or +2.2%) or above. [2008 level: 38 173] | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how |

| 4.9 | 4.12 | Maintenance/enhancement of operational RBSN upper-air stations in the Region | Number of RBSN upper-air stations implemented and operational, to be maintained at 304 (no change) or above. [2008 level: 304] | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how |
| --- | --- | --- | --- | --- |
| 4.10 | 4.13 | Maintenance/enhancement of operational Regional Basic Climatological Network (RBCN) stations in the Region | Number of RBCN stations implemented and operational, to reach 765(or +0.1%) or above. [2008 level: 764] | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how |
| 4.11 | 4.14 | Maintenance/enhancement of operational GCOS surface stations in the Region | Number of GCOS surface stations implemented and operational, to be maintained at 294 (no change) or above. [2008 level: 294] | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how |
| 4.12 | 4.15 | Maintenance/enhancement of operational GCOS upper-air stations in the Region | Number of GCOS upper-air stations implemented and operational, to be maintained at 39 (no change) or above. [2008 level: 39] | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how |
| 4.13 | 4.16 | Maintenance/enhancement of operational weather radar stations in the Region | Number of weather radar stations implemented and operational, to reach 315 (or +1.0%) or above. [2008 level: 312] | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how |
| 4.14 | 4.17 | Maintenance/enhancement of ground station(s) in the Region to receive high-resolution images from geostationary meteorological satellites | Percentage of Members operating such ground station(s), to be maintained at 69% (no change) or above. [2008 level: 69%] | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how |
| 4.15 | 4.20 | Maintenance/enhancement of Global Atmospheric Watch (GAW) stations in the Region | Number of GAW stations implemented, to be maintained at 34 (no change) or above. [2008 level: 34] | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how |
| 4.16 | 4.21 | Maintenance/enhancement of operational tide gauges in the Region | Number of tide gauges implemented, to reach 235 (or +0.9%) or above. [2008 level: 233] | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how |
| 4.17 | 4.23 | Maintaining/recruiting more voluntary observing ships (VOS) for meteorological, oceanographic and/or upper-air observations | Number of VOSs operating in the Region (to be determined in the next survey). | Include item starting from the next survey among Members |
| 4.18 | 4.27 | Ensuring the accuracy of the instruments they use | (i) Percentage of Members using the service of RICs (Regional Instrument Centre), to reach 50% or above; (ii) Percentage of Members using the service of national standards laboratory / institution, to reach 50% or above. | (i) and (ii): Include items starting from the next survey among Members |
| 4.19 | 4.30 | Operation of AWSs on green technology (including use of renewable energy such as solar and wind power), for sustainable development | (i) Percentage of Members operating AWSs on green technology, to reach 25% or above; (ii) Total number of AWSs in the Region operating on green technology, to be determined in the next survey. | (i) and (ii): (a) Include items starting from the next survey among Members; (b) organize training course for Members |

| 4.20 | 5.1 | Migration from low-speed Category I (below 9.6 kbps) to higher-speed Category II (9.6 to 64 kbps) and III (over 64 kbps) GTS connections to the Regional Telecommunication Hubs (RTHs) | Percentage of Members who have migrated to Category II/III GTS connections, to ensure a continuing overall increasing trend. | (a) Continue monitoring; (b) encourage and facilitate exchange and training on relevant know-how; (c) render assistance to NMHS Nepal in respect of its very low-speed 50 bps circuit |
| --- | --- | --- | --- | --- |
| 4.21 | 5.2 | Connection to the Internet by broadband | A high percentage of Members connected to Internet by broadband, to reach 91% (or +1 Member) or above. [2008 level: 88%] | Continue monitoring |
| 4.22 | 5.3 | Connection to the Internet by telephone dial-up | A lower percentage of Members connected to Internet by telephone dial-up, to be kept at 35% (or -2 Members) or below. [2008 level: 41%] | Continue monitoring |
| 4.23 | 5.4 | Shift from the costly radiofacsimile broadcast of meteorological and oceanographic information in chart form to more economical modern communication means | Number of marine met service providers who are still running radiofacsimile broadcast, to be kept at 25% or below. | (a) Include item starting from the next survey among Members; (b) encourage and facilitate exchange on relevant know-how; (c) render assistance if needed to Members who wish to involve the operators and users in modernizing the service |
| 4.24 | 5.5 | Implementation of the WMO Information System (WIS) | (i) Percentage of Members successfully implementing WIS, to reach 50% or above; (ii) Percentage of Members benefiting from WIS in terms of data and products exchange, to reach 50% or above. | (i) and (ii) - Include items starting from the next survey among Members |

____________

ANNEX III

DRAFT RA II Operating Plan 2012-2015

Expected Results 4

(see Draft RA II OP WIGOS-WIS (ER4).ver2012.02.##.xls)