LOGOS OF OTHER SPONSORS TO BE ADDED

Roadmap for the Design of a Caribbean Regional Programme in Multi-Hazard Early Warning Systems (MHEWS) with National Capacity Development (as of 06/10/2010)

I. INTRODUCTION

In the Caribbean region, between 1980 and 2007, nearly 98% of disasters, 99% of casualties and 99% of economic losses related to natural hazards were caused by recurrent meteorological-, hydrological- and climate-related events such as tropical cyclones and storm surges, floods, droughts, and extreme temperature (EM-DAT).

- The “Training and Coordination Workshop on Multi-Hazard Early Warning Systems with Focus on Institutional Partnerships and Coordination,” (MHEWS Workshop, see Reference Section) was convened  by the World Meteorological Organization (WMO) with the support of the United States National Oceanographic and Atmospheric Administration - National Weather Service (NOAA-NWS), the United Nations International Strategy for Disaster Risk Reduction (UN-ISDR), United Nations Development Programme (UNDP), the World Bank, International Federation of the Red Cross  (IFRC), El Centro de Coordinación para la Prevención de los Desastres Naturales en América Central (CEPREDENAC), and the Caribbean Disaster Emergency Management Agency (CDEMA) on 22-25 March 2010 in San Jose, Costa Rica. Participants included directors and high-level representatives from the National Meteorological and Hydrological Services (NMHS) and National Disaster Risk Management (DRM) Agencies of 36 Members from WMO Regional Association IV (North and Central America and the Caribbean), eight regional agencies and centers, six UN and international organizations, and representatives from eight development and bi-lateral donors.

Building on the outcomes of the MHEWS Workshop and follow up consultations, a road map for the design of a Caribbean regional programme in MHEWS with national capacity development is outlined in this document.

II. OVERALL OBJECTIVES

A Caribbean regional programme in MHEWS (with a 6-8 year vision) will be developed together with phase I project (with 2-year implementation cycle) (see Table 1):

- To strengthen national and regional institutional capacities and cooperation among the NMHS and DRM agencies through development/strengthening of components of early warning systems with a multi-hazard approach for hydro-meteorological hazards;

- To enhance coordination among hydro-meteorological warning systems (building on the existing regional coordination for tropical cyclones) other hazards (e.g., tsunamis).

The development of programme is based on a phased approach engaging consultations with countries/territories and the regional mechanisms and agencies and other stakeholder including:

- 2010 - early 2011:Development of programmatic and technical aspects based on extensive consultations with the stakeholders in the countries/territories, regional agencies and institutions, and other stakeholders;

- 2011: Identification of institutional partnerships, resource mobilization strategy and development of implementation, monitoring and evaluation processes founded in the regional processes in the Caribbean; and

- 2011-2012: Launch of the Programme and phase I project upon confirmation of available resources and funding.

- 2012 – on wards: Implementation and systematic coordination for monitoring progress and evaluation and expansion planning..

III. SCOPE (ISSUES AND REGIONAL COVERAGE)

The scope of a coordinated Caribbean MHEWS regional programme with national development component, including:

- Strengthening of disaster risk management and emergency preparedness coordination frameworks and governance as linked to hydrometeorological EWS;

- Strengthening,  regional harmonization, and interoperability of the observing networks and data sharing as linked to these EWS;

- Capacity development in risk assessment and modeling for hydro-meteorological hazards to support EWS and emergency management with considerations for risks associated with climate variability and change;

- Strengthening of operational forecasting capacities for hydro-meteorological and marine-related hazards and stronger coordination with the tsunami warning system;

- Strengthening of warning dissemination mechanisms, service delivery, operational cooperation  and quality management systems engaging NMHS and DRM agencies;

- Building/improving national watch and warning systems, and exploring coordination in the region;

- Strengthening coordination and realize opportunities for interoperability of crosscutting activities across national and regional agencies, particularly noting the linkages of the hydrometeorological warning system with other such as tsunami;

- Educational programmes in hydrometeorological hazards and warning systems targeted at the public and officials.

The design of this programme will consider countries and territories (islands) of the Caribbean with expressed interest: Antigua and Barbuda, the Bahamas, Barbados, Belize, Bermudas, the British Caribbean Territories, Cuba, Dominica, the Dominican Republic, the French West Indies, Grenada, Guyana, Haiti, Jamaica, the Netherland Antilles and Aruba, Saint Kitts and Nevis, Saint Lucia, Saint Vincent and the Grenadines, Suriname, and Trinidad and Tobago.

IV. KEY STAKEHOLDERS

The design of the programme will engage extensive consultations with and input from various national, regional and international stakeholders:

National: NMHS and DRM Agencies of the beneficiary countries. Other EWS national stakeholders will be identified during the consultations.

Regional: Regional centers and agencies of the Caribbean Community (CARICOM) such as the Caribbean Disaster Emergency Management Agency (CDEMA), the Caribbean Meteorological Organization (CMO) and its technical and training branch, the Caribbean Institute of Meteorology and Hydrology (CIMH); WMO Regional association IV Management Group and its DRR Task Team, WMO RA IV Hurricane Committee, WMO Regional Specialized Meteorological Center (RSMC) – Miami Hurricane Center, and regional agencies such as the Organization of American State (OAS), the Association of the Caribbean States (ACS), the Eastern Caribbean Donor Group, Caribbean Development Bank (CDB) and the Inter-American Development Bank (IDB). Other regional partners will be identified during the consultations.

International and donors: United Nations and other international agencies such as the UN-ISDR, UNDP, IFRC, the development banks and donors including, the World Bank, USAID/OFDA, the Canadian International Development Agency (CIDA), the Finnish Ministry of Foreign Affairs, the Spanish International Cooperation Agency and the Japan International Cooperation Agency (JICA). Other international partners will be identified during the consultations.

| Table 1: Roadmap for the Design of the programmatic and technical aspects Caribbean Regional Programme in MHEWS with National Capacity Development in 2010 |
| --- |
| CONSULTATIONS AND DELIVERABLES | ORGANIZERS/SPONSORS | EXPECTED OUTCOMES | DATE & VENUE |
| 1. Training and Coordination Workshop on Multi-Hazard Early Warning Systems with Focus on Institutional Partnerships and Coordination | WMO with NOAA, ISDR, CDEMA, CEPREDENAC, UNDP, World Bank, IFRC, NMHS and DRM of Costa Rica | Identified and prioritized concrete areas for development and cooperation at national and (sub) regional levels in MHEWS | 22 – 26 March 2010, San Jose Costa Rica |
| 2. Consultants’ missions in the region | WMO and UNDP | Identification and confirmation of gaps and needs in MHEWS; Identification of national, regional and international stakeholders; Identification of priorities for design of the programme and phase I project. | 1 July – 15 September 2010 |
| 3. Consultation at the 2nd Meeting of the Work Programme Development and Review Sub-Committee of the CDEMA Technical Advisory Committee | CDEMA | Introduction of the road map and feedback. | 21 July 2010, Barbados |
| 4. Consultation at the Sixth (6th) Meeting of the Comprehensive Disaster Management Coordination and Harmonisation Council (CDM CHC) and 2010 Programming Consultation on Comprehensive Disaster Management (CDM) | CDEMA | Introduction of the road map and feedback for incorporation of the Caribbean MHEWS Programme in CDM Programming. | 19 – 20 August 2010, Barbados |
| 5. 18th meeting of the Committee on Disaster Risk Reduction | Association of Caribbean State (ACS) |  | 9 – 10 Sept, 2010 Santo Domingo, DR |
| 6. Technical Workshop for the Development of Caribbean Regional Programme in Multi-Hazard EWS (MHEWS) | WMO, RA IV DRR TT with CMO/CIMH, CDEMA, UNDP, World Bank, NOAA, Finish meteorological Institute and Ministry of Foreign Affairs, NMHS and DRM agencies of Barbados Other potential sponsors: ISDR, ACS, , others (TBD) | Development of priorities for Caribbean MHEWS Programme; Prioritization of activities for Phase I project and development of a detailed project implementation plan. | 2-5-November 2010 Barbados |
| 7. Consultation with Government Ministers and Directors of NMHS in CMO Member States at the 50th session of the Caribbean Meteorological Council | CMO | Feedback on the first draft of the Caribbean Regional MHEWS programme and phase I project | 19 – 22 November 2010 Cayman Island |
| 8. Consultations during the Conference of the Directors of the Ibero-American Hydrometeorological Services | Iberto-American Cooperation | Feedback on the first draft of the Caribbean Regional MHEWS programme and phase I project | November, 2010 Chile |
| 9. 1/2-day High-level special session for finalisation of the Caribbean Regional Cooperation MHEWS Programme (TBC) | WMO and its RA IV Management Committee with CDEMA, CMO/ CIMH, UNDP, NMHS and DRM of Jamaica Other potential sponsors: ISDR, World Bank, ACS, NOAA, Finland Meteorological Institute and Ministry of Foreign Affairs, others (TBD) | Revised draft of the Caribbean MHEWS programme and phase I project | 6 December 2010 Montego Bay, Jamaica |
| 10. Presentation of aspects of the programme Seventh (7th) Meeting of CDM CHC | CDEMA | Presentation of the Draft of the Caribbean MHEWS Programme and Phase I Project in CDM Programming | 6 – 9 December 2010 Montego Bay, Jamaica |
| 11. Draft of the Caribbean MHEWS programme + phase 1 project delivered to donors and other stakeholders |  |  | 23 December 2010 |

VI. CONSULTATIONS

Building on the outcomes of the MHEWS Workshop, a consultant was hired by WMO to work to compile and review various assessments and projects related to EWS in the region and to carry out follow-up missions to further explore the gaps and needs. A preliminary draft of the programme and Phase I Project will be developed during a technical workshop in Barbados engaging meteorological, hydrological and DRM experts from the region and other countries of good practices as well as the WMO RA IV DRR Task Team (see Table 1, Item 6). The first draft will be presented for further consultations during workshops and meeting outlined in Table 1 with Directors of DRM agencies (Items 3, 4, 5 and 11), and with Directors of NMHS (Item 8 and 9). The revised draft will be presented to CDEMA Comprehensive Disaster Management Coordination and Harmonisation Council in Jamaica on 6-9 December 2010, for their consideration and endorsement (Item 11).

VII. RESOURCE MOBILIZATION

In coordination with the development banks and bilateral donors, a resource mobilization strategy is being developed to ensure systematic and coordinated funding for the implementation of the programme and Phase I project. Potential funding agencies will be invited to all technical consultations and meetings (Items 6 and 10) for drafting of the programme and project document.

VIII. REFERENCES

- EM-DAT is the International Disaster Database of the Center for Research on the Epidemiology of Disasters - Université de Louvain – Belgium - www.em-dat.net

- MHEWS Workshop website:  http://www.wmo.int/pages/prog/drr/events/MHEWSCostaRica/index_en.html

For more information contact:

Dr Maryam Golnaraghi

Chief , Disaster Risk Reduction Programme

World Meteorological Organization

Tel: +41.22.730.8006; Fax: +41.22.730.8128

Email: mglonaraghi@wmo.int