# WORKPLAN:  Focus Area: Measurement, Monitoring and Infosystems

| Activities | Actions | AWG Member | Outputs | Resources | Milestones | Linkages |
| --- | --- | --- | --- | --- | --- | --- |
| WHOS: development and implementation of WHOS phase II, offering standardized web services, data hosting, archival, data rescue and dissemination, and relevant training, based upon data policies and adopted standards, and provide support to the HydroHub functions related to WHOS; | Establish user requirement (data providers and data consumers), Definition of WHOS architecture Implementation Plan Development Develop new Statement Of Guidance (SOG) and requirements ----------------- TBD once plan approved: Pilot Training Communication to Members | S. Pecora T. Kanyike | WHOS Implementation Plan Technical documents SOG and contribution to RRR | WHOS focal points in each RWGH, NHSs HydroHub (F. Teichert) | User requirements defined – Sept 2017 Definition of WHOS architecture – Dec 2017 Draft Plan presented to EC-70 - June 2018 SOG Q1 2018 | RAs, Global Centers, other observations and information systems, CBS, |
| GHSF (newly called HydroHub, including WHYCOS): serve as a member of the GHSF advisory council; provide technical guidance on WHYCOS activities to the HydroHub; support the hydrological services information platform and liaise with AWG members responsible for WHOS, Project X and Innovation and new data; | Populate and organize meetings the Advisory Council and the InnoC Help implement the approved HydroHub structure and activities to ensure it is fully operational in 2018. Serve as Chair and members of GHSF Advisory Council Help develop the new WHYCOS strategy (including funding and communication), help existing and new HYCOS projects, including integrating them into HydroHub ------------- Review, revise and add information needed to transform INFOHYDRO into HISP. Recruit organisations to provide help via the Help Desk Ensure adequate links with other CHy (and wider) activities as appropriate – including WHOS, Project X and Innovation Ensure HydroHub links with RA priorities and RAWG Hydrology. Promote the development and use of free and open source software for hydrology (such as MCH). | H.Lins and H.Dixon (both in the Advisroy Council) | Fully operation HydroHub in 2018. Sustainable operational & funding model established for HydroHub beyond 2018. Continued implementation of existing and new HYCOS projects (Senegal and IGAD transitional phase). Conversion of INFOHYDRO into HISP. Active and fit-for-purpose Help Desk. | Hydrohub (Sophia Sandström for preparing baseline docs and day to day activities, Iwona for HISP and HelpDesk) OPACHE AWG members Regional HAs and relevant WGs | AC populated by June 2017; 1st AC meeting – before Sep 2017 -WHYCOS draft strategy June 2017, final August 2017 Milestones to be agreed by Advisory Council Dec 2018: Fully operation HydroHub June 2018: Sustainable operational & funding model established | World Bank / GFDRR UNESCO IHP (including HOPE Initiative) RAs CBS WMO Secretariat |
| Project X: Chair the Management Committee, finalize and test basic uncertainty analysis (UA) software, develop UA capacities for ADCP, including standardization of computation of discharge, discharge estimation via various techniques, and produce guidance documentation for calibration and performance testing, design of “regattas” for intercomparison of flow measurement instruments and techniques, ultimately supporting quantification of discharge uncertainties (with error bands at stated confidence levels); | Update Management group Membership Conduct meetings with committee via phone/internet/face to face Finalize the first module of UADAT Comparison Test ADCP software Compare point meter UA softwares Support HydroHub goal of free and open software for hydrology UA methods. Interface with HMEI and ISO to promote vendor and NHS adoption of best UA practices | J.Fulford (Chair) | Finalize contract with Qualisyst (support: Claudio) work plan for next period. At least 6 per year (one face-to-face a year) Hereafter: depending on workplan to be adopted Software distribution Field Discharge Survey 2018 Guidance conducting ADCP regattas for QA and recommendations Repository of Instrument test reports Guidance for ADCP & point meter UA standards Guidance for UA methods for discharge ratings Technical report of developing rating curves with various field conditions Free, Open and easy Software for developing index rating | WMO secretariat (Dom, Tommaso) OPACHE members ISO rep HMEI rep IAHS rep IAHR rep RAII WGHS HydroHub 1 f2f meeting in 2017 | April 2017 AWG Review, revise and adopt work plan for next period: July 2017 Hereafter: depending on Work plan Revise previous survey & conduct survey Request updating of NHSs Q standards Regatta guidance doc completed/finalized ADCP dataset(s) to conduct software comparisons collected Other meter discharge datasets to conduct UA schemes/software comparisons collected Datasets collected & selected for comparison of rating UA schemes. Conduct ADCP UA software tests w/datasets Conduct other meter UA tests w/ datasets Conduct comparison of rating UA schemes with datasets | Innovation Hub Manufacturers (HMEI) Others as appropriate |
| QMF-H: continue the development of relevant QMF-H guidance material, including training support material; deliver QMS training and guidance material to NHSs at all levels (measurements, monitoring, forecasting and related products) and promote adoption and appropriate implementation of QMS in NHSs; | develop and implement QMS training strategy Support to implementation of QMS possibly through the CoP? | J. Danhelka A member of the QMS WG N.Tuteja (forecasting) | Training support materials Application results of QMS in RAs | OPACHE C.Caponi Secretariat support for publishing training materials including paper and online/video QMS Working group | Concept of the training strategy (AWG-2) Training materials gradually developed | NHSs RAs |
| Networks: further develop guidance on hydrometric network optimization and prioritization of stations taking into account all users’ needs, including the modelling community; update recommendation on station density; also consider the possibility of promoting the concept of hydrological “heritage” stations; | Establish expert task team taking into account RAs experts to support the initiative; Collect case studies of existing hydrological networks developments Review of the existing WMO recommendation on station density, and network optimization principle Propose new guidance material | Y. Jianqing | Task team established Report on case study outline of the guidance The guidance. | OPACHE RAs WGH Expert Task Team WMO Secretariat (lead Iwona) | List of expert task team–June 2017 Report on case study– September 2018 outline of the guidance - September 2019 the guidance – December 2020 | UNESCO IHP ISO-TC113, CEN RAs WMO Secretariat Research institutes ? |
| Innovation and new data: advise on calls for proposals and assess existing hardware and software issued by the Global Innovation Hub and other developers, with a view to their operational use in NHSs, including non-traditional data sources such as citizen observations, and remote sensing technologies including satellites. In this regard consider new developments and applications with respect to big data. | Serve as member of GHSF Innovation Hub Committee. Help design and implement innovation calls. Promote the update of Innovation Hub outputs within NMHSs. Establish links with other similar initiatives outside of WMO Develop links with the private sector regarding monitoring and data technologies | H.Lins J.Fulford (both in the InnoC) | Innovation Hub calls successfully designed and implemented. Some of the outputs of the Innovation Hub applied within NMHSs. | OPACHE Regional HAs and relevant WGs (for input on priorities) HydroHub (Florian) | Milestone to be agreed by Innovation Hub Committee. Innovation workshop by Dec 2017 Innovation call prepared by Dec 2017, depending on opportunities and funding | World Bank / GFDRR UNESCO IHP RAs CBS, CIMO WMO Secretariat IAHS+IAHR ISO Private Sector Others as appropriate |