CBS Extraordinary session 2002

# Cairns, Australia, 4 to 10 December 2002

# ACTION SHEET

| Para. | Subject | Action required | Responsible | Deadline | Status/remarks |
| --- | --- | --- | --- | --- | --- |
| Rec 6.1/1 6.1/x 6.2/1 6.2/x 6.3/1 9/1 10.2/1 | Approval of recommendations | To prepare EC document on the report of CBS-Ext.(02) with recommendations | D/WWW-B | February 2003 | done |
| 3.4 | Innovative Collaboration | (a) The OPAGs to consider the report of the Rapporteur on Innovative Collaboration and to identify the subjects that are relevant to their respective programme areas and to take benefit of the relevant findings. (b) The Secretariat to develop a project for an Internet Newsgroup, and to submit it to the Management Group for consideration and possible follow-up action | Chairs of the OPAG D/WWW-B | May 2003 May 2003 | Consultant (March 03) |
| 4.5 (PINK4(1)) | Future WMO Information System | The Secretary-General to submit the outcome of CBS work to the Executive Council Advisory Group on the Role and Operation of NMHSs. | C/TEM | Feb 2003 | Draft available; to be sent to chair of EC group; contribute para to EC/R&Ops report to Cg thru D/PLA and develop Add to Doc 3.1.2 |
| 4.3 (PINK 4(2)) | Total quality management | The Secretary-General to make information material on ISO 9000 and related quality management systems available to Members. | D/WWW-B | May 2003 |  |
| 4-4 to 4-15 (PINK 4(2)) |  | To inform Cg, EC and the bureau of the views of CBS on the issue | D/WWW-B | February 2003 | Done; include in Cg Doc 3.1.0 |
| 6.1.11 | Plans for multi-purpose geostationary and polar-orbiting satellites | To suggest that the Republic of Korea should approach CGMS for appropriate consultations. | SSO/SAT | February 2003 |  |
| 6.1.19 | Requirement for four LEO satellites | To update the Manual on GOS | AC/OSY | ASAP |  |
| 6.1.20 | Redesign of the GOS | (a) To develop as soon as possible an infrastructure and implementation plan including a detailed time schedule within WMO to assure full utilisation of the evolving GOS; (b) To support a focused funded activity for the study of observing system design; (c) To continue updating the database of user requirements and observing system capabilities and include user reviewed R&D expected performances; (d) To continue the RRR process in application areas already started and expand into new areas relevant to missing disciplines; (e) To facilitate organisation of the next Workshop on Impact of Various Observing Systems on NWP during the first quarter of 2004; (f) To pursue early implementation (with particular attention to the developing countries). | Chair of the OPAG-IOS AC/OSY, SSO/SAT | (a) , (b), (c), (d), (f) and (e) ongoing during 2003 |  |
| 6.1.26 | OSEs and OSSEs | Leading NWP centres and relevant scientific groups to continue their efforts in OSEs and OSSEs. | Chair of the OPAG-IOS | Ongoing |  |
| 6.1.30 | Satellite system utilisation and products | To implement the recommendations and strategies as contained in the Status of the Availability and Use of Satellite Data and Products by WMO Members, (WMO/TD-No. 1119, SAT-30) | Chair of the OPAG-IOS SSO/SAT | Ongoing |  |
| 6.1.32 | Requirements and representation of data from AWSs | To implement the recommendations of the Expert Team on Requirements for Data from Automatic Weather Stations | Chair of the OPAG-IOS AC/OSY | Ongoing | Also involving OPAG-ISS and CIMO |
| 6.1.33 | Manual on the GOS | The Secretary-General to publish the revised document at the earliest practical time | AC/OSY | I Quarter 2003 |  |
| 6.1.35 | Improvement of Volume A | (a) To describe the consequences of the changes in the index numbering system. (b) To initiate the implementation of the proposed changes to Volume A. | AC/OSY | II Quarter 2003 | Consultant (Apr 03) |
| 6.1.37 | GCOS | To invite countries concerned to assume responsibilities of the CBS lead monitoring centres (one for GUAN and one for GSN) on a trial basis | AC/OSY in coordination with C/TEM and GCOS Office | May 2003 |  |
| 6.1.38 |  | Points of Contact (POC) to be nominated by each NMHS |  |  |  |
| 6.1.39 |  | To re-emphasise that GCOS CLIMAT and CLIMAT TEMP messages should be produced and distributed globally on the GTS. |  |  |  |
| 6.1.40 |  | To urge all Members concerned to assure that network operators, monitoring centres, telecommunication centres, CBS Lead Centres for GCOS Data and the GCOS Data and Analysis Centres to adhere to the guidelines given in the Guide to the GCOS Surface and Upper-Air Networks: GSN and GUAN |  |  |  |
| 6.1.x.7 PINK 6.1(3) | New WMO Space Programme | (a) To formulate relevant tasks for the OPAGs (including both IOS and ISS). (b) To include representatives from the R&D space agencies the membership of appropriate Expert Teams and Implementation/Coordination Teams . | Chairs of the OPAG-ISS and IOS, SSO/SAT | June 2003 | CBS-MG meeting June 03 |
| 6.1.x8 PINK 6.1(3) | CGMS | WMO Members to be kept informed of the need to convert satellite ground receiving stations as and when new satellite systems become available. | SSO/SAT | Ongoing |  |
| 6.1.x5 PINK 6.1(4) | Scientific Evaluation Group (SEG) of the Coordination Group on the Composite Observing System for the North Atlantic | The Management Group to review the working arrangements of the OPAG-IOS with respect to retaining in the OPAG the tasks of the SEG, which are carried out by the global NWP Centres. | CBS/MG | June 2003 | CBS-MG meeting June 03 |
| 6.2.15 | GTS protocols | (a) To assess a practical date for the implementation of the file naming convention (b) To develop urgently the detailed complementary procedures for the application of the file naming convention (c) To address the requirements of the distribution and downloading modes | Chair of the OPAG-ISS C/TEM | CBS-XIII | ET-EUDCS tasks; 2nd half of 2003 |
| 6.2.17 | Request-reply mechanisms using Internet | The OPAG on ISS to study further that matter in the more general framework of delivery of information upon request | Chair of the OPAG-ISS C/TEM | CBS-XIII | ET-EUDCS tasks; 2nd half of 2003 |
| 6.2.18 | Guidance for using the Internet between GTS centres | To publish the guidance document on VPNs in an electronic form on the WMO server and to provide in printed form to NMHSS on request | C/TEM | February 2003 |  |
| 6.2.19 | Online information on data comms systems & techniques | To invite all WWW centres to continue contributing to, and making use of, those information resources | C/TEM | ongoing |  |
| 6.2.20 | Functions and responsibilities of RTHs | To invite RAs I, II, III and IV to consider aligning, accordingly, the corresponding text in their respective parts of Volume II. | C/TEM | ongoing | Reg. WG-PIW |
| 6.2.21 | Extension of the maximum length of messages to 500 Koctets | The OPAG on ISS to assess a realistic implementation date, and the Secretariat to carry out an enquiry to RTHs | Chair of the OPAG-ISS C/TEM | End 2003 Enquiry: March 2003 |  |
| 6.2.27 | Allocation of abbreviated headings for the migration to TDCF | Tables (B3, C6 and C7) of Attachment II-5 of the Manual on the GTS to be reviewed and revised accordingly, as soon as the actual need for exchanging the various type of "migrated data" arose, and the OPAG on ISS to keep the matter under continuous review. | Chair of the OPAG-ISS C/TEM SO/DPS | Ongoing | ICT-ISS task |
| 6.2.38 | Radio frequencies for meteorological activities | CBS and Secretariat to pursue as high priority activities related to radio frequency allocations; Participation in WRC-03 | Chair of the OPAG-ISS C/TEM | Ongoing June 2003 | SG-RFC task |
| 6.2.42 | Radio frequencies for meteorological activities | To urge Members to ensure that their respective national Radiocommunication Authorities were fully aware of the impact of the relevant WRC-03 issues for meteorological operations and to seek their support for issues relevant to meteorology | C/TEM | done | CL Nov. 2002 |
| 6.2.47 | Metadata standards | To pursue the development of the WMO metadata standard, and to involve, to the largest extent possible, members of other Commissions in assessing the proposal and in testing the standard by applying it to their data. | Chair of the OPAG-ISS X/WDM | 2003 | ET-IDM task |
|  |  | President of CBS to address that important matter at a future meeting of presidents of technical commissions. | Acting President of CBS | Feb 2003 | done |
| 6.2.48 | Guide on WWW Data Management | To review the content of the guide, to design it for electronic publication, and to establish a process to verify and update the references at an appropriate frequency. | Chair of the OPAG-ISS X/WDM | 2003 | Consultant |
| 6.2.51 | Monitoring the BUFR bulletins | To invite RTHs on the MTN to consider participating with high priority in the preparation of a pilot study and in preliminary tests for the monitoring of BUFR bulletins. | C/TEM X/WDM | May 2003 |  |
| 6.2.52 | Monitoring data on 1 January | To further consider that issue with respect to all monitoring activities. | C/TEM | CBS XIII |  |
| 6.2.53 | Operational trial on the WWW integrated monitoring | To analyse the results of the trial, and, in light of the outcome, consolidate and submit the procedures for the integrated monitoring to the Commission, at its next session. | C/TEM | CBS XIII | Workshop Toulouse, June 2003 |
| 6.2.63 | Data representation and codes | (a) Templates to be on the WMO Web server and as an Attachment to Volume I.2 of the Manual on Codes. (b) New reporting practices linking observations with BUFR or CREX formats to be listed as an Attachment to Volume I.2 of the Manual on Codes. | SO/DPS | Ongoing |  |
| 6.2.65 | Data representation and codes | To keep the focal points informed of the code changes recommended by the Expert Team | SO/DPS | Ongoing |  |
| 6.2.67 | Use of XML format | To organise of a workshop on the use of XML in meteorology to elaborate further on requirements, problems and solutions and to develop standards for describing meteorological parameters and objects | SO/DPS | 2003/2004 | Depending on funding |
| 6.2.71 | Migration to table-driven code forms | To promote the development of a turn key software package in a PC-Windows environment to decode and encode BUFR data via the Internet | Chair of the OPAG-ISS SO/DPS | April 2003 | Requirement to be submitted to EUMETNET |
| 6.2.72, |  | Manufacturers to be included in the training, preferably in the form of a workshop to be held in 2003 at no cost to WMO. |  | 2003 or 2004 | Discussed with HMEI in Jan 2003 |
| 6.2.73 |  | To carry out pilot projects beginning in 2003 |  |  |  |
| 6.2.77 |  | (a) The final version of the plan to be made available in the WMO Web server (b) To submit the migration plan, to Fourteenth Congress for consideration and approval. |  | February 2003 | done |
| 6.2.86 | Future WMO information system | (a) To develop into more details the comparison and mapping of the respective functions and responsibilities of FWIS and WWW centres | Chair of the OPAG-ISS, ITT-FWIS C/TEM X/WDM | 2003 | ITT-FWIS task |
| 6.2.88 |  | To urgently compile and consolidate the requirements from the relevant WMO Programmes |  |  |  |
| 6.2.90 |  | To organize the consultant(s) study; To inform Cg and EC of the outcome of CBS on the issue; and assist to outcome of study | D/WWW-B C/TEM | Feb. 2003 March 2003 | done Incl. in Cg Doc 3.1.2 + planned ADD |
| 6.3.4 | Ensemble forecasting methodology and progress | To update the Manual on the GDPS to include EPS. Seek consultant to develop a new chapter in the Guide on the GDPS (WMO-No. 305. | C/DPS | 2003 |  |
| 6.3.6 | EPS verification procedures | Include EPS verification procedures in the Manual on the GDPS | C/DPS | 2003 |  |
| 6.3.13 | Use of forecasts and warnings in flood forecasting | Take part in WMO Action Programme on Flood forecasting/warning | DHWR, D/AREP, D/WWW-B, C/DPS | 2003 | Preparatory meeting for a workshop on flood forecasting being planned for April 2003 |
| 6.3.20 | Emergency response activities and atmospheric transport products | To explore expansion of modelling applications and response procedures to non-nuclear incidents including potential incidents that a Member(s) may consider imminent and for which RMSC transport model output support is required. | Chair of the Co-ordination Group on ERA C/DPS | 2003 | 2nd half of 2003 |
| 6.3.21 | Update to ERA procedures | Update ERA procedures in the Manual on the GDPS and WMO/TD-No 778 | C/DPS | June 2003 |  |
| 6.3.24 6.3.25 6.3.36 | Seasonal to Internal forecasting | Availability of SI forecasts from global producing centres | C/DPS | 2003 | Workshop held 10-13 February 2003 |
| 6.3.34 | Verification system for long-range forecasts | Include verification system for long range forecasts in the Manual on the GDPS Further update the verification system in the light of experience | C/DPS ET on VS for long range forecasts | June 2003 Ongoing |  |
| 6.3.38 | Use of GRIB 2 for EPS and long range forecasts | OPAG on ISS to monitor use of GRIB 2 and remedy deficiencies or omissions | ET /DRC SO/DPS | Ongoing |  |
| 6.3.43 | Update of procedures for quality control | Update quality monitoring procedures in the Manual on the GDPS | C/DPS | June 2003 |  |
| 6.3.44 | Training activities | Development of preparatory meeting and related workshop on EPS Co-sponsorship of ECMWF training course on use of products | C/DPS C/DPS | 2003 October 2003 | Depending on funding Proposal sent |
| 6.3.45 | Development of guidance for training on DPFS | Develop a capacity training policy using approaches similar to those of satellite activities | C/DPS | 2003-2004 | consultant |
| 6.3.46 | Training in NWP and ATM | Organization of training workshops on NWP and ATM | C/DPS, SO/DPS | 2004 |  |
| 6.3.47 | Work programme | Develop further the work programmes of ETs on Infrastructure, Verification of LRF , EPS the ERA Co-ordination Group and possibly Nowcasting activities | Chair of OPAG on DPFS , C/DPS | 2003 |  |
| 6.4.7 | Use of official and consistent information by the media | Continue to work on reinforcing the authority of NMSs as the official source of information, in particular the warnings of severe weather. | C/PWS | During 2003-2004 |  |
| 6.4.8 | Training seminars and workshops on improving presentation and communication skills of forecasters | The PWS Programme to continue to organise such training events | C/PWS | During 2003-2004 |  |
| 6.4.11 | Improvement of the PWS | The OPAG/PWS Programme to continue to develop material on quality management practices in the delivery of PWS | C/PWS and relevant OPAG teams | 2004 |  |
| 6.4.16 | Improving the capacity of NMSs to provide users and the public with high quality warning products | Forecasters to receive specific training | C/PWS | As part of PWS training events in 2003-2004 |  |
| 6.4.19 | Olympic games | Prepare draft guidelines for weather support to Olympic games for submission to the International Olympic Committee | Chair of the OPAG/PWS C/PWS | 2004 |  |
| 6.4.22 6.4.27 | Pilot Web sites | Language issues to be studied | C/PWS | 2004 |  |
| 6.4.29 | PWS Guidance materials | To strive to translate the guidance materials and post them on the Web | C/PWS | .. | Done; all Published Guidelines are posted on the Web Translations will be done when funding available |
| 6.4.32 | Links with WWRP | Chair of the OPAG-PWS to maintain close links with WWWRP | Chair of the OPAG-PWS | Ongoing |  |
| 6.4.36 | Technical Conference on PWS | to organize a technical conference on Public Weather Services to be held in conjunction with next session of CBS | Chair of the OPAG-PWS C/PWS | 2004 |  |
| 7.2.3 | Working Group on Antarctic Meteorology | To inform Cg, EC and the bureau of the views of CBS on the issue | D/WWW-B | May 2003 | done |
| 7.2.5 | Renaming CBS | the CBS Management Group to further study the issue and develop a proposal for consideration by the next session of the Commission | CBS Management Group | 2004 | To be discussed at the June meeting |
| 7.2.6 | Renaming GDPS programme | To recommend to Fourteenth Congress that the GDPS programme be named the GDPFS programme. | D/WWW-B | May 2003 | Done |
| 7.2.7 | Sixth WMO Long-term Plan | To update the Sixth WMO Long-term Plan | D/WWW-B | May 2003 | Done |
| 8.2 | Terms of reference and tasks of the Expert Teams and Rapporteurs of each OPAG | (a) each OPAG chairperson to ensure that the specific tasks be adequately addressed. (b) The Management Group to keep under review the work programme and make arrangements, as necessary, upon proposals of OPAG chairpersons | Chairs of OPAG CBS Management Group | June 2003 | June meeting |
| 8.3 | Total Quality Management | Management Group to make necessary arrangements, including within the OPAGs, for efficiently carrying out the tasks that would stem from the relevant decisions and directives of Congress | CBS Management Group | September 2003 | To be discussed at the June meeting taking into account pertinent Cg decisions |
| 10.1.2 | WMO server | To post on the WMO server the content of the Manual on Codes and the Manual on the GTS | C/TEM, SO/DPS | March 2003 |  |
| 10.2.1 Rec. 10.2/1 | Broadening the function of and RSMC | Recommend to EC update functions of RSMC Offenbach in the Manual on GDPS to include provision of U-V Index | C/DPS | June 2003 | done |
| 10.1.4 10.1.6 10.1.7 10.1.8 10.1.9 | WMO Publication Nos. 9 and 47 | (a) The expanded introductory and explanatory texts related to Weather Reporting and the International List of Selected, Supplementary and Auxiliary Ships to be made be made available in English, French, Spanish and Russian. (b) To delete Volume B from the list of WMO Mandatory Publications and to distribute the WWW Technical Progress Report on the GDPS on a CD-ROM instead of a paper format. (c) To urge all MTN centres to implement the new database procedures for the maintenance of their own parts of Volume C1. (d) To invite Members to include the lists of bulletins transmitted through distribution systems in their routeing catalogues and to continue providing updates on data distribution systems as well as a summary of the transmission programmes in electronic format, to be then included in Volume C2. (e) To consider the development of interactive on-line access services to all components of the OIS with the highest priority within the framework of the development of the OIS. | C/DPS, C/TEM | May 2003 | Document for Cg?? |