CBS – Twelfth Session

# Geneva, 29 November-8 December 2000

# ACTION SHEET

| Paragraph | Subject | Action required | Responsible | Deadline | Status/remarks |
| --- | --- | --- | --- | --- | --- |
| 3.8 | ISO 9000 | Investigate whether and how the concept could be applied to the WWW System | Rapporteur WDM | Dec 2001 | Two reports to CBS-MG meeting |
| Recs 6.1/1, 6.2/1, 6.2(3)/1, 6.2(3)2, 6.2(3)/3, 6.3/1, 6.3/2, 10/1 | Approval of recommendations | (a) prepare EC doc on report of CBS-XII with recs. (b) send relevant recommendations to PTCs for comment | WDM | Feb. 2001 | done |
| Res 8/1, 8/2, 9/1, 10/1 | Working Structure of the Commission | Work programme for intersessional period | WDM | Dec. 2000 | Done; Dec. 00 |
| 6.1.5 | Loss of surface and upper-air data | To refer the issue to the ICT on the GOS to identify problem areas and work with Members and RAs to reduce the data losses. | Chair of the OPAG/IOS | Ongoing | To be included in the Agenda for ICT meeting in 2002. |
| 6.1.24 | WWW Technical report No. 20 | Distribute among Members WWW Technical report No. 20 entitled “Observing System Technologies and Their Use in the Next Decade” | AC/OSY | January 2001 | done |
| 6.1.30 | Rapporteur on Scientific Evaluation of OSEs and OSSEs | Rapporteur to be appointed by the CBS MG. | Chair of the OPAG/IOS | January 2001 | Done; two rapporteurs were appointed by the CBS-MG; PRs concerned have agreed |
| 6.1.35, 6.1.36 | Joint funding or cost-sharing for observing network operations in developing countries | The need for such a funding mechanism should be brought to the attention of the EC | President | June 2001 | Done, see EC-LIII fin report, para 3.1.11 |
| 6.1.44, 6.1.46 | Requirements and representation of data from AWSs | Invite WMO technical commissions concerned to review and validate the draft functional specifications to support present and future AWS applications for final approval by CBS; Inform CIMO of the new tables for Present Weather and to invite it to keep these under review. | AC/OSY | February 2001 | Done |
| 6.1.52 | Manual on the GOS | Draft of the updated Manual to be reviewed by Expert Group and submitted to the next session CBS for approval. | AC/OSY | November 2001 | To be considered by Task Team meeting (Geneva, 26-30.II.2002) |
| 6.1.53, 6.1.54 | Composition of the RBSNs | Invite RA to consider the development of criteria in order to ensure a more objective selection of RBSN stations in the region; Invite Members through designated focal points within each NMS and the WMO Secretariat to advise the regional rapporteurs of any changes in the status of the RBSN in their respective regions. | AC/OSY | February 2001 | Done |
| 6.1.55 | Volume A of WMO Publication NO. 9 | Invite Members to designate focal points in NMSs who are authorized to inform the WMO Secretariat directly on changes in Volume A of WMO Publication No. 9 | AC/OSY | February 2001 | Done |
| 6.1.68 | Availability of CLIMAT and CLIMAT TEMP reports | RTHs to provide regular information on availability of CLIMAT and CLIMAT TEMP reports from their zones of responsibility during the WWW monitoring; Invite Members to ensure that their operational observing stations which belong to climate reporting networks compile and transmit CLIMAT/CLIMAT TEMP messages according to the existing regulations. | C/TEM AC/OSY | On-going February 2001 | Included in the Special MTN Monitoring (SMM) Done |
| 6.1.69 | Monitoring of CLIMAT and CLIMAT TEMP reports | CBS and GCOS monitoring centres to review how the existing arrangements can be used to improve monitoring of CLIMAT and CLIMAT TEMP reports. | AC/OSY | March 2001 | To be included in the Agenda for Coordination Meeting on the implementation of GSN and GUAN (May, 2002) |
| 6.2.45 | Improved MTN | President to submit the fundamental principles and concepts of the Improved MTN project to next EC | C/TEM |  | Done, see EC-LIII fin rpt, para 3.1.13-15 |
| 6.2.47 | Internet Guide | Print information in the Internet guide on establishing a connection to the Internet and to distribute via hardcopy to NMHSs not yet connected. | WDM |  | Waiting for translation (Spanish pending) |
| 6.2.47 | Internet Guide | Translate guide into French, Spanish and Russian and publish on Web server | WDM |  | French done for CBS-XII in Dec. 2000; R + S versions submitted in Feb 2001 with May deadline, Russian done |
| 6.2.93(a) | Table Driven Codes | Distribute guidance describing simply the advantages of Table Driven Codes | SO/DPS |  | In preparation |
| 6.2.93(a) | Training in Table Driven Codes | Implement a training programme on Table Driven Codes for all developing countries. | SO/DPS | On-going | Plans start with event in RA I (tent. Tanzania, Feb 2002) |
| 6.2.101 | Manual on Codes | Provide other parts of the volumes of the Manual on Codes on digital media. | SO/DPS | On-going | Progress depending on availability of a DPS/WDM secretary |
| 6.3.5 6.3.6 | Assessment/evaluation of impact changes to GOS | ICT on DPFS to address issues and develop attachment to the Manual | OPG Chair, C/DPS | May 2002 | To be considered by meeting of ICT |
| 6.3.7 | Guidelines to minimize impact of loss of observations | Publish guidelines in the Guide on the GDPS | C/DPS | August 2001 |  |
| 6.3.9 | Alerts on WMO web page | Implement flashing “What’s New” for recent updates to GOS | AC/ OSY |  |  |
| 6.3.14 | Update verification area for the tropics. | ICT on DPFS to harmonize current standards with the proposed experimental areas. | OPAG Chair, C/DPS | May 2002 | To be considered by meeting of ICT |
| 6.3.18 | Alignment of RA II precipitation reporting and global reporting of 24h ppt | Update RA II reporting practice Update global reporting practice for zero ppt and 24h amount | SO/DPS SO/DPS |  | To be considered by RA II To be considered by CBS-Ext. (02) |
| 6.3.21 | Guidance on GPCC procedures Procedures and formats for exchange of monitoring results | Publish guidance in the Guide on the GDPS Lead centres to develop and complete procedures and formats for inclusion in the Manual on the GDPS | C/DPS C/DPS | June 2001 August 2002 | Draft supplement done Expert meeting to be arranged |
| 6.3.25 6.3.26 | EPS Training | EPS topics to be included in all future GDPS planned training events | C/DPS SO/DPS |  | Two planned events in 2001 include EPS introductory topics |
| 6.3.31 6.3.32 | Availability and use of NWP guidance on occurrence of severe weather | Topic to feature in all future GDPS planned training events | C/DPS SO/DPS |  |  |
| 6.3.35 | Long-range forecasting infrastructure | ET on infrastructure long-range develops its proposals and input to the inter-commission Team on RCCs | Team Chair, C/DPS | November 2001 | To be considered by meeting of ET |
| 6.3.38 6.3.39 6.3.40 6.3.41 6.3.42 | Co-operation with CTBTO Dissemination of CTBTO Met data. Joint ICAO/WMO requirements Enhancement of ERA procedure | Development of practical ways for co-operation with CTBTO Develop relevant procedure for dissemination of the data Statement of requirements for CTBTO infrasonic and seismic data Address relevant issues resulting from evaluation of exercise and current limitation in communications | ERA Group Chair, C/DPS - do - - do - - do - | May 2002 - do - - do - - do - | To be considered by group meeting in September 2001 -do – do – -do - |
| 6.3.46 | Arrangements with UN/OCHA | Test the existing arrangements as to their suitability | OPAG chair, OCHA, C/DPS C/PWS | May 2002 | To be considered by meeting of ICT |
| 6.3.50 | Report on Workstations | OPAG on DPFS to address recommended actions | OPAG chair C/DPS | May 2002 | To be considered by meeting of ICT |
| 6.4.7 | Pilot project on tropical cyclone Website | Continue to develop the project without delay and at a rapid pace and test the site | C/PWS | During the typhoon season (July-November 2001) | The HK Observatory launched the site, the results to be evaluated at the end of the season |
| 6.4.9 | Improved partnership with the media | Continue efforts to develop better partnership between NMSs and the media, both national and international | C/PWS | December 2001 for guidelines. Ongoing for training | Guidelines on the subject produced by the ET/Media Issues (met June 2001) published. Focus on the subject in training workshops |
| 6.4.15 | Product development and service assessment | Continue to work on assisting Members with the use of new technology in PWS and overall service assessment | C/PWS | Mid 2002 | The ET/product development and service assessment meeting in Honolulu Dec 2001, to prepare guidelines on: a) application of new technology and research b) service assessment |
| 6.4.17 | Pilot project on city forecasts | Further develop the concept of a collecting centre for city forecasts and launch the pilot project | C/PWS | Phase 1 by end 2001, phase 2 end 2002 | Phase 1 will be launced in Dec 2001 with a news release by HK Observatory. |
| 6.4.20 | Exchange of warnings | Prepare guidelines on exchange of warnings | C/PWS | Mid 2002 | ET/Warning and forecast exchange to meet Feb 2002 in Hon Kong, to prepare guidelines |
| 6.4.25 | Capacity building | Continue to give high priority to training | C/PWS | Training planned on regional basis in 2001-2002 | PWS workshop done for RAI in La Réunion Nov. 2001. one workshop for RAIV Hurricane Committee region, one for RAIII/IV and a third one for RAII are planned for 2002. |
| 6.4. 32 | Overall coordination of PWS | Keep under review in particular emergency management issues and document improvements in national PWS programmes | OPAG chair C/PWS | Ongoing to end 2002 | ICT to meet mid 2002 to prepare guidelines and case studies on PWS improvements. |
| 6.5.4 | Pub 9 Vol A | Improve the utility of Vol A | Rapporteur AC/OSY | On-going | Report to CBS-Ext(02) |
| Rec. 6 CBS-XII Rec. 7 CBS-XII | Amendments to the Manual on the GDPS Designation of RSMC on Tropical cyclones | Upon approval by EC-LIII, to issue relevant supplement - do - | C/DPS C/DPS | June 2001 - do - | Done Done |
| 7.4 | Long-term plan | OPAG chairs to develop key goals and priorities for their sub-programmes, seeking input from the chairs of the Regional WG-PIOW | OPAG chairs and chiefs | On-going | Report to the CBS-Ext(02) |
| 7.8 | Innovative collaboration | Investigate the results of cooperative arrangements or agreements | Rapporteur WDM | Dec 2001 | Preliminary report to CBS-MG meeting, Final in March |