| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS OPAG on DPFS Meeting of the Expert Task Team to review the WMO Technical Note 170 Geneva, Switzerland, 12-14 February 2013 |  | CBS-DPFS/ET-Review-TN170/Doc. 3(3) (30.I.2013) _______ Agenda item : 3 ENGLISH ONLY |
| --- | --- | --- |

3.  Introduction and Background

Participants, Terms of work, Draft Roadmap

(Submitted by Secretariat)

##### Summary and purpose of document

This document provides basic information on the work of the expert task team.

1.  The participants at the first meeting of experts include:

Experts:

Mr Pierre Bessemoulin

Mr James Dent

Mr Jeff McQueen

IAEA:

Mr Sujit Samaddar

WMO Secretariat:

Mr Peter Chen

Mr Bruce Stewart

2.  Terms of Work for the experts in the revision of TN No. 170 are:

To participate in a small task team to carry out the revision of TN 170, referred to as TT-TN170.  The duties in 2013 are:

- Review WMO TN 170

- Review IAEA SSG-18 (2011)

- Identify up-to-date literature that is relevant to the subject matter

- Develop a TT work plan, and a document plan for the revised technical note (for EC approval)

- Draft content for the revised technical note, in accordance with the approved document plan

- Update content following targetted expert review

- Two (2) travel missions (3 days each, WMO Geneva, or IAEA Vienna)

(Work is expected to continue into 2014, with the first milestone of reporting to the session of the Presidents of th Technical Commissions.)

3  Publication (to be discussed between WMO and IAEA)

4.  Draft Roadmap

The roadmap is intended as a guide to the development of the TT work plan (see Annex 1)

Annex - Draft roadmap for the revision of

WMO Technical Note No. 170:

“Meteorological and Hydrological Aspects of Siting and Operation of Nuclear Power Plants”

Vol. 1: Meteorological Aspects, Vol. 2: Hydrological Aspects

1.  Identify experts, and form task team for the review, for subject areas:

- Weather: monitoring and forecasts for operations

- Climate: siting, hazards

- Hydrology: monitoring and forecasts, siting, hazards

- Nuclear safety and security (IAEA)

Target: 14 December 2012 DONE.

2.  Consult WMO Publications

- (D/WDS, D/CLW)

- Should this be a co-sponsored publication with IAEA?

3.  Review by experts

- TN 170

- Identify and review related literature

Target: 31 January 2013

4.  First meeting of task team

- develop a work plan (with dated milestones)

- develop a document plan (with assignments for lead and author(s) for sections)

Target: week of 11 February 2013 (WMO Geneva)

5.  Drafting (monthly Webex to manage work of task team)

Target: February – September 2013

6.  Second meeting of task team

- review of consolidated first draft, make revisions

- revise work plan and document plan

Target: October  2013 (option, WMO Geneva or IAEA Vienna)

7.  Review

- Engage broader review (key countries, and CBS, CCl, CHy)

- Report to PTC- 2014

Target: January 2014

8.  Complete final draft of document

Target: March 2014

9.  Publication process (WMO, IAEA)

- Publish, distribute

Target: Q1 2015