| EC-LXI Action Sheets related to CBS Comments made by MG-10 are highlighted in red |
| --- |
| TOR Item: | Action Required: | Responsible: (Secretariat) | Responsible: | Deadline for action: | Action Status: |
| DPFS: |
| 3.1.7 | SG to facilitate the access to increased resolution gridded data set (0.5 deg.) from ECMWF DPFS to define global sets of NWPs ISS to assess the telecom impacts | C/DPFS | ICT - DPFS | Mar. 2010 |  |
| 3.1.10 | CIMO, CBS, CAS address the current availability and quality of lightning data, for applications in nowcasting and other applications IOS, PWS to consider the applications in nowcasting and other applications ISS to consider data representation aspects, data availability, frequencies matters, flow of the data | D/OBS, D/WDS, D/ARE | Relevant OPAGs | Mar. 2010 |  |
| 3.1.11 | Implement Resolution 3.1/1 (EC-LX1) – amendment to the Manual on the GDPFS DPFS to take action | C/DPFS | Chair DPFS | Sep. 2009 |  |
| 3.1.14 | CBS and CCl to work together in close collaboration with RAs in development of WMO climate services network, including expansion of RCC network DPFS and PWS to contribute | D/WDS, D/CLW | ET-E&LRF | Dec. 2009 |  |
| 4.1.4 b | CAS and CBS collaboration to establish SDS-WAS Centres, and to clarify the future of these Centres in the context of the GDPFS and RSMC structures DPFS to take action | D/WDS, D/ARE | Chair DPFS | Dec. 2009 |  |
| IOS (incl. WIGOS): |
| 3.4.4 | Develop a new version of the Implementation Plan for Evolution of Space and Surface-Based Sub Systems of the GOS that will incorporate the “Vision for the GOS in 2025”. | C/OSD | ET-EGOS | Dec.09 |  |
| 3.4.5 | Organize the fifth workshop on the Impact of Various Observing Systems on the NWP in 2012 DPFS also to contribute | C/OSD | ET-EGOS | Dec.09 |  |
| 3.4.6 | Arrange for inclusion of the approved “Functional Specifications for Automatic Weather Stations” in the Guide on the GOS (Resolution 3.4/1 (EC-XLI)). | C/OSD | Rap. on Regulatory Material | Oct.09 |  |
| 3.4.7 | Arrange for inclusion of the approved “Basic Set of variables to be reported by a Standard AWS for Multiple Users” in the Guide on the GOS (Resolution 3.4/1 (EC-XLI)). | C/OSD | Rap. on Regulatory Material | Oct.09 |  |
| 3.4.8 | CBS (and CIMO) to promote the inclusion of a suitable humidity sensor with a generic software and hardware solution for all major aircraft types and models. | H/AIR (H/IMO) | ET-AIR (CIMO ET-UGUN) | Dec.09 |  |
| 3.4.9 | Work with Members to collect AMDAR data from outside their national territories, in compliance with national laws and regulations, and to exchange these on the GTS. ISS to facilitate the exchange of observations | H/AIR | ET-AIR | Nov.09 |  |
| 3.4.9 | Work with Members to enhance the cost-effectiveness of AMDAR observations by implementing a data optimization system. | H/AIR | ET-AIR | Nov.09 |  |
| 3.4.10 | EC encouraged consultation between the USA, WMO, CGMS and relevant RA III Members, regarding replacement of the GOES-10 mission regarding coverage in the Southern Hemisphere. | D/SAT | ET-SAT | Ongoing |  |
| 3.4.12 | EC encouraged actions at the regional level to address the limitations expressed by WMO Members regarding access to, and use of, satellite data and products. ET-SAT and ET-SUP to review the requirements and ensure the availability of metadata ISS also to consider facilitating the access to data and metadata | D/SAT | ET-SUP | Ongoing |  |
| 3.4.15 | EC recommended that Members increase their support to WMO Space Programme activities in supplementing the budgeted space programme resources with extrabudgetary and in-kind support as appropriate, in adopting Resolution 3.4/1 (EC-XLI) President and vice-president to consider strategies to increase the support to the WMO Space Programme, as well as to other CBS related programmes/activities | D/SAT |  | Ongoing |  |
| 3.4.32 | Monitor the preparation of a GCW implementation strategy for consideration by the WMO Congress in 2011 as requested by EC-LXI. | C/OSD | ET-EGOS | Dec.09 |  |
| 3.4.34 | EC encouraged IGDDSs further development and expansion as operational components of the WIS architecture. ISS also to contribute | D/SAT |  | Ongoing |  |
| 3.4.43 | Provide Members with information on WIGOS benefits Contribution also expected from the EC WG-WIGOS-WIS | WIGOS PO | CBS-MG | Oct.09 |  |
| 3.4.43 | Provide Members with guidelines on WIGOS related activities be implemented by Members | WIGOS PO | CBS-MG | Oct.09 |  |
| 3.4.44 | Collaborate in testing, developing, and implementing the WIGOS concept, and provide their input to WDIP | WIGOS PO | CBS-MG | ongoing |  |
| 3.4.44 | Update WIGOS web pages reflecting outcomes of EC-LXI | WIGOS PO |  | June 09 |  |
| 3.4.45 | Draft WIGOS comprehensive costed development and implementation strategy CIMO to be involved | WIGOS PO | CBS-MG | Oct.09 |  |
| 3.4.48 | Elaborate a detailed project implementation plan and work plan for WIGOS Pilot Projects for AMDAR, CIMO, GRUAN and GSICS. | C/OSD, D/GCOS, D/SAT |  | July 09 |  |
| 3.4.55 | Start elaboration of WIGOS related publication | WIGOS PO |  | Oct.09 |  |
| ISS (incl. WIS): |
| 3.5.1.1 | NMHSs, technical commissions, regional associations and the ICG-WIS to pursue interaction and contribution to the WIS Project Plan and WIS Implementation Plan. | D/WIS | ICG-WIS OPAG-ISS | Ongoing |  |
| 3.5.1.2 | To promote the value and benefits that are expected from the WIS; Donors to further contribute to the WIS Trust Fund or in staff secondments. | D/WIS D/RMO | ICG-WIS OPAG-ISS | Ongoing |  |
| 3.5.1.3 | ICG-WIS to ensure that the WIS elements and components required for the implementation and operation of the WIGOS pilot projects be developed and coordinated to meet the respective projects’ aims and requirements | D/WIS | ICG-WIS OPAG-ISS | Ongoing |  |
| 3.5.1.4 | To develop the Manual on WIS; To train on metadata guidelines and development tools. | D/WIS | CBS (OPAG-ISS) | Ongoing |  |
| 3.5.1.5 | Technical Commissions to pursue contributions to the refinement of WIS Rolling Review of Requirements | D/WIS | ICG-WIS | Ongoing |  |
| 3.5.1.6 | To treat the migration to and participation of the developing countries and LDCs in WIS as a high priority; Regional Associations to develop and promote pilot projects for early use of WIS functions and services; NMHSs from developed countries to support and assist in these initiatives; Members in Region I to participate in the development of the WIS Demonstration Project in Southern Africa; To facilitate resource mobilization efforts to support WIS initiatives in Southern Africa. | D/WIS D/DRA D/RMO | ICG-WIS CBS MG | Ongoing |  |
| 3.5.1.7 | To make known to Members as soon as possible the technical details on the GISC and DCPC designation process (a. develop guidance, b. organise demonstrations, submit formal designations to Cg XVI) | D/WIS | CBS (OPAG-ISS) | Nov.09 |  |
| 3.5.1.10 | CBS and the ICG-WIS To develop in more detail the concept and implementation plan for AMDCNs and the WIS core network. | D/WIS | ICG-WIS CBS (OPAG-ISS) | Nov.09 |  |
| 3.5.2.1 3.5.2.2 | Members to pursue efforts for the GTS implementation and improvements; The Secretariat to amend the manual on the GTS (ref. Res. 3.5/1 (EC-LXI); CBS to pursue the effort to further improve the GTS for the effective and flexible exchange of data, products (messages and files) and related metadata for all WMO Programmes, with a view to WIS | D/WIS | CBS (OPAG-ISS) Secretariat | Ongoing August 2009 for the amendments |  |
| 3.5.2.4 | To encourage IGDDSs further development and expansion as operational components of the WIS architecture | D/SAT | ET-SAT (ET-CTS) | Ongoing |  |
| 3.5.2.5 | To coordinate and join efforts on water-related pilot projects | D/WIS | ICG-WIS | Ongoing |  |
| 3.5.2.7 | Members and RAs to ensure that the implementation of CAP benefits all user communities. PWS to inform user communities on CAP | D/WIS | CBS (OPAG-ISS) | Ongoing |  |
| 3.5.2.8 | To develop code tables in an appropriate electronic format for facilitating their use in automated processing systems of NMHSs | D/WIS | CBS (OPAG-ISS) | Ongoing |  |
| 3.5.2.9 | The Secretariat to amend the Manual on Codes (ref. Res. 3.5/1 (EC-LXI) | D/WIS | Secretariat | August 2009 |  |
| 3.5.2.10 | Members to develop and implement their national plans; RTHs to facilitate the step-by-step migration by assisting in the definition of ad hoc arrangements between zones of responsibility of RTHs, and by monitoring the exchange of TDCF bulletins and reports on the GTS; To provide training on TDCF in the WMO Regional Training centres and to develop and implement projects under technical cooperation activities required to support the migration | D/WIS D/ETR D/DRA | CBS (OPAG-ISS) | Ongoing |  |
| 3.5.2.11 | Technical Commissions to urgently consolidate a comprehensive WIS data representation systems policy | D/WIS | CBS (OPAG-ISS) | Ongoing |  |
| 3.5.2.12 | To use WMO core profile version 1.1 of the ISO 19115 Metadata standard; To develop guidance material and some metadata entry and management tools to enable NMHS to start to create the required metadata; To conduct training workshops and provide metadata experts to assist developing countries and LDCs; All WMO Programmes to review their requirements of in terms of metadata and to submit relevant proposals for the further development of the WMO core profile of the ISO Metadata standard and contribute to the CBS activities; GRDC to contribute to the CBS/IPET-MDI; CBS and JCOMM to continue their work on the development of the Marine Metadata Profile. | D/WIS D/DRA D/HWR D/WDS | CBS (OPAG-ISS) | Ongoing |  |
| 3.5.2.13 | WMO programmes to define Feature Data Dictionaries and Feature Catalogues | D/WIS | CBS (OPAG-ISS) | Ongoing |  |
| 3.5.3.2 | To identify recommended procedures and practices for managing access rights, registration and identification of users based on international standards and current technologies for ensuring the security of data and products in accordance with data policies. | D/WIS | CBS (OPAG-ISS) | Ongoing |  |
| 3.5.3.4 | To establish close collaboration between CCl and other WMO Programmes, co-sponsored programmes and technical commissions to promote multi-disciplinary DARE projects for other type of data such as for marine, hydrology and remote-sensing and build up on the existing experience in these entities | D/WIS (Lead) D/CLW D/WDS D/SAT D/RMO D/ETR | CCl (OPAG-I) OPAG-ISS (IPET-MDI) | To start |  |
| 3.5.3.6 | Members to continue their full support to modernize Climate Data Management Systems (CDMSs) | D/WIS D/RMO D/ETR | CCl(OPAG-I) OPAG-ISS (IPET-MDI) | Ongoing |  |
| 3.5.3.7 | Members to provide full support to monitor CDMSs operating in NMHSs and identify the status of operational migration from CLICOM | D/WIS | CCl (OPAG-I) | Ongoing |  |
| 3.5.3.9 | Members to ensure free and unrestricted exchange of IPY data; CBS/OPAG on ISS to assist the EC Panel to facilitate acquisition, exchange, and archiving of observational data from Polar Regions in compliance with WIS requirements related to data exchange. IOS to contribute to the definition of the requirements | D/WIS | CBS (OPAG-ISS) | Ongoing |  |
| PWS: |
| 4.2.2 | Work on ways of promoting advocacy groups for PWS among user communities. | C/PWS | ICT - PWS |  |  |
| 4.2.3 | Coordinating with the EC Working Group on Disaster Risk Reduction and Service Delivery in developing a Policy Framework for Service Delivery | C/PWS | ICT - PWS | 30 November 2009 |  |
| 4.2.13 | Include PWS aspect especially user-based assessments of the usefulness of weather warning and forecasts and enhancement of communication in SWFDP in RA III and RA V | C/PWS | ET-COPE | Meeting of ET to discuss in November 2009 |  |
| 4.2.22 | Continue to build the capability of NMHSs in communication; public education and awareness raising and; improving delivery of Nowcasting services | C/PWS | ICT-PWS ET-COPE | June 2010 |  |
| 4.2.25 | Continue to support the Learning through Doing (LTD) projects (Madagascar, Latin America, WENS) as an effective approach to capacity-building in NMHSs. | C/PWS | ICT-PWS | June 2010 |  |
| 4.2.27 | Explore the possibility of repeating the RA II City Specific NWP Project in other WMO Regions | C/PWS | ET/SPI | June 2010 |  |
| 4.2.28 | Support the use of RANET communication initiatives to rural communities in developing and least developed countries. ISS to be involved | C/PWS | ET/COPE, ET/DPM | November 2009 |  |
| 4.2.40 | Coordinating with the WMO Forum in the implementation of the Madrid Action Plan (MAP) including: Pilot projects and Production of guidance materials on user-provider dialogue. | C/PWS | ICT-PWS | June 2010 |  |

Miscellaneous

| 5.2.22 | Carry out, in consultation with WMO Members involved in GEO, a review of WMO’s participation in GEO/GEOSS to evaluate the contributions to GEOSS and the benefits/results WMO has gained and also potential opportunities for enhanced involvement. | D/SAT with B.O’Donnell | CBS coordinator on GEO/GEOSS activities related to CBS | EC-LXII |  |
| --- | --- | --- | --- | --- | --- |

___________