Action sheet of the eleventh session of the Management Group (MG-11) (Geneva, 17-19 March 2010) as at 11 June 2010

Note: The numbers in the first column (“para.”) of the table are the numbers of the paragraphs in the report of MG-11

| Para. | Subject | Action required | Responsible entity | Action taken |
| --- | --- | --- | --- | --- |
| 3.1.1.2 | Full integration of the AMDAR Programme into CBS and WWW structures as well as the integration of the AMDAR/Aircraft Observations into WIGOS. | To address the issue of the full support to AMDAR activities from the WMO regular budget in the budget preparation for the next financial period. | Secretariat |  |
|  |  | To place priority on the harmonization of work plans of ET-AIR and the AMDAR Panel and on the development of standard practices for aircraft-based observation, especially those carried under WIGOS Pilot Project | OPAG-IOS | Work Plan has been harmonized. Work on standard practices has been initiated through WIGOS PP. |
| 3.1.1.3 | Functional specifications for AWS | To keep under review functional specifications for AWS | ET-AWS | Update will be presented to ET-AWS meeting (Geneva, 22-25 June) |
| 3.1.1.4 | Recommendations of the ET-EGOS (see CBS-MG-XI/Doc.3.1.1(1)) | To finalize those recommendations during the ICT-IOS (July 2010) and submit them to CBS-Ext.(2010) for consideration. | Chair of OPAG-IOS | Document prepared for ICT-IOS-6 (Geneva, 28 June – 2 July 2010) |
| 3.1.1.5 | WMO databases for user requirements and observing systems capabilities | To develop a proposal for implementing and maintaining the databases for presentation at CBS-Ext.(2010) | ICT-IOS | Doc. 2(2) prepared for ICT-IOS-6 identifies four potential organizations for hosting and operating the subject database. Each organization has been requested to submit proposals if interested in partnering with WMO on this effort. Proposals will be reviewed at ICT-IOS-6. |
| 3.1.1.6 | More effective and complete representation of the Regional Associations was required at ICT-IOS meetings | To nominate appropriate experts to the ICT-IOS meeting | Regional Associations Secretariat | Done |
| 3.1.1.7 | Cooperation between CBS and CIMO going from instruments to systems and network | To continue the beneficial and positive cooperation | OPAG-IOS ET-SBRSO | On-going |
| 3.1.1.8 | Recommendations proposed by the ET-SBRSO (see CBS-MG-XI/Doc.3.1.1(1)) | To consult with CIMO to let the WMO Guidance Statement on Weather Radar/Wind Turbine Siting be approved | OPAG-IOS | Guidance is being finalized by CIMO for inclusion into the CIMO Guide. |
|  |  | To accommodate proposed WMO Guidance Statement on Weather Radar/Radio Frequency Shared Spectrum Use into the final WMO statement | SG-RFC |  |
| 3.1.2.1 | Difficulties met by countries in meeting the deadline of November 2010 to complete the migration of the data category 1 (SYNOP, TEMP, PILOT and CLIMAT) to TDCF | To dispatch a letter to the WMO Members after EC-LXII: Urging those Members not yet having developed or implemented their national migration plan to do so Inviting those Members having developed and/or implemented their national migration plan to assist other Members to do so, and to continue exchanging TAC and TDCF data in parallel when needed | Secretariat |  |
| 3.1.2.2 | Migration to TDCF | To encourage all RTHs to facilitate the migration to TDCF, in particular by assisting countries in their zone of responsibility | OPAG-ISS |  |
| 3.1.2.4 | Implementation and operation of the WIS part B (DAR) | To consider the establishment of an ad-hoc group of experts to consider issues related to the implementation and operation of the WIS part B (DAR) and to develop recommendations to facilitate this implementation and operation | OPAG-ISS |  |
|  | Real-time monitoring activities | To develop the real-time monitoring activities with a view to identifying deficiencies in the exchange of data through the WIS and with a view to mitigating the possible deficiencies | OPAG-ISS |  |
|  | Quantitative monitoring of the availability of data and products | To consider separating the quantitative monitoring of the availability of data and products, that involves both WIGOS and WIS, from the monitoring of the performance of the data transport network, that basically involves WIS | OPAG-ISS |  |
|  | Membership of the ET-WISC | To add a core member in the membership of the ET-WISC to represent a potential GISC in Region I | OPAG-ISS |  |
| 3.1.3.3 | SWFDP data-policy issues | To pursue strategies for raising this issue at the appropriate levels. | MG |  |
| 3.1.3.4 | Strategy and appropriate documentation related to SWFDP | To describe the new functionalities established through the cascading forecasting process of the SWFDP, and include them for example in the new version of the Manual on the GDPFS | OPAG-DPFS | Expert discussions have taken place; on-going. |
| 3.1.3.5 | Designation of a new GPC for the CPTEC (Brazil) | To submit a formal CBS Recommendation to the sixty-second session of the WMO Executive Council (June 2010) to include CPTEC in the list of designated GPCs in the Manual on the DPFS | President of CBS | All necessary steps for EC-62 have been completed (DPFS) |
| 3.1.3.8 | Review of the WMO Technical Note 170, entitled: “Meteorological and Hydrological Aspects of Siting and Operations of Nuclear Power Plants” | To continue collaboration with the International Atomic Energy Agency (IAEA) in relation to their current revision of their Safety Guide: “Meteorological and Hydrological Hazards in Site Evaluation for Nuclear Installations | OPAG-DPFS | Conducted initial expert review of relevant sections to nuclear emergency response activities (ERA), on-going. |
| 3.1.3.9 |  | To clarify which aspects of the review process are relevant to CBS and to CCl, and to report to EC accordingly | Secretariat | Re-contacted CLW, on-going (DPFS). |
| 3.1.4.1 | CBS software registry | To invite WMO Members to consider offering meteorological application software for free exchange among Members and to provide the Secretariat with the information required to update the CBS software registry | Secretariat | A WMO letter to all WMO Members is being finalised |
| 3.1.4.2 | Routing of CLIMAT bulletins on the GTS | To inform the WMO Members operating an MTN centre of the status of updating the catalogue of meteorological bulletins and the routeing catalogues, and to urge them to review and update these catalogues in accordance with the functions and responsibilities of an MTN/RTH given in the Manual on the GTS. | Secretariat | A WMO letter to all WMO Members is being finalised |
| 3.1.4.3 |  | To review of the activities of the GCOS Monitoring Centres and CBS Lead Centres for GCOS to align their monitoring activities in coordination with RTH centres | GCOS OPAG-IOS OPAG-ISS |  |
| 3.2.2 | Developments of the WWIS | To develop a well-crafted usage policy. | OPAG-PWS | This will be on the agenda for discussion by PWS OPAG Implementation Coordination Team (ICT) meeting (Shanghai, Sept 2010) |
| 3.2.3 | WENS project in Shanghai | To share the valuable experience and lessons learned from the project with other WMO Members | OPAG-PWS | This will commence in 2011 following the conclusion of WENS |
| 3.3.1 | Strategy for monitoring climate from space and accompanying comprehensive architecture | To review the concept and early plans | ET-SAT | A white paper articulating the challenges and opportunities for such an architecture has been developed, and will be presented in an EC-LXII side event scheduled for Friday, 11 June. Three space agencies (CMA, EUMETSAT and NOAA) will describe their current and planned climate missions, as well as comment on the need for such an architecture. |
| 4.2.1 | Expert services needed in the development and implementation of projects within the framework of the WMO Technical Cooperation Programme. | To invite the WMO Members to inform of the availability of such experts and the nature of the services, which their experts could provide, including possible constraints | Secretariat | A WMO letter to all WMO Members is being prepared by DRA |
| 4.2.2 | Sustainability of the operation of the upper-air network | To continue seeking for resources required to assist countries in the operation of the upper-air network with a priority for the stations of the GCOS upper-air network (GUAN) | GCOS Secretariat |  |
|  |  | To consider developing innovative arrangements to reduce the costs of operation of the upper-air network | Secretariat | On-going activity |
|  |  | To draft of a paper on the benefits derived from the operation of the GOS that could help the WMO Member countries in ensuring the sustainability of their observation networks by themselves | Secretariat |  |
| 4.3.3 | Development of guidelines for standardization of databases, metadata and hazard analysis for meteorological hazards | To discuss alignment of commissions and their cooperation in this area | ICTT for the Development of guidelines for standardization of databases, metadata and hazard |  |
| 4.4.2 | Development of a set of performance and target indicators for monitoring the operation of the WWW | To develop a strategy | MG |  |
| 4.5 | Relationship between GEO and WMO, particularly CBS | To continue to improve the linkages between the ongoing and planned activities of CBS with related activities in GEO, particularly with regard to GEOSS | CBS GEO/GEOSS coordinator | EC-LXII Doc. 5.2(2) calling for a reaffirmation of Cg-XV guidance was presented on Wednesday, 9 June. [ Add’l information to be added after EC deliberations] |
| 5.1.1 | CBS Operating Plan (OP) | To continue developing the CBS operating plan | CBS OPAGs Secretariat | Contributions to the CBS OP provided by OPAG IOS, ISS and PWS |
| 5.2.3 | Working mechanisms between CBS and Regional Associations | To clarify the Working mechanisms between CBS and Regional Associations | MG Secretariat |  |
| 6.2 | Arrangements for CBS-Ext.(2010) | To ensure that the parts of the documentation, that are critical for decisions by the session, be made available in the WMO working languages | Secretariat | The documentation plan for CBS-Ext.(2010) was prepared in this respect. |
| 6.5 |  | To identify the Internet bandwidth required for the WIS demonstrations. | Secretariat | Done (Internet bandwidth estimated to 5 Mbits/s) |
| 6.6 |  | To foster the use of synchronization software if possible for both PCs (e.g. “Allway Synch” tested during EC-LXI) and Macintosh platforms To continue posting a spreadsheet showing the availability of the documents | Secretariat | On-going |
| 7.1 | TECO | To further develop the program and to coordinate with GEO Secretariat in finalising it | Sub-group tasked to prepare the TECO |  |
| 7.2 | TECO | To liaise with Namibia for information on the support provided by Namibia to the organisation of the TECO | Secretariat |  |
| 8.1 | Meetings of the MG | To organise meetings of the MG (informal meetings, MG-12, MG-13) | Secretariat | On-going |
| 9.2 | Communication of information related to CBS | To prepare monthly on a rotation basis informative reports on the activities of CBS | Members of the MG |  |
|  |  | To continue the practice of including an executive summary at the beginning of the reports of meetings of ETs be continued To prepare an action sheet for each meeting of ETs, including decisions and follow-up action To make the reports and action sheets available from the WMO server and inform the recipients of the WWW monthly operational letter of the availability of this information To review the contents, including the links, and the presentation of the CBS home page | Secretariat | The CBS home page was reviewed (see http://www.wmo.int/pages/prog/www/BAS/CBS-info.html) |