| WORLD METEOROLOGICAL ORGANIZATION ______________ COMMISSION FOR BASIC SYSTEMS MANAGEMENT GROUP, FIFTH SESSION GENEVA, SWITZERLAND, 26-29 APRIL 2005 |  | CBS-MG-V/Doc. 3.2(2) (25.IV.2005) ______ ITEM 3.2 Original: ENGLISH |
| --- | --- | --- |

#### OPAG on Information Systems and Services

Teams deliverables and work schedule

(Submitted by the Secretariat)

Summary and Purpose of Document The document includes the OPAG on ISS Teams tasks, as decided by CBS-XIII, and submits a proposal for the targets for deliverables and work schedule for the Expert Teams.

## ACTION PROPOSED

The CBS-MG is invited to agree upon the targets for deliverables and work schedule for the ICT and the ETs of the OPAG on ISS.

______________

References:	CBS-XIII/PINK 9, 3.2(1), 3.2(2), 3.2(3) and 3.2(4)

Appendices:	A.	TORs for the ISS/ ICT and ETs and proposed work plan and deliverables;

B.	Outcome of ICG-FWIS, first session, 12-14 January 2005, Geneva

###### DISCUSSION

- CBS-XIII agreed on its work programme, decided to re-establish the Open Programme Area Group on Information Systems and Services (OPAG-ISS) and agreed to establish teams as well as rapporteurs within the OPAG with their respective Terms of References (TORs).

- The overall structure established under the OPAG-ISS and the teams’ membership is discussed in Doc. 3.2(1) submitted to this session of the MG.  The TORs for the respective teams, as approved by the Commission and the proposed teams work plans and targets for deliverables are included in Appendix A.  The Management Group is invited to consider and agree upon the proposed deliverables and work plan for the OPAG-ISS teams during the current intersessional period (2005-2006).

- As CBS is requested to continue to play a leading role in the development of the (future) WMO Information System, the main outcome of the first session of the Intercommission Coordination Group on FWIS, as submitted to the 2005 Meeting of Presidents of Technical Commissions, is provided in Appendix B for information to the CBS-MG.

__________________________

## OPAG on Information Systems and Services (OPAG-ISS)

- Implementation-Coordination Team on Information Systems and Services (ICT-ISS)

- Assess the implementation aspects at regional and global levels, including sustainability, of the recommendations and proposals developed by the ISS Teams;

- Review and consolidate the recommendations and proposals developed by the ISS Teams with a view to their submission to CBS;

- Monitor, assess and take follow-up action on ISS requirements emerging from the cross-cutting WMO Programmes and other international Programmes/projects such as THORPEX, IPY, DPM and GEOSS;

- Identify matters requiring the urgent consideration of the OPAG-ISS, and develop proposals for tasks and organization of activities.

#### ICT- ISS work plan and deliverables

  - One meeting of the ICT-ISS is planned in Q3 2006 to review and consolidate all the proposals and recommendations to CBS from the ISS/ETs and rapporteurs.

- Coordination Team on Migration to Table Driven Code Forms (CT-MTDCF)

- Coordinate, monitor and assess the overall implementation of the migration plan to table-driven representation forms and related training activities.  Work with National and Regional Focal Points to identify possible pilot projects;

- Identify and solve in cooperation with national and regional focal Points problems that may arise during the migration phase;

- Define and review the related software projects for distribution of universal BUFR, CREX and GRIB encoding/decoding software;

- Work with ET-DRC to identify and develop additional BUFR and CREX descriptors to address the optional sections of existing code structures within the current alphanumeric code forms; and to address regional and national coding and reporting practices as needed;

- Provide central coordination of activities including experimental and operational exchange.  Work with the Secretariat to report on these activities in a “Migration News” section of the WWW newsletter;

- Work together with other relevant international bodies including ICAO, CAeM, IOC, JCOMM and satellite operators, to co-ordinate, agree and resolve migration issues related to specific code types;

- Monitor the impact of the migration process on the GTS and data processing centres.  Identify problems and coordinate with National and Regional Focal Points, RTH Focal Points, other Teams and OPAGs as needed to develop and implement solutions;

- Coordinate and work with National Migration to TDCF Steering Groups (MTSG) and National Focal Points to assist their development and implementation of their National Implementation Plans;

- The chairman of CT-MTDCF would sit as a member on ET-DRC and other groups as needed.

#### CT- MTDCF work plan and deliverables

- Accomplishing real coordination task and providing necessary assistance (mostly in the form of information) when requested by the various regional rapporteurs and groups concerned.  It is also fundamental that the CT on MTCDF coordinates with the regional rapporteurs dealing with Codes and Data Management matters (or ISS).  Information should be systematically sent to the Permanent representative of all the countries, in addition to the 100 focal points on Code matters, to help countries for the migration including developing a national migration plan.

- An important task stems from the implications on the Manual on Codes of the Migration to Table-Driven Code Forms.  CBS reasserted the need to separate and update reporting practices from the Traditional Alphanumeric Codes (TAC).  Additional work would need to consider what would be the best order for BUFR template parameters both from a migration standpoint and a coding standpoint.  CBS noted that national coding practices for TDCF that are not recorded in the Manual on Codes would make migration to TDCF more difficult.  Consultancy work supervised by the CT will be necessary to finalize these tasks.

- One meeting of the CT-MTCDF in 2005 (last quarter) and another one in 2006 prior to the ICT on ISS in 2006 will be appropriate to monitor and mitigate adequately the migration process and the related difficulties encountered by the WMO Members.

- Training on MTDCF will be organised for East RA VI and West RA II countries in 2005.  It will be organised for Russian speaking RA VI countries in 2006.  East RA V and again RA I should also receive training in 2006 or 2007.

- Expert Team on Data Representation and Codes (ET-DRC)

Requirements for changes to representation forms should be provided by the other OPAGs, especially IOS and DPFS.

- Maintain all WMO data representation forms and further develop table driven codes in particular BUFR, CREX, and GRIB2, by defining descriptors, common sequences and data templates, including the data representation of regional practices, so they meet the requirements of all Members and other concerned International Organizations, such as ICAO, most efficiently;

- Adapt and update current reporting practices in the alphanumeric code regulations for adaptation to Table Driven Code Forms; work with OPAG-IOS to ensure that statements on observing practices are consistent and in appropriate formats and locations;

- Invite and assist Members to participate in the experimental exchange of data encoded in modified or new formats, and provide Members with guidance on data representation of national practices, on a bilateral basis;

- Determine the continuing use of the different WMO data representation forms and recommend options for their future roles or disposition;

- Update the content of the Manual on Codes and the Guide on table driven codes as required;

- Develop guidance and practices for the meteorological information representation based on XML and on NetCDF.

#### ET- DRC work plan and deliverables

- CBS agreed to consider the use of XML, more and more used within the Internet community, for the presentation of WWW data and products to users outside the WMO community.  Knowledgeable experts and consultants should be used for to developing standards to exchange meteorological data in XML. A consultant will compile information on the use of XML by WWW centres by end of October 2005.

- Constant cooperation with the CT - MTCDF is required for defining new descriptors to fit templates for migration traditional data in BUFR, as well redefining the regulations of the Manual to adapt them for BUFR/CREX representation, and also in the near future XML data representation.

- Coordination of WMO request to ICAO to seriously consider for the future, to bring into phase the implementation date of WMO code changes and the corresponding Annex 3 amendments.  ICAO indicated its the firm intention to ensure, in co-ordination with WMO, that the applicability dates of future amendments to ICAO Annex 3/Technical Regulations [C.3.1] related to aeronautical meteorological codes and of the corresponding changes to the WMO codes would coincide.

- Importance of streamlining the approval of code changes, for example by striving to adapt the calendar of the meetings on code matters with a view to meeting the target dates for code changes.  For that purpose a meeting in the fourth quarter of 2005 will be appropriate for considering necessary changes for the next amendments of ICAO/Annex 3, which will have to be examined by CBS in November 2006 for implementation in November 2007.

- Inter-Programme Expert Team on Metadata Implementation (IPET-MI)

- Pursue the development of the metadata standard to be used in the WMO information system (WIS) as a WMO core profile within the context of the ISO 19115 geographic information standard, and contribute to and interact with ISO as appropriate, including creating a core feature catalogue in compliance with ISO 19110;

- Develop WMO Metadata standard extensions specific to the WWW Programme, and promote development of extensions specific to other WMO Programmes in liaison with respective Technical Commissions;

- Further study the use of related ISO metadata standards, especially the ISO 19100 series, for the development of the WIS;

- Coordinate the development of reference XML Metadata1 templates and reference implementation;

- Develop guidance for the implementation and use of operational information catalogues.

#### IPET- MI work plan and deliverables

- To finalise the draft version 1.0 of the WMO Core Profile of the ISO Metadata Standard, including an XML representation, taking into account the results of the test of the draft version by WMO Programmes and the development of a Core Feature Catalogue compliant with ISO 19110;

- To review the requirements for the extensions of the WMO Core Profile of the ISO Metadata Standard specific to the WMO Programmes and prepare relevant draft extensions for tests;

- To develop a reference implementation of the Profile so that it can be used as a guide by implementers; develop or provide references to tools to facilitate the manual creation of metadata and for applications to maintain metadata in the standard Profile;

- To develop proposals for the establishment and the maintenance of operational information catalogues required for WIS;

- To identify mechanisms for users to search globally amongst metadata catalogues;

- To present the draft version 1.0 of the WMO Core Profile of the ISO Metadata Standard to the ISO Technical Committee (TC) 211 responsible for the series 19100 of ISO standards.

- To develop proposals for the possible application of the ISO 1900 series of standards for the implementation of WIS;

- To draft the parts of the WMO Guide on Data Management, that the team is responsible for;

- To organise a workshop on metadata and hold a meeting of the team in the third quarter of 2005.

- Rapporteur on the WMO Guide on Data Management

- Coordinate the revision of the WMO Guide on Data Management and its updating.

Work plan and deliverables

- To liaise with the OPAG chairs for sharing the responsibilities for the edition of the guide between the OPAGs (reference: Annex to paragraph 7.13 of the report of ICT-ISS 2004);

- To compile the contributions of the OPAGs to the guide and incorporate them in a draft guide.

- Expert Team on WIS-GTS Communication Techniques and Structure (ET-CTS)

Co-chair on Enhanced Utilization of Data Communication Techniques; Co-chair on WIS-GTS data communication structure.

- Develop recommended practices and technical guidance material for data communication techniques and procedures (GTS, WIS and Internet), including security aspects, with a view to ensuring efficient and safe operations of information systems, and inform Members of relevant developments in ITU and ISO;

- Review standard TCP/IP procedures and applications, including new developments (e.g. IPv6) that are relevant to WWW and other WMO Programme requirements, and develop recommended practices;

- Review and develop updates to recommended practices for data-communication and data access procedures, including OPeNDAP, NetCDF and HDF, as well as consolidation of the file naming convention for operational routeing and distribution;

- Develop the organization and design principles for the WIS data communication structure, and coordinate related pilot projects;

- Review and propose updates to the organization and design principles for the GTS to take the best benefits of ICT development, especially as regards its smooth evolution towards the core communication component of WIS;

- Provide guidance on technical, operational and administrative/financial aspects of data-communication services for WIS implementation, especially for the GTS-WIS at global, regional and national levels, including dedicated and public services (e.g. satellite-based telecommunications, managed data-communication network services, the Internet);

- Review current and anticipated data-communication and information system requirements of the WWW and other WMO Programmes.

#### ET- CTS work plan and deliverables

- Finalize the Guide on use of FTP and FTP servers at WWW centres, the Guide on Information Technology Security (ITS) at WWW centres and review the Guide on Internet Practices as necessary  (End of 2005).

- Finalize the general new file naming convention, in collaboration with the ET-OI (End  2005).

- Finalize a new IP address scheme and migration plan to resolve the issue of IP addresses for GTS links, in close association with the centres that are the main users of the current IP addresses  (mid 2005). Study IPv6 and the possibility of registering IPv6 addresses for WMO purposes (End of 2006). Update and refine as required the current Guide on Virtual Private Networks (VPN) via the Internet between GTS centres.

- Draft recommended practices for data-communication and data access procedures, in particular OPeNDAP, NetCDF and HDF (Q3 2006).

- Draft Organization and Design principles for the WIS data communication structure (Q3 2006); promote/coordinate related pilot projects, including the WIS VPN pilot project in Regions II and V.

- Proposed updates to the organization and design principles for the GTS, especially the MTN, taking benefits from ICT development (e.g. MPLS), including its evolution towards the core communication component of WIS (End of 2006).

- Promote and facilitate with operating NMSs and organizations the integration of satellite-based data-distribution systems into the GTS/WIS as coordinated components for the distribution of large volume of information, including the new WMO Space Programme Integrated Global Data Dissemination Service (IGDDS).

- Guidance (consolidation, update and new development) on technical, operational and administrative/financial aspects of data-communication services for WIS implementation, especially for the GTS-WIS at global, regional and national levels, including dedicated and public services (e.g. satellite-based telecommunications, managed data-communication network services, the Internet) (Q3 2006).

- A session of the ET-CTS is planned for Q2 2006.

- Expert Team on WIS GISCs and DCPCs (ET-WISC)

Co-chair on WIS GISCs, Co-chair on WIS DCPCs

- Develop technical and operational specifications for the different components of the WIS GISCs;

- Develop technical and operational specifications for the different components of the WIS DCPCs

- Develop criteria for interoperability and certification for actual implementation;

- Coordinate related pilot projects.

#### ET- WISC work plan and deliverables

- Draft technical and operational specifications for different components of the WIS GISCs, including finalization of the Virtual GISC Prototype (End of 2005).

- Initial draft technical and operational specifications for different components of the WIS DCPCs (End of 2005), and consolidated specifications (mid 2006).

- Initial criteria for interoperability and certification for actual GISC and DCPC implementation (End of 2005).

- Identification and Coordination of pilot projects related to GISCs and DCPCs, including VGISC, Roshydromet CliWare (CCl), the European SIMDAT project, the End-to-End Data Management Project -E2EDM (JCOMM), the US-GOOS DMAC and foreseen projects in the framework of GTN-H and WHYCOS (CHy), GAW and THORPEX (CAS) and WAMIS (CAgM).

- Coordination of related contributions to the CBS-Ext. 06 Technical Conference on WIS (Q4 2006).

- A workshop on GISC development, jointly with a CBS/ET-WISC session, is planned for Q4 2005.  Note: The 2nd session of the ICG-FWIS is planned from 24-28 October 2005, Boulder, USA, with the recommended participation of the chairs of the most relevant TCs’ Teams as experts, including CBS/ IPET-Metadata, ET-CTS and ET-WISC.

- Steering Group on Radio-Frequency Coordination (SG-RFC)

- Keep under review allocations of radio-frequency bands and assignments of radio-frequencies to meteorological activities for operational requirements (telecommunications, instruments, sensors, etc.) and research purposes, in close coordination with other technical commissions, especially CIMO and the CBS/OPAG on IOS;

- Coordinate with WMO Members, with the assistance of the WMO Secretariat, to:

- Ensure the proper notification and assignment of frequencies used for meteorological purpose;

- Determine their future use of the radio spectrum for meteorological purpose;

- Keep abreast of the activities of the Radiocommunication Sector of the International Telecommunication Union (ITU-R), and in particular of the Radiocommunication Study Groups, on frequency matters pertaining to meteorological activities, and assist the WMO Secretariat in its participation in ITU-R work;

- Prepare and coordinate proposals and advice to WMO Members on radio-regulation matters pertaining to meteorological activities with a view to ITU Radiocommunication Study Groups, Radiocommunication Assembly, World Radiocommunication Conferences and related regional/global preparatory meetings;

- Facilitate the coordination between WMO Members for the use of frequency bands allocated to meteorological activities with respect to:

- Coordination of frequency use/assignments between countries;

- Coordination of frequency use/assignments between various radio communication services (e.g. meteorological aids and DCPs) sharing the same band;

- Facilitate the coordination of WMO with other international organizations which address radio-spectrum planning, including specialized organizations (e.g. CGMS, SFCG) and regional telecommunication organizations (e.g. CEPT, CITEL, APT);

- Assist WMO Members, upon request, in the ITU coordination procedure of frequency assignment for radio communication systems sharing a frequency band with meteorological radio communication systems.

#### SG-RFC work plan and deliverables

- Organize a Workshop on Radio Frequencies for meteorology, including sharing aspects between Met Aids and Met Sat in common bands (3rd quarter 2005).

- Contributions to issues on radio frequencies for meteorology, in particular related to the protection of spaceborne passive sensing bands.  Close collaboration with CIMO as well as with the OPAG on IOS on radio-frequency matters pertaining to instruments. Promote/facilitate (by providing information and guidance) Members’ participation in national, regional and global (i.e. ITU-R) activities regarding radio frequencies.

- Finalize updates of the joint ITU-WMO publication "Handbook on use of radio spectrum for meteorology" in coordination with the ITU-R (mid 2005)

- Guidance and information for Members on relevant issues for the next World Radiocommunication Conference 2007 (end 2006).

- One meeting of the SG-RFC is planned in 2006, in conjunction with ITU-R/WP 7C meeting, to coordinate WMO’s participation and contribution to relevant ITU-R work.  (One meeting was also held from 2-4 March 2005)

- Rapporteur on WWW Monitoring

- Review and coordinate the continuous improvement of the current WWW monitoring (AGM and SMM), including ad hoc monitoring exercises especially for products and in the framework of the migration to TDCF;

- Coordinate operational trial of enhanced WWW monitoring and assess the impact, in particular as regards the resources needed at RTHs and NMCs, including the possible sharing of software applications (e.g. “WWW monitoring PC”);

- Review the overall monitoring requirements for the WIS with a view to developing the WIS monitoring scheme.

#### Work plan and deliverables

- To submit proposals for the extension of the current WWW monitoring (AGM, SAM, SMM) required for the migration to TDCF in liaison with RTH focal points;

- To organise an operational trial of the Integrated WWW Monitoring (IWM), based on the use of PCs (e.g. use of DWD METDATA software) and involving an RTH in Region I, and to make a report on the impact on RTHs and NMCs;

- To develop proposals for the WIS monitoring scheme, in particular the monitoring tasks of the WIS GISCs,  DCPCs and NCS

- Expert Team on GTS-WIS Operations and Implementation (ET-OI)

(Activities to be carried out in close coordination with the ET-DRC chair, CT- Migration to TCDF chair, Rapporteur on WWW Monitoring, Rapporteur on the WMO Guide on Data Management and Focal points of RTHs located on the MTN, with the assistance of the Secretariat, mainly by correspondence – e-mail).

- Monitor the GTS-WIS operational information flow and coordinate management of operational information exchange procedures, routing and traffic; co-ordinate  the allocation of abbreviated headings required for the exchange of data and products and for the  migration to TDCF;

- Coordinate and further develop recommended practices and guidance on the management of and access to operational information related to WWW information exchange, specially for GTS-WIS operation (Abbreviated Heading tables, catalogue of bulletins and files, routing directories, etc.);

- Develop recommendations for coordinated implementation and planning of techniques, procedures and systems for the MTN and MTN centres, including towards the core communication component of WIS;

- Develop a mechanism for allocation of unique identifiers required for the file naming convention, and other identification purposes;

- Identify implementation issues requiring the urgent consideration of the OPAG-ISS.

#### ET- OI work plans and deliverables

  - In coordination with ET-CTS assess the status of GTS operational procedures at RTH centres and their respective NMCs with respect to their ability to receive, handle and relay binary messages, and the maximum message length that is possible in their Message Switching system (End of 2005).

  - In coordination with ET-CTS examine the use of the International Alphabet No.5 (8 bits) with a view to allow a more flexible usage in meteorological messages containing plain text, in particular the use of upper and lower case characters (Q4 2006)

  - Examine and review the present and future requirements for the allocation of abbreviated headings TTAAii CCCC YYGGgg (BBB) to facilitate the migration to table-driven code forms, to distribute “migrated data” encoded in BUFR and CREX (On-going).

  - Maintain and update a comprehensive and coherent set of Tables in Attachment II-5 of the Manual on GTS (WMO No. 386) and to develop extensions of the Tables to cover the requirements including the “migrated data”, the ensemble prediction GRIB data issued by numerical weather prediction centres and BUFR messages issued by the WAFCs (On-going).

  - Develop jointly with ET-CTS as a matter of urgency a mechanism and common approach for assigning unique identifiers in a wide range of activities, including documents, file names and station identifiers based on a sequence of delegating authority to generate identifiers (End 2005).

  - An Implementation-Coordination Meeting on the MTN (GTS-WIS) is planned for 2006 for coordinating implementation and planning of techniques, procedures and systems for the MTN and MTN centres, including towards the core communication component of WIS.

Intercommission Coordination Group on FWIS

(ICG-FWIS, first session, 12-14 January 2005, Geneva)

    - The Fourteenth Congress endorsed the concept of the Future WMO Information System (FWIS), as an overarching approach to meet information exchange requirements of all WMO Programmes.  Congress requested CBS to pursue the further development of the FWIS, while emphasizing that all WMO Programmes and technical commissions should actively participate and contribute its own expertise and resources in all phases of the development of the FWIS.

    - EC-LVI agreed that a strong, high-level coordination and collaboration mechanism spanning across the technical commissions was needed for achieving the challenging task of the development of FWIS.  By Resolution 2 (EC-LVI) EC-LVI established the Intercommission Coordination Group on FWIS (ICG-FWIS), chaired by Prof. G.-R. Hoffmann (Germany) with the following terms of reference:

(a) To coordinate the refinement and consolidation of the FWIS based on the approved concept and then the implementation planning phases;

(b) To assess in detail the data exchange and data management requirements of WMO Programmes, at present and for the foreseeable future, which should be met by the FWIS;

(c) To advise the technical commissions on the development in data-communications and management functions to be required in the FWIS as regards their respective programmes;

(d) To guide the orderly evolution of existing WMO information systems towards FWIS;

(e) To address the major issues that had been identified.

[The major issues that had been identified include metadata standard, data catalogue, practices for the collection, exchange and electronic archival of data and related metadata, coordinated data-communication practices, mapping information functions of WMO Programme centres to the functional components of FWIS (i.e. NCs, DCPCs and GISCs functions).]

    - The ICG-FWIS held its first session from 12-14 January 2005, in WMO Headquarters, Geneva. It noted the outcome of the final session (Geneva, IX.2004) of the CBS/ Inter-Programme Task Team on FWIS (ITT-FWIS).  The ITT-FWIS reviewed pilot projects that have a strong relationship to the development of the FWIS, including the WMO Core Metadata Standard, the Virtual (distributed) Global Information System Centre (VGISC) in RA VI, the Virtual Private Network project in RA II & V, the EUMETNET UNIDART project, the JCOMM End-to-End Data Management Project (E2EDM), the Roshydromet CliWare project, the Earth System GRID, the Community Data Portal and the European SIMDAT project.

    - The ICG-FWIS emphasized that the implementation of FWIS would build upon the most successful components of existing WMO information systems.  Based on the information collected by the CBS/ITT-FWIS and on contributions from TCs’ representatives at its meeting, the ICG-FWIS reviewed data exchange and data management requirements of WMO Programmes and considered respective data management and communication structures and plans.  It stressed that significant further work was required from the individual WMO Programmes, as well as through a common effort, to consolidate a comprehensive and consistent status of data exchange and data management requirements, as well as a mapping of information functions of WMO Programme centres to the functional components of FWIS.

    - The ICG-FWIS recommended that a consultant be hired to compile and consolidate a document, by mid-2005, on the data exchange and data management requirements of WMO Programmes, which should be met by the FWIS, through interaction with the respective TC representatives in the ICG-FWIS.  The consultant would also address the mapping, with respect to information and communications components, of the current and future structure of WMO Programmes to the functional components of FWIS (i.e. NCs, DCPCs and GISCs functions).  The TCs’ replies to the questionnaire on their programme(s) information exchange requirements would be used as background material.  ICG-FWIS TC representatives should prepare for contributing information to the consultant.  They were also expected to make sure, before the next ICG-FWIS meeting, that the document content would be consistent with their TCs Programme strategy and plans.

    - The ICG-FWIS strongly supported the establishment and activities of TCs’ Expert Teams that are relevant to FWIS (data-management, metadata, XML, data-exchange) for fostering the FWIS development.  It noted that CBS would pursue its proactive role in and contribution to the further development of the FWIS through activities relevant to its OPAGs, in particular the OPAG on Information System and Services, and that CBS-XIII would consider establishing an Expert Team on FWIS/GTS Communication Techniques and Structure, an Expert Team on FWIS GISCs and DCPCs, and an Inter-Programme Expert Team on Metadata Implementation.  The ICG-FWIS emphasized that the cooperation and coordination between corresponding TCs’ Expert Teams was of prime importance. The cross-participation/involvement of experts between corresponding TCs’ Expert Teams was strongly encouraged to facilitate consistent and rapid progress.

    - The ICG-FWIS recommended that its next session be held from 24-28 October 2005, (tentatively Boulder, USA).  It recommended participation of the chairs of the most relevant TCs’ Teams as experts, including the CBS/IPET-Metadata and ET-FWIS/GTS.

    - Metadata aspects are crucial for the FWIS development, and should be quickly consolidated. The ICG-FWIS fully endorsed the WMO Core Profile of the ISO Metadata Standard.  It invited Technical Commissions to develop and contribute WMO metadata extensions specific to their respective WMO Programmes.  It noted with appreciation the foreseen CBS/ Inter-Programme Expert Team on Metadata Implementation, and recommended that the TC focal points on metadata be members of the Team.  Pilot projects on Metadata implementation, including translators for various programme data sets, should be actively pursued (e.g. NCAR/VGISC, Roshydromet CliWare).  The ICG-FWIS recommended that a workshop on metadata be organized, jointly with a CBS/IPET-Metadata session, by September 2005.

    - The ICG-FWIS emphasized that the success of FWIS was depending upon pilot projects related to various WMO Programmes that would be actively supported by volunteering Members.  The experience gained through pilot projects would be shared with all Members to promote and facilitate an early introduction of FWIS elements.  The ICG-FWIS noted with satisfaction the progress made on the Virtual GISC Project with participation of DWD, UK MetOffice, MeteoFrance, ECMWF, EUMETSAT, and NCAR, the Virtual Private Network project in RA II & V led by JMA, the Roshydromet CliWare (CCl), the European SIMDAT project, the End-to-End Data Management Project -E2EDM (JCOMM) and the US-GOOS DMAC.  It also noted with appreciation that pilot projects related to FWIS were under consideration in the framework of GTN-H and WHYCOS (CHy), GAW and THORPEX (CAS) and WAMIS (CAgM).  The ICG-FWIS invited all Members concerned to further develop and promote current FWIS-related Pilot Projects, and to launch new Pilot projects.  It requested the CBS/ET-GISC&DCPC to assist in identifying and listing the recognized projects contributing to FWIS.

    - The ICG-FWIS recommended a proactive promotion of the awareness of FWIS in WMO bodies sessions, including TCs and RAs by a systematic inclusion as an agenda item, and by adequate presentation in conferences and various events (e.g. AMS, EMS, etc.).  Each TC representative was invited to take appropriate action within his TC in this respect.  The ICG-FWIS also recommended the implementation of a dedicated FWIS Web page on the WMO Web site, with a pointer on the WMO main page.  The FWIS Web page would include basic reference documents and presentations, that would be kept updated to reflect the progress in FWIS plans.

    - The ICT-FWIS agreed that the qualifier “Future” in the name “Future WMO Information System (FWIS)”, which was relevant when the concept had been launched, was not adequate any longer when entering the implementation phase.  It noted that the ITT-FWIS had recommended that the name be changed;  two proposals emerged, as “Framework for the WMO Information System (FWIS)” or “Global WMO Information System (GWIS)”.  The ICT-FWIS finally recommended that the name “WMO Information System (WIS)” be adopted, which would well reflect the structure and purpose of the system and appear as a logical phase after the initial future WMO Information System project.  This recommendation also took into account difficulties created in other languages by the pleonasm “Global World” as regards the name “Global WMO Information System (GWIS)”.  The PTC meeting is invited to recommend the change to the Executive Council.

    - With respect to the EOS initiative, the ICG-FWIS emphasized that the FWIS (WIS) should be an initial component as well as an important backbone building block within the GEO system of systems (GEOSS) for achieving a greater interoperability and connectivity among individual component observing systems.  It agreed that the participation of the WMO Information System as a critical component of the GEOSS, which was a unique opportunity as well as a challenge, should be actively promoted.

______________________

# Footnotes

Used for describing information