| WORLD METEOROLOGICAL ORGANIZATION ______________ COMMISSION FOR BASIC SYSTEMS MANAGEMENT GROUP, EIGHTH SESSION (REDUCED) GENEVA, SWITZERLAND, 16-17 JUNE 2008 |  | CBS-MG-8(RED)/INF. 4 (05.VI.2008) ______ Original: ENGLISH |
| --- | --- | --- |

CBS MANAGEMENT GROUP SEVENTH SESSION ACTION SHEET

__________

CBS Management Group, Seventh session

# Geneva, Switzerland, 18 - 20 June 2007

# ACTION SHEET

| Para. of the Fin. Report | Subject | Action required | Responsible | Deadline | Status/remarks |
| --- | --- | --- | --- | --- | --- |
| 2.5 | CBS working methods | Develop proposals for improving CBS working methods | Secretariat (C/ISS-lead, C/OSY, C/DPFS, C/PWS) | End of 2007 | Impact of proposed procedures on inter-sessions direct adoption of amendments to be discussed under AOB at MG-8. |
| 2.7 | Membership of CBS Expert Teams | Preparation of nomination forms prior to CBS-XIV | Chairs of: OPAG-IOS OPAG-ISS OPAG-DPFS OPAG-PWS In coordination with the Secretariat (C/ISS-lead, C/OSY, C/DPFS, C/PWS) | October 2008 | Proposed use of ET-ADRS nomination forms as exemplar (incl. PR’s commitment on experts’ time); Revised proposed structure of OPAGs required for seeking nominations |
| 2.8 | CBS certificate for recognition | Develop proposals for certificates of recognition of significant contributions of experts to the CBS activities | Secretariat (C/OSY-lead, C/ISS, C/DPFS, C/PWS) In collaboration with President and OPAG Chairs | September 2008 | Completed. Draft prepared and will be discussed under AOB at MG-8. |
| 2.9 | Establishment of the Trust Fund | Initiate a project for the establishment of a Trust Fund for the CBS OPAG Expert Teams | Secretariat C/ISS-metadata, C/DPFS-SWFD, C/OSY-WIGOS, C/PWS) | December 2007 | Completed. CLs to potential Donors were sent in Jan 08. WIGOS Trust Fund had been established in Feb 08, and WIS Trust Fund pursued. |
| 3.3 | CBS Operational Planning Framework document | Develop a document presenting CBS operational planning framework for 2010-2011 to be submitted to CBS-XIV | President, Vice-president OPAG Chairs | September 2008 | Completed. FOR DISCUSSION AT MG-8, AGENDA ITEM 5 |
| 3.5 | CBS strategic planning input | Coordinate and submit consolidated CBS input for initial draft strategic Plan 2012-2015 | Secretariat (D/WWW, Strategic Planning Office) | July 2008 | Completed. FOR DISCUSSION AT MG-8, AGENDA ITEM 5, |
| 4.1.1.7 | OPAG-IOS activities | OPAG-IOS to give all possible support to the implementation of the Congress resolution on the GOS through planning and implementation of specific actions in the work programmes of its expert teams and rapporteurs; | OPAG-IOS Chair/Co-chair, Chairs of : ET-EGOS, ET-SUP, ET-SAT, ET-AWS, OPAG-IOS and Regional Rapporteurs, Secretariat (C/OSY-lead, C/SBOS) | According to the work programmes | Support provided through available working mechanism |
|  |  | OPAG-IOS to participate and continue to support studies of observation targeting strategies based on the THORPEX, AMMA and IPY results; |  | November 2007 | THORPEX, AMMA and IPY supported by OPAG-IOS and ET-EGOS. |
|  |  | OPAG-IOS, through its ET-EGOS, ET-SUP, ET-SAT, ET-AWS and rapporteurs, following the guidance given in the Implementation Plan (Framework) for Evolution of Space and Surface-Based Sub-systems of the GOS (IP-EGOS), to pursue, especially in developing countries a wider use of observing systems (e.g., satellite, AMDAR) that were less dependent on infrastructure, expertise and funding; |  | According to the work programmes | NFP were provided with the IP-EGOS and the Statement of Guidance. |
|  |  | OPAG-IOS, through its ET-AWS and ET-EGOS, to promote the use of automatic weather observing systems that enable cost effective real-time measurements, compatible with data from conventional systems, of quality and reliability suitable to all climate conditions; | OPAG-IOS Chair/Co-chair, Chairs of : ET-EGOS, ET-SUP, ET-SAT, ET-AWS, OPAG-IOS and Regional Rapporteurs, Secretariat (C/OSY-lead, C/SBOS) | February 2008 | ET-AWS prepared a draft guidance material for Members. |
|  |  | OPAG-IOS, through its ET-EGOS, to establish coordination with national points of contact responsible for reporting progress and plans in their country related to IP-EGOS; |  | June 2008 | Members requested to nominate NFP. Nominated NFP were provided with the IP-EGOS and requested to provide national reports to be assess by ET-EGOS. |
|  |  | OPAG-IOS, through its ET-EGOS, ET-SUP, ET-SAT, ET-AWS and rapporteurs, in coordination with WG PIW to promote implementation/evolution of the GOS in the Regions through sustainable functioning of RBSNs/RBCNs and keeping under continuous review related regional requirements. |  | September 2008 | The WG PIW of RA II (Khabarovsk, 2007) developed: (a) Regional IP, (b) proposed revised list of RBSN/RBCN stations, (c) proposed changes in the Manual on the GOS. Secretariat requested RA II Members to (re)activate silent stations or replace them. |
| 4.1.1.7 | OPAG-IOS & OPAG-ISS activities | Recognizing the limitations of the current monitoring statistics, Congress asked CBS to consider new ways of measuring the effectiveness of the GOS. CBS asked OPAG-IOS in coordination with OPAG-ISS, to address this issue. The experience gained in this respect by certain countries should be taken into account; | OPAG-IOS & OPAG-ISS Chair/Co-chair, Secretariat (C/ISS-lead, C/OSY, C/SBOS) | December 2007 | 7. Issue discussed by ET-EGOS. This would need establishment of a group of expert to agree on common principle for all Regions. |
| 4.1.1.11 | WMO Integrated Observing Systems (WIGOS) | Develop input for the EC WG WIGOS-WIS | President, Vice-president OPAG Chairs, Secretariat (C/OSY-lead, C/SBOS, C/ISS) | October 2007 | Completed. EC WG WIGOS-WIS meeting held in December 2007. |
| 4.1.1.12 | WIGOS Documents &Background material | Provide available WIGOS documents to CBS MG members | Secretariat (PCO/WWW) | July 2007 | Done |
| 4.1.1.14 | AMDAR | Convey CBS-MG concern on AMDAR to the AMDAR Panel | Secretariat (C/AEM-lead, C/OSY) | November 2007 | Following the information on concerns regarding the accuracy and reliability of the water vapour sensor, the AMDAR Panel undertook a visit to the sensor producer, Spectra Sensors Inc, in late 2007, and a dialogue between Panel Experts and Spectra Sensors has been established to address these concerns. |
| 4.1.2.2 | Migration to Table-Driven Code Forms | Review of migration plans | ET-MTDCF Chair, Secretariat (C/DPFS) | To be submitted as a document to CBS-XIV | Questionnaire sent- 31 answers- Report will be made by CT/MTDCF meeting in September 2008 |
| 4.1.2.3 | Establishment of the Expert Team on the Assessment of Data Representation Systems (ET-ADRS) | Finalize the membership of the ET-ADRS and designate the chairman | OPAG-ISS Chair and Co-chair, Secretariat (C/DPFS) | July 2007 | Completed. ET-ADRS held April 2008. |
| 4.1.2.4 | Nomination of CAeM representative in the ET-ADRS | Invite CAeM to nominate a representative in the ET-ADRS | Secretariat (C/AEM-lead, C/DPFS) | July 2007 | Completed. CAeM (Mr Bart Nicolaï) |
| 4.1.3.4 | WMO Information System | Develop specifications for the GISC/DCPC/NC interfaces, including a unified user interface for WIS components; Responsible: Develop the specifications of WIS functions for GISCs and DCPCs to be used for the statement of compliance and for demonstrations of capabilities in the framework of the procedures for the designation of Global Information System Centres (GISC) and the Data Collection or Production Centres (DCPC), as supported by Congress; | OPAG-ISS Chair, Chairs of ET-WISC and ICG-WIS, Secretariat (C/ISS, seconded expert) OPAG-ISS Chair, Chair of ET-WISC and ICG-WIS, Secretariat (C/ISS, seconded expert) |  | GISC/DCPC/NC interfaces specs, WIS functional architecture, etc developed and reviewed by ET-WISC, ICG-WIS (July) |
|  |  | Develop practices, procedures and guidelines for the metadata generation and exchange including finalization of the metadata profile references and relevant implementation tools | OPAG-ISS Chair, Chair of ET-WISC and ET-CTS, Secretariat (C/ISS, seconded expert) |  | In progress, to be reviewed by IPET-MI (July) |
|  |  | Development of regulatory documentation (Manual on WIS) including organization and recommended practices and procedures and guidance material for implementation as well as the need for a WIS guide for NCs; | OPAG-ISS Chair, Chair of ET-WISC and ET-CTS, Secretariat (C/ISS, seconded expert) |  | Strawman and some parts developed and reviewed by ET-WISC, ICG-WIS (July) |
| 4.1.3.4 (cont’d) |  | Development of scheme and practices for security, authentication and authorization procedures for WIS services; | OPAG-ISS Chair, Chair of ET-WISC and ET-CTS, Secretariat (C/ISS, seconded expert) |  | Limited progress, Included in implementation plan and tasks for ET-WISC, ET-CTS and ICG-WIS |
| 4.1.3.5 | Participation of developing countries in WIS | Develop a coordinated building capacity and action plan in developing countries to facilitate their participation in WIS | ICG-WIS Chair with contribution from the Chairs of OPAG-ISS, ET-WISC, ET-CTS, IPET-MI, Secretariat (C/ISS, seconded expert) |  | Actions initiated for RA I, and current in RA V; taken up when current requirements and focus on GISC/DCPCs implementation will allow. |
| 4.1.5.2 | CBS software registry | Invite the WMO Members to review the list of software packages included in the CBS software registry, for example every two years; | Secretariat (C/ISS) |  | Letter to Members issued |
|  |  | The OPAGs and their teams should highlight the software packages, that could be used to contribute to the implementation of the WWW in their domain of interest, should foster their possible use, and in a more general way should contribute to the development and better use of the registry. | OPAG-ISS Chair and Chairs of respective ETs, Secretariat (C/ISS) |  |  |
| 5.1 | Executive Summaries of ET Meetings | Provide one-page executive summary report of each ET meeting to the MG | OPAG Chairs | Upon the final report of the ET meeting is completed | Completed. (included in reports available on Web |
| 5.6 | Collaboration with GEO | Develop appropriate communication to the GEO Secretariat covering the following CBS concerns: Need by WMO Members to better understand the benefit to NMHSs; Need to better understand the development and implementation strategy; GEO Branding of WMO Member products. | President, Secretariat (D/WWW) | October 2007 | [Done with no impact by geo in changing branding process] |
| 5.13 | Quality Management Framework (QMF) | Based on the list of all the available CBS technical documents, identify CBS standards that would benefit Members if they were considered for submission as joint ISO/WMO standards; submit this sublist to the MG for review | CBS Rapporteur on QMF, OPAG Chairs | April 2008 |  |
| 5.23 | Flash Flood Guidance System (FFGS) | Provide feedback requested by the CHy President. Work with the CHy President to develop a proposal for the partnership in FFGS project | OPAG-IOS and OPAG-ISS Chairs CBS DRR Rapporteur | September 2007 December 2007 |  |
| 6.4 | Adoption of amendments to the Manuals | Initiate a pilot project to test the direct adoption of recommendations for amendments to the Manual on Codes between CBS sessions with a view to saving time during the CBS sessions and reducing the delays in the approval of the amendments. | Secretariat - (C/DPFS) | To be submitted as a document to CBS-XIV | Completed. See MG-8 Document 4.2 (2) |
| 7. | Technical Conference in conjunction with CBS-XIV | Develop proposals on the topic for the Technical Conference to be held in conjunction with CBS-XIV | President, members of the MG | October 2007 | Done. The president had agreed that the theme for the Technical Conference will be “ WMO Integrated Global Observing Systems (WIGOS)”. Note: a number of issues (invalid links..) have been solved |
| 8.1 | WMO website | Provide a feedback on new WMO website, taking into account CBS requirements | Secretariat (C/ISS-lead, C/OSY, C/DPFS, C/PWS) | September 2007 | WMO web site updated. Input required from MG members prior to MG-9. |