Time table for preparation of CBS-XIV and TECO-WIGOS

TeCo WIGOS 23-24.III.2009; CBS-XIV 25.III-2.IV.2009, Dubrovnik, Croatia

15 November 2008: D - 4.3 months (129 days)

| Technical Conference |
| --- |
| Organisational preparation | deadline | comments |
| Decision on topic Designation of Conference Director and Conference committee | D -12 months D -12 months | Done Done Done |
| Conference organization, agenda, sessions | D -10 months | Provisional done |
| Call for presentations, posters, call for financial contributions | D -8 months | Done |
| Consolidated list of presentations & lecturers | D -3 months | - |

| CBS Session |
| --- |
| Administrative procedures | deadline | comments |
| Offer to host Conference | D -300 days | Received – Agreement WMO-Host being finalized (for signature) |
| SG informs all Members of proposed session | D -240 days | Done on 14 August 2008 |
| Members inform of intent to participate | D -180 days | current |
| Procedures for visa etc confirmed by host | D -135 days | current |
| Notification to Members of date & place | D -120 days | - |
| Support Services |  |  |
| Preparation interpreters contracts | D -8 to 3 months | current |
| interpreters contracts | D -6 to 3 months | current |

15 November 2008: D - 4.3 months (129 days)

| CBS Session |
| --- |
| Organisational preparation | deadline | comments |
| Draft future work programme and draft OPAG structure (ETs) | D -6 months | MG and OPAGs |
| Call for experts’ nomination to participate in OPAGs and ETs | D -4 months | With a view to OPAGs & ET membership |
| Finalization prov. agenda | D -4 months | Draft from MG-VIII |
| Organization of CBS session (committees’ chairs, time plan, etc) | D -2 months | - |
| CBS Operational Planning Framework document | D -3 months | MG responsibility |
| Technical preparation |  |  |
| OPAG-IOS ETs | D -3 months | Meetings held |
| OPAG-IOS ICT | D -2 months | Session held Sept. 2008 |
| OPAG-ISS ETs | D -3 months | Meetings held |
| OPAG-ISS ICT | D -2 months | Session 10-13 Nov. 2008 |
| OPAG-DPFS ETs | D -3 months | Meetings held |
| OPAG-DPFS ICT | D -2 months | Session held Oct. 2008 |
| OPAG-PWS ETs | D -3 months | Meetings held |
| OPAG-PWS ICT | D -2 months | Session held May 2008 |