# WORKPLAN

B2: CIMO Expert Team on New Technologies and Testbeds

(2011-2014)

| No. | Task description | Person responsible | Action | Deliverable | Deadline for deliv. | Status [%] | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Guidance on meteorological use of GNSS | S. de Haan R. Ware | Finalize development of guidance document on theory and operational use of GNSS for meteorology, incl. comparison with other systems such MWR and radiosondes, guideline on operational use of WP, recommendations on data exchange protocols, if appropriate Develop update for CIMO Guide chapter | 1. IOM report 2. Updated CIMO Guide Chapter | 2011 2012 |  |  |
| 2. | Guidance on operational use of passive microwave profilers | A. Koldaev R. Ware P.W.Chan D.Klugmann | Develop guidance material on operational use of passive microwave profilers (with emphasis on PBL performance) Review relevant CIMO Guide chapter and develop update if appropriate | 1. Document with guidance material 2. Updated CIMO Guide Chapter | 2011 2012 |  | ET-RSUT&T, para 4.1.19 |
| 3. | Standard on LIDARs used for visual range | D.Klugmann M. Nakazato | Inform ET and MG on status of development of ISO standards (incl. recommendation & justification on whether WMO should approach ISO to develop them as ISO-WMO standards) Collaborate with ISO working group on development of standards on lidars | Document to CIMO MG Input to ISO standards | 2012 (MG-10) In phase with ISO development process |  |  |

| 4. | Monitor, evaluate and report on development and implementation of new remote-sensing technologies and their operational application | MWR-A.Koldaev R. Ware GNSS- S. Haan R. Ware J. Won Raman WV A.Apituley Wind-finding H. Klein-Baltink Cloud radars D.Klugmann A. Koldaev Aersol&volca-nic ash detection A.Apituley J. Won Other: R.Kivi G. Yuchun | Review and evaluate development and implementation of various new remote-sensing technologies and their potential/readiness for operational application, including path to operation use and traceability to SI (MWR, GNSS, Raman WV lidar, wind-finding systems, cloud radars, aerosol&volcanic ash detection, etc…) Prepare reports on performance and use of those systems If appropriate, compile IOM report out of report on the various systems Responsibilites for various subdocuments: MWR, GNSS Raman WV lidar wind-finding systems cloud radars aerosol&volcanic ash detection other | Report on performance, implementation and operational use of various systems to the attention of WMO Members IOM report on new RS technologies | March 2012 2013 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5. | Monitoring of CIMO testbeds | J.G. Won D.Klugmann A. Apituley | Monitor and review outcomes of all CIMO Testbeds and Lead Centres (with focus on performance & limits of new surface-based RS technologies) Assess need to, and develop, up-date for relevant part of CIMO Guide, as necessary. | Document summarizing main outcomes of testbeds relevant to ET Terms of Reference 2.1 Report to OPAG-A Chair if update required Revised CIMO Guide Chapter | 2012 (MG-10) Dec. 2013 |  | ET-RSUT&T, para 4.1.20 |
| 6. | Assessment of the uncertainty and traceability to SI of vertical profiles in the atmosphere by various remote-sensing technologies | J.G. Won D.Klugmann A. Apituley H. Klein-Baltink M. Nakazato | Based on the testbeds outcomes, develop principles for optimal mix of surface-based in-situ & RS technologies (incl. satellites) Identify tools and techniques to verify to what extent the remote-sensing observations meet criteria that ensure conformity and traceability to SI Develop recommendations on how to improve traceability of RS observations relevant to ET Terms of Reference | 1.1 Preliminary report 1.2 Document listing principles for optimal mix of various technologies (incl. justification) Document with assessment of traceability of RS techniques Document with proposals on how to improve traceability of RS techniques | 2012 (MG-10) 2013 2013 Apr. 2014 |  | CIMO-XV, para 5.20 |
| 7. | Contribute to the implementation of WIGOS and provide relevant advice and support to the CIMO-MG | TBD | Address relevant items of WIGOS Implementation Strategy approved by Cg-XVI and subsequent WIGOS IP | TBD after Cg-XVI |  |  |  |
| Lower priority |
| 8. | Report on modern possibility of remote sensing of snow depth by means of passive and active radar airborne and spaceborne systems | A. Koldaev G. Yuchun | Study the latest results of different research groups in Canada, Europe, Russia and Japan concerning the space born and aircraft remote measurements of the snow pack. | Recommendations for the implementation of the remote sensing tools into the program of international inter -comparisons of snow precipitation measurements | 2012/13 |  | In cooperation with A3 (SPICE Intercomparison) |
| 9. | Examine the reliability and consistency of wind measurements by wind profilers towards the development of an ISO-WMO standard | P.W.Chan | Study the different possibilities of the validation of the remote sensing wind profiler data by means of high meteorological towers, unmanned airplanes, tethered balloons and others | 1. Report to CIMO-MG on potential for development of a CIMO standard | 2013/14 |  | In close cooperation with A1 and B1 |

# Footnotes

To be confirmed by ET Chairperson

To be confirmed by ET Chairperson

To be confirmed by ET Chairperson

To be confirmed by ET Chairperson

To be confirmed by ET Chairperson