# WORKPLAN

# B4: CIMO Theme Leaders on Satellite Observations (2011-2014)

| No. | Task description | Person responsible | Action | Deliverable | Deadline for deliv. | Status [%] | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Update of CIMO Guide chapter on satellite observations | SUN Anlai | Review update of chapter proposed by ET-SAT/SUP (in particular with regards for homogeneity with rest of guide) and addressing requirements for ground-truth validation and calibration of satellite observations to achieve SI traceability | 1 Proposals of improvements to author(s) | In phase with development of document by ET-SAT |  | TL-B4 ToR 3 |
| 2. | Ground-truth validation of satellite observation of surface variables | SUN Anlai | Liaise with ET-SAT and ET-SUP to determine the specific requirements of the satellite community for ground-truth validation of satellite remote-sensing of surface variables (incl. through review of GSICS WIGOS pilot project) Initial investigation on the uncertainties of satellite and in-situ measurements of comparable surface and upper-air variables identified in Part I of CIMO Guide. Develop proposals for CIMO actions(involvement) to improve traceability of satellite observations | 1 Report to MG on requirements of satellite community 2.1 Report to MG Initial recommendations on how to incorporate satellite-derived quantities into Part I of the CIMO Guide Provide input to ET-EGOS 3. Report to MG | 2012 (MG-10) 2012 (MG-10) 2013 2013 Jan. 2014 |  | CIMO-XV, para 4.22 |
| 3. | Contribute to the implementation of WIGOS and provide relevant advice and support to the CIMO-MG | TBD | Address relevant items of WIGOS Implementation Strategy approved by Cg-XVI and subsequent WIGOS IP | TBD after Cg-XVI |  |  |  |