# WORKPLAN

C5: CIMO Theme Leader on Surface-based Instrument Performance Monitoring (2011-2014)

| No. | Task description | Person responsible | Action | Deliverable | Deadline for deliv. | Status [%] | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Establishment of a working group on surface-based instrument performance monitoring from members of WMO | PEI Chong | 1. Establish a working group (composed of about 5 experts) on surface-based instrument performance monitoring from members of WMO 2. Prepare contributions to a session of TECO on national experience with instrument performance monitoring | 1. Identification of experts 2.1 Report to MG on progress 2.2 Presentations/posters at TECO-2012 | 2011 MG-10 TECO-2012 |  |  |
| 2. | Development of basic requirements and configuration for Real-time monitoring of surface-based operational instrument performances. | PEI Chong | 1. Develop a framework of guidance on how to conduct the monitoring, including requirements and structure for the basic information systems etc | Document identifying requirements and proposal of basic structure (methods, criteria, standards and procedures) for the monitoring system (possibly to be published as IOM report) | 2013 |  |  |
| 3. | Development of working mechanisms between the monitoring system and other Capacity Building facilities, such as Regional Instrument Centers, etc | PEI Chong | 1. Exchange experiences among Members, especially with RICs, through expert visits, workshops, etc. 2. Verify requirements and structures for the basic monitoring system. | Document with comments and suggestions on strengthening Capacity Building inputs to Technical Documents | 2013 2014 |  |  |
| 4. | Follow-up on identified performance issues | PEI Chong | 1. Liaise with CIMO and HMEI on instrument performance and development | Reports to CIMO-MG, HMEI and relevant Members | 2014 |  |  |
| 5. | Contribute to the implementation of WIGOS and provide relevant advice and support to the CIMO-MG | TBD | Address relevant items of WIGOS Implementation Strategy approved by Cg-XVI and subsequent WIGOS IP | TBD after Cg-XVI |  |  |  |