| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS OPAG on DPFS IMPLEMENTATION COORDINATION TEAM Geneva, Switzerland, 12-16 February 2018 |  | CBS/ICT-DPFS/Doc. 6.1/6.2 (05.II.2018) _______ Agenda item : 6 ENGLISH ONLY |
| --- | --- | --- |

# REVIEW OF S/GDPFS IMPLEMENTATION PROCESS

(Submitted by A. Harou)

##### Summary and purpose of document

This document describes the process for the development of the implementation plan for Seamless GDPFS

##### Action Proposed

The meeting is invited to take note of steps taken so far for the implementation of Seamless /GDPFS and to initiate discussion for the provision of inputs to the plan.

Annex 1:   PTC/PRA presentation

Annex 2:  Timeline for completion of the IP

Annex 3:  Table of activities required for the Implementation Plan

- Introduction

Congress 17 (2016) decided through Resolution 11, to move to the gradual establishment of a future enhanced, integrated and seamless WMO Data-processing and Forecasting System in the light of the conclusions of the first World Weather Open Science Conference held in Montreal, Canada in August 2014. . Congress  also requested EC to:

- To formulate terms of reference for this process, and a description of the set of products

the system should produce, and to steer the activity accordingly;

- To ensure the active participation and representation of the constituent bodies concerned and also the participation, as appropriate, of technical experts and representatives of partner agencies;

- To strengthen the link between the research activities on seamless prediction and the development of downstream related services;

- To submit a comprehensive report on the integrated and seamless WMO Data-processing and Forecasting System to Eighteenth Congress;

- Actions taken

EC-68 (2016) responded to Cg-17 request through the Decision 55 to establish an EC SG/Seamless GDPFS chaired by the Pres of CBS and composed of Reps from TCs and  RAs. The SG met twice to address the issue. The CBS-16 (Nov 2016) decided, through its  Decision 27, to speed up the process for the implementation of  by using the results of the first and second meetings of the Steering Group on the Seamless DPFS (Geneva, February and November 2016, respectively) where notions of the vision and a white paper were developed and urged  the Steering Group to make its first order of priority the completion of the white paper and the development of the implementation plan, which includes a communication plan, for tabling at the sixty-ninth session of the Executive Council;

EC 69 considered the recommendation of CBS-16  and decided (Decision 17 (EC-69)) to adopt the vision of S/DPFS and requested EC SG/seamless GDPFS to table the Implementation Plan for consideration by EC-70. In addition it directed that the Pres of CBS and the President of CAS co-chair the EC- SG.

Both President (CBS and CAS) decided to establish a Drafting Team (DT) composed Experts from hydrology, atmospheric composition / air quality, weather and climate, Earth system modelling. They were asked the team to develop a way forward based on three main areas: System, Research and Innovation and Accessibility/availability.  The DT met in December 2017 and brainstormed on key components and subcomponents of each of the key areas under consideration. Based on the work of the DT, a PowerPoint  was prepared and presented to PTC/PRA in January 2018. The ppt is attached as Annex 1. The draft of timeline for the development and approval of the implementation plan can be found at Annex 2.

Following the presentation at PTC/PRA the DT developed a set of tables to help gather information on key activities that could be initiated in the short, medium and long terms for the implementation of S/DPFS.  These tables are attached as Annex 3 separately under agenda item 6.2.

Annex 1- PTC PRA Presentation

Annex 2:  Timeline for completion of the IP

Timeline (Draft zero)

| January 2018 | Actions | Comments |
| --- | --- | --- |
| 19 | Presentation of Results of the work of Drafting Team (DT)to PTC/PRA |  |
| 22 | PPT shared with DT for comments | Drafting Team was informed that additional request will be sent to them to identify potential activities related to identified focus areas |
| 24 | A set of Tables related to focus areas to be sent to the DT so they can identify potential activities (short, medium and long term) with the deadline to return their inputs by 9 February | Tables sent 27 Jan |
| February 2018 |  |  |
| 9 | Inputs from DT to be received for compilation and consolidation - |  |
| 12-15 | ICT-DPFS meeting - Discussion on seamless | PTC/PRA ppt will be presented |
| 16 | Joint ICT/DT teleconference to discuss the IP incl Co-Chairs S/GDPFS | PPT and DT identified activities and next steps will be discussion Feb 16 at 2pm (Geneva) |
| 16 Feb – 9 March | Consolidation of comments/inputs into Draft v1.0 of the IP |  |
| March 2018 |  |  |
| 9 | Draft v1.0 of the IP ready and distributed to EC SG on S/GDPFS and setting up of a teleconference to obtain their feedback |  |
| 9-26 | Preparation for TECO/CBS MG |  |
| 26-29 | Discussion at TECO/CBS |  |
| April 2018 |  |  |
|  | Preparation of IP Draft v2.0 for Executive Council |  |
| June 2018 |  |  |
| 20-29 | Executive Council 70 |  |
| 29 - | Lobbying for and securing pilot projects |  |
|  | Assessment of pilots projects |  |
|  | Update of IP |  |
| June 2019 | Congress |  |
|  | Submission for Congress approaval |  |