SEVERE WEATHER FORECASTING DEMONSTRATION PROJECT

REGIONAL SUBPROJECT – SOUTHERN AFRICA

FINAL PROGRESS REPORT

WMO Secretariat 20 June 2011

This report has been prepared by:

- Mr Jean Coiffier (WMO consultant)

- Mr Laurie Wilson (WMO consultant on verification matters)

- Mr Peter Chen and Ms Alice Soares (WMO Secretariat, Data-Processing and Forecasting Division)

- Ms Haleh Kootvall and Mr Sam Muchemi (WMO Secretariat, Public Weather Services Division)

The 16 participating countries in the SWFDP - Southern Africa project

Foreword

Numerical Weather Prediction (NWP) systems have become increasingly relevant and indeed essential to the severe weather forecasting process, with a growing number and variety of sophisticated outputs, currently available from NWP producing centres, which could be beneficial to many National Meteorological and Hydrological Services (NMHS).

The Severe Weather Forecasting Demonstration Project (SWFDP) was organized as potentially a series of regional subprojects to explore and test the usefulness of the products currently available from NWP centres, or products which could be readily made available from current NWP systems of global and regional meteorological centres, with the goal to improving severe weather forecasting services in countries where sophisticated model outputs are not currently used.  The principal focus of the project is on the phenomena of heavy precipitation that could cause serious flooding, and strong destructive winds.

After the very positive SWFDP field phase involving 5 NMHSs in southern Africa that took place from 6 November 2006 to 9 November 2007, CBS decided to continue this regional project from 24 November 2008 to 31 December 2010 and to extend the participation to all 16 countries of the region, and maintaining the involvement of the same regional and global products centres, as follows:

- NMHSs: Angola, Botswana, Comoros, DR-Congo, Lesotho, Madagascar, Malawi, Mauritius, Mozambique, Namibia, Seychelles, South Africa, Swaziland, Tanzania, Zambia, Zimbabwe;

- Regional Centres: RSMC Pretoria, RSMC La Réunion

- Global Products Centres: Exeter (Met Office UK), Washington (NCEP USA), and ECMWF.

RSMC Pretoria continued to make available on a dedicated Web site and portal the required datasets from the Global Products Centres and output from limited area models UM-SA12 and ALADIN-Réunion as well as EUMETSAT/MSG derived products for nowcasting purpose.  Moreover RSMC Pretoria prepared and issued the RSMC Daily Severe Weather Forecasting Guidance Product, including descriptive text, maps and risk and probability tables, according to the agreed format, in order to assist forecasters to prepare their own forecasts and warnings.

By using the information provided through the quarterly reports submitted by the NMHSs, Quarterly Progress Reports were prepared to summarize the occurrence of severe weather events throughout the quarter, to assess the utility and quality of the RSMC Daily Guidance, the relevance and the skill of the various NWP products relative to severe weather, the pertinence of the severe weather warnings issued by the NMHSs, and the improvement of the services they delivered to Disaster Management and Civil Protection Authorities (DMCPA).

This final report covering the two-year period from 24 November 2008 to 31 December 2010, is a synthesis of the eight Quarterly Progress Reports. It is a comprehensive evaluation of the organization and procedures carried out under the framework of the SWFDP.  It attempts to describe the shortcomings as described by the participants and proposes improvements in order to ensure the sustainability of the Cascading Forecasting Process and the organization among the participating centres of the GDPFS, as well as to further enhance public weather services and other meteorological services.

1.	Introduction

1.1	Objectives of the SWFDP

1.1.1	The main objective of the Severe Weather Forecasting Demonstration Project (SWFDP) is to test the usefulness of the products currently available from NWP centres, or products that could be made available from current NWP systems, with the goal to improve severe weather forecasting services in countries where sophisticated model outputs are not currently used.  This project uses a Cascading Forecasting Process concept of operations to provide greater lead-time for alerting of severe weather and at the same time contributes to capacity building and improving national level links with the respective national DMCPAs.

1.1.2	According to the recommendations of the CBS-XIII (2005) the goals of the SWFDP were defined by SWFDP Steering Group in Geneva (14-16 December 2005) as follows:

- to improve the ability of NMCs to forecast severe weather events;

- to improve the lead time of alerting of these events;

- to improve interaction of NMCs with DMCPA before and during events;

- to identify gaps and areas for improvements;

- to improve the skill of products from GDPFS centres through feedback from NMCs.

1.1.3	The CBS-Ext.(06) stressed the need to involve civil protection authorities to improve delivery of severe weather warning services.  Regarding this aspect, collaboration with the Public Weather Services (PWS) and with the Disaster Risk Reduction, “DRR” programmes is encouraged.

1.2	The Cascading Forecasting Process

1.2.1	In the framework of the general organization of the Global Data-Processing and Forecasting System (GDPFS), the SWFDP implies a co-ordinated functioning among three types of GDPFS centres.

- global NWP centres to provide available NWP products, including in the form of probabilities;

- regional centres to interpret information received from global NWP centres, run limited-area models to refine products, liaise with the participating NMCs;

- NMCs to issue alerts, advisories, severe weather warnings; to liaise and collaborate with Media, and disaster management and civil protection authorities; and to contribute to the evaluation of the project.

1.2.2	The first phase of this project took place during November 2006 to November 2007, and had included the participation of five NMHSs in southeast Africa, focused on heavy rain and strong winds.

1.2.3	According to the decisions taken by the Regional Technical Implementation Team (RTIT) during his meeting that took place in Pretoria (24-27 February 2009) the SWFDP Regional Subproject  was expanded to include the entire region of Southern Africa,

1.2.4	The  Services and Centres that participate to the SWFDP Southern Africa include the following:

- NMHSs: (16): Angola, Botswana, DR Congo, Lesotho, Madagascar, Malawi, Mauritius, Mozambique, Namibia, Tanzania, Seychelles, South Africa, Swaziland, Zambia, Zimbabwe.  In addition, Comoros participated in all SWFDP Training Workshops;

- Regional Centres (2): RSMC Pretoria, RSMC La Réunion;

- Global Products Centres: Exeter (Met Office UK), Washington (NCEP USA), and ECMWF.

1.2.5	The severe weather related hazards to be monitored were extended by the RTIT from the original two (heavy rain and strong winds) to a representative group of seven for which NMHSs issue warnings to the public at large.  These include heavy rain, strong winds, high seas and swell, severe convective storms, very cold conditions, snow and flooding.  Thresholds and criteria are in line with general needs of the region and current detecting capabilities.  The impact of tropical cyclones (heavy rain, strong winds, high seas) on land areas are to be associated with the tropical cyclone guidance provided by RSMC La Reunion.

1.2.6	Evolution of the implementation of the project:

- From 10 to 21 November 2008 (2 weeks) a joint GDPFS/PWS preparatory training workshop took place in Pretoria.  During the first week, the workshop covered the forecasting aspects, such as various NWP and RSMC guidance products, EPS products, verification techniques, nowcasting using MSG products, while the second week focused on PWS topics and included the additional and important participation of representatives of national disaster management organizations.

- This expanded phase of the SWFDP – Southern Africa experiment started officially on the 24 November 2008 and will last to the 31 December 2010.  It is however expected that the SWFDP “Cascade” infrastructure will be maintained thereafter, indefinitely.

- A meeting of the expanded Regional Technical Implementation Team (RTIT) took place in Pretoria from 24 to 27 February 2009.

- At the end of every quarter (i.e. at the end of March, June, September and December) each of the participants is required to prepare a Quarterly Report,  which  is used to review the activities of the various Centres, and also used to track the  progress of the project by means of the SWFDP Quarterly Progress Reports.

- From 26 October to 6 November 2009 (2 weeks) a joint GDPFS/PWS Training Workshop on Severe Weather Forecasting and Warning Services took place in Pretoria.

- From 23 to 26 February 2010, the third meeting of the Steering Group of the Severe Weather Forecasting Demonstration Project was held in Geneva (Switzerland), including important experiences learned from the Southern Africa project, and a joint half-day session with the Commission on Atmospheric Sciences (CAS) GIFS-TIGGE Working Group.

- From 2 to 13 November 2010, a session on SWFDP/forecasting was held in Saint-Denis (La Réunion) as part of the Fifth RA I Training Course on Tropical Cyclones and Public Weather Services. Forecasters from participating countries in the SWFDP-Southern Africa attended this Training Course. It covered forecasting aspects, such as various NWP and RSMC guidance products, EPS products, verification techniques, nowcasting using MSG products.

- A meeting of the SWFDP-Southern Africa RTIT is planned to be held in Flic en Flac, Mauritius, from 19 to 22 July 2011, to review progress, evaluate the full expanded demonstration of the project, and to plan and define the transition of the SWFDP – Southern Africa into routine activities, ensuring the long-term sustainability of the benefits gained with the project, including the project’s management within the Southern African Development Community (SADC) and WMO Regional Association for Africa (RA I).

2.	Presentation of the SWFDP Final Progress Report

2.1	This final report summarizes the results obtained at the end of the two-year experimentation period (i.e. from 24 November 2008 to 31 December 2010) of SWFDP and is based on the eight Quarterly Progress Reports.  Many of these reports are available at the following WMO Web page:  http://www.wmo.int/pages/prog/www/CBS-Reports/DPFS-index.html.

2.2	The list of the reports received from the participating countries, that is given in Table 1, shows that many NMHSs had difficulties to ensure a regular feedback, especially during the second year of experimentation. By contrast the regular work that carry out by NMHSs Botswana, South Africa, Swaziland, Tanzania and Zimbabwe for preparing quarterly reports has to be emphasized.

Table 1 – Quarterly reports received from NMHSs

( X means relatively complete feedback while x indicates incomplete information)

2.3	This report has used as much as possible, wording provided in the NMHSs’ reports and feedback from the participating centres, while summarized for the sake of clarity and for combining various related pieces of information.

2.4	The information provided by the participating centres has been analysed with the aim to assess the utility and quality of the RSMC Daily Guidance, the relevance and the skill of the NWP products, the pertinence of the severe weather warnings issued by the NMHSs and the improvement of the warning services they delivered to Disaster Management and Civil Protection Authorities, “DMCPA”.  The quarterly evaluation table is used to identify all severe weather events of the reporting period, that occurred (forecast or not), and forecast (occurred or not).

3	The weather during the period 24 November 2008 - 31 December 2010

3.1	The periods going from November to March (the austral summer) corresponds more or less to the normal rainy season for most of the countries of southern Africa. The tracks of the southern hemisphere mid-latitude perturbations shift northward, while the ITCZ remains very active and results in strong convective events. Tropical storms and cyclones develop in the Indian Ocean and generally travel westwards so that several can hit the eastern part of the African continent. During the first rainy season (2008-2009), heavy precipitation which caused serious damage were reported especially in Namibia, Malawi, Mozambique, and South Africa, while Lesotho experienced very strong wind events. During the second rainy season (2009-2010) important heavy rainfall were reported particularly in Angola, Botswana, Tanzania, South Africa and Swaziland while Lesotho experienced very strong wind events.

3.2	The periods going from April to June corresponds to the end of the rainy season and the predominance of dry and cold weather.  With the reversal of the monsoon conditions over the western part of the Indian Ocean the tropical cyclone season ends. During the two successive periods (2009 and 2010), heavy rains giving floods occurred especially in Namibia and Malawi; the southern parts of South Africa experienced winter rainfall patterns with strong wind and rough seas that occurred several times in South Africa. In Lesotho snowfall events with very cold conditions were experienced in high ground areas.

3.3	The period going from July to October corresponds to the Southern Hemisphere winter season with a predominance of dry and cold weather without any heavy precipitation events. Nevertheless significant snowfalls occurred during this period over areas of higher elevation of South Africa and Lesotho; strong winds were experienced in Tanzania during the winter season 2010.

3.4	The two-year period of SWFDP comprises two full cyclonic seasons:  2008-2009 and 2009- 2010 and the beginning of the cyclonic season 2010-2011 in the western part of the Indian Ocean.   Tropical cyclones (TC) or storms (TS) were identified and tracked by the RSMC La Réunion during this period. The TC or TS threatening periods for the SWFDP - Southern Africa region are given below:

Cyclonic season 2008-2009:

- moderate Tropical Storm ASMA: from 20/10/2008 to 24/10/2008;

- moderate Tropical Storm ERIC: from 18/01/2009 to 21/01/2009;

- intense Tropical Cyclone FANELE: from 19/01/2009 to 23/01/2009;

- intense Tropical Cyclone GAEL: from 04/02/2009 to 09/02/2009;

- strong Tropical Storm IZILDA: from 22/03/2009 to 29/03/2009;

- strong Tropical Storm JADE: from 04/04/2009 to 12/04/2009.

The Tropical Storm JADE caused severe damage when it arrived at the eastern coast of Madagascar.

Cyclonic season 2009-2010:

- severe Tropical Storm ANJA: from 14/11/09 to 19/11/2009;

- moderate Tropical Storm BONGANI: from 23/11/2009 to 24/11/2009;

- Intense Tropical Cyclone CLEO: from 07/12/2009 to 14/12/2009;

- Tropical Disturbance DAVID: from 21/12/2009 to 25/12/2009;

- Intense Tropical Cyclone EDZANI: from 08/01/2010 to 11/01/2010;

- Tropical Storm FAMI that crossed Madagascar on 01/02/2010;

- Tropical Cyclone GELANE, from 17/02/2010 to 20/02/2010;

- Tropical Storm HUBERT, from 10/03/2010 to 11/03/2010;

- Tropical Storm IMANI, from 20/03/2010 to 25/03/2010;

- Tropical Low JOEL, from 24/05/2010 to 28/05/2010.

The Tropical Storm Gelane caused strong winds and rough seas over Seychelles and Mauritius.

The Tropical Storm Hubert caused many damages and casualties in Madagascar.

The Tropical Storm Joël crossed the southern parts of Mozambique Channel and  Madagascar.

Cyclonic season 2010-2011 (up to 31 Dec. 2010):

- Tropical Storm ABELE: from 1/12/10 to 12/12/2010.

Its track was located too far from the Island countries participating in SWFDP to represent a threat.

4.	RSMC Pretoria Daily Guidance for forecasting Severe Weather Events

4.1	The RSMC Daily Guidance prepared and issued by the senior forecasters at RSMC Pretoria consists of 2 bulletins: the first one focuses on short-range forecasts (day-1 and day-2), issued in the morning, while the second addresses the medium-range forecasts (day-3, day- 4, and day-5), issued in the afternoon.  Each comprises a discussion about forecast evolution, often supported by relevant figures (model charts or satellite images), a table giving for each day the risk or probability of occurrence of severe weather in the countries participating in the SWFDP, and a synthetic map indicating the critical areas for heavy rain,  strong winds, high seas, very cold conditions, snow and severe convective storms over the entire Southern Africa region, with the day-1 map overlaid on a current satellite image.  RSMC Pretoria utilizes a wide selection of information, data, and NWP outputs to prepare the Daily Guidance, including those provided by the global products centres, RSMC La Réunion (Tropical Cyclone), EUMETSAT, and participating NMHSs. The comprehensive list is included in the Regional Subproject Implementation Plan for this project.

4.2	The main method of dissemination of the SWFDP products and RSMC Daily Guidance are still the RSMC Web page hosted and maintained by RSMC Pretoria.  The list of product on this Website was continually expanded to include new products, as follows:

- a selection of outputs from the 10 km Aladin-Réunion model of Meteo-France run by RSMC La Reunion covering the Indian Ocean region where tropical cyclones are frequent during the Southern Hemisphere summer; As a consequence the entire SWFDP region is now well covered at high resolution by two  operational high resolution limited-area NWP models: Aladin-Réunion and the UM-SA12 (South Africa);

- MSG/Unified Model combined products prepared hourly at RSMC Pretoria that estimated cumulative rainfall amounts, i.e., the “hydro-estimator”.  These products have increased in number, and as well a diagnostic product has been added, i.e., the “global instability index “GII”.

RSMC Pretoria also maintains an online archive of the SWFDP guidance products produced by Pretoria.

4.3	The demonstration period began on the 24 November 2008 but the production of the short range and medium range risk tables was maintained for the original 5 countries, and included all the 16 participating countries only since 2 March 2009, following the first RTIT meeting.  The guidance map, however, covered the entire southern African region from the beginning.

4.4	The expansion of the SWFDP – Southern Africa to include all 16 countries of the region represented a major effort by RSMC Pretoria, in virtually all aspects of its roles and responsibilities within the project’s Implementation Plan.  Significant adjustments to the routine tasking of RSMC senior forecasters had to be made.   This included adaptation of forecasting shifts to allow more time for guidance preparations and the training of all forecasters in RSMC Pretoria to deal with the activities of the shift.

5.	Evaluation of SWFDP support by NMHSs

5.1	Synthetic tables summarizing NMHSs assessment

5.1.1	Tables 2a and 2b summarize, for the years 2009 and 2010 respectively, the number of severe weather events, the assessment of usefulness that was reported by the NMHSs and the number of warnings issued to alert the various users. The figures that are given in these tables were obtained by taking into account information given in the Quarterly Evaluation Tables provided by the NMHSs. The character “-“ in a cell indicates that the corresponding NMHS did not send any quarterly reports ; blank cell indicate that the information is not provided explicitly in the quarterly report).

5.1.2	The NMHS were asked to assess, on one side, the usefulness of the RSMC Daily Guidance and, on the other side, the usefulness of SWFDP NWP/EPS Products and high resolution limited area models by giving a mark ranking from 1 to 4 (1 for “misleading”, 2 for “not useful”, 3 for “useful” and 4 for “very useful”, for each severe weather event). As a few NMHSs attributed separate marks to the various models, the mark qualifying the NWP/EPS usefulness corresponds to a global mark for the NWP guidance.

5.1.3	It has to be emphasized that the interpretation of the figures of the Table 2a and Table 2b has to be made with care and caution.  Indeed it is difficult to define and determine objectively what is an occurrence of a severe weather event.  Should it only be based on locally and officially recorded amounts of precipitation and wind gusts?  What if observational networks “under-catch” qualifying events?  In addition, the decision to issue a warning depends not only on the anticipated intensity of the event but also on the anticipated impacts and consequences for life and property (to be potentially mitigated by using warnings).  For these reasons, taking into account the diversity of the practices and standards relative to the issuing of warnings, it is felt that the information base could be incomplete so that it would be difficult if not unjustified to evaluate the respective performances of the NMHSs based on these indices alone.  Qualitative and anecdotal information could supplement the objective diagnostics to assess overall performance.

Table 2a: Summary of the severe events which occurred during year 2009, NMHSs
assessment of RSMC guidance and products and performance of the warnings.

Table 2b: Summary of the severe events which occurred during year 2010, NMHSs
assessment of RSMC guidance and products and performance of the warnings.

5.1.4	The absence of information on the line corresponding to South Africa does not mean that there is no feedback from NMHS South Africa. Indeed NMHS South Africa prepared regularly a well documented Quarterly Report but did not document the Quarterly Evaluation Table so that they are not suitable to fill in the cells of Table 2a and Table 2b). Nevertheless most of the Quarterly reports prepared by NMHS South Africa include a very detailed list of the various severe weather events and some objective verification of the warnings as well as interesting case studies.

#### 5.2	Usefulness of RSMC Daily Guidance

5.2.1	Examination of the figures given in Table 2a and Table 2b shows that the categorical assessment of the usefulness of the RSMC Pretoria Daily Guidance is somewhat difficult to interpret. Indeed, the percentage of good marks (3 and 4) was 44% for the year 2009 and only 30% for the year 2010. The trend and these relatively weak percentages contrast dramatically with the very good assessments given by the NMHSs in their comments. All the participants in the SWFDP agree to recognize that this guidance is not only used in the context of severe weather forecasting but also for the day-to-day routine forecasting. Careful examination of the quarterly evaluation table provided by NMHS s show that many recorded heavy precipitation or strong wind events occur in a context of active convection at several places. The difficulty to include information about local convective events in the RSMC Pretoria daily guidance is probably the reason why the ratings given in the Table2a and Table 2b seem to contradict the appreciation of the NMHSs in their comments. It is worth noting that many forecasters of the region are learning through the project to use the collection of SWFDP guidance products “on their own”, which could imply their gradual decrease in dependence on, or possibly their taking a more critical view of the Daily Guidance products.

5.2.2	The RSMC Pretoria Daily Guidance, which is a central feature of the SWFDP concept, enables the forecaster coming on duty to efficiently gain an insight of the behaviour of the weather systems at a glance, and is incorporated into the routine by many NMHSs forecasting centres as a starting point for the discussions about the evolution of the large scale features of the atmosphere over their country up to five days ahead.

5.2.3	It is also important to point out that island countries located in the south-western Indian Ocean (Madagascar, Mauritius, Seychelles) were very satisfied with the information provided on the sea state and the wave heights despite a few misses. NMS Tanzania also emphasized the value of this guidance in forecasting strong winds along coast of the western Indian Ocean.

5.2.4	The NMHSs seem to be satisfied with the format of the RSMC Pretoria Daily Guidance and there is not any proposal for changing the actual presentation.

5.3	Usefulness of METEOSAT Next Generation Satellite (MSG) products

5.3.1	MSG/Unified Model combined products are primarily used for tracking and “nowcasting” convective storms in real-time, especially those of rapid onset and with the potential to develop into severe thunderstorms.  At the present time, under the AMESD (PUMA 2010) project, a majority of participating NMHSs should soon have functioning satellite receive and data-processing computer workstations to receive EUMETCast (broadcast) MSG products and the suitable software applications to carry out local image data processing.

5.3.2	The “hydro-estimator products that are often referenced in the RSMC Pretoria Daily Guidance showed its usefulness for short-range forecasting as it was reported by Swaziland, Zambia and Zimbabwe during year 2009. Nevertheless, during year 2010, there is a lack of comments about the usefulness of stability indices and hydro-estimator, which are products especially devoted to convective event forecasting.

5.4	Usefulness of SWFDP NWP/EPS Products and high resolution limited area models

5.4.1	The ratings that appear in the right-hand parts of Table 2a and 2b confirm the usefulness of NWP model products that are available through the SWFDP Website and portal and show the high degree of satisfaction expressed by the NMHSs. The percentage of good marks (3 and 4) is 54% for the year 2009 and 49% for the year 2010. Both deterministic and ensemble products coming from ECMWF, NCEP and UKMO in conjunction with the RSMC Pretoria guidance are fully appreciated by the forecasters who become familiar and more committed to the project. There is also a great interest for the products resulting from high resolution limited area models (UM-SA12A and ALADIN-Réunion) that provide the forecasters with more details in the forecast fields.

5.4.2	The NMHS are extremely satisfied with EPS products and especially with EPSgrams that provide them with concrete local information several days ahead. They generally stated that this product allowed effectively to increase the lead time of the advisories and warnings.

5.4.3	In many NMHS, forecasters understand that the models can have different behaviours and they are now accustomed to work with outputs from different models, which enable them to evaluate in a qualitative way the extent of the spread of the predicted solutions through a subjective “poor-man’s” ensemble forecasting approach.  Nevertheless several NMHSs mentioned difficulties practically to access and examine rapidly at multiple Web sites.

5.4.4	In spite of the general satisfaction, many NMHSs point out the weakness of the present model output to forecast the convective events or to accurately forecast rainfall (or snowfall) amounts. Such deficiencies common to all the models are pointed out by several NMHSs, and particularly the difficulty to forecast strong winds (Lesotho) or hailstorms (Zimbabwe). There is no doubt that forecasting severe convective events accurately remains a challenge.  Thus, there is a need to pursue the training effort to show them how to make the best use of all the available SWFDP guidance products for diagnosing the convective environment, and then to use satellite products for monitoring and “nowcasting” these storms.

5.5	Warning issuing by the NMHSs

5.5.1	The number of warnings issued from NMHS is given in the last two columns of the Table 2a and Table2b. Nevertheless, it is important to note that several NMHSs indicated that severe weather advice was included in their current weather bulletins without necessarily issuing a formal warning.

5.5.2	There is no doubt that the different practices for issuing advice or warning in the various NMHSs do not allow to really draw conclusions about the performance of the warning system in the various countries or to try to make comparisons between them. Moreover it is important to recall that the MMHS's decision to issue a formal warning toward the users does not always depend on expected values of meteorological parameters (local amount of precipitation or wind speed above agreed thresholds); some other considerations can be taken into account such as the vulnerability of the  threatened areas or the occurrence of events attracting many people.

6.	Project evaluation against SWFDP goals

The general goals of the SWFDP were adopted at CBS.  The participating NMHSs were requested to indicate how the project has fulfilled each of the goals.

6.1	To improve the ability of NMCs to forecast severe weather events

6.1.1	All the participating NMHSs reported a positive impact of daily use of SWFDP products (for both day to day and severe weather event forecasting). Generally, RSMC guidance and model output help increase the skill of the forecasters and boost their confidence. The significant improvement of the forecasts results in a real and positive change in the opinion the various users have about the pertinence of the warnings.

6.1.2	All the participating NMHSs emphasize especially the value of probabilistic products issued from various Ensemble Forecast Systems running in global centres: ECMWF, MOGREPS, and GEFS (Global Ensemble Forecast System); ECMWF products such as strike probability or EFI proved its efficiency for tracking named storms and forecasting heavy rainfall events.

6.1.3	The availability of the ALADIN-Réunion products issued by RSMC La Réunion also contributed to improve the forecasts over the southwestern Indian Ocean.

6.2	To improve the lead-time of alerting these events

6.2.1	All the NMHSs that experienced severe weather events indicated that SWFDP products allowed them to improve the lead time of providing alerts to these events : several events were detected and tracked 5 days in advance and South Africa mentioned that some references to expected events with lead limes approaching 6 to 7 days were made thanks to EPS-based guidance.

6.2.2	Thanks to the probabilistic forecasts from the Global Centres the lead time of the warnings can now reach 2 days while the lead time of advisories can sometimes be increased up to 4 or 5 days  when there is some agreement between the models.

6.2.3	Several NMHSs that are responsible for marine forecasts mentioned that SWDP allowed them to increase the lead time of warnings not only in case of heavy rainfall over ground, but also when strong winds threatened the mariners over seas.

6.3	To improve the interaction of NMHSs with DMCPAs and other related users before, during and after severe weather events

6.3.1	The present SWFDP Regional Subproject provides an opportunity to establish (for several NMHSs) or to strength (for most of them) links with their national DMCPA.  Joint meetings and training sessions organized by several NMHSs, as well as those organized by WMO, help DMCPAs staff better understand the significance and the limitations of the meteorological warnings.

6.3.2	Even if it is difficult to assess the regularity of the feedback from the DMCPAs, the quarterly reports show that the NMHSs made valuable efforts to develop closer relationships with this category of users. By means of regular meetings, training workshops, implementation of focal points, it seems that in most of the participating countries the setting up of formal mechanisms of co-operation between NMHSs and DMCPAs progressed significantly and enabled to improve the preparedness of the various public services.

6.3.3	The implementation of the SWFDP resulted in the development of a real cooperation between meteorological services and disaster management authorities in various countries and particularly:

- in Angola the implication in the SWFDP give the opportunity to make the interaction more efficient between the meteorological service INAMET and the disaster management and civil protection service DMCP;

- in Botswana, remarkable progress has been achieved as the two institutions have seen interaction between them grow from strength to strength. The National Disaster Management Office and its regional offices now play an active role in disseminating warnings issued by the DMS ;

- in Lesotho, the relationship and collaboration of the Meteteorological  Service with DMA has improved from the past 3 years or so but it is getting stronger day by day especially in winter where the weather is most active. This active collaboration results partly from the training sessions organized by WMO involving forecasters and people in charge of Disaster Management; such sessions contributed to strength coordination and unify communication between the two services. Nevertheless, getting feedback from DMA after severe events have occurred remains a challenge;

- in Malawi, generally the project has increased interaction between Meteorological  Service and Disaster Management and Civil Protection authorities which receive now all the weather warnings issued;

- in Mauritius the role and responsibilities of Disaster Management were revisited;

- in Tanzania, the interaction between Tanzania Meteorological Agency (TMA) and Prime Minister’s Office Department of Disaster Management (PMO-DMD) continued to improve. Also coordination has been very good with Tanzania Red Cross Society (TRCS) and the United Nations Children’s Fund (UNICEF).

- In South Africa, a good relationship has been established between SAWS and DM at both provincial and national levels. DM has also established a flood alert task team (including members of the SAWS Regional Office that provide a daily weather briefing) in order to  be prepared and identify communities at risk. DM would also release press statements to local newspaper based on the alerts and warnings issued by SAWS. It is alos important to highlight the very good collaboration with SA Police and South Africa National Defense Force (SANDF) during daily weather briefings organized at National Joint Operational Centre (NATJOC) for 2010 Soccer World Cup held in South Africa from 11 June -11 July 2010;

- in Swaziland the new Disaster Management Authority that has been just established, is working closely with the NMS;

- in Zambia, advisories are regularly issued toward the Disaster management service (DMMU) and the Red Cross Society of Zambia before, during and after the floods

6.4	To identify gaps and areas for improvements

6.4.1	Many NMHS mentioned difficulties to forecast quantitatively strong winds and heavy precipitation associated with strong convection and stressed that large scale forecasts need to be downscaled to give local values of the parameters. This problem is always mentioned as the major drawback of the numerical models that are used to prepare the products on the RSMC Website in the framework of the SWFDP.

6.4.2	The occurrence of such events can be anticipated by using nowcasting techniques based on real-time frequently updated satellite products, and on radar images where they are available. While MSG products well cover the region, during the project period ground receiving and data-processing systems were generally not available or not in working order in many of the NMHSs.  As well most of the participating countries do not have operating radars to support timely warnings in the very short-range forecasting period.

6.4.3	Many NMHSs (and especially Namibia and Zambia) pointed out the deficiencies of their surface observational networks especially for the evaluation of precipitation forecasts, even with the help of the MSG-hydro-estimator.  As a consequence, is was very difficult to perform the verification of the forecasts, especially in sparsely populated areas.

6.4.4	RSMC Pretoria recognized the need to ensure consistent and continuity of the RSMC Guidance from one day to the next, and is trying to better streamline the production of guidance between the  successive shifts.

6.4.5	A few NMHS mentioned some problem for the dissemination of the warnings toward the media and also to formalize and get their feedback after the events.

6.4.6	NMHS Tanzania insists on the need to establish Standard Operating Procedures (SOPs) with Agencies involved in Early Warning and Disaster Management. The dialogue in this area has already started; it is expected that the planned workshop on developing SOPs on tsunamis (that will be held in November 2010 in Dar es Salam) will also give guidelines for developing SOPs for severe weather hazards.

6.4.7	The floods that occurred from 15 to 22 March 2009 over the western region of Zambia gave the opportunity to detect deficiencies in the communication with cooperating agencies that has to be  strengthened in the future.

6.4.8	On the technical level:

- NMS Mauritius points out that the coverage area for the Combined Instability Index (CII) and the Hydro-estimator storm track prepared with UM SA12 model could be extended beyond the 55° East in order to include both Mauritius and Rodrigues islands. Mauritius would be also interested to benefit from a SUMO-like software in order to display MSG images over the Indian Ocean.

- Swaziland is interested to receive accurate forecast guidance over an enlarged area covering their country, would like to have the possibility to zoom in model outputs issued by NCEP.  Unfortunately such facility is not easy to implement on the Pretoria Web site which only enables to display images of the plotted charts.

- In 2009 Angola mentioned that EPS products were not received in Luanda.  This was quickly corrected, however no further  information was provided by Angola in 2010.

- NMHS Namibia also mentions that verification of the warnings remains a challenge,

6.5	To improve the skill of products from Global Centres through feedback from NMCs

6.5.1	The NMSs are convinced of the importance of the feedback between participating countries and Global Centres and are willing to provide a feedback about the performance of their products. For the moment, the feedback has consisted mainly of information given in the quarterly reports, and in the case studies prepared by some NMHSs and it seems that there is no significant progress with regards to this activity.

6.5.2	While the SWFDP called for enhanced interactions among the operational centres, ongoing feedback and interactions in real-time very rarely or did not occur. It has been stressed that providing feedback to RSMC Pretoria before and during a severe weather event can help to eventually improve the RSMC Guidance; after a severe event, feedback allows to better understand the meteorological situation. However, operational contact information (telephone, fax, e-mail) were exchanged as part of the implementation. Perhaps, it would be useful to carry out regular (weekly) communication tests during active severe weather seasons, as a facilitating measure.

6.5.3	There is not possible actually to draw any firm conclusion about the efficiency of the feedback provided by the NMHSs to improve the skill of the Global Centres products. In the future, there will be a need to clearly identify the information that is requested from the NMHSs by the Global Centres.

7	Evaluation of the weather warnings issued from the NMHSs

7.1	Feedback from the public

7.1.1	Many NMHSs noted the difficulty to assess the feedback from the public especially in the rural areas due to a general lack of a regular mechanism of evaluation but informal discussions with several categories of users or occasional surveys shows that the public generally noted some improvement of quality of the forecasts issued by the NMHS.

7.1.2	Among the various actions that were undertaken to get feedback from the public it is important to note :

- the co-operation engaged between NMS South Africa and the University of Cape Town to perform evaluation of forecast products;

- the user assessment surveys performed by the NMS Zimbabwe and NMS Swaziland (such surveys are also considered in Botswana and Seychelles);

- outreach activities have been carried out in several schools and rural areas in Mozambique.

7.1.3	NMS Swaziland noted a very positive appreciation of the public on the improvement of the weather forecasts that led several users (forestry managers, railway company, hotels) to formulate requests for specialized forecast bulletins.

7.1.4	In Madagascar comments from the public point out the need to qualify severe events by making comparison with well known weather events from the past when issuing warnings.

7.1.5	In Tanzania following some complaints about the formulation of the weather forecasts issued for the public, NMS Tanzania continued to popularize the terms used in weather bulletins through participation in various exhibitions, celebrations and press briefings. The preparation of a guide of the terms to be used in forecasts in order to be more understandable by the public is also under way.

7.2	Feedback from DMCPAs

7.2.1	The SWFDP provided to NMHSs, through improved forecasting methods and increased confidence, the opportunity to contact the DMCPAs and to organize common meetings in view to strengthen their cooperation and to discuss the best way to exchange information before, during an after severe weather events. Nevertheless, by taking into account the information given by the NMHSs in the quarterly reports it is difficult to assess clearly the level of cooperation and the definition of common operational procedures.

7.2.2	Although there exists no systematic feedback from the DMCPAs in all the countries, the participation in SWFDP encouraged the NMHSs to develop closer relationships with this category of users.  Even if only brief information is given on the feedback from those who are the beneficiaries of improved forecasts and warnings, including the public, decision makers, and the media, it seems that some real efforts were made in most of the NMSs participating to SWFDP to strengthen the links with their DMCPAs, to improve the dissemination of warnings and to get feedback through various meetings or workshops.

7.2.3	During the few SWFDP Training Workshops that have been undertaken, it is evident that inviting representatives to participate with the NMHS participants has been very positive with improving mutual understanding and relations.  Participation has not, however, been at 100%.

7.3	Feedback from the media

7.3.1	Generally the media appreciated the weather forecasts and the warnings issued by the NMHS, nevertheless they do not hesitate to express their dissatisfaction in the case of missed forecasts.

7.3.2	Most of the NMHSs do not have formal feedback but maintain nevertheless good relationships with the media.  The recognition by the media of the improvement of the forecasts is very encouraging.  As a consequence meteorologists are more often asked to give special interviews for the radio or the television especially in Botswana, Lesotho and Seychelles.  Nevertheless, although several NMHSs (Malawi, Mauritius, Seychelles, and Swaziland) expressed in their quarterly report their willingness to undertake actions to improve relationships with the media, it clearly appears that NMHSs have to work actively to take up this challenge.

7.3.3	In Zimbabwe the public relation desk which become operational in the first quarter continue to work with the media and organized a half day workshop to inform about the WMO media kit.  This is indeed a very efficient way to improve the relationships with this category of users.

7.3.4	In Angola a survey has been conducted trough the Web page of the NMHSs to measure the users satisfaction in order to improve the way the weather forecasts are delivered to the users.

7.3.5	With regard to transmitting the warnings several NMHSs (Botswana, Madagascar) reported communication problems with the media that are responsible for some delay in the dissemination of the information to the public.

7.4	Objective Verification by the NMCs

7.4.1	One of the recommendations following the 5-country pilot Southern Africa SWFDP was that verification activity be encouraged and increased, both to assist forecasters in their daily evaluation of the large numbers of guidance products available to them, and to help WMO and managers of the project (Regional Technical Implementation Team) assess the impacts of the project on the quality of severe weather forecasts. Several specific activities were undertaken to focus more attention on verification of the forecasts:

- Presentations on verification were made at project management meetings, in order to demonstrate the benefits of verification activity, to increase the understanding of verification statistics, and to simplify the process of verification as much as possible.

- A recommended verification procedure for the NMS forecasts was laid out in detail and presented in a hands-on laboratory session in November, 2009.  The procedure was also fully documented in the project’s  Implementation Plan.

- Verification procedures to be applied to the RSMC graphical guidance product were discussed and agreed with RSMC Pretoria.

7.4.2	We can claim moderate success in the uptake of verification information and application in the NMSs involved in the project.  Some NMSs were following good objective verification practices before the expanded project started, but more NMSs have been using at least part of the recommended procedures by the end of 2010.  There was an upswing in verification activity following the November 2009 workshop..  There was also a quite sensible tendency to pay more attention to objective verification during the rainy season, when the frequency of hazardous weather events is higher.  The activity level however subsequently dropped off.

7.4.3	The participating RMSCs have been asking for verification information on the global products and the daily guidance products from the RSMC, so that they can choose the most reliable guidance from among the large number of products received. Accordingly, recommendations were made from an early stage for objective verification of all the guidance products from the global centres and RSMC Pretoria.  Given the large amounts of data involved, it makes most sense to do such verification at the originating centre.  A methodology was defined for the RSMC daily guidance product, but was not implemented. This is unfortunate, because the planned method would not only have helped assess the RSMC graphical product, but would have helped evaluate the MSG hydroestimator, and would have produced a valuable dataset for further evaluation of spatial verification techniques.

7.4.4	In the case of the global centres, ECMWF offered to do the verification if African observation data would be provided to them.  ECMWF also does some verification in map form, superimposing the African observations they do have over the corresponding forecast map; this map is an internal ECMWF product. This remains among the most important unaddressed aspects of the project:  as of the end of 2010, no systematic objective verification of any of the global center products or the RSMC daily guidance has been completed over the SWFDP – Southern Africa region.

7.4.5	As an important limited alternative, the NMSs could extract the necessary data from either the global or regional products and do their own verification in exactly the same way as was recommended for their own forecasts, or numerical data files with suitably extracted data (e.g. QPF, surface winds and temperature) could be provided by the NWP centres.  Two important findings were noted, one in a verification study along these lines was carried out in one country during the project (Tanzania), which showed that the NMS was able to improve on the guidance from the RSMC.  In another separate study, NMS Madagascar demonstrated that the “medium” category of risk is the best threshold to use to trigger a warning. While these individual studies are encouraged and produce interesting and useful results, they are limited in scope.  There is no substitute for a full verification of the forecasts from the global models, with respect to observations of the region at all stations, beginning with stations whose observations are included on the GTS, and extending to include data which are not on the GTS, with the help of the NMSs.  Results from this verification are badly needed by the NMS forecasters.

7.4.6	Verification activity through 2009 and 2010 in each country is summarized in the following paragraphs and in Table 3.  Wherever possible, the data tables submitted in the quarterly reports were used to complete contingency tables and scores if this was not done by the NMSs.  For countries where one event per day was reported, the tables were completed assuming the rest of the days of the year were days where no severe weather occurred and none forecast, that is, “correct negatives”.  A few general points are noted:

- The project documentation system is event-based.  That is, all events are documented and the assessment focuses on whether or not a warning was issued.  This could be one reason most participants reported few false alarms in their reports (cases where a warning was issued, but nothing happened).  However, another important factor expressed by some of the participants is a general fear of losing credibility if even one false alarm is recorded.  This led to underforecasting the frequency of severe weather (or increasing “misses”) in some countries; as it was considered better to miss some events rather than cause a false alarm.

- The verification was for the most part limited to evaluating the accuracy of forecasting severe weather days over the whole country, rather than evaluating forecasts regionally within each country.  This is fine for smaller countries, and also fine as a first step for larger countries, but the utility of warning information for disaster-preparedness agencies depends on accurate forecasting of the approximate location of the severe event as well as its timing.  In the guidelines for verification that were established for the project, several criteria were stated to guide the regionalization of forecasts within larger countries:

- The location and readiness of disaster relief agencies:  The regional domains should be small enough that disaster relief agencies can respond effectively to warnings within the lead time that is normally provided.

- The availability of observation data. Each domain should have at least one representative and reliable observation site for forecast verification purposes

- Climatology/terrain type:  It is most useful to define regions so that they are as climatologically homogeneous as possible.  If there are parts of the domain that are much more likely to experience severe weather than others, these could be kept in separate regions.

- Severe weather impacts:  The domain locations and sizes should take into account factors affecting potential impacts such as population density, disaster-prone areas etc.

- Within these guidelines, it is also useful if the warning areas are roughly equal in size, since that will help ensure consistent verification statistics.  And, within each country, the warning criteria should be constant for all domains.  Finally, for the purposes of the Southern Africa project, and for possible comparisons with the results of verification of the global model forecasts over multiple countries, it would be useful if the subdomains in all countries would be roughly similar in size.

- One standout example where regional verification was undertaken was in Zimbabwe for 2009, where the country was divided into 6 regions, and forecasts for each verified separately.  Botswana also verified their forecasts regionally. These are two examples where forecast and verification practice came closest to the guidelines and serve as an example for others to follow in future verification activities.

- For computation of contingency tables and their scores, participants were encouraged to include in a single table all types of severe weather that were documented, since this would give a more general indication of forecast accuracy.  Whenever enough events are recorded of a particular type, separate tables could be computed.  Most NMSs followed this guideline; tables were often computed only for heavy precipitation, since this was the phenomenon with the greatest threat and also of the most frequent occurrence.

- A few countries submitted complete enough data to permit a comparison of forecast accuracy for the two years.  There is evidence (Botswana and Tanzania) that the forecasts did improve in the second year compared to the first, and there was no evidence in the available data of a decrease in the quality of forecasts from 2009 to 2010.  Forecast quality in Lesotho was about the same in 2009 and 2010.

- There were significant differences among the countries concerning the definition of the severe weather event.

- Some NMHSs defined each day as an event, so that the total sample size will equal the number of days in the verification period.  For these countries, the contingency table will include all 4 boxes, since inactive days are counted as correct negatives.

- Other NMHS’s considered only the active days as events, so that their contingency table includes only 3 of the boxes (hits, misses and false alarms) and their sample size is equal to the number of active days. In those cases it is not always clear whether false alarm days (warning issued, but no event reported) are included or not.

- A third interpretation of event was also found where inactive days were counted as one event, while active days resulted sometimes in more than one event.

As a result, it is not always clear whether the location of the observed events versus the forecast is taken into account when compiling the contingency tables.  In other words, if the forecast specifies a location for severe weather, and it occurs, but somewhere else, is that counted as a hit, or a false alarm and a missed event for the forecast and observed location respectively? More importantly, differences in the definition of the severe weather event in both forecast and observation among the countries means that the verification results should not be compared between countries. Such a comparison would not be meaningful.

7.4.7	Table 3 summarizes the verification activity of the 16 NMSs. 9 of the 16 countries prepared severe weather data tables in the suggested format, 9 also computed contingency tables, at least when warranted by the occurrence of sufficient events, and 9 NMSs computed related contingency table scores.  4 NMSs went farther, discussing the scores obtained and in some cases preparing reports comparing results from different sources.  These reports are informative and interesting, and believed to indicate increasing regard for the importance of verification in quality assurance of warnings and warning programmes in the NMS participating in the project.

Table 3. Summary of verification information contained in quarterly reports from the 16 NMHSs involved in the Southern Africa SWFDP, 2009 and 2010.

8	Conclusions

## 8.1	Improved weather forecasting and warnings services and improved verification

8.1.1	Rolling out the RSMC Daily Guidance Products to all 16 countries in the region has progressed quite well. Most of the involved countries use RSMC Daily Guidance and SWFDP products available on the SWFDP Web site and give regular feedback for the preparation of the Quarterly Reports during the year 2009. On the other hand, as it can be seen on Table 1, some NMHSs had difficulties to provide their Quarterly Reports during the year 2010.

8.1.2	The difficulty to get regular feedback during the second year of the experimentation is suggested from some redundancy of answers given by the NMHSs to the questions formulated in the Quarterly Report template. The answers to questions concerning the usefulness of the RSMC Pretoria Daily Guidance and SWFDP products always showed that all the NMHS were really satisfied with the products of modern numerical weather prediction systems. However, after two or three quarters there is perhaps no longer the need to continue to ask NMHSs about the usefulness of the support provided by SWFDP. The information provided quarterly by the NMHSs should essentially provide the Quarterly Evaluation Table carefully filled and report on the significant actions undertaken by the NMHS to reach the goals of SWFDP.

8.1.3	Only a few NMHSs (Angola, Comoros and Democratic Republic of Congo) did not send useful feedback to WMO Secretariat. Nevertheless, it is important to point out that WMO Secretariat received some information from two of these countries:

- The NMHS Angola submitted reports for the fourth quarter of 2009 and the first quarter 2010.

- In November 2009, Democratic Republic of Congo nominated a representative to the Regional Technical Implementation Team (RTIT) of the SWFDP, showing thus its clear willingness to participate actively in the project but did not send any feedback.

- Even though Comoros has not yet nominated a representative to the project’s management team (RTIT), a short report about severe weather for the fourth quarter 2009 was submitted.

8.1.4	All the countries that reported are globally satisfied by the support that the SWFDP provided, not only for severe weather forecasting but also useful for the day-to-day routine forecasting. In contrast to the feedback received from the earlier first phase of the SWFDP, there were no remarks concerning difficulties to access the products through the SWFDP Web site and portal via the Internet.  During the SWFDP Training Workshop (November 2008), and the SWFDP - Southern Africa planning meeting (February 2009), none of the sixteen NMHSs of southern Africa indicated any local Internet access problems, hence this first quarter reporting is consistent with the conclusion that most, if not allof the NMHSs (except DR Congo), are able to adequately access the various SWFDP guidance products.

8.1.5	The RSMC Web site continues to be the main means of communicating the SWFDP products prepared by the global and regional centres to the 16 NMHSs.  Some important modifications were made to introduce new products available under the “Nowcasting” section of the SWFDP Web site (hydro-estimator, the instability index).  The availability of the products of the high-resolution ALADIN-Réunion model provided by RSMC La Réunion complements those from the UM-SA12 (South Africa) model, together provide high resolution model coverage over the entire geographical domain of the SWFDP.

8.1.6	All the participants agreed on the usefulness of the RSMC Daily Guidance and NWP guidance products for severe weather forecasting.  The shortcomings of the NWP model output that were reported in the context of severe convective situations are well known and this is the reason why the use of nowcasting tools in the very short-range, including improved access and better use of MSG-satellite products must be encouraged.  It is also important to note that the island countries of the Southwest Indian Ocean are particularly satisfied with the information that is provided on sea-state and wave height when severe weather occurred.

8.1.7	Verification activity has increased at the NMHS level during the project.  A contingency table based objective verification system was designed and is being actively used by some of the participating NMSs

8.1.8	The balance of evidence from the verification activity is that the quality of the severe weather forecasts improved over the course of the two year period.

8.1.9	Verification training appears to have had a positive impact, encouraging greater activity, but there is also some tendency to “fading”.  To correct this, workshops including verification exercises should be held once a year; the training could be given by representatives of those NMSs which have been most active in using the suggested procedures.

8.1.10	Some technical improvements were suggested by several NMHSs :

- NMHS Mauritius would appreciate to receive the short-range RSMC Daily Guidance earlier in the day due to its advanced time zone from that of the east coast of Africa.  However substantial dedicated time is needed by the forecasters to prepare this to formulate a clear assessment about the expected weather for the entire region of half a continent.  Taking the time shift between South Africa and Mauritius in to account, with the latter’s workday starting a few hours before RSMC Pretoria, the products for days 1 and 2 become only available during the afternoon of day 1 in Mauritius.

- There were some complaints of the size of the NCEP graphical maps (Swaziland) and the difficulty of identifying their country in the RSMC Guidance (Malawi). Consequently it is important that RSMC Pretoria forecasters identify geographically the threatened areas by referring to the names of the countries.

- Small countries expressed a request for the possibility of zooming the model fields to get a better view of the fields over small areas. It is important to recall first that zooming can be efficient only if the fields are provided as grid point data (while products available on the RSMC Web site are images of the fields), and secondly that zooming cannot provide more detail or better accuracy than the resolution of features resolved by the model.

- Many NMHSs highlighted the importance of the training workshops that were carried out in the framework of the SWFDP (Pretoria, 10 to 21 November 2008,  26 October to 6 November 2009, Saint-Denis de la Réunion, 2 to 13 November 2010) . They continue to express a real need for training for forecasters about the performances and the possible shortcomings of the various NWP models that provide guidance to forecasting (e.g. medium-range global products, limited area predictions, how to interpret the probabilistic forecasts combined with the deterministic ones), and to propose to them a way of working to deal with the large amounts of information.

8.2	Issues and challenges: verification of guidance products from global and regional centres, improvement of the quarterly evaluation table

8.2.1	An evaluation system for the RSMC guidance maps against satellite rainfall as measured using the Hydro-estimator system running at the RSMC has been planned.  Once this proves to be a viable method, it will be used to attempt verification of the rainfall areas on the guidance maps since the beginning of this project. It is important to continue to make an effort to develop a tool to enable to perform objective verification of the areal precipitation forecast charts, such as provided in the RSMC Pretoria Daily Guidance. Verification of operational guidance products is an important part of the forecast process, not only for the users of those products but also for the developers of automated products such as the hydroestimator and for modelers.  RSMC Pretoria is urged to assign resources in 2011 to carry out the agreed verification of the graphical severe weather forecast chart.

8.2.2	One of the aims of the Quarterly Evaluation Table was to provide feedback about the occurrence of severe weather events enabling to perform some objective verification of the quality of the Risk Tables provided by the RSMC Pretoria Daily Guidance and thus to assess the value of this information in the countries participating to SWFDP. This task needs to make in every country a comparison between the data that appear in the Risk Tables and the observed severe weather events for the various ranges. Limited studies to evaluate the risk tables were done in Tanzania and Madagascar, but no verification of these products was carried out at the RSMC Pretoria. It is important to carry out this verification as part of the guidance information.  To ensure consistency and considering the large data volumes involved in a full verification across the entire 16 countries, this work should be done at the RSMC. It is recommended that RSMC Pretoria assign higher priority to verification of all the products issued by the RSMC.

8.2.3	There is still a complete lack of systematic objective verification of all of the NWP products from the global centres.  This shortcoming must be addressed to provide guidance to the forecasters to enable them to select the best guidance from the large quantity of products received daily. Verification of the ensemble-based products is also needed (on relevant hazards) as an essential prerequisite to the introduction into SWFDP of outputs from GIFS-TIGGE- related experiments on combined ensemble products.  It is recommended as a start to this process that all existing diagnostic products relevant to operational SWFDP forecasts, such as the precipitation maps of Africa prepared in ECMWF, be provided to the participating NMHSs as soon as they are available. It is further recommended that the global centers carry out systematic verification of the surface variable forecasts from their models and ensembles for the domains of all operational SWFDPs. If the global centers are not able to do the actual verification, it is suggested that, as an absolute minimum effort, they make it possible for the NMSs to carry out verification by sending timeseries of forecasts for prespecified locations periodically to the NMSs (for example, monthly) so that verification can be carried out by others.

8.2.4	The last SWFDP Steering Group meeting recognized the need to improve the Quarterly Evaluation Table summarizing the weather events forecasted of observed during the quarter. Some exchanges between participants in this meeting that took place at the middle of the experimentation period enabled to propose an improved form. Nevertheless it has been thought that it was not efficient to change the format of this document in the course of the experimentation period. The improvement of the Quarterly Evaluation Form should be addressed for the continuation of the severe weather project.

8.3	Issues and challenges: increase interaction with the users

8.3.1	One of the goals of the SWFDP is to strengthen links between the NMHSs and their respective DMCPAs, including flood and water management services.   While some progress has been mentioned in many participating countries, it is important to stress the necessity to continue discussions with all the users concerned by severe weather events, to clearly understand and define information they need, and the most efficient way to alert them in a timely fashion.

8.3.2	Moreover, the implementation of a regular evaluation programme supports regular assessment of the efficiency and effectiveness of the alerting system and to identify areas for improvement.  Evaluation should take into account the lead-time of the warnings, the transmission of the information to the concerned users and stakeholders, the mitigation actions, and the feedback from the end users during and after the event. NMHSs need to continue to work with the DMCPAs to ensure that the warning services meet the requirements, and to sustain and continue to improve these services beyond the SWFDP demonstration.

8.3.3	It is also important to point out that terminology that is used for different types of alerting messages (early warning, advisory, warning, alarm, alert …) must be clearly defined. The specific word(s) used should clearly qualify an alerting message, and should give clear indications on both the severity of the event, the lead-time, and where they exist also the emergency level with well defined associated protective measures.  Lead time for issuing a specific alerting message always depends on the protective measures DMCPA and users have to invoke, or advised to take, in order to mitigate the disastrous consequences of the expected severe event.

8.3.4	To obtain valuable feedback from the public and media about the usefulness and effectiveness of warnings, it is necessary to define clearly all the information required, and to prepare and send a questionnaire to be filled by the users after each severe weather event. The overall recommendation on PWS aspects is that the NMHSs should continue to pursue seriously real evaluation of their improved products and services in order to get the users’ community engaged in a positive way.

8.3.5	Guidance materials provided by PWS are freely available and contain most of the materials needed by the participating NMHSs to assist and show them how to create channels of communication with these two large user groups. In addition, the WMO Joint GDPFS/PWS Training Workshops, where participants from NMHSs share experience on developing dialogue with user communities and responding to their requirements as stakeholders, have proved to be a rich sources of information and guidance for all NMHSs.

8.4	Issues and challenges: feedback toward Regional and Global Centres

8.4.1	It seems that there is no significant improvement with regards to the feedback from the NMHSs for the Global Centres, which are intended to improve the skill of their NWP guidance products (SWFDP Goal 5).  While feedback of substance is highly desirable, Global centres would also like to receive any additional surface observational data (over and above data already made available on the GTS) for inclusion in their NWP verification activities of surface parameters.  Clearly at training sessions expert lecturers from the Global Centres meet the forecasters from the participating countries face-to-face; such infrequent events offer a real opportunity to discuss the performance of the numerical models, including their shortcomings with help of well documented case studies.

8.4.2	It is necessary to improve the feedback from NMHS.  After each observed (or forecast) severe event, it was difficult to obtain from the NMHS the required Event Evaluation Form designed by the Regional Subproject Management Team to be used to regularly assess the usefulness and quality of the RSMC Daily Guidance issued by RSMC Pretoria.  The Management Team (RTIT) agreed that its simplified format should help gather relevant information about the individual events.  The lack of such responses could indicate that: 1) during severe weather periods forecasters are simply too busy to fill in immediately such event evaluation forms; 2) the verification of the guidance, forecasts and warnings against actual occurrence of severe weather is often difficult because meteorological observations or damage reports are simply not available.

8.4.3	Timely real-time feedback to RSMC Pretoria is essential to improve the skill of the senior forecasters who prepare the RSMC Daily Guidance for the entire southern Africa region. Moreover it is only with this information that it is possible to evaluate objective measures of quality (FAR and POD), and their trends over time.   It was suggested that forecasters at NMCs should contact the RSMC prior to issuing forecasts and warnings during anticipated severe weather situations, to discuss and confirm the latest data and information available.  This has not occurred.

8.5	Issues and challenges: verification by the NMHSs

8.5.1	Data and information regarding the actual occurrence of severe weather events are crucial for verification of warnings and establishing the necessary future improvements of the forecasting and warnings system.  It was often mentioned that observational data in affected areas and information on damage and impacts were generally sparse or not available.

8.5.2	There needs to be greater attention paid to regionalized forecasting and verification within the larger countries.  To provide the best possible advance warning of severe weather, NMSs of the larger countries are encouraged to divide their countries into predefined regions according to the guidelines described above, to issue severe weather forecasts which contain region-specific information, and then to verify the forecasts for these regions.  For example a weather warning that covers an area much larger than the affected area is less useful than a warning that covers an area closer in size to the affected area.  Regionalization would make the warnings more useful to disaster response agencies, and if they are verified regionally, the results would be more useful to forecasters and the forecast product developers.

8.5.3	A couple of NMHSs accumulated events from successive reporting quarters information to compute the table and scores on the full sample; this is a good idea, particularly when there are few events.  The computed tables can be compared with what was obtained for the previous quarters to see if any significant changes occurred.

8.5.4	While some NMHSs are following quite closely the verification methods laid out in detail in the project documentation and presented at the training workshop in November 2009, the contingency table and score computation still needs to be tightened up in several ways, to improve its value. If the methodology outlined in the project documentation is followed, the results will be more useful to all users of the verification results, and will result in improved tracking of benefits of the project.

8.5.5	As part of every quarter’s report of the SWFDP, the NMHSs were requested to prepare case studies and to archive the complete documentation (relevant NWP fields, satellite images, warnings, and observations).  In principle this material is very important for modellers and developers to use them as test cases, to run improved models, and as well be used to for training forecasters.  So far, little use has been made of these case studies, although they serve as important illustrations of severe weather forecasting in this region.

8.5.6	Finally, for the completeness of the future SWFDP Quarterly Progress Reports, all NMHSs’ quarterly reports should follow closely the agreed format (template) in the SWFDP - Southern Africa Regional Subproject Implementation Plan, including the Quarterly Evaluation Table (all severe events). It is particularly important to understand the definition of what is a single severe weather event. See paragraph 9.4.4 especially, where this is clearly stated and described.

9.	Annexes

Annex 1: Summaries of verification activity in each country as indicated in the quarterly reports.

Annex 2:  List of the abbreviations used in conjunction with the SWFDP.

Annex 3:  List of the available documentation related to the implementation and reports of

SWFDP Southern Africa.

10.	Acknowledgement

This report has been made possible by the inputs of regular reports and other communications from the participating centres of the SWFDP – Southern Africa project, including global products centres ECMWF, Met Office UK, NCEP USA; Regional Centres RSMC Pretoria, RSMC La Réunion; and the National Meteorological Centres of Southern Africa.

ANNEX 1

Summaries of verification activity in each country as indicated in the quarterly reports

Angola:  The one report received from Angola contains basic contingency table information for the 2009-10 wet season.  No attempt was made to compute the contingency table scores.

Botswana:  Botswana provided the most complete verification information of all the 16 countries in the project.  A running contingency table was kept throughout the two years, following the suggested procedure of counting a single event for each 24h. The verification was also done regionally. The table was updated with results from each of the quarters.  Scores were computed each time from the accumulated tables; the score values were not discussed in the reports.  Only a small amount of extra processing needed to be done to effect a comparison between the performance for 2009 and 2010.  Results showed that the performance of the Botswana NMS did indeed improve in 2010 compared to 2009.  The sample is probably large enough that one could be confident in this result, and even the scores (equitable threat and Heidke skill) which take account of variations in the climatology from year to year indicated an improvement during the project.

Comoros:  The one quarterly report received contains no verification information.

D. R. Congo.  No reports received.

Lesotho: Fairly complete verification information was provided both in the form of data tables and also in contingency table format for some quarters.  From the data tables listing the 63 severe weather events, it was possible to complete the verification information for 2009 and 2010 with some additional work, and to produce tables and scores for both years. Results showed probability of detection of the severe events at about 38%.  Overall forecast accuracy was about the same for both years.  There seems to be a significant underforecasting tendency perhaps due to a wish to avoid false alarms, since only 1 false alarm was reported in the two years.

Madagascar: Although only two quarterly reports were received from Madagascar, these contained some unique and interesting verification analyses.  Contingency tables were produced to evaluate the RSMC severe weather risk guidance, rather than the local office forecasts.  For the 2008-2009 rainy season, separate contingency tables were built under the assumption that low, medium or high risk would trigger the issue of a severe weather warning. (three thresholds).  The results suggested that the use of the “medium” risk as threshold for issuing a warning gave the best results.  The table built this way showed the best frequency bias, and the highest Heidke, threat, and Hanssen-Kuipers scores.  The NMS Madagascar also prepared separate tables for two regions of the country, following the recommended procedure.  The results of this evaluation were used in presentations at the February, 2009 meeting and in the documentation accompanying the verification lab sessions to show how this analysis can be used to demonstrate the utility of the forecasts for decision-making.

Malawi: Malawi submitted a complete set of quarterly reports (8).  On one of these, the verification included a contingency table analysis, while on most of the other quarters there were considered to be too few severe events to warrant a contingency table.  The data from Malawi was further studied by compiling the event tables over the two year period for heavy rain events only; no objective reports are included in the event table for wind speed, thus these types of severe events could not be verified.  Results indicate a hit rate of about 50% and an underforecasting tendency, especially in 2010, when no false alarms were reported.

Mauritius:  Mauritius contributed contingency table verification results from the beginning until the first quarter of 2010; no reports have been received since then.  Contingency tables were computed without consideration of “correct negatives”, (an acceptable procedure) and the relevant scores were computed from hits, false alarms and misses.  Mauritius uniquely presented results for both 50 mm and 100 mm thresholds. Their results were further processed by adding correct negatives to the table assuming one per day, and totaling the tables through the entire period available, November 2008 to March 2010.  The combined table scores show that, for the 50 mm category, frequency bias was near 1, severe events were forecast with about the same frequency they were observed.  Events exceeding the higher threshold were significantly underforecast, perhaps because of a reluctance to incur too many false alarms.  Mauritius apparently also does a good job of discriminating severe weather situations from non-threatening situations, as indicated by a relatively high Hanssen-Kuipers score.

Mozambique:  Quarterly reports were sent only for the first two quarters of 2009.  The first of these included a good verification analysis of the 28 events recorded, with both contingency table and scores shown.  In the second quarter there were not enough events to justify a full verification analysis.  It is unfortunate that the good verification work was not carried on again for the 2009-10 rainy season.

Namibia: No systematic objective verification was carried out during the entire period.  The data table of events was presented only once, for the second quarter of 2009.

Swaziland:  No data or results of verification activity reported.  The quarterly reports indicate that the NMS understands the value of verification, but also indicate that learning is still going on.  The report for the third quarter of 2010 specifically promised a verification study during the 2010-2011 rainy season, but no severe events were reported by the end of 2010.

Seychelles:  Quarterly reports from Seychelles were received only for 4 of the 8 quarters during 2009-10.  The reports received mention 5 severe weather events, of which two were “hits” and three were missed.  No verification was done by the Seychelles NMS.

South Africa:  No verification was reported from South Africa until the third quarter of 2009, despite a relatively large number of warnings issued even in the dry season.  For the rainy season of 2009-10, some contingency table scores were computed and reported. In addition to hit rate, false alarm rate and threat score, South Africa also reported something called “Accuracy” which is not defined in the reports. Verification activity faded after the first quarter of 2010.  The RSMC in Pretoria didn’t undertake any verification activity, citing lack of resources, although a comprehensive verification of the graphical severe weather chart was planned in detail.  Had this been done, it would have provided very useful information to the participating NMSs and would have set an example for verification in the other countries.

Tanzania:  Until the third quarter of 2009, TMA reported only the severe weather event list according to the specified format.  After that, for all quarters where sufficient severe weather events occurred, contingency tables and scores were also computed, for both the TMA forecasts and for the guidance forecasts from RSMC Pretoria.  These comparisons showed that TMA routinely is able to improve on the RMSC guidance that is available.  Results for the full year 2009 (actually November 1 2008 to December 31, 2009) and the full year 2010 were compiled in contingency table format using the tables from TMA wherever possible, and augmenting those with data from the tables in the quarterly reports for quarters where tables were not computed.  In 2009, few false alarms were reported, perhaps suggesting too few warnings were issued.  The scores for 2010 are more balanced compared to those for 2009, with increased hit rate and higher frequency of warnings compared to observations, but only a small percentage increase in false alarms.  Here too, the warning service seems to have improved during the course of the project.

Zambia: No verification information contained in any of the quarterly reports. They state without supporting details that verification is valuable and that it is carried out in real time by individual forecasters.

Zimbabwe:  In the first part of the two year period, Zimbabwe showed excellent attention to verification by preparing a full verification report on the 2008-09 rainy season (authored by Tirivanhu Muhwati and Reynold Ndoro).  In this work, they followed the recommended procedure of dividing the country into fixed regions of a manageable size (from a disaster-preparedness perspective) and compiled the verification statistics for those regions.  Contingency tables were produced along with all scores, then these were analysed to draw conclusions about the forecasts.  Unfortunately, this was not followed up with a similar effort for the 2009-2010 season, although promises were made in the early 2010 quarterly reports to do so.  Data is available in the prescribed format in the quarterly reports to do the analysis for 2010, but this is less detailed than would be required to match the comprehensive study completed for 2008-09.

ANNEX 2

List of the abbreviations used in conjunction with the SWFDP

ALADIN          : High Resolution Limited Area Model run by La Reunion, 10 km mesh

DMCPA	: Disaster Management and Civil Protection Authority

ECMWF	: European Centre for Medium Range Weather Forecasts

FAR		: False Alarm Ratio

NWP		: Numerical Weather Prediction

GDPFS	: Global Data Procession and Forecasting System

Met Office	: Meteorological Office (UK)

NCEP		: National Centers for Environmental Prediction (USA)

NMC               : National Meteorological Centre

NMHS 	: National Meteorological (and Hydrological) Service

POD 		: Probability Of Detection

RA I		: Regional Association I (Africa)

RSMC		: Regional Specialized Meteorological Centre

RSMT		: Regional Subproject Management Team (SWFDP)

RTIT               : Regional Technical Implementation Team (SWFDP – Southern Africa)

UM-SA12	: Unified Model, Southern African area, 12 km mesh,

SAWS		: South African Weather Service

SWFDP	: Severe Weather Forecasting Demonstration Project

ANNEX 3

List of the available documentation related to the implementation

and reports of SWFDP Southern Africa.

All the documents can be accessed at the following webpage of the WMO Internet site:

http://www.wmo.ch/pages/prog/www/CBS-Reports/DPFS-index.html

Guidebook on Planning Regional  Subprojects  - Rev. September 2008

http://www.wmo.int/pages/prog/www/DPFS/Meetings/RAI-SWFDP-RTIT_Pretoria2009/documents/SWFDP_Guidebook_Updated_24sept2008.doc

SWFDP Southern Africa - Meeting of the Regional Technical Implementation Team (RTIT) – February 2009
http://www.wmo.int/pages/prog/www/CBS-Reports/documents/FINAL-REPORT_RAI-SWFDP-RTIT_Pretoria2009.doc

SWFDP Southern Africa - Regional Subproject Implementation Plan : 2008-2011 Southern Africa (pdf) – February 2009

http://www.wmo.ch/pages/prog/www/CBS-Reports/documents/Regional-Impl-Plan_2008-2011.pdf

Project Quarterly Reports:

Project Q1 Progress Report : 24 November 2008 - March 2009
http://www.wmo.ch/pages/prog/www/CBS-Reports/documents/SWFDP_SrnAfr_Q1_Final24VII2009.pdf

Project Q2 Progress Report : April - June 2009
http://www.wmo.ch/pages/prog/www/CBS-Reports/documents/Q2_ProgRep_4XII09.pdf

Project Q3 Progress Report : July - September 2009
(in preparation)

Quarterly Reports from NMHSs and RSMCs can be found at the following address:  http://www.wmo.int/pages/prog/www/BAS/DPFS-RAI-TW-SWFDP-Pretoria09_DocPlan.html

Final Report of the Third CBS Steering Group Meeting, Geneva 23-26 February 2010.
http://www.wmo.int/pages/prog/www/CBS-Reports/documents/SG-SWFDP-3_FINALREPORT.doc

Review and Evaluation of SWFDP Project – Verification activities in the SWFDP.

http://www.wmo.int/pages/prog/www/DPFS/Meetings/SG-SWFDP_Geneva2010/documents/doc3-4.doc

# Text boxes

| Country | Q1 2009 | Q2 2009 | Q3 2009 | Q4 2009 | Q1 2010 | Q2 2010 | Q3 2010 | Q4 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Angola |  |  |  | X | X |  |  |  |
| Botswana | X | X | X | X | X | X | X | X |
| Comoros |  |  |  | X |  |  |  |  |
| D.R. Congo |  |  |  |  |  |  |  |  |
| Lesotho | X | X | X | X | x | x | x | x |
| Madagascar | X | X |  |  |  |  |  |  |
| Malawi | X | X | X | X | X |  |  |  |
| Mauritius | X | X | X | X | X |  |  |  |
| Mozambique | X | X |  |  |  |  |  |  |
| Namibia | X | X |  | X |  |  |  |  |
| Seychelles | X | X | X |  | x |  |  |  |
| South Africa | X | X | X | X | X | X | X | X |
| Swaziland | X | X | X | X | X | X | X | X |
| Tanzania | X | X | X | X | X | X | X | X |
| Zambia | X | X | X | x | x | x | x | x |
| Zimbabwe | X | X | X | X | X | X | X | X |
| RSMC Pretoria | X | X | X | X | X | X | X | X |

| Country | Data table | Contingency Table | Scores | Analysis/Discussion |
| --- | --- | --- | --- | --- |
| Angola | No | No | No; total hits, misses, FA stated | No |
| Botswana | Yes, complete | Yes, accumulated | Yes | No |
| Comoros | No | No | No | No |
| R.D. Congo | No | No | No | No |
| Lesotho | Yes | Yes | No | No |
| Madagascar | No | Yes, for RSMC | Yes | Yes |
| Malawi | Yes | Yes, when enough events | Yes | No |
| Mauritius | Yes | Yes | Yes | No |
| Mozambique | Yes | Yes | Yes | Yes |
| Namibia | Yes, once | No | No | No |
| Seychelles | Yes | Not enough events | Hits and misses stated | No |
| South Africa | No | No | Yes | No |
| Swaziland | No | No | No | No |
| Tanzania | Yes | Yes | Yes | Yes, full comparative analysis |
| Zambia | No | No | No | No |
| Zimbabwe* | Yes | Yes, for 6 regions | Yes | Yes |

| USEFULNESS OF SWFDP SUPPORT |
| --- |
| Country |  | Guidance usefulness | NWP/EPS usefulness | Number of warnings |
| 2010 | Mark | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  |
|  | Nb. events |  |  |  |  |  |  |  |  |  |
| Angola | - |  |  |  |  |  |  |  |  |  |
| Botswana | 44 | 1 | 27 | 7 | 8 |  | 23 | 18 | 3 | 18 |
| Comoros | - |  |  |  |  |  |  |  |  |  |
| R.D. Congo | - |  |  |  |  |  |  |  |  |  |
| Lesotho | 17 |  | 7 | 2 | 2 |  | 3 |  | 4 | 7 |
| Madagascar |  |  |  |  |  |  |  |  |  |  |
| Malawi | 33 |  | 13 | 19 |  |  |  |  |  | 21 |
| Mauritius | 4 |  |  | 4 |  |  |  | 4 |  | 4 |
| Mozambique |  |  |  |  |  |  |  |  |  |  |
| Namibia | 5 |  |  | 5 |  |  |  | 5 |  | 5 |
| Seychelles |  |  |  |  |  |  |  |  |  |  |
| South Africa |  |  |  |  |  |  |  |  |  |  |
| Swaziland |  |  |  |  |  |  |  |  |  |  |
| Tanzania | 164 | 23 | 33 | 11 | 22 | 12 | 57 | 40 | 37 | 94 |
| Zambia |  |  |  |  |  |  |  |  |  |  |
| Zimbabwe | 40 | 2 | 23 | 13 |  |  |  | 18 | 22 | 11 |
| Total | 307 | 26 | 103 | 61 | 32 | 12 | 83 | 85 | 66 | 160 |

| USEFULNESS OF SWFDP SUPPORT |
| --- |
| Country |  | Guidance usefulness | NWP/EPS usefulness | Number of warnings |
| 2009 | Mark | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  |
|  | Nb. events |  |  |  |  |  |  |  |  |  |
| Angola | - |  |  |  |  |  |  |  |  |  |
| Botswana | 61 | 3 | 28 | 14 | 16 |  | 24 | 34 | 3 | 28 |
| Comoros | - |  |  |  |  |  |  |  |  |  |
| R.D. Congo | - |  |  |  |  |  |  |  |  |  |
| Lesotho | 25 |  | 9 | 3 | 13 |  | 6 | 2 | 16 | 11 |
| Madagascar |  |  |  |  |  |  |  |  |  |  |
| Malawi | 46 |  | 13 | 30 | 3 |  |  |  |  | 25 |
| Mauritius | 6 | 2 |  | 2 |  | 1 |  | 5 |  | 3 |
| Mozambique | 29 |  |  |  |  |  |  |  |  |  |
| Namibia | 7 |  | 1 | 2 | 4 |  | 1 | 2 | 4 |  |
| Seychelles | 4 |  | 3 |  | 1 |  |  | 1 |  | 1 |
| South Africa |  |  |  |  |  |  |  |  |  |  |
| Swaziland |  |  |  |  |  |  |  |  |  |  |
| Tanzania | 80 | 9 | 38 | 10 | 17 |  | 19 | 42 | 19 | 42 |
| Zambia | 1 |  |  |  |  |  |  |  |  |  |
| Zimbabwe | 50 | 16 | 11 | 21 | 2 |  | 10 | 19 | 21 | 14 |
| Total | 309 | 30 | 103 | 82 | 56 | 1 | 60 | 105 | 63 | 124 |