| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS OPAG on DPFS Severe Weather Forecasting Demonstration Project (SWFDP) Regional Subproject Management Team ARUSHA, TANZANIA 27 – 31 MAY 2013 |  | DPFS/RAI-SWFDP-EA-RSMT/Doc.3.2 (15.V.2013) _______ Agenda item : 3 ENGLISH ONLY |
| --- | --- | --- |

Summary of experience and progress of the Severe Weather Forecasting Demonstration Project (SWFDP) for Eastern Africa (RA I)

(Submitted by Mr James Kongoti)

##### Summary and purpose of document

This document …

##### Action Proposed

The meeting is invited to…

Annex(es):	- …….

- …….

Reference(s):	- …….

- …….

1 	Introduction

The World Meteorological Congress, at its sixteenth session (Cg-XVI, May 2011) recommended the use of the SWFDP as a framework or project development process for regionally-driven initiatives to improve the capability and capacity of WMO Members in the production of forecasts, warnings and advisories with greater precision, for multi-hazard Disaster Risk Reduction and Service Delivery. In this context, Cg-XVI agreed that the SWFDP concept should be further implemented, expanded into more regions, and requested the Commission for Basic Systems (CBS) to further consider the possibility of implementing similar projects, with particular attention to LDCs and SIDSs.

Therefore, the SWFDP framework represents a systematic approach for building capacity and for transferring knowledge and skills to NMHSs, especially those of developing countries. The SWFDP has much strength, in concept and in the design, including user engagement, addressing regional needs; building of cross-programmatic integration when it contributes to the project’s goals, and creating sustainable development.

The SWFDP is currently progressing well in the five regional Subprojects worldwide.  However, there are a few participating countries that have been experiencing difficulties to fully participate in the activities that are designed to improve their essential capacities in relation to severe weather forecasting and the delivery of warning and advisories services.

Successful planning and implementation of the regional Subprojects points to the need for strong working partnerships, coordination and capacity development among the climate/weather producers and the climate/weather users to create an end-to-end  value chain that supports and integrates adaptive and strategic decision making and more effective development. Coordination will be required among a number of the independently-funded implementing institutions such as WMO, Global Products Centres, Development Partners, Regional Centres, NMHSs, Disaster Managers and Users.

2	Objectives of the SWFDP

The main objective of the Severe Weather Forecasting Demonstration Project (SWFDP) is to test the usefulness of the products currently available from NWP centres, or products that could be made available from current NWP systems, with the goal to improve severe weather forecasting services in countries where sophisticated model outputs are not currently used.  This project employs a Cascading Forecasting Process concept of operations to provide greater lead-time for alerting of severe weather events and at the same time contributes to capacity development and improving national level links with the respective national Disaster Management and Civil Protection Agencies (DMCPAs).

According to the recommendations of the CBS-XIII (2005) the goals of the SWFDP were defined by SWFDP Steering Group in Geneva (14-16 December 2005) as follows to:

- improve the ability of NMCs to forecast severe weather events;

- improve the lead time of alerting of these events;

- improve interaction of NMCs with DMCPA before and during events;

- identify gaps and areas for improvements; and

- improve the skill of products from GDPFS centres through feedback from NMCs.

The CBS-Ext.(06) stressed the need to involve civil protection authorities to improve delivery of severe weather warning and advisories services.  Regarding this aspect, collaboration with the Public Weather Services (PWS) and with the Disaster Risk Reduction (DRR) programmes was encouraged.

The Cascading Forecasting Process

In compliance with the Global Data-Processing and Forecasting System (GDPFS) organizational framework, the SWFDP employs a well co-ordinated triple functional GDPFS centres. These are:

- Global NWP Centres to provide available NWP products, including in the form of probabilities;

- Regional Centres to interpret information received from global NWP centres, run limited-area models to refine products, liaise with the participating NMCs;

- NMCs to issue alerts, advisories, severe weather warnings; to liaise and collaborate with Media, and disaster management and civil protection authorities; and to contribute to the evaluation of the project.

4.	Milestone of the First Phase of the SWFDP-Eastern Africa:

- From 4 to 8  October  2010, the Technical-Planning Workshop on Severe Weather Forecasting Demonstration Project (SWFDP) Development for Eastern Africa was held in Nairobi, Kenya where it was  unanimously agreed that the implementation of an SWFDP in Eastern Africa would be technically feasible and would bring benefits in terms of enhancement of technical capacity in operational weather forecasting and advancement in service delivery to general public and key application areas such as agriculture and fisheries, in countries of the region. Specifically, the proposed regional Subproject would focus on the following severe weather events in order of decreasing priority (and associated hazards such as flooding, droughts, etc):

- Heavy rain/flooding and deficit of precipitation/dry spells;

- Strong winds in relation to thunderstorms and any other phenomena over the Indian Ocean and major lakes;

- Hazardous Indian Ocean and major lake waves.

After an in-depth discussion on the various aspects in the planning of an SWFDP in Eastern Africa, following guidelines as laid out in the “SWFDP Guidebook for Planning Regional Subprojects (2010)” (hereafter referred to as the Guidebook), the First Phase of the project was projected as per guidelines spelt out in the Guidebook.  The report is available at the following WMO Web page:

http://www.wmo.int/pages/prog/www/CBS-Reports/documents/Final_report_SWFDP-Eastern_Africa-Nairobi_workshop.pdf

- From 18 to 29 October 2010, a Preparatory Training on severe weather forecasting and warning services in support of disaster risk reduction, fishing on Lake Victoria and farming communities, was conducted in Dar es Salaam, Tanzania., to ensure that NMHSs in the region start familiarizing with the various NWP/EPS, satellite based and guidance products that will be made available through this project, from the major NWP and satellite centres, and to prepare user focused information. The training included one week training for Forecasters on the use of NWP/EPS and nowcasting guidance products for severe weather forecasting; the second week was focused on the delivery of forecast and warning services to key users (including general public, agriculture and fisheries) in the context of emergency preparedness and response. The training involved end user communities.

- From 9 to 11 May 2011, the NWP/Web Developers’ Workshop for the Severe Weather Forecasting Demonstration Project (SWFDP) - Eastern Africa was held in Nairobi, Kenya.

The meeting reviewed the outcomes of the Technical-Planning Workshop on Severe Weather Forecasting Demonstration Project (SWFDP) Development for Eastern Africa (Nairobi, Kenya, 4-8 October 2010) and discussed the roles and contributions by Global Centres, Regional Centres and NMHSs over the project footprint including the Lake Victoria region. A draft web portal was also discussed, launched and hosted on KMD server: http://www.meteo.go.ke/rsmc/index.php

- From 21 to 24 June 2011, the Regional Subproject Management Team (RSMT) for the Severe Weather Forecasting Demonstration Project (SWFDP) for Eastern Africa was held in Nairobi, Kenya.  Participants included representatives of:

- Global Products Centres: Exeter (Met Office UK), Washington (NCEP USA), and ECMWF and DWD (Germany);

- Regional Centres: RSMC Nairobi (Kenya) and RFSC Dar es Salaam (Tanzania);

- National Meteorological Centres (forecasters and Agrimet):  Burundi, Ethiopia, Kenya, Rwanda, Tanzania, and Uganda; and

- The representative from the East African Community (EAC); and

- The WMO Secretariat (DPFS, PWS and AgM programmes).

The meeting discussed the respective roles and capacities in the cascading forecasting process involving participating centres, with respect to severe weather forecasting, production and dissemination of warnings; Public Weather Services and Agrometeorological Applications in accordance with SWFDP Guidebook for Planning Regional Subprojects (Rev.2010).

The meeting was informed of the national warning criteria (in-country thresholds for creating warnings) and agreed on the criteria for alerting severe weather in the RSMC Daily Guidance charts, which would be:

- Heavy rain: ≥ 50 mm/24hr;

- Strong winds: ≥ 25 Kts;

- Ocean/lake large waves: ≥ 2m;

- Dry spells: up to 5 days (from LAMs); up to 10 days (from global models).

The full report is available on the WMO Web site at: http://www.wmo.int/pages/prog/www/CBSReports/documents/Final_report_SWFDPEastern_AfricaNairobi_workshop.pdf

- From September 2011, the First Phase of this project commenced and focused on heavy rain, strong winds, sea/lake waves and prolonged dry spells.  The Services and Centres that participate in the SWFDP Eastern Africa include:

- NMHSs: Kenya, Uganda, Ethiopia, Rwanda, Burundi and Tanzania;

- Regional Centres: RSMC, KMD - Nairobi, RFSC, TMA- Dar es Salaam; and

- Global Products Centres: Exeter (Met Office UK), Washington (NCEP USA), DWD (Germany) and ECMWF.

The following map indicates the footprint of the project.

- From 18 to 29 October 2011, a joint GDPFS/PWS capacity development training workshop was held, at Dar es Salaam, Tanzania and from 21 November to 2 December 2011 at Arusha, Tanzania.

During the first week, the workshop covered the forecasting aspects, such as various NWP and RSMC guidance products, EPS products, verification techniques, nowcasting using MSG products, while the second week focused on Agro-met issues and PWS topics.

The participants were drawn from participating NMHSs and representatives of national disaster management organizations.

From 19 to 30 November 2012, a further training on severe weather forecasting and warning services in support of disaster risk reduction, fishing on Lake Victoria and farming communities, was conducted in Entebbe, Uganda., to ensure that NMHSs continue utilizing the various NWP/EPS, satellite based and guidance products that were made available through the project, from the major NWP and satellite centres, and to prepare user focused information. The training included one week training for Forecasters on the use of NWP/EPS and nowcasting guidance products for severe weather forecasting; the second week was focused on the delivery of forecast and warning services to key users (including general public, agriculture and fisheries) in the context of emergency preparedness and response. The training involved end user communities.

- From 25/2/2013 to 15/3/2013, four officers (two from each Regional Centre) underwent through a training program on severe weather forecasting which was held in UKMet Office for regional forecasters over the Eastern Africa and Lake Victoria region.

- In March, 2013, WMO procured a server for RSMC-Nairobi. The WMO would provide financial support for an ICT expert from SAWS to assist in the migration of SWFDP-EA Web-portal from Microsoft Windows based platform to Linux platform to ensure sustainable and secure operations of the RSMC-Nairobi. The exercise is envisaged to take place from 20 – 31 May, 2013.

5	Regional Centres

RSMC-Nairobi Daily Guidance Forecasts for Severe Weather Events

The RSMC-Nairobi issues Daily Guidance Forecasts at 0900 GMT after a consensus forecasts. This consensus forecast is given after a Videoconference among forecasters at UK Metoffice, RSMC-Nairobi and RFSC-Dar es salaam. The Daily Guidance Forecasts consists of three bulletins:

- the first one focuses on short-range forecasts (day-1 and day-2);

- the second addresses the medium-range forecasts (day-3, day- 4, and day-5);

Each comprises a discussion about forecast evolution, often supported by typical figures (model charts or satellite images), a table giving for each day the risk or probability of occurrence of severe weather in the countries participating in the SWFDP, and a synthetic map indicating the critical areas for heavy rain (50mm/24 hours>), strong winds (25 knots>), wave height (2m>) along the Indian Ocean and severe convective storms over the Eastern Africa region, with the day-1 map overlaid on a current satellite image.

- The third addresses the agro-meteorology products where maps of Eastern Africa region indicating the comparison of the Normalized Difference Vegetation Index (NDVI) of the current dekatal and the previous one and that of the Rainfall Estimate (RFE) and anomaly.

RFSC-Dar es Salaam Daily Guidance Forecasts for Severe Weather Events

The RFSC-Dar es Salaam issues Daily Guidance Forecasts at 0900 GMT after a consensus forecasts among three Centres participating in the daily Videoconference.  Day 1 and 2 forecasts are issues on a synthetic map indicating the critical areas for heavy rain (50mm/24 hours>), strong winds (20 knots>), wave height (2m>) and severe convective storms over the Lake Victoria region

The SWFDP products and RSMC/RFSC Daily Guidance Forecasts are disseminated through the RSMC Web page hosted and maintained by RSMC-Nairobi: http://www.meteo.go.ke/rsmc/index.php The product list on this Web page was continually updated as new products were made available.

6	The Rainfall seasons

The period under review corresponds to the October – November – December (OND), 2011, March-April- May (MAM), 2012 and OND 2012 rainfall seasons for areas around the equator. The ITCZ remains very active and results in strong convective events.  Heavy precipitation, which caused flooding were reported especially in Uganda, Kenya, Tanzania, Rwanda and Burundi. Strong wind events and high waves over the Lake Victoria were also experienced.

7	Usefulness of SWFDP NWP/EPS Products and Guidance Products

Forecasters found the guidance products posted on the RSMC-Nairobi web portal quite useful. The probability risk tables and sea state predictions close to the East African coast and Lake Victoria proved to be accurate and useful. The ECMWF, UKMO and NCEP ensemble and deterministic products were extensively utilized, which improved the ability of the NMHSs to detect the severe weather events in advance.

Forecasters appreciate being accessible to the  large-scale medium-range deterministic and probabilistic forecasts given by the Global Centres, high-resolution refinements and details in the model fields given by the limited area models and the chronological evolution of the model parameters through the EPSgrams in longer lead-times.

Forecasters are now accustomed to work with outputs from different models, which enable them to evaluate in a qualitative way the extent of the spread of the predicted solutions through a subjective “poor-man’s” ensemble forecasting technique.

8	Project evaluation against SWFDP goals

8.1	To improve the ability of NMCs to forecast severe weather events

The participating NMHSs reported a positive impact of daily use of SWFDP products for issuance of severe weather events including daily, five-day, and Ocean/lake Victoria waves.  Generally RSMC guidance and model output help increase the skill of the forecasters and boost their confidence.  The improvement of the forecasts results in a real and positive change in the opinion the various users have about the accuracy of the warnings/advisories.

8.2	To improve the lead-time of alerting these events

The NMHSs that experienced severe weather events indicated that SWFDP products allowed them to improve the lead time of providing alerts and advisories to these events.

8.3	To improve the interaction of NMHSs with DMCPAs before, during and after severe weather events

The present SWFDP Regional Subproject provides an opportunity to improve the links with their national DMCPA.  Joint meetings and training sessions organized by NMHSs, WMO, as well as those organized by ICPAC during the RCOFs, has improved the interactions between DMCPAs and the weather forecasters.

8.4	To identify gaps and areas for improvements

Regular or daily feedbacks and interactions among the Focal-points in the participating Global Centres, Regional Centres and NMHSs through teleconferencing, on-line discussions, telephone, fax, e-mail or whatever communication media need to be enhanced.

8.5	To improve the skill of products from Global Centres through feedback from NMCs

NMHSs are eager to provide feedback to the Global Centres about the performance of their products because it will eventually enhance the performance of their value-added products to their clients.

9	Evaluation of public weather warnings

9.1	Feedback from the public

Some NMHSs engaged the RANET FM Radio stations to receive views from the public especially those vulnerable to vagaries of extreme weather events.

9.2	Feedback from DMCPAs

NMHSs participating to SWFDP have strengthened their links with their DMCPAs, improved the dissemination of warnings/advisories and obtained feedbacks through various meetings or workshops.

9.3	Feedback from the media

The NMHSs in the region have established good relationships with the media through their regular participations in RCOFs.  The media has been trained to articulate and disseminate the weather/climate information including warnings and advisories accurately.

9.4	Objective Verification

NMHSs, Regional Centres and Global centres participating in the regional Subproject are engaged in the verification exercise, namely:

- Statistical verification to determine the skill scores of various models;

- Videoconference, which entails real-time verification by UK Metoffice, RSMC-Nairobi and RFSC – Dar es Salaam.

10	Conclusion

The participating NMHSs were satisfied by the support that the SWFDP provided, not only for severe weather forecasting but also useful for the day-to-day routine forecasting. The RSMC/RFSC Daily Guidance and NWP guidance products were found to be very useful for severe weather forecasting.

11	Emerging Issues

11.1	The NMHSs and their respective DMCPAs need to build strong synergies to ensure response and feedback mechanisms to the warnings/advisories by the agencies and communities involved.

11.2	NMCs should prepare simple and clear forecast information and warning/advisory messages, giving clear statements on what is happening, forecasts of what may happen and expected impact including what action should be taken.

11.3	NMHSs should design an appropriate strategize to obtain feedback from the public and media about the usefulness and effectiveness of warnings/advisories, using maybe a questionnaire to be filled by the users after each severe weather event.

11.4	“Fine tune” the Web portal design for easy navigation and accessibility by the participating NMHSs, including the improvement of the Internet connectivity by all the participating Regional Centres and NMHSs.

11.5	Encourage open discussions or fora of the “Expert Group” or focal points to address the key operational issues pertaining to the SWFDP.

11.6	Focal points in the participating NMHSs should submit  SWFDP Quarterly Progress Reports as prescribed and on regular basis.

11.7	Possibility of expanding the SWFDP for Eastern Africa Subproject to other neighbouring countries within the region such as Somali Republic, Djibouti, Eritrea, South Sudan, Democratic Republic of Congo, Central African Republic, among others.

12	Annexes

ANNEX 1 : List of the abbreviations used in conjunction with the SWFDP

CBS		: Commission for Basic Systems

COSMO	: The Consortium for Small-scale Modeling

DMCPA	: Disaster Management and Civil Protection Authority

### DWD		: Deutscher Wetterdienst

ECMWF	: European Centre for Medium Range Weather Forecasts

GDPFS	: Global Data Procession and Forecasting System

HRM		: A Regional High Resolution Numerical Weather Prediction Model

KMD		: Kenya Meteorological Department

LDCs 		 : Least Developed Counties

Met Office	: Meteorological Office (UK)

NCEP		: National Centres for Environmental Prediction (USA)

NDVI 		: Normalized Difference Vegetation Index

NMC               : National Meteorological Centre

NMHS 	: 	National Meteorological (and Hydrological) Service

NWP		: Numerical Weather Prediction

PWS 		: Public Weather Service

RA I		: Regional Association I (Africa)

RCOF		: Regional Climate Outlook Forums

RANET	: RAdio InterNET

RFE		: Rainfall Estimate

RFSC:		Regional Forecasting Support Centre

RSMC		: Regional Specialized Meteorological Centre

SIDSs:		 Small Island Developing States

SWFDP	: Severe Weather Forecasting Demonstration Project

RSMT		: Regional Subproject Management Team (SWFDP)

TMA		: Tanzania Meteorological Agency

WRF		: The Weather Research and Forecasting (WRF) Model

WMO		: World Meteorological Organization

ANNEX 2

List of the available documentation related to the implementation and reports of SWFDP Eastern Africa.

All the documents can be accessed at the following webpage of the WMO Internet site:

http://www.wmo.ch/pages/prog/www/CBS-Reports/DPFS-index.html

http://www.wmo.int/pages/prog/www/BAS/CBS-meetings.html

Technical/Planning Workshop on SWFDP Development for Eastern Africa:

http://www.wmo.int/pages/prog/www/DPFS/Meetings/RAI-EA-TPW-SWFDP_Nairobi2010/DocPlan.html

http://www.wmo.int/pages/prog/www/CBS-Reports/documents/Final_report_SWFDP-Eastern_Africa-Nairobi_workshop.pdf

Regional Subproject Management Team (RSMT) SWFDP) for Eastern Africa:

http://www.wmo.int/pages/prog/www/DPFS/Meetings/RAI-EA-SWFDP-RSMT_Nairobi2011/docplan.html

http://www.wmo.int/pages/prog/www/CBSReports/documents/Final_report_SWFDPEastern_AfricaNairobi_workshop.pdf

SWFDP Overall Project Plan (2010)” and the “SWFDP Guidebook for Planning Regional Subprojects (2010)”

http://www.wmo.int/pages/prog/www/DPFS/Meetings/RAIEASWFDPRSMT_Nairobi2011/docplan.html.

13	References

First Quarterly Reports from participating NMHSs – SWFDP for Eastern Africa

14	Appendices