| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS OPAG on DPFS Severe Weather Forecasting Demonstration Project (SWFDP) - Southern Africa, Meeting of the Regional Technical Implementation Team PRETORIA – SOUTH AFRICA – 24-27 FEB. 2009 |  | CBS-DPFS/SWFDP-RTIT/Doc. 5.1(1) (18.II.2009) _______ Agenda item : 5.1 ENGLISH ONLY |
| --- | --- | --- |

Met Office SWFDP Implementation Update

(Submitted by the Met Office, UK)

##### Summary and purpose of document

This document summarizes current and proposed future Met Office activities in support of the SWFDP in Southern Africa.

##### Action Proposed

The meeting is invited to note the contents of this document and to provide further guidance on how the Met Office can continue to actively contribute to the SWFDP sub-project in Southern Africa.

##### Progress Report

1. Overview

1.1	The Met Office is the national meteorological service provider for the United Kingdom providing services and products for the general public, government departments, the media, the military, aviation and a variety of commercial customers to name but a few.

1.2	Internationally the Met Office is an active member within WMO and has various international responsibilities for the provision of services.  The Met Office is a Regional Specialised Met Centre (RSMC) for Emergency Response and a World Area Forecast Centre (WAFC).

1.3	The services provided by the Met Office are underpinned by an active research and development programme whilst the forecasting and climate prediction capability is supported by one of the best numerical weather prediction computer models in the world.

1.4	Met Office NWP encompasses mesoscale, regional and global scale models together with a pseudo-operational ensemble prediction system known as MOGREPS.

1.5	The Met Office was invited to participate in the SWFDP RA1 South-eastern Africa sub-project in early 2006.

2. Met Office Support to SWFDP

2.1	SWFDP-RA1 Planning and Implementation

Mr Ian Lisk attended the preliminary start-up meeting on behalf of the Met Office at RSMC Pretoria between 31st July and 3rd August 2006 and assisted in the formulation of the project implementation plan.  Mr Lisk then actively contributed to the SWFDP-RA1 Management Team meeting in Maputo, Mozambique in February 2007.

2.2	SWFDP-RA1 Training Courses

Adhering to the requirements of the project implementation plan, the Met Office led the development of the 4-day training course at RSMC Pretoria in October 2006.  Two members of staff, including Paul Davies, a Chief Forecaster at the Met Office Operations Centre, led the delivery of the training course.  Paul Davies has since helped in the delivery of the two additional SWFDP courses, again both held in Pretoria in November 2007 and November 2008.

2.2	SWFDP-RA1 E-learning Website

A ‘MOODLE’ training website (http://www.met-elearning.org/moodle/ courses\SWF in Africa) with NWP training resources, useful links and feedback forums has also been developed by the Met Office to facilitate additional learning.  This has been designed to complement the traditional face-to-face training activities.  This resource works effectively when it is actively facilitated and regular interaction and input from the trainees is taking place.  The site has now been ‘live’ since October 2006 but is now receiving only a limited number of ‘hits’ and is no longer being facilitated by the Met Office.  The Met Office also understands that a similar e-learning site has recently been set-up by SAWS.  It is therefore the intention of the Met Office to soon retire this resource and we would therefore ask the meeting to provide advice in relation to this course of action.

2.4	Met Office Deterministic Products in Support of SWFDP RA1

Met Office Global NWP model products are provided via the GTS and the Met Office Africa Limited Area NWP model products via the www.metoffice.gov.uk/weather/africa/lam/ website.  The deterministic NWP products disseminated are consistent with the requirements of the SWFDP RA1 Implementation plan.  The Met Office Global Model also operationally supplies, under license, the lateral boundary conditions for the SAWS Limited Area Model.

2.5	Met Office Global Regional Ensemble Prediction System (MOGREPS) Products

MOGREPS data has been available via the Met Office ftp server at ftp.metoffice.gov.uk since the end of October 2006.  Connecting to the ftp server has presented problems for some of the participating NMHSs so arrangements have been in place since early 2007 for the MOGREPS products to also be hosted RSMC Pretoria SWFDP website.  The Met Office would like to advise the meeting that the Met Office ftp server is due to be upgraded in 2009 and so there is likely to be a short period of disruption to this service.

The MOGREPS products disseminated are consistent with the requirements of the SWFDP RA1 Implementation plan. MOGREPS ‘Meteograms’ are also currently available for two locations in each of the five ‘original’ SWFDP-RA1 countries.  The Met Office is willing to provide two Meteograms per country in support of the wider SWFDP project and would ask the meeting for guidance on the desired locations for these additional products.  The Met Office also intends to broaden the Meteogram list to five per country in the near future.

Please see Annex 1 for examples of threshold charts and Annex 2 for an example of an EPS Meteogram.

2.6	Met Office Tropical Cyclone Prediction Products

The Met Office would like to seek guidance from the meeting on the desirability of the Met Office adding a suite of tropical cyclone EPS forecasting products.  If requested, these will likely be available in July or August 2009.

Please see Annex 3 for examples of the tropical cyclone EPS charts (please note that these are trial South Pacific examples).

2.7	Global Centre Feedback

The Met Office continues to actively encourage all members of the SWFDP in southern Africa to proactively provide the following:

- Feedback (particularly strengths and weaknesses) on the performance of the participating centre’s models;

- Weather case-studies for the purposes of model verification and future training activities;

- Documented case-studies to include high-level testimonial evidence of the impact of the SWFDP sub-project in terms of (i) increasing the forecast lead time of severe weather and; (ii) increasing the visibility/integration of the capabilities of the NMHS with government and the civil protection agencies.  Such evidence is crucial if the project is to build sustainable capacity whilst also attracting future resource mobilisation opportunities.

Annex 1 – Sample MOGREPS Threshold Probability Charts for Rainfall and Wind Speed

Annex 2 – Sample MOGREPS Meteogram

Annex 3 – Met Office Trial Tropical Cyclone Forecast Track Products