| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS OPAG DPFS SEVERE WEATHER FORECASTING DEMONSTRATION PROJECT (SWFDP) RA I South-eastern Africa Meeting of the Regional Subproject Management Team (RSMT) MAPUTO, MOZAMBIQUE 27 February – 2 March 2007 |  | CBS-DPFS/RA I/RSMT-SWFDP/Doc. 4.1(2)Rev. (24.I.2007) _______ Item: 4 ENGLISH ONLY |
| --- | --- | --- |

Met Office SWFDP Implementation

(Submitted by the Met Office UK)

##### Summary and purpose of document

REVISED
This document summarizes Met Office activities in support of the SWFDP RA1 - South-eastern Africa.

##### Action Proposed

The meeting is invited to note the contents of this document and to provide further guidance on how the Met Office can continue to actively contribute to the SWFDP RA1 sub-project.

##### Progress Report

1. Overview

1.1	The Met Office is the national meteorological service provider for the United Kingdom providing services and products for the general public, government departments, the media, the military, aviation and a variety of commercial customers to name but a few.

1.2	Internationally the Met Office is an active member within WMO and has various international responsibilities for the provision of services.  The Met Office is a Regional Specialised Met Centre (RSMC) for Emergency Response and a World Area Forecast Centre (WAFC).

1.3	The services provided by the Met Office are underpinned by an active research and development programme whilst the forecasting and climate prediction capability is supported by one of the best numerical weather prediction computer models in the world.

1.4	Met Office NWP encompasses mesoscale, regional and global scale models together with a pseudo-operational ensemble prediction system known as MOGREPS.

1.5	The Met Office was invited to participate in the SWFDP RA1 South-eastern Africa sub-project in early 2006.  After consultation with various interested parties within the Met Office it was agreed to nominate Ian Lisk of the International Relations Section as the Met Office representative for the project.

2. Met Office Support to SWFDP

2.1	Attendance at the SWFDP-RA1 Planning Meeting

Mr. Lisk attended this meeting on behalf of the Met Office at RSMC Pretoria between 31st July and 3rd August and actively contributed to the formulation of the project implementation plan.

2.2	Membership of the SWFDP-RA1 Management Group

The Met Office is represented on the MG by Mr. Lisk.  This is a co-ordination, advisory and point of contact activity, primarily by correspondence although Mr. Lisk will also attend the mid-term MG meeting in Maputo, Mozambique in late February.

2.3	Preparatory NWP Training Course for SWFDP-RA1

Adhering to the requirements of the project implementation plan, the Met Office led the development of the 4-day training course at RSMC Pretoria.  Two members of staff, including Paul Davies, a Chief Forecaster at the Met Office Operations Centre, then led the delivery of the training course.  An accompanying ‘MOODLE’ training website (http://www.met-elearning.org/moodle/ courses\SWF in Africa) with NWP training resources, useful links and feedback forums was also developed by the Met Office to facilitate additional learning both before and after the classroom element of the course.

2.4	Met Office Deterministic Products in Support of SWFDP RA1

Met Office Global NWP model products are provided via the GTS and the Met Office Africa Limited Area NWP model products via the www.metoffice.gov.uk/weather/africa/lam/ website.  The deterministic NWP products disseminated are consistent with the requirements of the SWFDP RA1 Implementation plan.  The Met Office Global Model also operationally supplies, under license, the lateral boundary conditions for the SAWS Limited Area Model.

2.5	Met Office Global Regional Ensemble Prediction System (MOGREPS) Products in Support of SWFDP RA1

MOGREPS data has been available via the Met Office ftp server at ftp.metoffice.gov.uk since the end of October.  Connecting to the ftp server has presented problems for some of the participating NMSs so arrangements have been put in place for RSMC Pretoria to host the MOGREPS products on the RSMC Pretoria SWFDP website.  It is anticipated that these MOGREPS internet products will be available at the beginning of February.

The MOGREPS products disseminated are consistent with the requirements of the SWFDP RA1 Implementation plan and include the revised probability accumulated precipitation thresholds (50mm in 6 hours; 25mm in 6 hours; 50mm in 24 hours; 100mm in 24 hours) that were agreed at the Preparatory Training Session in November.  Additional EPS ‘Meteograms’ for South Africa were also added to the existing SWFDP Meteogram list at the end of November.

Please see Annex 1 for examples of threshold charts and Annex 2 for an example of an EPS Meteogram.

Annex 1 – Example SWFDP RA1 MOGREPS Threshold Products

Annex 2 – Example SWFDP RA1 MOGREPS Meteogram Product