| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS OPAGs on DPFS and PWS Severe Weather Forecasting Disaster Risk Reduction Demonstration Project SWFDdP – South Pacific Project Meeting of the Regional Subproject Management Team Noumea, New Caledonia, 27-28 July 2018 |  | WDS/TCP-RAV-TCC17&DPFS-RSMT-SWFDDP/Doc. 3.1 (18.VII.2018) _______ Agenda item: 3.1 ENGLISH ONLY |
| --- | --- | --- |

SUMMARY FROM THE PROGRESS REPORTS

(Submitted by James Lunny)

##### Summary and purpose of document

This document reviews the results of the Progress Reports of the SWFDDP against the criteria required to be achieved before the project can move to the “continuing development phase”.

##### Action Proposed

The meeting is invited to discuss and identify strengths and weaknesses in the progress made by the participating NMHSs in relation to the criteria set by the third meeting of the RSMT, as well as the five main goals of the SWFDDP.

Reference(s):	- http://www.wmo.int/pages/prog/www/CBS-Reports/DPFS-index.html

- Overview

The RSMT will review and discuss the Progress Reports of the SWFDDP, spanning the period from 1 June 2016 to 30 April 2018 (Progress Reports No. 13, 14, 15 and 16). This covers the reporting period between the fourth and fifth meetings of the RSMT. For comparison, the summaries for Progress Reports No. 8, 9, 10 and 11 are included, having been discussed at the fourth RSMT meeting in Honiara.

The five main goals of the SWFDDP are:

- to improve the ability of NMHSs to forecast severe weather events;

- to improve the lead-time of alerting these events;

- to improve the interaction of NMHSs with Disaster Management and Civil Protection Authorities (DMCPAs) before, during and after severe weather events

- to identify gaps and areas for improvements; and

- to improve the skill of products from Global Centres and RSMCs through feedback from NMHSs.

The third meeting of the RSMT (Nadi, Fiji, 26 – 29 August 2013) noted there were no hard criteria for the transition of the Project from Demonstration to the subsequent Phase IV, known as the “operational” or “continuing development phase”. The RSMT in Nadi (Aug 2013) agreed to the following set of criteria to be implemented by each participating NMHS:

- an appropriate non-TC warning system is implemented and operating smoothly;

- severe weather and wave forecasts & warnings are verified using the spreadsheet provided;

- all participating countries produce at least one case study per year;

- all participating countries to complete all SWFDDP progress reports in full before the deadlines prescribed (six monthly); and

- demonstrate on a continual basis that the relationships between NMHSs and Disaster Management and Civil Protection Authorities (DMCPAs), the media and the public are strong and healthy, with regular communications before, during and after severe weather events.

The fourth meeting of the RSMT, Honiara, Solomon Islands, 25-27 August 2016 reiterated the requirement for the above criteria to be met before transitioning to Phase IV.

The RSMT at this meeting will discuss and identify strengths and weaknesses in the progress made by the participating NMHSs in relation to the criteria, as well as the five main goals of the SWFDDP.

- SWFDDP achievements and gaps against the criteria for SWFDDP progressing to phase 4

2.1 Appropriate non-TC warning system is implemented and operating smoothly

This first criterion requires NMHSs to demonstrate that their non-TC warning system is functioning smoothly. One aspect of quality management is to: ‘say what you do and do what you say’. With this in mind, it was deemed beneficial if each NMHS described their non-TC warning system and a few of them did this.  NMHSs should also provide evidence of their warning program by forwarding the alerts, warnings or advisories to RSMC Wellington. The second aspect of this criterion is to show that the system is working smoothly. What is required here is evidence of the interactions with their DMCPAs. In a smoothly functioning system the DMCPA should acknowledge receipt and respond to warnings. Evidence of that response is required.

In summary, the first aspect of this criterion is to inform RSMC Wellington of all non-TC warnings; the second aspect requires the NMHS to provide evidence of the interactions with the DMCPA. These aspects were achieved to varying degrees.

Fiji issues warnings for: Niue; Kiribati; Cook Islands; and Tuvalu, so all were considered compliant when NMHS Fiji forwarded warnings to RSMC Wellington (see Figures 1 and 2).

Figure 1: Summary of compliance from participating NMHSs with regard ‘All NMHSs include RSMC Wellington on the distribution list for all alerts, warnings and advisories’ for Progress Reports No. 8 to 16.

Figure 2: Summary of compliance from participating NMHSs with regard ‘All NMHSs in collaboration with DMCPAs provide feedback on the performance of the warning system in the country’s progress reports’ for Progress Reports No. 8 to 16.

2.2 Severe weather and wave forecasts & warnings are verified

In reporting prior to Progress Report No. 8 the NMHSs were required to fill out an events table as part of Annex I. In the Regional Subproject Implementation Plan (RSIP), this was changed to a separate verification spreadsheet that allowed the NMHSs to verify their forecasts and confirm what South Pacific Guidance (SPG) charts were issued one to four days in advance.

The four partially compliant NMHSs for Progress Report No. 8 (Figure 3) was a result of omission of correct negatives in the verification spreadsheet. This was rectified somewhat for Progress Report No. 9, where Solomon Islands, Tonga and Niue were fully compliant, and all but one NMHS submitted their verifications. Subsequent submission of verification spreadsheets has decreased, with no verification provided in Progress Report No. 16.

At times the verification spreadsheet has been filled out on a monthly basis. For ease, this would be better done as one spreadsheet to cover the 6-monthly reporting timeframe.

The noticeable trend is the decrease in submission of verification data.

Figure 3: Summary of compliance from participating NMHSs with regard ‘All NMHSs submit verifications to RSMC Wellington with each progress report’ for Progress Reports No. 8 to 16.

2.3 All participating countries produce at least one case study per year

All participating countries are required to submit at least one case study per year. After the third RSMT in Nadi, August 2013, a case study guide and template were distributed to the participants. Case studies are uploaded to MetConnect Pacific, appearing under the ‘Case Studies’ tab. Since the fourth RSMT meeting, a further five case studies have been submitted (Kiribati x 2; Samoa x 2; and Tuvalu x 1). The case studies submitted were:

- Kiribati – Large Waves affecting Christmas Island (Jan 2016);

- Kiribati – Strong Winds (Mar 2016);

- Samoa – Hail (Sept 2016);

- Samoa – Severe afternoon convection (May 2018); and

- Tuvalu – Large Waves (May 2018).

Countries that submitted case studies are commended for the efforts they have put in to producing them. They are extremely informative, allowing insight in to how participating NMHSs are progressing in relation to the goals of the SWFDDP.

Note: Annex Hs should be completed in addition to producing case studies.

Figure 4: Summary of compliance from participating NMHSs with regard ‘All participating countries produce at least one case study per year, using the SWFDDP template or an equivalent template’ for the twelve months preceding the end date of Progress Reports No. 8 to 16.

2.4 All participating countries to complete all SWFDDP progress reports in full before the deadlines prescribed (six monthly; in April and October)

Deadlines have been assigned for the submitting of the 6-monthly progress reports. At times this has been difficult to achieve due to recent severe weather within a country. The overall trend, however, has been down.

Figure 5: Summary of compliance from participating NMHSs with regard ‘All participating NMHSs to complete all SWFDDP progress reports in full before the deadlines prescribed’ for Progress Reports No. 8 to 16.

2.5 Demonstrate on a continual basis that the relationships between NMHSs and Disaster Management and Civil Protection Authorities (DMCPAs), the media and the public are strong and healthy, with regular communications before, during and after severe weather events

NMHSs were encouraged to provide evidence of their interactions with DMCPAs, the media and the public. This may be emails, newspaper clippings, telephone conversations, relevant workshops, disaster reports or other evidence. If multiple events take place over the reporting period, then as much evidence as possible should be submitted; on occasion, one event would be covered, but not the other two, or three, or more.

During the fourth RSMT meeting it was noted that Tonga provided a copy of the National Emergency Operations Management procedures which clearly indicates the relationship of the meteorological office with the DMCPA. Tonga also provided a screen shot of an email from the local Red Cross to a number of Tongan leaders regarding TD07F, the precursor to TC Ian (Jan 2014); this was evidence of strong communication with the public.

On several occasions, strong interactions were claimed between meteorological offices and their respective disaster management offices, but little/no evidence was presented.

Discussions at the third and fourth RSMT meetings suggested the interactions between NMHSs with DMCPAs, the media and the public were strong, but, in general, progress reporting has provided a lack of evidence to support these interactions (see Figs 6, 7 and 8).

Figure 6: Summary of compliance from participating NMHSs with regard ‘Demonstrate on a continuing basis that the relationships between NMHSs and other DMCPAs are strong and healthy, with regular communications before, during and after severe weather events’ for Progress Reports No. 8 to 16.

Figure 7: Summary of compliance from participating NMHSs with regard ‘Demonstrate on a continuing basis that the relationships between NMHSs and the media are strong and healthy, with regular communications before, during and after severe weather events’ for Progress Reports No. 8 to 16.

Figure 8: Summary of compliance from participating NMHSs with regard ‘Demonstrate on a continuing basis that the relationships between NMHSs and the public are strong and healthy, with regular communications before, during and after severe weather events’ for Progress Reports No. 8 to 16.

- Discussion

The meeting is invited to discuss and identify strengths and weaknesses in the progress made by the participating NMHSs in relation to the criteria set by the third meeting of the RSMT, as well as the five main goals of the SWFDDP.