Severe Weather Forecasting Demonstration Project (SWFDP)

Regional Subproject – RA II – South Asia

SWFDP- South Asia

(formerly SWFDP-Bay of Bengal)

Regional Subproject Implementation Plan (RSIP)

1 December 2018

Table of Contents                                                                                 	        Page

1.	INTRODUCTION                                                                              		 	  4

1.1	The SWFDP and its ‘cascading forecasting process’ 		 	  	  4

1.2	The four phases of the SWFDP						 	  5

1.3	The development of SWFDP-South Asia (formerly SWFDP-Bay of Bengal) 	  5

1.4  	Hydrometeorological hazard situation in South Asia                 		  	  8

2.       FRAMEWORK OF SWFDP – SOUTH ASIA IN RA II				 	  8  	2.1	Key Objectives								 	  8

2.2	Participating countries / organizations	             	 			  8

2.3	Severe weather events and threshold values to be used in RSMC Guidance 			product	  									  9

2.4	Target domain								 	 10

2.5	The Demonstration Phase							 10

2.6	Projects and activities in synergies with SWFDP-South Asia			 10

2.6.1 Synergy with Tropical Cyclone Programme (TCP) activities in RA II (Asia)	 10	2.6.2 Synergy with other projects and activities	 in RAII	 			 11

2.7	Regional Subproject Management Team (RSMT)				 11

2.7.1 Role and Responsibility of RSMT       		                              	 12

2.7.2 Members of RSMT                                                                    	 	 12

2.7.3 Responsibilities of the Members of RSMT				 	 13

2.8	Responsibilities of Participating Centres in Subproject Implementation  		 14

2.8.1	The Global Centres							 14

2.8.2	The Regional Centre (RSMC New Delhi)					 15

2.8.3	The NMCs/NMHSs							 16

3.	DATA, PRODUCTS AND SUPPORT FROM PARTICIPATING CENTRES		 16

3.1	Data and Products to be issued from contributing Global Centres		 16

3.1.1	Current Deterministic NWP Fields up to 5 days				 17

3.2.2 	Probabilistic Forecast Products based on EPS				 17

3.2.3	Satellite data-processing systems and products for nowcasting		 18

3.2	Data and Products to be issued from RSMC New Delhi				 23

3.2.1	Current deterministic Limited Area Model (WRF)			 23

3.2.2 	RSMC Tropical Cyclone Information/Advisory			 	 23

3.2.3	RSMC Daily Severe Weather Forecasting Guidance		 	 23

3.3	Data and Products from other on-going projects or activities		 	 24

3.4	Verification of Technical Capability of Participating NMCs/NMHSs		 25

3.4.1	Technical feasibility							 25

3.4.2	Status of internet infrastructure and requirements 		 	 25

4.	PUBLIC WEATHER SERVICES (PWS) COMPONENT OF SWFDP			 26

4.1	The WMO Strategy for Service Delivery 					 26

4.2	Impact-Based Forecast and Warning Services (IBFWS)			 	 26            4.3	Delivery of Warnings and Common Alerting Protocol (CAP)		 	 27 4.4	Communications								 28 4.5	Urban Services									 28

4.6	Implementation plan to improve warnings and forecasts services

in NMHSs									 29

5.	CAPACITY DEVELOPMENT - SWFDP TRAINING ACTIVITIES			 29

5.1	Overview									 29

5.2	Training Topics for SWFDP Training Activities					 31

6.	EVALUATION OF SUBPROJECT							 32

6.1	Overview									 32

6.3	Quarterly Progress Reports by NMCs/NMHSs					 33

6.2	Feedback from users from the viewpoint of PWSD				 33

7.	TIMELINE OF SUBPROJECT ACTIVITIES						 33

8.	SUBPROJECT COSTS AND RESOURCES						 34

9.	COMMUNICATION & PUBLICITY OF THE PROJECT					 35

11.	LIST OF THE ANNEXES								 35

12.	REFERENCES										 36

ANNEX A: List of Stations for EPSgrams (ENS Meteograms) provided by Global Centres		 38

ANNEX B: The list of Deterministic NWP and Ensemble Products to be made available to IMD

New Delhi by Global Centres 	   42

ANNEX C: The list of Deterministic Global and Regional NWP Products to be available from

IMD/RSMC New Delhi 							 	44

ANNEX D: List of Products provided by RSMC New Delhi – Tropical Cyclone  Centre		45

ANNEX E: Warning Hazards and Thresholds applicable to the Daily Regional Guidance   	51

ANNEX F: Template of Daily Regional Guidance to be issued by RSMC New Delhi	 	52

ANNEX G: The Implementation Status of Impact-based Forecast and Warning Services

(IBFWS) in SWFDP countries in South Asia	 				 	55

ANNEX H: Template of Severe Weather Event Evaluation Form				 	56

ANNEX I: Summary of Procedure for Verifying Forecasts and Warnings using Contingency

Tables by NMCs/NMHSs						 		58

ANNEX J: Key Elements of SWFDP Quarterly Progress Report					61

ANNEX K: User Assessment Questionnaire						 	64

K.1: Evaluation Questionnaire for the Public					64

K.2: Evaluation Questionnaire for Disaster Management				65

K.3: Evaluation Questionnaire for Media					 	66

ANNEX L: Tentative Work Plan with estimated costs for 2017-2020				67

Version History

| Ver0 | 8 April 2012 | Dr. S. K Roy Bhowmik | Draft RSIP was prepared after the Technical Planning Workshop on SWFDP Development (New Delhi, India, 23-27 January, 2012) |
| --- | --- | --- | --- |
| Ver1 | August 2014 | Mr. B.K. Bandyopadhyay | Modified version of the draft RSIP taking into account recent development |
| Ver2 | 1 December 2018 | Dr M. Mohapatra (Chair of RSMT) | RSIP was reviewed and updated by the RSMT during its first meeting in Colombo, Sri Lanka (28 November – 1 December 2018) |

1.	INTRODUCTION

1.1	The SWFDP and its ‘Cascading Forecasting Process’

WMO Severe Weather Forecasting Demonstration Project (SWFDP) aims to enable all NMHSs to issue effective severe weather warnings to disaster management and civil protection authorities in their respective countries. Using a ‘Cascading Forecasting Process’, the Project makes global-scale products available to Regional Specialized Meteorological Centres (RSMC) that integrate and synthesize them in order to provide daily guidance for NMHSs in their geographical sub-region. Thus, the NMHSs have greater capability to identify hazardous weather conditions in the short- and medium-range and issue forecasts and warnings accordingly.

The SWFDP is guided by a Steering Group of the Commission for Basic Systems (CBS). The Steering Group has developed an overall Project Plan and a ‘SWFDP Guidebook’ on planning regional subprojects. These documents are reviewed and updated by the Steering Group. All SWFDP regional subprojects are developed and planned according to the guidelines provided in the guidebook. The SWFDP Guidebook is available on WMO website at the following link:

http://www.wmo.int/pages/prog/www/swfdp/index_en.html

The first ever SWFDP regional subproject was initiated in 2006 with involvement of just five countries in south-eastern Africa. The success story of this subproject provided basis for expansion of SWFDP into whole Southern Africa in 2009 with involvement of sixteen countries and later into other sub-regions of the world including Eastern Africa and South Pacific. Currently, SWFDP involves over 75 developing countries, least developed countries (LDCs) and small island developing states (SIDS) in eight sub-regions of the world. There are three SWFDP regional subprojects in WMO RA I (Asia) namely SWFDP-Southeast Asia; SWFDP-South Asia (formerly SWFDP-Bay of Bengal); and SWFDP-Central Asia.

A SWFDP regional subproject implies a coordinated functioning among three types of Global Data Processing and Forecasting Systems (GDPFS) centres to implement ‘Cascading Forecasting Process’.  Conceptually, it should involve one or more global centres, one regional centre and a number of NMHSs located in a sub-region or geographical area.  In practice, a subproject may involve additional regional centres, if beneficial and practical to do so.  In case more than one regional centres are involved, one of the regional centres will serve as a lead Centre for regional forecast guidance support and coordination with participating NMHSs/NMCs. The lead regional centre shall preferably be selected from within the geographical area of the  subproject. Capacity development through regular trainings forecasting and service delivery aspects is a critical component of the subproject. Forecasters need to know how to make optimal use of the various NWP products and satellite information coming from the contributing centres.

Figure 1 – The Cascading Forecasting Process of the SWFDP.

The SWFDP regional projects are developed in a phased approach, with three phases of development and demonstration including evaluation followed by a transition to sustainable operations in Phase IV as explained in next paragraph.

1.2	The Four Phases  of SWFDP

The  development and implementation of SWFDP regional subprojects including SWFDP-West Africa involves following four phases:

Phase I: Overall Project Planning

Phase II: Regional Subproject Implementation Planning and Execution

Phase III: Regional Subproject Evaluation

Phase IV: Regional Subproject Long-term Sustainability and Future Developments

More information on SWFDP including description of the four phases is available in the above referred project documents including SWFDP guidebook.

The four phases of SWFDP are somehow aligned with the general project cycle involving identification of a project; its preparation; implementation; completion and evaluation; and post-completion follow-up actions.

1.3	The Development of SWFDP- South Asia (formerly SWFDP-Bay of Bengal)

Noting the significant development and progress of the SWFDP, from concepts to the first SWFDP regional subproject, implemented in the south-eastern region of Africa in 2006, the Fifteenth World Meteorological Congress (Cg-15, Geneva, 2007) decided that the project should be expanded and implemented throughout RA I (Africa) and to other WMO Regions especially in developing countries. Subsequently, in RA II (Asia), the development process for implementing SWFDP regional subprojects in Southeast Asia and the Bay of Bengal (South Asia) subregions was started in 2010 and 2012 respectively.

To initiate the development of SWFDP, a WMO mission to the India Meteorological Department (IMD), New Delhi was carried out by a two members WMO team during 7-8 November 2011 in order to assess the potential for expanding role of the RSMC New Delhi to carry out the role of lead Regional Centre for the SWFDP-Bay of Bengal (now SWFDP-South Asia). As the outcome of the visit, a Technical-Planning Workshop on SWFDP Development in the region was held in New Delhi, India, during 23 to 27 January 2012 (http://www.wmo.int/pages/prog/www/CBS-Reports/DPFS-index.html). The Participants included representatives of Bangladesh, India, Maldives, Myanmar, Sri Lanka and Thailand, representatives from global centres (JMA, US NOAA/NCEP and IMD/NCMRWF), and the five member WMO delegations. As a global centre, IMD is supported by National Centre for Medium Range Weather Forecasting (NCMRWF) and Indian National Centre for Ocean Information Services (INCOIS).

The workshop concluded that the implementation of a SWFDP in Bay of Bengal (South Asia) region would be technically feasible and would bring benefits in terms of enhancement of technical capacity in operational weather forecasting and advancement in service delivery to general public, disaster management centres and civil protection authorities and key application areas such as agriculture and fisheries, in countries of the region, including Bangladesh, India, Maldives, Myanmar, Sri Lanka and Thailand.  It was agreed that RSMC New Delhi shall be carrying out the functions of the lead regional centre for the project. It shall be responsible for synthesizing all available and relevant products and information and making the best use of these products in order to provide daily severe weather forecasting guidance. RSMC New Delhi shall also be responsible for developing and managing the Project Web Portal. The participating countries shall be responsible for the warning services to the key users (general public, disaster managers, agriculture and fisheries).

The Steering Group for SWFDP at its fourth session (Geneva, Switzerland, 28 February – 2 March 2012) decided to promote the subproject in Bay of Bengal (South Asia). The Steering Group recommended that the roles and responsibility of the various centres, and the hazardous weather phenomena to be addressed in the first phase of this subproject, be clarified and well documented in the Regional Subproject Implementation Plan (RSIP). It also expressed some concern about the overlap of the subproject domain with the subproject in Southeast Asia, and the potential participation of the NMHS of Thailand in multiple subprojects. It was recommended that special attention be paid by the NMHS of Thailand to the avoidance any possible problems.

While noting that the subproject in Bay of Bengal (South Asia) is focused on the safety of coastal communities, the Steering Group expressed some concern about the complexity of this subproject due to (1) the variety of weather conditions occurring in the region; (2) the number of national organizations potentially engaged in this regional subproject; and (3) the number of global NWP centres involved in the subproject. The Steering Group recommended that these aspects, including the roles and responsibility of the various centres, and the hazardous weather phenomena to be addressed in the first phase of this subproject, be clarified and well documented in the Regional Subproject Implementation Plan (RSIP).

The initial draft of the RSIP was developed by the designated representative of IMD. Later, it was reviewed by the other potential contributing global centres including UK Met Office (UKMO) and JMA. Preparatory regional training workshops on severe weather forecasting and warning services were organized in Macao (China) and Bangkok (Thailand) in April 2013 and September 2015 respectively. The main objective of  the workshops was to develop capacity of the NMHSs on interpretation and use of the NWP products and satellite based information to improve severe weather forecasting and warning services, and to improve coordination of the NMHSs with targeted users including general public, media, and disaster managers for improved delivery of warning services and DRR activities. These workshops were jointly organized for the countries in Southeast Asia and Bay of Bengal (South Asia) subregions.

The subproject in Bay of Bengal/ South Asia) was mainly supported through a joint WMO-RIMES project during 2012-2015 with funds received from UN ESCAP through RIMES. The password-protected project website was made operational for the NMHSs by RSMC New Delhi in September 2015. In 2016, the subproject was expanded to include three more countries in the region namely Bhutan, Nepal and Pakistan. The RSMT during its first meeting (Colombo, Sri Lanka, 28 November–1 December 2018) reviewed the subproject progress and updated the RSIP considering the latest information the participating centres. The RSMT agreed on the schedule for demonstration phase and encouraged the NMHSs to strengthen impact-based forecast and warning services (IBFWS) in their respective countries. Considering expansion of the subproject, involving 9 countries in South Asia, the RSMT renamed the subproject as SWFDP-South Asia. Hereafter, the subproject is described as SWFDP-South Asia in this document. Timeline of key milestones in the development of the subproject are given below:

| 2011 | - Initial planning and preparatory work - Visit of two-members WMO team to IMD, India during 7-8 November 2011 to assess the role of the RSMC New Delhi for the SWFDP - Bay of Bengal (South Asia) |
| --- | --- |
| 2012 | - Technical-Planning Workshop on SWFDP development in Bay of Bengal (South Asia) was held in New Delhi, India (23 to 27 January 2012) - Development of initial draft of Regional Subproject Implementation Plan (RSIP) |
| 2013 | - Training Workshop on Severe Weather Forecasting and Warning Services (Macao, China, 8 – 19 April 2013) was jointly organized for countries in Bengal of Bengal (South Asia) and Southeast Asia |
| 2014 | - Review of the draft RSIP by RSMC New Delhi and potential global centres |
| 2015 | - Training Workshop on Severe Weather Forecasting and Warning Services (Bangkok, Thailand, 14 – 25 September 2015) was jointly organized for countries in Bay of Bengal (South Asia) and Southeast Asia - Launch of Project website by RSMC New Delhi |
| 2016 | - Subproject is expanded to include Bhutan, Nepal and Pakistan - Daily Guidance product (in graphics) by RSMC New Delhi since 2 May 2016 |
| 2018 | - First Meeting of the Regional Subproject Management (RSMT) (Colombo, Sri Lanka, 28 November – 1 December 2018) reviewed the subproject progress and updated the RSIP. - Regional Training Workshop on Severe Weather and Impact based Forecasting and Warning Services held in Colombo, Sri Lanka during 3-8 December 2018 |

1.4	Hydrometeorological hazard situation in South Asia

The region in South Asia is exposed to the hazardous weather phenomena such as tropical cyclones, monsoon, local severe storm and western disturbances. During the pre-monsoon months from March to May, there are cyclonic disturbances, storm surges, strong winds, high waves, heat waves, thunderstorms, lightning, squalls, severe localized storms, and tornados. Summer (or southwest) monsoon influenced the region mainly from June to September. Monsoon systems including depressions is associated with heavy rainfall, severe thunderstorms and lightning, strong winds, high waves, floods.  The north and western part of South Asia is affected by the winter season during January to March (the period may vary I the region) which is characterized by frontal weather systems (locally called western disturbances) which move across the area along westerly waves causing rainfall, cold waves, frost and fog. During the post-monsoon months of October to December, the northeast monsoon produces cyclonic disturbances.

2.	FRAMEWORK OF SWFDP-SOUTH ASIA IN RA II

## Key objectives

As per ‘SWFDP Guidebook’, the scope of the SWFDP is to test the usefulness of the products currently available from NWP centres, including EPS products  to improve severe weather forecasting and delivery of warning services in WMO Members especially where the use of NWP model outputs is limited.  The SWFDP-South Asia would make use of the cascading forecasting approach to improve severe weather forecasting and to provide greater lead-time for warnings and would, at the same time, contribute to capacity development of the participating NMHSs. It would improve links with users including especially Disaster Management and Civil Protection Authorities (DMCPA) to achieve SWFDP goals and objectives as envisioned by WMO. Given the need to work with DMCPA and media organizations to improve delivery of severe weather warning services to end users, the Public Weather Services Delivery (PWSD) and Disaster Risk Reduction (DRR) aspects are integrated into the SWFDP. Further, as part of WMO Strategy for Service Delivery (approved by Cg-17 , 2015), impact-based forecast and warning services (IBFWS) will be strengthened through improved engagement of NMHSs with users as part of SWFDP implementation. Ultimately, SWFDP-South Asia is expected to provide operational support to multi-hazard early warning services at regional and national levels as envisioned in WMO Road Map for DRR.

## Participating countries / organizations

The SWFDP-South Asia involves following nine countries: Bangladesh, Bhutan, India, Maldives, Myanmar, Nepal, Pakistan, Sri Lanka and Thailand. RSMC, New Delhi is the lead Region Centre to provide Regional Severe Weather Forecast Guidance product. The participating global centres include following:

  - IMD New Delhi (supported by NCMRWF and INCOIS)

  - ECMWF (WMC)

  - UK Met Office (WMC Exeter)

  - JMA (WMC Tokyo)

  - CMA (WMC Beijing)

  - KMA, Republic of Korea

## Severe weather events and threshold values to be used in RSMC Guidance product

Recognizing regional dominant and common hazardous weather conditions and

associated impacts (such as flooding, drought, high waves and swell etc.), SWFDP-South Asia shall focus on the following severe weather events in order of decreasing priority:

- Heavy rain (due to tropical cyclone, thunderstorm, monsoon, etc.) /flooding;

- Strong winds (due to tropical cyclone, thunderstorm, monsoon, etc.);

- Deficit of precipitation/dry spells;

- High waves / swells;

- Storm surge;

- Heat waves and cold waves / frost;

- Fog;

- Snowfall

The following thresholds values shall be used in the RSMC Daily Severe Weather Forecasting Guidance:

- Heavy rain

  - 50mm

  - 100mm

- Snowfall

  - 5 cm (subject to further consultation by NMHSs including Bhutan)

- Strong winds

  - 17 knots

  - 34 knots

- High waves / swells

  - 2.5 m

- Storm surge

  - 1 m

The following seasons shall be considered for the project region and the weather each country significantly experiences during each season:

- Winter: January - February

- Pre-monsoon: March - May

- SW monsoon: June - September

- NE monsoon: October - December

- Bangladesh: a, b, c, d

- Bhutan: a, b, c, d

- Maldives: only c, d (SW Monsson: mid-May to November, NE Monsoon: December to April)

- Myanmar: a (Winter: December – February), b (Pre-monsoon: mid-April to mid May), c (SW Monsoon: mid-May to mid-October), d (NE Monsoon: mid-October to November)

- Nepal: only a, b, c

- Pakistan: only a, b, c

- India: a, b, c, d

- Sri Lanka – only b (March to April), c (SW Monsson: mid-May to September), d  (inter-monsoon period: October-November, NE Monsoon: December to February)

- Thailand – only a, c (SW Monsson: mid-May to October), d (NE Monsoon: October to February)

The SWFDP-South Asia, in its demonstration phase, shall address heavy rain, snowfall, high waves, storm surge and strong winds only and it may consider other hazardous weather conditions and weather-related hazards in future phases.

## Target domain

The domain to be covered for monitoring, analyzing and predicting the various severe weather events is proposed to be bounded by 10°S to 45°N and 45°E to 110°E (Fig. 1).

Figure 2: The red-coloured rectangle is the target domain for SWFDP-South Asia.

## The Demonstration Phase

The pilot demonstration phase shall be executed from  1 June  2019 to 31 December 2020. The full demonstration phase can be started from 1 January 2021. Before commencement of full demonstration phase all the requisite products from the contributing global centres would be made available.  During the pilot and full demonstration phase, NMHSs will be required to submit quarterly progress reports/feedback through SWFDP database (www.wmo.int/cpdb).

## Projects and Activities in synergy with SWFDP-South Asia

The synergy with other regional projects that are on-going and shall be implemented during the demonstration phase in the target domain to benefit SWFDP-South Asia is relevant and important. The participating members are aware of the products of the regional projects and activities, as given in the below paragraphs, and which might be useful to improve severe weather forecasting and warning.

2.6.1 Synergy with Tropical Cyclone Programme (TCP) activities in RA II (Asia)

The RSMC New Delhi carries out special regional and international functions, such as, detection, monitoring and tracking and intensity forecasting for all tropical cyclones in its region, the provision of real-time guidance and advisory information for NMHSs in the region, information for the international community, the training of personnel, and research.

- The programme that was developed by JMA under the Tropical Cyclones Ensemble Forecast Project (TCEFP) in the Panel region has been implemented to the RSMC, New Delhi.

- Multi-model ensemble forecasts which are derived from the High Resolution Ensemble Forecast System (HREF) are available at the RSMC’s Website.

2.6.2 Synergy with other projects and activities in RA II (Asia)

- SWFDP-Southeast Asia

- SWFDP-Central Asia

- Coastal Inundation Forecasting Demonstration Project (CIFDP). The CIFDP-Bangladesh was completed in November 2017 and has been operational since then.

- Flash Flood Guidance System (regional implementation in South Asia)

- Provision of City-Specific Numerical Weather Prediction Products to Developing Countries via the Internet  in RA II.

- Develop Support for Developing Countries in the Aeronautical Meteorology Programme in RA II.

- Enhance the Availability and Quality Management Support for NMHSs in Surface, Climate and Upper-air Observations.

- RA II Pilot Projects:

- To develop support for NMHSs in NWP

- To sustain and enhance the capacity of NMHSs in the provision of official medium-range forecasts

- On Impact-based forecasting

- To enhance meteorological DRR capability in RA II

- To develop support for NMHSs in the collection and application of data from Aircraft Meteorological Data Relay

## Regional Subproject Management Team (RSMT)

A Regional Subproject Management Team (RSMT) has been set up for the subproject . It mainly consists of the designated representatives of participating NMHSs and Centres. The RSMT members from the participating NMHSs are designated by the Permanent Representatives of respective countries with WMO.

The management of the SWFDP-South Asia is the responsibility of the RSMT and within the activities of CBS. The RSMT has reviewed and updated the Regional Subproject Implementation Plan (RSIP) of the subproject to manage and control its execution.

The RSMT will also consult with regional groups and bodies such as the WMO/ ESCAP Panel on Tropical Cyclones for the Bay of Bengal and Arabian Sea, RA II Management Group and RA II Working Group on Weather Services during the implementation of the SWFDP-South Asia.

2.7.1	Role and Responsibility of RSMT

The RSMT is responsible for the review  and updating of the  Regional Subproject Implementation Plan (RSIP). The RSIP must include the following actions with milestones:

- to guide the participants in the development of the RSIP;

- to submit the RSIP to the Steering Group for SWFDP;

- to conduct preparatory training for the participants;

- to start the demonstration phase;

- to conduct a mid-term project review;

- to submit the final report to the Steering Group for SWFDP;

- to investigate the possible expansion of the current regional subproject;

- to liaise with regional groups and bodies.

2.7.2	Members of RSMT

The members of the RSMT are appointed by the PRs of countries/Heads of NMHSs and generally consist of the senior forecaster in-charge of the forecasting team in the NMHS (able to direct and guide other forecasters). Each member is accountable to his/her respective PRs. The list of the members of the RSMT is as follows:

- NMHSs:

  - Bangladesh: Ms Mossammat Ayesha Khatun, Deputy Director, BMD

  - Bhutan: Mr Tayba Buddha Tamang, Deputy Chief, Meteorology, NCHM

  - Dr Mrutyunjay Mohapatra, Head (Services), IMD & Head, RSMC New Delhi

  - Maldives: Mr Ahmed Rasheed, Director Meteorology, MMS

  - Myanmar: Mr Hla Tun, Deputy Director, Meteorological Division, DMH

  - Nepal: Dr Jagadish Karmacharya, Deputy Director General, DHM

  - Pakistan: Dr Muhammad Hanif, Chief Meteorologist

  - Sri Lanka: Ms Anusha Warnasooriya, Director (Forecasting), DoM

  - Thailand: Mr Somkuan Tonjan, Director, Central Forecasting Division, TMD

- Regional Centre:

  - RSMC New Delhi: Dr Mrutyunjay Mohapatra, Head, RSMC New Delhi

- Global Centres:

  - IMD1 (supported by NCMRWF Noida, INCOIS Hyderabad and IITM Pune):

Dr Mrutyunjay Mohapatra, Head (Services), IMD and Head, RSMC New Delhi

- UK Met Office: Ms Catherine Moore

- ECMWF UK: Dr (Ms) Anna Ghelli

- JMA: Mr Masaaki Ikegami

- CMA: Dr (Ms) Hoa Tong

- KMA: Dr (Ms) SeiYoung Park

- Regional PWS representative (RA II/ South Asia?)

1 For NWP support and for forecast of sea parameters, IMD is supported by National Centre for Medium Range Weather Forecasting (NCMRWF), Noida and Indian National Centre for Ocean Information Services (INCOIS), Hyderabad. Indian Institute of Tropical Meteorology (IITM), Pune will provide support for providing guidance for extended range forecast for SWFDP-South Asia on experimental basis. IMD is to liaison with the focal persons in NCMRWF,NICOIS and IITM for the necessary support and coordination.

## 2.7.3	Responsibilities of the Members of RSMT

The tasks of the members of the RSMT are as follows:

The chairperson of the RSMT:

- to draft a detailed regional subproject development plan and to share with participating centres;

- to coordinate training requirements that support the demonstration project and to provide information to WMO Secretariat;

- to report on the project to the Steering Group for SWFDP.

The lead persons/members of RSMT from participating global centres:

- To coordinate efforts as appropriate in discharge of responsibilities by their respective global centres as mentioned in above para 2.7.2;

- to coordinate all aspects of project implementation and execution at their respective global centres;

- to evaluate possible data-processing developments (e.g. work required to adjust or tailor NWP products);

- to identify training support requirements, and prepare regular evaluation of the products during the demonstration phase.

The lead persons/members of RSMT from participating regional centre(s):

- To coordinate efforts as appropriate in discharge of responsibilities by their respective regional centre(s) as mentioned in para 2.7.2 above;

- to coordinate all aspects of project implementation and execution at their respective regional centre(s);

- to evaluate possible data-processing developments (e.g. work required to adjust or tailor NWP products);

- to identify training support requirements, and prepare regular evaluation of the products during the demonstration phase;

- to analyse the feedback/case studies as submitted by the NMHSs/NMCs and evaluate the use of products by NMHSs/NMCs and suggest advice to improve the use of products and carry out case studies.

The lead persons/members of RSMT from NMHSs/NMCs from participating Members:

- To coordinate efforts as appropriate in discharge of responsibilities by their respective NMHS/NMCs as mentioned in para 2.7.2 above;

- to coordinate all aspects of project implementation and execution at  national and local levels;

- to evaluate possible data-processing developments (e.g. work required to adjust or tailor NWP products);

- to arrange for forecasters in NMHSs/NMCs to receive or have access to the agreed products;

- to define the information to be exchanged with DMCPAs and other end users at national and local levels;

- to define the information to be transmitted to the media;

- to identify training requirements;

- to prepare regular evaluation of the forecasts and warnings during the demonstration phase and ensure submission of feedback including case studies and regular progress reports by NMHSs/NMCs to global and regional centres.

    - The regional PWS representative (from RA II or South Asia?) will be responsible to:

- promote the awareness of the SWFDP-South Asia to stakeholders (disaster management centre, agriculture and fisheries sectors, media and the public), including through existing forums and organizations;

- enable and assist staff of participating NMHSs to build effective dialogue with stakeholders for service provision;

- in liaison with stakeholders, identify improvements and changes to products for consideration of the NMHSs’ forecasting team;

- advise participating NMHSs on methods of evaluation of public forecasts and warnings and their use by stakeholders.

Each of the participating NMHSs are requested to involve their respective national  PWS focal point nominated at the invitation of WMO in the SWFDP-South Asia to also act as the PWS focal point for the project. Where such a national focal point has not been nominated yet, the NMHSs concerned are invited to do so and inform the Secretariat.

The Chair of the RSMT  will be responsible to liaise with the Steering Group for SWFDP and the WMO Secretariat on aspects of the regional subproject.

# 2.8 Responsibilities of Participating Centres in Subproject Implementation

Specific tasks are attributed to the three types of centres participating to the SWFDP in the cascading process.

## 2.8.1	The Global Centres

    - The responsibilities of the Global Centres are:

- to provide the other centres with medium-range NWP guidance and EPS output including probabilistic products specially adapted to the concerned severe weather events;

- to tailor products to the requirements of the Regional Centres including the provision of sub-domain and probabilistic products.

- to suggest suitable existing satellite imagery and satellite based products that are helpful in assessing the current meteorological situation, and therefore also assess the quality of global NWP/EPS products;

- to maintain a dedicated webpage at their Websites to provide NWP guidance and EPS products or the products be provided through Project Website maintained by RSMC New Delhi;

- to evaluate the efficiency of products dedicated to medium-range severe weather forecasting through the feedback provided by the other centres.

## 2.8.2 The Regional Centre (RSMC New Delhi)

2.8.2.1 Regional Centre for Regional Forecast Support and Training

The RSMC New Delhi, in addition to its mandate as a specialized centre for tropical cyclone forecasting, shall provide support for regional forecast and training for SWFDP-South Asia. The responsibilities include following:

- to redirect toward the NMHSs relevant products issued from the Global Centres (if necessary);

- to provide NMHSs with its own interpretation of the medium-range guidance, including EPS products;

- to provide the NMHSs with the short-range NWP guidance (including products adapted to severe weather events), as frequently as possible;

- to indicate existing satellite/radar imagery and satellite/radar based products that could be used for nowcasting purposes;

- to issue Daily Severe Weather Forecasting Guidance products summarizing interpretation of NWP products with respect to severe weather over the responsibility area of the NMHSs;

- to provide the other centres with short-range NWP guidance and EPS output including probabilistic products specially adapted to the concerned severe weather events;

- to tailor products to the requirements of the National Centres including the provision of sub-domain and probabilistic products.

- to evaluate its own interpretation of EPS products as well as its NWP guidance;

- to provide global centres with a feedback about the usefulness and efficiency of global products;

- to facilitate the flow of all forecasting guidance information to all participating Centres in the SWFDP through a dedicated password protected Web site and portal. Ideally this Web site would be maintained on a 24/7 basis and dedicated for the Regional Subproject;

- to coordinate real-time communications among the participating centres in the region of the project (to maintain a list of contact information; e-mail , telephone, fax).

- to help the RSMT to organize training workshops;

- to provide the NMHSs with the technical support in response to their requests;

- to provide guidance and advice in the use of multi-media facilities at training workshops.

## 2.8.2.2 The Regional Centre for Tropical Cyclone Support

The responsibilities of the RSMC New Delhi are:

- to provide the other centres with NWP guidance and EPS output, including probabilistic products specially adapted to tropical cyclone;

- to provide NMHSs with its own interpretation of the NWP guidance and EPS products adapted to tropical cyclone / typhoon;

- to evaluate its own interpretation of EPS products as well as its NWP guidance;

- to facilitate the flow of all forecasting guidance information to all participating Centres in the SWFDP through a dedicated password protected Web site and portal. Ideally this Web site would be maintained on a 24/7 basis and dedicated for the Regional Subproject.

## 2.8.3	The National Meteorological Centres (NMCs)/NMHSs

The responsibilities of the National Meteorological Centres of the NMHSs are:

- to interpret the guidance provided by the global centre and the regional centre;

- to issue special bulletins and warnings as required by the users (hydrological services, Disaster Management Civil Protection Authorities (DMCPA) services, media…) for dissemination to the end users when severe weather is expected;

- to use available nowcasting tools (satellite imagery or satellite based products, radar products) to update warnings;

- to exchange information on warnings between participating NMHSs, and between NMHSs and RSMC;

- to provide regional and global centres with a feedback on the efficiency of the global and regional products;

- to develop a communication strategy and plan with the media and end users to ensure effective response when warnings are issued;

- to establish contacts with DMCPA services and  end users prior and during severe weather events;

- to obtain feedback from media, the public and other users as appropriate after the event (opportunity of warning, usefulness of warnings, lead time, degree of impacts)

- to obtain feedback from the disaster risk management agencies on utilization/benefits of warnings issued by NMHSs (under the SWFDP);

- to prepare a compiled report on the severe weather events that contains all the data needed to perform the evaluation of both RSMC Daily Severe Weather Forecasting Guidance relevant to the country, and actual warnings issued by  NMHSs;

- to evaluate the warnings;

- to develop training to facilitate improved communication with the users;

- to develop a generic basic set of standard operational procedures between a NMHS and disaster risk management agencies to ensure effective use of the SWFDP products.

# 3. DATA,  PRODUCTS AND SUPPORT FROM CONTRIBUTING CENTRES

## 3.1 Data and Products to be issued from contributing Global Centres

Global NWP graphical products which can be made available by the global centres IMD (supported by NCMRWF & INCOIS), JMA, CMA, KMA, ECMWF, UKMO should be cut and formatted to fit the project area (10°S to 45°N, 45°E to 110°E).  NWP forecasts should be updated every 12 hours, or every 6 hours if available. In addition to the daily production all the forecasts should be archived for a minimum of 7 days.

Products which are not routinely transmitted through the GTS should be provided in graphical form (Web pages) via Internet for rapid display and dissemination. Provision of data in digital format may assist regional centres in producing charts of derived parameter.

## 3.1.1 Current Deterministic NWP Fields up to 5 days

The products are provided at 6-h Intervals up to 2 days and 12-h intervals after 2 days. The recommended products include:

- Upper air charts to depict the large-scale flow (e.g. 200 hPa, 300 hPa, 500 hPa , 700 hPa, 850 hPa geopotential heights, temperature, upper air winds);

- Surface charts to depict the large-scale flow (e.g. MSLP, surface streamlines, wind flow);

- Surface weather elements and parameters (e.g. 6-hour accumulated precipitation, surface (10m) wind-speed, and relative humidity);

- Special charts to assist with forecasts of tropical cyclone formation, movement and intensification (e.g. 850hPa, 200hPa relative vorticity and convergence, 850-200hPa deep layer mean flow, 500-200hPa deep layer mean flow, 300-100hPa deep layer mean flow, vertical wind shear, vertical motion).

## 3.1.2 Probabilistic Forecast Products based on EPS

The recommended products include:

- probability of severe weather events such as precipitation and wind higher than given thresholds;

- “spaghetti” plots (e.g. 500 hPa geopotential height in extra-tropics, precipitation and wind higher than given thresholds);

- stamp maps (e.g. streamlines in the tropics, wind speed, accumulated precipitation);

- dispersion diagrams (plumes and EPSgrams) for weather elements at specific locations;

- representative members of a classification of weather pattern such as clustering or tubing (optional product depending on possibilities of Global Centre);

- severe weather risk index such as Extreme Forecast Index (where available).

If severe weather is associated with a Tropical Cyclone other relevant products could include:

- surface or 850hPa vortex track charts;

- tropical cyclone position fix and track forecast spread (strike probability);

- tropical cyclone formation probability (wind probability, rainfall probability).

The list of the Stations of EPSgrams to be provided by Global Centres is given in Annex A.

The list of Deterministic NWP and EPS Products to be made available to IMD New Delhi by Global Centres is shown in Annex B and the list of Deterministic Global and Regional NWP Products to be available from  IMD/RSMC New Delhi is given in Annex C respectively.

## 3.1.3 Satellite data-processing systems and products for nowcasting

3.1.3.1 Satellite based products at IMD New Delhi

At present IMD is receiving and processing meteorological data from two Indian satellites namely INSAT-3D & INSAT-3DR. INSAT-3D launched on 26 July 2013 is positioned at 82°E and INSAT 3DR launched on 28th Aug 2016 is located at 74°E. INSAT-3D and INSAT-3DR have an advanced imager with six imagery channels {Visible (0.55-0.75 µm), Short wave Infra-Red (SWIR) (1.55-1.70 µm), Medium Infra-Red (MIR) (3.80-4.00 µm), Thermal Infra-Red-1(TIR-1) (10.2-11.3 µm), TIR-2 (11.5-12.5 µm), & WV (6.50-7.10 µm)} and a nineteen channel sounder (18 IR & 1 Visible) for derivation of atmospheric temperature and moisture profiles. It provides 1 km. resolution imagery in visible band, 4 km resolution in IR band and 8 km in WV channel.

At Present about 48 numbers of satellite images are taken daily from INSAT-3D and INSAT-3DR. Images from imager data are available every 15 minutes and Sounder multi-level imagery is obtained half hourly from the sounder channels of INSAT-3D and INSAT-3DR satellites in staggered mode. All the received data from the satellite are processed and archived in National Satellite Data Center (NSDC), New Delhi. INSAT-3D Meteorological Data Processing System (IMDPS) is processing meteorological data from INSAT-3D and INSAT3-DR that supports real time satellite based monitoring of severe weather events. Cloud Imagery Data are processed and available to SWFDP. The following products derived from the satellite are useful for monitoring of severe weather:

- Enhanced grey scale imagery of cyclone.

- Enhanced coloured imagery of cyclone.

- Lower level Vorticity

- Upper level Divergence.

- Lower level convergence.

- Vertical wind shear.

- Wind shear tendency.

- Outgoing Long wave Radiation (OLR) at 0.250X0.250 resolution

- Quantitative Precipitation Estimation (QPE)

- Sea Surface Temperature (SST)

- Cloud Motion Vector (CMV)

- Water Vapour Wind (WVW)

- Upper Tropospheric Humidity (UTH)

- Temperature, Humidity profile

- Value added parameters from sounder products

- Geo-potential Height

- Layer Precipitable Water

- Total Precipitable Water

- Lifted Index

- Dry Microburst Index

- Maximum Vertical Theta-E Differential

- Wind Index

With the Web Archival System developed at IMD, INSAT-3D and 3DR products & imageries are archived and accessible to SWFDP member countries.

The real time satellite products as well as archived products are available in a separate web page of IMD website with the link,  http://satellite.imd.gov.in/insat.htm.

Real time Analysis of Products & Information Dissemination called RAPID is a web based quick visualization and analysis tool for satellite data and products. This tool was conceptualized and developed by Satellite Application Centre (SAC), ISRO in collaboration with India Meteorological Department (IMD), New Delhi to enhance the visualization and analysis of INSAT Meteorological Satellite data on real time basis by the forecasting community. This system is operationally sustained by National Satellite Meteorological Centre (IMD), New Delhi. This tool is hosted at http://www.rapid.imd.gov.in/. It is accessible to all including SWFDP member countries. The examples of image products analysis using RAPID tool are given below. It can help to derive geo-referenced information for each pixel so as to monitor severe weather and provide the nowcast.

The salient features of RAPID are as follows:

➢ It connects atmospheric science and geosciences.

➢ There is no specific Operating System/ software/ library / compiler required on the desktop to access RAPID. It is accessed through web browser.

➢ It provides features of interest to scientific community

➢ RAPID follows Open Geospatial Consortium’s (OGC) open standards.

➢ Web Mapping Service (WMS) – For visualization of meteorological data (Satellite and ground observations).

➢ Extensions written for scientific community

➢ Zero learning curve

➢It can overlay Map Boundaries (World Coastline, State, District Boundaries, Gridlines) with configurable: Color; Opacity; Thickness, Contrast Stretch, Lookup Table Application

➢ It has Probe Data feature (on the fly) i.e. analysis of data Point,  Time Series, Vertical Profile, Transect, Area Measurement, Distance Measurement

➢ Animation can be generated and visualized in it.

➢ Day and Night time microphysics RGB Composites imageries are available in it.

➢ Contouring feature over meteorological data.

➢ Map background can be changed based on user preference.

Satellite based nowcast of cloud imagery based on brightness temperature is available based on INSAT-3D through RAPID system. The product is available every half an hour for nowcast up to 3 hours at the interval of every half an hour (i.e. 30, 60, 90, 120, 150 and 180 minutes forecast). An example of 60 minute forecast is given below.

3.1.3.2 Satellite products from CMA

CMA provides the Visible, Infra-red and Water Vapor satellite imagery products of FY-4A for SWFDP in RA II since 2018. FY-4A series are geostationary meteorological satellite with five channels (Visible, Infra-red, Split-window, Water Vapor and Mid-infrared). FY-4A were launched in December 2016, carrying the advanced observing functions. It is located 105° E and the time intervals of full disk are about 15 minutes. CMA built a website (http://eng.nmc.cn/swfdp/satellite/94) to provide the satellite images for the SWFDP in RA II. Example satellite images of FY-4A as available on above website and the sketch map of coverage areas for FY-2 series is shown below.

FY-2H are the 8th (last) flight unit of the FY-2 series launched in June 2018. It is located at 79° E that well suitable to supporting the SWFDP-South Asia. A Satellite Weather Application Platform(http://rsapp.nsmc.org.cn/geofy/en/) is built to provide the near-real time satellite imagery services of FY-2H and FY-4A for each observing band an RGB composite images. These images are updated every 15 minutes for FY-4A and every 30 minutes for FY2H, respectively.

3.1.3.3 Satellite products from JMA

Himawari-8 and -9 were launched in 2014 and 2016, respectively, carrying the advanced observing functions. Both satellites are located around 140.7 degrees east, and the imagery data of the satellites is disseminated and distributed through the HimawariCast and the HimawariCloud services to the most National Meteorological and Hydrological Services (NMHSs) in the satellite observing coverage including the South Asia region [1, 2].

JMA provides satellite black-and-white images for each observing band and RGB composite images showing cloud microphysics, convective storm, airmass and dust on the Himawari Real-Time Image website [3]. These images are updated every 10 minutes.

JMA launched its new international service called “HimawariRequest” in January 2018 in collaboration with the Australian Bureau of Meteorology (AuBoM). The service enables registered NMHSs to request Target Area observations of every 2.5 minutes by Himawari-8/9 [4]. JMA expects the service to support disaster risk reduction activities in the Asia and Pacific regions.

[1] http://www.data.jma.go.jp/mscweb/en/himawari89/himawari_cast/himawari_cast.php

[2] http://www.data.jma.go.jp/mscweb/en/himawari89/cloud_service/cloud_service.html

[3] http://www.data.jma.go.jp/mscweb/data/himawari/index.html

[4] http://www.jma.go.jp/jma/jma-eng/satellite/HimawariRequest.html

Example images on the Himawari Real-Time Image website: Sandwich (Blended Infrared - High Resolution Visible) product (left) and True Color Reproduction imagery (right; courtesy CSU/CIRA, JMA and NOAA/NESDIS) at 06:00UTC on 22 November, 2018.

The Himawari products for South Asia can be accessed from the following links:

http://www.data.jma.go.jp/mscweb/data/himawari/sat_img.php?area=fd_

http://www.data.jma.go.jp/mscweb/data/himawari/sat_img.php?area=se4

3.1.3.3 Precipitation products for Nowcasting through SCOPE-Nowcasting (Sustained Coordinated Processing of Environmental Satellite Data for Nowcasting)

The goal of the WMO Sustained, Co-Ordinated Processing of Environmental Satellite Data for Nowcasting (SCOPE-Nowcasting) initiative is to demonstrate continuous and sustained provision of consistent, well-characterized satellite products for nowcasting and severe weather risk reduction. The products for SWFDP sub-regions are available at: http://sigma.cptec.inpe.br/scope/

SCOPE-Nowcasting is supported by CGMS satellite operators, and aligned with a number of WMO initiatives, in particular SCOPE-CM and the Severe Weather Forecasting Demonstration Project (SWFDP). The SWFDP is focused primarily on NWP including EPS outputs and its use in severe weather forecasting and early warning services; the observational focus of SCOPE-Nowcasting has the high potential to complement and enhance SWFDP final output and thus lead to improved warning services. More on SCOPE-Nowcasting can be found at http://www.wmo.int/pages/prog/sat/scope-nowcasting_en.php.

## 3.2 Data and Products to be issued from RSMC New Delhi

## 3.2.1 Current deterministic Limited Area Model (WRF) fields up to 2 days

Products are provided at 6-hour intervals. Products could include:

- Upper air charts to depict the large-scale flow (e.g. 200 hPa, 300hPa, 500 hPa, 700 hPa, 850 hPa geopotential height, temperature, specific humidity,  tropopause height, upper air winds);

- Surface charts to depict the large-scale flow (e.g. MSLP, surface streamlines, wind flow)

- Surface weather elements and parameters (e.g. 6-hour accumulated precipitation, surface (10m) wind-speed and gusts (if available), 2m temperature, humidity);

- Maps of vertical motion, potential vorticity or height of specified PV surface;

- Maps of convective indices such as CAPE, Lifting Index, helicity

- relevant satellite images (where NMHSs do not have satellite receiving capability);

- Special products derived from satellite images (e.g. derived precipitation or images annotated with guidance notes).

- Special charts to assist with forecasts of tropical cyclone formation, movement and intensification (e.g. 850hPa, 200hPa relative vorticity and convergence, 850-200hPa deep layer mean flow, 500-200hPa deep layer mean flow, 850-200hPa vertical wind shear, vertical motion).

## 3.2.2 RSMC Tropical Cyclone Information/Advisory

RSMC Tropical Cyclone Information and Advisory are official information on tropical cyclones. Annex D gives the information of all products and services provided by RSMC New Delhi – Tropical Cyclone Centre.

3.2.3 RSMC Daily Severe Weather Forecast Guidance

Daily Severe Weather Forecasting Guidance should be issued by RSMC New Delhi once per day at 0800UTC to indicate the likelihood of severe weather occurrence:

- a short range (up to 48 h) guidance, including the risk-table, and a medium range (up to 5 days) guidance.

This guidance contains:

- Synopsis of weather (analysis and forecast);

- the interpretation of deterministic and ensemble NWP products from the Global and Regional Centres;

- severe weather predictions (risk or probability estimates) including tropical cyclone information.

The threshold values used in RSMC Daily Severe Weather Forecasting Guidance are determined as follows:

- Heavy rain: 50 and 100mm (the risk over 200mm/24h should be described in discussion)

- Wind speed: 17 knot and 34 knot.

- High waves/ swells: 2.5 m

- Storm surge; 1 m

A table of warning hazards and thresholds applicable to the Daily Regional Guidance is shown in Annex E and a template of Daily Regional Guidance to be issued by the RSMC New Delhi toward the NMHSs is given in Annex F.

## 3.3 Data and Products from other on-going projects or activities

The SWFDP-South Asia expects the additional data and products from other on-going projects or activities in the target domain. These data and products are provided voluntarily by courtesy of these projects or activities so that these are additional materials. The list of available data and products with the contact point of respective projects or activities should be made available so that when the data and products become unavailable during the field phase, RSMT should contact a contact person of relevant projects or activities.

## 3.4 Verification of Technical Capability of Participating NMCs/NMHSs

## 3.4.1 Technical feasibility

The SWFDP-South Asia requests the Global and Regional Centres to provide their products on GTS or/and Internet. Therefore, the participating NMCs/NMHSs need to be equipped with the internet infrastructure enough to accommodate the high-speed access to NWP products of foreign countries.

Regarding the PWS, the NMCs/NMHSs are requested to have the infrastructure to be developed to be able to obtain feedback from users, including media, disaster risk management agencies and pubic.

## 3.4.2 Status of internet infrastructure and requirements

## 3.4.2.1	Bangladesh

The Internet access speed at BMD is 25 Mbps. The forecasters of BMD rely on the Internet as essential for severe weather forecasting because they are always monitoring satellite imagery and products, radar products and model outputs of different centres.

(Information needs to be reviewed and updated by BMD representative)

3.4.2.2	Bhutan

(Information to be provided by NCHM representative)

## 3.4.2.3	India

IMD, New Delhi has 2 Internet lines from Internet Service Providers with internet speeds  100 Mbps & 1 Gbps.

The forecasters of IMD rely on the NWP products available in the Internet as well as in the synergy workstations, as essential for severe weather forecasting.

(Information needs to be reviewed and updated by IMD representative)

## 3.4.2.4	Maldives

Maldives Meteorological Service (MMS) has 1 Internet leased line with 10 Mbps of Dhiraagu LTD. The forecasters rely on the NWP products, satellite pictures and other relevant products available on the Internet. Apart from GTS, MMS out stations and SADIS are also connected using the internet. Fast and reliable internet is very useful for delivering alerts and warnings to Public during severe weather situations. Forecasters feel that current internet speed is relatively slow at times and there should be a backup internet line with a different service provider.

3.4.2.5 	Myanmar

The Internet speed at DMH is 2 Mbps. The forecasters of DMH rely on the Internet as essential for severe weather forecasting. However, the internet speed needs to be improved.

(Information needs to be reviewed and provided by DMH, Myanmar)

## 3.4.2.6	Nepal

The Internet speed at DMH is 3 Mbps. The forecasters of DHM rely on the Internet as essential for severe weather forecasting. However, the internet speed needs to be improved as forecasters rate the current internet speed ‘slow’.

(Information needs to be reviewed and provided by DHM representative)

## 3.4.2.7	Pakistan

The Internet speed at MMS is 9 Mbps. The forecasters of MMS rely on the Internet as essential for severe weather forecasting. However, the internet speed needs to be improved.

## (Information to be reviewed and updated by PMD representative)

## 3.4.2.8	Sri Lanka

The Internet access speed at the Department of Meteorology (DoM), Sri Lanka is 7 Mbps. The forecasters consider the existing internet access at NMC as “slow”. They rely on the Internet as essential for severe weather forecasting.

## (Information to be reviewed and updated by DoM representative)

## 3.4.2.9 Thailand

The TMD’s NMC has the internet line whose speed has 50 Mbps (domestic)/10Mbps (international). The forecasters rely on the Internet as essential for severe weather forecasting at the NMC. However, the NMC recognized that the internet access is “good” to access to TMD’s database and for dissemination of information to public but it is ’’slow” to access to data from NWP centres.

## (Information to be reviewed and updated by TMD representative)

# 4. PUBLIC WEATHER SERVICES (PWS) COMPONENT OF SWFDP

Public Weather Services Delivery (PWSD) and warning services by NMHSs is an important component of SWFDP. NMHSs/Members have designated their focal points for PWSD. Effective service delivery is a fundamental requirement for NMHSs if they are to meet national needs. There are many different interpretations of the concept of service delivery as it relates to the provision of weather-, climate- and water-related services.

## 4.1 The WMO Strategy for Service Delivery

The WMO Strategy for Service Delivery and its Implementation Plan (WMO No. 1129) were developed and approved by Congress and the Executive Council respectively to guide Members in their service delivery activities. The publication is freely accessible through the following link:

http://www.wmo.int/pages/prog/amp/pwsp/documents/WMO-SSD-1129_en.pdf

The Implementation Plan reflects the fundamental role of Service Delivery in all WMO programmes and initiatives, particularly in PWS and DRR; Describes practices for strengthening service delivery by Members using a flexible methodology, and Provides NMHSs’ management with tools to understand use of NMHSs services in decision-making processes by users. All participating NMHSs of SWFDP-South Asia are strongly encouraged to use the Strategy and its Implementation Plan to assist them with the improvement of their PWS delivery under the subproject.

4.2 Impact-based Forecast and Warnings Services (IBFWS)

For a NMHS, providing impact-based forecast and warning services (IBFWS) represents a paradigm shift in service delivery focusing on what the weather will do as opposed to just what the weather will be. The “WMO Guidelines on Multi-hazard Impact-Based Forecast and Warning Services (WMO-No 1150)” is also available on WMO website at the following link: https://library.wmo.int/pmb_ged/wmo_1150_en.pdf

In an effort to inculcate this shift, the sixty ninth session of the Executive Council (EC-69, May, 2017) requested the EC Panel on Education and Training, in conjunction with Regional Associations (RAs) to include IBFWS in the curricula of WMO RTCs and to develop training materials, taking into consideration the different regional and national cultural approaches and circumstances. EC requested RAs to develop training materials in close collaboration with the PWSD Programme. EC-69 also requested RAs to develop a mechanism for the collection and processing of impact-related data and information for GDPFS centres and to share digital data with SWFDP.

WMO is assisting NMHSs develop their IBFWS by organizing the “Stakeholders Workshop to Implement a Pilot Project on Impact-based Forecasting and Risk-based Warnings”. In South Asia, such training workshops have been conducted in Maldives and Myanmar  during 2015-2016.  Additionally, the following Regional Workshops on IBFWS have been performed in RA:

- First KMA/WMO RA II (Asia) Workshop on Impact-based Forecasts - Seoul, Republic of Korea, 7-9 November, 2017.

- Second KMA/WMO RA II (Asia) Workshop on Impact-based Forecasts - Seoul, Republic of Korea, 19–21 November 2018.

Training on IBFWS is also provided at the SWFDP workshops at which participants from different countries benefit. All participating countries of SWFDP-South Asia have also attended at least one training event (and an in-country pilot project, in one case) on IBFWS including above Regional Workshop on IBFWS (Seoul, Republic of Korea,  2017 & 2018).  All participating NMHSs of SWFDP-South Asia are also strongly encouraged to strengthen IBFWS in their respective countries as part SWFDP implementation. The implementation status of IBFWS in SWFDP countries in South Asia is provided at Annex-G.

4.3	Delivery of Warnings and Common Alerting Protocol (CAP)

The PWSD Programme is leading the implementation by NMHSs of the Common Alerting Protocol (CAP). CAP is based on XML language and compatible with computers which enables automation of dissemination of warnings. It facilitates simultaneous communication of warnings through all forms of media including radio and television as well as new technologies such as Web services, to the public and all user communities. The Guidelines for Implementation of Common Alerting Protocol (CAP)-Enabled Emergency Alerting are available at the following link:

https://library.wmo.int/pmb_ged/wmo_1109_en.pdf

CAP training has been conducted in several countries of different WMO RAs in the form of  Jump-Start Workshop (e.g. Caribbean, SIDS Pacific) or as Regional Workshops.  Various “International CAP Implementation Workshops” have been held during the last years. “The 2018 Common Alerting Protocol (CAP) Implementation Workshop” was hosted by Hong Kong Observatory (HKO)- Hong Kong, China during 31 October-1 November, 2018. In South Asia only few countries which have received the training are utilizing CAP operationally. Thailand is utilizing CAP as a warning dissemination method and has registered in the  WMO Alerting Authority Data Base. Members/NMHSs that might wish to implement CAP are invited to contact the WMO PWSD/Service Delivery Division for further information.

The Severe Weather Information Centre (SWIC) Website (which can be accessed here: http://severe.worldweather.wmo.int) continues to be a source of official warnings of tropical cyclones on a global scale. The site also provides information on heavy precipitation and thunderstorms. Users’ suggestions on how the site could be improved to serve you better are welcome. It can be accessed at: http://severe.worldweather.org/

The World Weather Information Service (WWIS) is a platform for displaying official weather forecasts and observation data provided by NMHSs. One of the challenges of WWIS is that some NMHSs do not provide 5-day weather forecasts for their chosen cities consistently. Members/NMHSs are encouraged to participate in the SWIC and WWIS platforms. In order to see the respective level of performance by each NMHS, the meeting may visit: http://worldweather.wmo.int/en/home.html

4.4	Communication

It is important for NMHSs to develop multiple channels of communication in order to reach the maximum number of people, especially when they have to disseminate a warning. In addition to the traditional media which include television, radio, websites, etc., the use of social media communication methods such as Facebook, Twitter, YouTube, Blogs and mobile phone Apps, in communicating forecasts and warnings are an effective way for NMHSs to communicate forecasts and warnings to the public. WMO has produced a set of guidelines on strategies for use of social media in PWS which is available at the following link: https://library.wmo.int/pmb_ged/wmo_1086.pdf

4.5	Urban Services

Urbanization is rapidly becoming the dominant feature of population dynamics exerting large influence on sustainable urban development. Considering this and related expectations of increase in weather, climate, hydrological and other environmental extremes, an urgent need exists to enhance the resilience of cities and their inhabitants in withstanding environmental hazards, and to factor these extremes  to city planning, power and water supply, disaster risk reduction, climate change adaptation and mitigation, and the health of citizens. To this end, the WMO Congress at its seventeenth Session (Cg-17) held in 2015, adopted Resolution 68 (Cg-17) – establishing a WMO Cross-Cutting Urban Focus to address urban issues in a holistic manner. A group of experts across the technical commission was collected to develop a Guide for integrated urban services. NMHSs are expected to play an important role in the provision of effective delivery of user-targeted meteorological, hydrological and other related services in urban areas.

## 4.6 Implementation Plan to improve Delivery of Forecasts and Warnings

## Services in NMHSs

Participating NMHSs are expected to develop an implementation plan based on the WMO Strategy for Service Delivery and other PWSD initiatives e.g. IBFWS, CAP etc. as mentioned above for achieving the improvement in delivering warnings and forecasts services to stakeholders. The plan will be tested during the pilot demonstration phase and be evaluated to verify its usefulness and identify the area of improvement after the pilot demonstration phase. The improved plan will be applied during full demonstration phase.

# 5.	CAPACITY DEVELOPMENT - SWFDP TRAINING ACTIVITIES

## 5.1 Overview

Capacity development of NMHSs through SWFDP training activities is necessary to ensure that forecasters from Regional Centres and NMHSs are able to correctly interpret the various NWP/EPS and guidance products made available for the SWFDP regional subproject and to prepare user-focused information. Also, the training will inform forecasters of all responsibilities as outlined in the RSIP.

The training should include specific topics on coordination and collaboration between NMHSs, DMCPAs, media, governmental and non-governmental organizations and any other relevant agencies as part of the Public Weather Services component of the SWFDP.  Such training should take place with reference to any documented guidelines about service delivery principles and practices. It is important to note that any special training session devoted to a regional subproject could be planned in conjunction with existing training programmes organized by the WMO Secretariat or WMO Members.

Based on the regional and national needs, the following approach is followed for planning and designing of the SWFDP training programmes:

- SWFDP training workshops – include training on interpretation and use of NWP including EPS products, and satellite-based information to improve severe weather forecasting. The workshops also focus on PWS including delivery of warning services, impact-based forecasts and warning services (IBFWS), use of common alerting protocol (CAP) in dissemination of warnings. Subject to availability of resources, generally the SWFDP training workshops are held on annual basis preferably and are rotated among the participating countries of a subproject so that maximum staff can be trained in each of the participating country. Such workshops are mainly conducted for operational forecasters and public weather services (PWS) staff of the NMHSs. These workshops are organized with involvement of WMO’s GDPFS and PWS programmes and through collaboration from other relevant programmes (as appropriate and necessary) such as, Tropical Cyclone Programme (TCP), Marine Meteorology and Oceanography (MMO), Hydrology and Water Resources (HWR) and Agricultural Meteorology (AgM) Programmes.

- RSMC Training Desk - involves short-term deployment of forecasters/experts  from participating countries at the regional centre to familiarize themselves with the mechanism for the preparation and issuance of guidance products and to improve the guidance product through sharing of local information and forecast experience. The establishment of a training desk at the Regional Centre (or RSMC) can also be considered if so required for the region. For this purpose, a few forecasters from NMHSs of participating countries are invited to work with the RSMC forecasters for a week or so. The RSMC training desk can serve two objectives: firstly, to improve the skills of invited forecasters by engaging them in the process of NWP, EPS and satellite products inference and analyses to develop RSMC Daily Guidance for the NMHSs; and secondly to provide opportunity for the RSMC forecasters to gain local knowledge from the invited forecasters through discussion in order to improve RSMC Daily Guidance for the benefitting countries.

- In-country Training - This approach is mainly adopted for relatively small NMHSs especially from  Small Island Developing States (SIDS).

- eLearning Opportunities - eLearning sources are increasing becoming useful and  popular. Forecasters are recommended to complete the on-line courses on variety of topics related to SWFDP objectives including, for example, radar and satellite nowcasting, tropical meteorology, forecast verification, ensemble systems and products etc. Additionally, the forecasters nominated for a SWFDP training workshop need to complete a list of online training resources before coming to the workshop to better prepare for the face-to-face training.  A list (not complete) of online resources is given below:

- COMET MetEd, ECMWF  websites : https://www.meted.ucar.edu/training_detail.php

- ECMWF website: https://www.ecmwf.int/assets/elearning

- EUMETCAL/EUMETNET: https://eumetcal.eu/

NMCs/NMHSs are also encouraged to have a daily video conference with RSMC especially during rainy season in order to have discussions on current weather, synoptic analyses and inference from the NWP model products and satellite information to identify areas of potential severe weather in short- and/or medium-range.

Additionally, participants from SWFDP countries are also supported and sponsored for NWP and EPS products interpretation and high resolution limited-area NWP Modelling trainings offered by various global and regional NWP centres such as: DWD, NOAA/NCEP and WMO RTCs etc.

So far, as part of SWFDP-South Asia, WMO has conducted training workshops in Macao (China) in April 2013, in Bangkok (Thailand) in September 2015 and in Colombo, Sri Lanka in December 2018.

## 5.2 Training Topics for SWFDP Training Activities

Possible contents of the SWFDP-South Asia training activities are listed as follows:

- Interpretation and best practice use of deterministic and probabilistic NWP products for the forecasting of severe weather;

- Understanding and interpretation of specialized NWP products for forecasting severe weather associated with tropical cyclones:

  - Madden-Julian Oscillation (MJO) diagnostics and predictors;

  - tropical cyclone genesis parameters;

  - environmental controls on tropical cyclone movement and intensification;

  - strike probability maps;

  - Lagrangian meteograms;

  - feature-based tropical low probability maps;

  - sea state probability maps;

  - Feedback mechanisms and contingency plans;

  - Use of probabilities in the preparation of weather forecasts;

  - Model verification as part of the forecast process;

  - Verification of forecasts and warnings issued by the NMCs/NMHSs

  - Interpretation of Daily Severe Weather Forecasting Guidance produced by RC Hanoi and TC guidance products produced by RSMC Tokyo and RSMC New Delhi;

  - Use and applications of the SWFDP-South Asia project website;

  - Guidance on the completion of the SWFDP- South Asia evaluation form(s)

  - Coordination activities with DMCPAs

  - Constructing case-study.

Especially, PWS-related topics should typically include the following:

  - User Focus

  - Coordination with Disaster Management and Civil Protection Authorities (DMCPAs)

  - Innovative Ways to Improve Working Relationships between NMHSs and DMCPAs

  - Communication Skills

  - Media Skills Workshop

  - Working with the Media

  - Writing Workshop

  - Public Education and Outreach

  - Communicating Uncertainty in Forecasts

  - Service Evaluation

Additionally, as the ‘cascading forecasting process’ concept has been evolved (please see SWFDP Guidebook (2016)) and the expected outcomes now include:

- Enhanced capability for NMHSs to forecast severe weather and issue warnings at the national level, including improved accuracy and longer lead-times;

- Established warning processes agreed with national disaster management and civil protection authorities, along with planned responses for protection of lives and property;

- Established forecast processes and Quality Management Systems (QMS), and strengthened forecast capabilities in support of other user sectors in society (such as water, DRR, agriculture and food security, aviation, marine safety and transportation, etc.) at the national level;

- Raised awareness of the value of NMHSs with national governments and their agencies, leading in the long-term to greater national support and investment and leading, in turn, to improved supply of observations and feedback into the GDPFS; and

- Reduced loss of life and damage to property and infrastructure, and contributions to the UN 2030 Agenda for Sustainable Development (Sustainable Development Goals) and Sendai Framework for DRR in achieving their respective goals and targets.

The SWFDP training activities may include such topics as may be appropriate to contribute to the above mentioned expected outcome(s). Further more detailed information about the training program for a SWFDP training activity will be made available later before the training activity.

# 6.	EVALUATION OF SUBPROJECT

## 6.1 Overview

Every SWFDP Regional Subproject is required to be evaluated against the SWFDP goals and objectives as mentioned in ‘SWFDP Guidebook’ (see Para 2.1 above). The aim of the SWFDP evaluation also include:

- to assess the performance of RSMC’s Forecast Guidance Product;

- to assess the performance of the NMC/NMHS’s forecasting and warning system;

- to inform about the efficiency of the SWFDP and the level of satisfaction of the users.

During the demonstration phase, a continuous evaluation procedure using regular progress report must be implemented to check if the ‘cascading forecasting process’ works efficiently. At the end of the demonstration phase, a final evaluation of the regional subproject needs to be carried out by the RSMT to identify gaps and areas for improvement to ensure future sustainability of the demonstrated procedures and for other similar subprojects. In this evaluation, a qualitative assessment will be made of the success of the SWFDP related to the specific benefits of the Project and in particular the measurable improvements that have been noted in the warning services that are provided to the National Disaster Management and Civil Protection Authorities (DCMPAs) and the media.

6.2 Quarterly Progress Reports by NMCs/NMHSs

To keep regularly informed the RSMT and WMO about the progress of the implementation of SWFDP-South Asia and the project evaluation against SWFDP goals, each participating NMHS shall prepare quarterly progress reports including case studies and submit to WMO online through SWFDP database within the ten days after the end of each quarterly period. A progress report should contain information about the way the SWFDP is being implemented, such as the usefulness of NWP/EPS products in preparing severe weather forecasts and warnings, number of events observed, number of warnings issued, forecast verification e.g. probability of detection (POD) and false alarm ratio (FAR), clients’ feedback etc. The quarterly progress reports shall be prepared and submitted as per schedule given in Section 8.

A SWFDP database has been developed using WMO’s Country Profile Database (CPDB) web portal (https://www.wmo.int/cpdb/). Each of the NMHSs involved in SWFDP shall have a specific user ID and password to have access to the SWFDP database for submission of its progress reports.  The national focal points for SWFDP-South Asia (RSMT members) shall be responsible for implementation of the tasks related to the project at national levels including submission of quarterly progress reports.

## A Template of Severe Weather Event Evaluation Form is shown in Annex H and the Summary of Procedure for Verifying Forecasts and Warnings using Contingency Tables (for calculating POD, FAR etc.) is available as Annex I. The list of Key Elements of SWFDP Quarterly Progress Report and related information which required to be reported as part of a progress report are given in Annex J.

## 6.3 Feedback from Users from the Viewpoint of PWSD

Feedback of users and clients are quite useful to improve the severe weather forecasting services. The clients’ feedback need to be reported as part of the SWFDP quarterly progress report. During the demonstration phase it will be particularly important for the NMHSs to keep regular contacts with users and clients (e.g. DMCPAs, media etc.) to ensure smooth flow of information with a view to measuring the level of user satisfaction. The information in this continuous evaluation should be consolidated into regular quarterly progress reports. The NMCs/NMHSs can obtain the feedback from clients/users  using the User Assessment Questionnaires. Templates of such questionnaire for the public, DMCPAs and the media are available in Annex K. Clients’ feedback should be included in quarterly progress reports.

# 7. TIMELINE OF SUBPROJECT ACTIVITIES

| When | What Task | Who |
| --- | --- | --- |
| 1 June 2019 | Start a Pilot Demonstration phase) | All |
| 10 October 2019 | 1st progress report for the period (June-September 2019) | All participating NMHSs |
| 10 January 2020 | 2nd Progress Report for the period (October-December 2018) | All participating NMHSs |
| 10 April 2020 | 3rd Progress Report for the period (January-March 2020) | All participating NMHSs |
| 10 July 2020 | 4th Progress Report for the period (April-June 2020) | All participating NMHSs |
| 10 October 2020 | 4th Progress Report for the period (July-September 2020) | All participating NMHSs |
| Q3/Q4 2020 | Regional Training Workshop on Severe Weather and IBFWS (subject to availability of resources) | WMO |
| Q4 2020 | Second Meeting of RSMT of SWFDP-South Asia to review the subproject progress and update the RSIP (subject to availability of resources) | WMO |
| 1 January 2021 | Start a Full Demonstration Phase (Subject to availability of products from CMA, JMA and KMA) | All |
| 10 January 2021 | 5th Progress Report for the period (July-September 2020) | All participating NMHSs |

# 8.	SUBPROJECT COSTS AND RESOURCES

The SWFDP activities are financed through a variety of sources. The contributing global and regional centres also support SWFDP as their in-kind contributions (e.g. provision of products for NMHSs, and experts for training workshops) through WMO to assist NMHSs in developing countries, LDCs and SIDS. The project activities especially SWFDP training workshops and RSMT meetings are mainly funded through extra-budgetary resources. So far, the implementation of SWFDP-South Asia (formerly SWFDP-Bay of Bengal) has been funded through joint RIMES-WMO projects. However, financial assistance from multiple sources may be needed to carry out the subproject activities. There is also potential for additional assistance as part of ongoing projects and activities in the region. The potential impact of demonstration phase project-related activities on operational staffing should be considered by all contributing and participating centres. For the purpose of evaluating the total cost of the SWFDP-South Asia, participating centres are required to estimate all additional costs associated with the SWFDP. This should include human costs (equivalent person-months) as well as expenditures of funds if any directly related to the project.

Mainly the SWFDP expenditures are related to the capacity development activities (e.g. SWFDP training workshops) for NMHSs and to support their engagement with users including general public, DMCPAs, media (generally held every year) and to conduct RSMT meetings in alternate years.

CBS has commended the efforts of the Secretariat in supporting the SWFDP through optimizing activities across WMO programmes and in seeking support from development partners and donors. Following the recommendations of CBS, Members are also urged to seek funds from potential development partners and other agencies who stand to benefit from the important results of the SWFDP.

A tentative work plan of activities along with estimated costs for 2019-2021 is available as Annex L.

# 9. COMMUNICATION AND PUBLICITY OF THE PROJECT (Stakeholder engagement)

Informing stakeholders about the Project is an important on-going task. There should be publicity about the initiation of the Project as well as regular progress reports.

Stakeholders include:

- NMHSs in the region, including spreading information within the NMHS of the participants;

- RSMC New Delhi (IMD)

- RA II President and Management Group;

- Relevant RA II Working Groups and Theme Leaders;

- Executive Council;

- Aid agencies and development partners : Asian Development Bank, World Bank;

- WMO/ ESCAP Panel on Tropical Cyclones

- WMO Secretariat

Communication could be through newsletters, information pamphlets, presentations (e.g., at the TC sessions, regular session of RA II and other regional meetings)

This Regional Subproject Implementation Plan (RSIP) should be passed to stakeholders for information and feedback. Responsibility for communicating the Project and publicity is a task for all participants, but with overall coordination by the Chairman.

# 10. LIST OF THE ANNEXES

ANNEX A: List of Stations for EPSgrams (ENS Meteograms) provided by Global Centre

ANNEX B: The list of Deterministic NWP and Ensemble Products to be made available to IMD New Delhi by Global Centres

ANNEX C: The list of Deterministic Global and Regional NWP Products to be available from IMD/ RSMC New Delhi

ANNEX D: List of Products provided by RSMC New Delhi – Tropical Cyclone  Centre

ANNEX E: Warning Hazards and Thresholds applicable to the Daily Regional Guidance

ANNEX F: Template of Daily Regional Guidance to be issued by RSMC New Delhi

ANNEX G: The Implementation Status of Impact-based Forecast and Warning Services

(IBFWS) in SWFDP countries in South Asia

ANNEX H: Template of Severe Weather Event Evaluation Form

ANNEX I: Summary of Procedure for Verifying Forecasts and Warnings using

Contingency Tables by NMCs/NMHSs

ANNEX J: Key Elements of SWFDP Quarterly Progress Report

ANNEX K: User Assessment Questionnaire

K.1: Evaluation Questionnaire for the Public

K.2: Evaluation Questionnaire for Disaster Management			    	      K.3: Evaluation Questionnaire for Media

ANNEX L: Tentative Work Plan with estimated costs for 2017-2020

# 12. REFERENCES

- Abridged Final Report with resolutions, decisions and recommendations of the sixteenth session of CBS (Guangzhou, China, 23–29 November 2016). Available at: http://www.wmo.int/pages/prog/www/CBS/Reports/2016_Guangzhou_1183/1183_en.pdf

- Final Report of the sixth meeting of CBS Steering Group of the SWFDP (Geneva, Switzerland, 14–18 March, 2016). Available at:

http://www.wmo.int/pages/prog/www/CBS-Reports/documents/SG-SWFDP_Final_Report_000.pdf

- Final Report of the Technical Training Workshop on Severe Weather Forecasting and Warning Services (Dakar, Senegal, 2-6 November 2015). Available at: http://www.wmo.int/pages/prog/www/CBS-Reports/DPFS-index.html

- Abridged Final Report with resolution of the sixteenth session of Regional Association I (Africa) (Praia, Cabo Verde, 3-9 February 2015). Available at: https://library.wmo.int/pmb_ged/wmo_1151_en.pdf

- Abridged Final Report with resolutions and recommendations of the Extra-ordinary session of CBS (Asunción, Paraguay, 8–12 September 2014) (CBS-Ext.(2014)). Available at: http://www.wmo.int/pages/prog/www/CBS/Reports/2014_Ext14_Asuncion_1140/1140_en.pdf

- Final Report of fifth meeting (extra-ordinary) of CBS Steering Group of  the SWFDP, Geneva, Switzerland, 3–5 December, 2013). Available at: http://www.wmo.int/pages/prog/www/CBS-Reports/documents/SG-SWFDP_Final_Report.pdf

- Abridged Final Report with resolutions and recommendations of the fifteenth session of CBS (Jakarta, Indonesia, 10-15 September, 2012). Available at: http://www.wmo.int/pages/prog/www/CBS/Reports/2012_15th_Jakarta_1101/1101_en.pdf

- Final Report of the forth meeting of CBS Steering Group of the SWFDP, Geneva, Switzerland, 28February to 2 March 2012). Available at: http://www.wmo.int/pages/prog/www/CBS-Reports/documents/SG-SWFDP-4_Final_Report.pdf

- Final Report of the third meeting of CBS Steering Group of the Severe Weather Forecasting Demonstration Project (Geneva, Switzerland, 22-26 February, 2010). Available at: http://www.wmo.int/pages/prog/www/CBS-Reports/DPFS-index.html

- Abridged Final Report with resolutions and recommendations of the fourteenth session of CBS (Dubrovnik, Croatia , 25 March -2 April, 2009). Available at: http://www.wmo.int/pages/prog/www/CBS/Reports/2009_14th_Dubrovnik_1040/1040_en.pdf

- Abridged Final Report with resolutions and recommendations of the Extra-ordinary session of CBS in 2006 (Seoul, Republic of Korea,  9-16 November 2006). Available at: http://www.wmo.int/pages/prog/www/CBS/Reports/2006_Ext06_Seoul_1017/1017_en.pdf

- Abridged Final Report of the thirteenth session of CBS (St. Petersburg, 23 February - 3 March 2005). Available at http://www.wmo.int/pages/prog/www/CBS/Reports/2005_13th_StPetersburg_985/985_en.pdf

Annex A

List of Stations for EPSgrams (ENS Meteograms) provided by Global Centres

Remark: ECMWF provides EPSgrams (known at ECMWF as "ENS Meteograms")

Bangladesh

| Sr. # | Station name/ ID | Station Index | Lat. | Lon. | Alt. (m) | ECMWF | NCMRWF | JMA | CMA | KMA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Barisal | 41950 | 22°45′N | 90°22′E | 3.0 | x | x | x | x |  |
| 2 | Chittagong | 41978 | 22°16′N | 91°49′E | 4.0 | x | x | x | x |  |
| 3 | Cox’s Bazar | 41992 | 21°26′N | 91°56′E | 2.0 | x | x | x | x |  |
| 4 | Dhaka | 41923 | 23°46′N | 90°23′E | 8.0 | x | x | x | x |  |
| 5 | Jessore | 41936 | 23°11′N | 89°10′E | 6.0 | x | x | x | x |  |
| 6 | Khulna | 41947 | 22°47′N | 89°32′E | 3.0 | x | x | x | x |  |
| 7 | Mymensingh | 41886 | 24°43′N | 90°26′E | 18.0 | x | x | x | x |  |
| 8 | Rajshahi | 41895 | 24°22′N | 88°42′E | 17.0 | x | x | x | x |  |
| 9 | Rangpur | 41859 | 25°44′N | 89°14′E | 33.0 | x | x | x | x |  |
| 10 | Sylhet | 41891 | 24°54′N | 91°53′E | 34.0 | x | x | x | x |  |
| 11 |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |

Bhutan

| Sr. # | Station name/ ID | St. Index | Lat. | Lon. | Alt. (m) | ECMWF | NCMRWF | JMA | CMA | KMA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Bumthang | - | 27.54539722 | 90.753725 | 2470 | x | x | x | x |  |
| 2 | Gasa | - | 27.90505556 | 89.72673056 | 2760 | x | x | x | x |  |
| 3 | Haa | - | 27.38643611 | 89.27854167 | 2751 | x | x | x | x |  |
| 4 | Samdrup Jongkhar | - | 26.85973611 | 91.46325 | 890 | x | x | x | x |  |
| 5 | Samtse | - | 27.00874167 | 88.88211667 | 413 | x | x | x | x |  |
| 6 | Sarpang | - | 26.87790556 | 90.26511944 | 390 | x | x | x | x |  |
| 7 | Thimphu | - | 27.441475 | 89.66277222 | 2310 | x | x | x | x |  |
| 8 | Trashi Yangtse | - | 27.61274722 | 91.49461389 | 1810 | x | x | x | x |  |
| 9 | Trashigang | - | 27.28205278 | 91.51855 | 1980 | x | x | x | x |  |
| 10 | Trongsa | - | 27.50542222 | 90.50503889 | 2120 | x | x | x | x |  |
| 11 | Paro | - | 27.38718611 | 89.41955278 | 2406 | x | x | x | x |  |
| 12 | Punakha | - | 27.58032222 | 89.86493889 | 1236 |  | x | x | x |  |
| 13 | Wangdiphodrang | - | 27.48909444 | 89.89804444 | 1180 |  | x | x | x |  |
| 14 | Zhemgang | - | 27.21506944 | 90.65883056 | 1820 |  | x | x | x |  |
| 15 | Monggar | - | 27.27924167 | 91.23551667 | 1580 |  | x | x | x |  |
| 16 | Lhuentse | - | 27.60652778 | 91.20677778 | 1339 |  | x | x | x |  |
| 17 | Phuentsholing | - | 26.85623333 | 89.38656389 | 270 |  | x | x | x |  |
| 18 | Tsirang | - | 27.00812222 | 90.12165278 | 1520 |  | x | x | x |  |
| 19 | Dagana | - | 27.09563056 | 89.85985556 | 1460 |  | x | x | x |  |
| 20 | Pema Gatshel | - | 27.03042778 | 91.43789722 | 1780 |  | x | x | x |  |

India

| Sr. # | Station name/ ID | Station Index | Lat. | Lon. | Alt. (m) | ECMWF | NCMRWF | JMA | CMA | KMA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Ahmadabad | 42647 | 23° 04′N | 72° 38′E | 55.0 | x | x | x | x |  |
| 2 | Bangalore | 43295 | 12° 58′N | 77° 35′E | 917.0 | x | x | x | x |  |
| 3 | Chennai | 43279 | 13° 00′N | 80° 11′E | 14.0 | x | x | x | x |  |
| 4 | Guwahati | 42410 | 26° 06′N | 91° 35′E | 54.0 | x | x | x | x |  |
| 5 | Hyderabad | 43128 | 17° 27′N | 78° 38′E | 530.0 | x | x | x | x |  |
| 6 | Kolkata | 42809 | 22° 39′N | 88° 27′E | 6.0 | x | x | x | x |  |
| 7 | Lucknow | 42369 | 26° 45′N | 80° 53′E | 122 | x | x | x | x |  |
| 8 | Mumbai | 43003 | 19° 07′N | 72° 51′E | 14.0 | x | x | x | x |  |
| 9 | New Delhi | 42182 | 28° 35′N | 77° 12′E | 211.0 | x | x | x | x |  |
| 10 | Port Blair | 43333 | 11° 40′N | 92° 43′E | 79.0 | x | x | x | x |  |
| 11 | Srinagar | 42042 | 33° 59′N | 74° 47′E | 1664.0 | x | x | x | x |  |
| 12 |  |  |  |  |  |  |  |  |  |  |

Maldives

| Sr. # | Station name/ ID | Station Index | Lat. | Lon. | Alt. (m) | ECMWF | NCRMWF | JMA | CMA | KMA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Hdh.Hanimaadhoo | 43533 | 6.75137 | 73.13106 |  | x | x | x | x |  |
| 2 | N.Manadhoo | - | 5.7663 | 73.4065 |  | x | x | x | x |  |
| 3 | B.Daravandhoo | - | 5.15676 | 73.12602 |  | x | x | x | x |  |
| 4 | K.Male' | 43555 | 4.19625 | 73.47948 |  | x | x | x | x |  |
| 5 | Adh.Maamigili | - | 3.47484 | 72.83087 |  | x | x | x | x |  |
| 6 | M.Muli | - | 2.91904 | 73.57692 |  | x | x | x | x |  |
| 7 | Dh.Kudahuvadhoo | - | 2.69269 | 72.86276 |  | x | x | x | x |  |
| 8 | L.Kadhdhoo | 43577 | 1.86198 | 73.51786 |  | x | x | x | x |  |
| 9 | Gdh.Kaadedhdhoo | 43588 | 0.48778 | 72.98485 |  | x | x | x | x |  |
| 10 | S.Gan | 43599 | -0.69449 | 73.14702 |  | x | x | x | x |  |
| 11 | HA.Thuraakunu |  | 7.10442 | 72.8982 |  |  | x | x | x |  |
| 12 | HA.Dhihdhoo |  | 6.88743 | 73.1062 |  |  | x | x | x |  |
| 13 | Hdh.Kulhudhffushi |  | 6.62327 | 73.06018 |  |  | x | x | x |  |
| 14 | Hdh.Makunudhoo |  | 6.4091 | 72.7008 |  |  | x | x | x |  |
| 15 | Sh.Funadhoo |  | 6.15283 | 73.27291 |  |  | x | x | x |  |
| 16 | R.Ungoofaaru |  | 5.6683 | 73.028 |  |  | x | x | x |  |
| 17 | B.Thulhaadhoo |  | 5.02178 | 72.83668 |  |  | x | x | x |  |
| 18 | Lh.Olhuvelifushi |  | 5.27825 | 73.60234 |  |  | x | x | x |  |
| 19 | K.Kashidhoo |  | 4.95709 | 73.42464 |  |  | x | x | x |  |
| 20 | AA.Ukulhass |  | 4.2148 | 72.8617 |  |  | x | x | x |  |
| 21 | V.Fulidhoo |  | 3.6805 | 73.41488 |  |  | x | x | x |  |
| 22 | V.Rakeedhoo |  | 3.31406 | 73.46854 |  |  | x | x | x |  |
| 23 | F.Nilandhoo |  | 3.05745 | 72.8777 |  |  | x | x | x |  |
| 24 | Th.Kandoodhoo |  | 2.32122 | 72.91223 |  |  | x | x | x |  |
| 25 | L.Isdhoo |  | 2.11927 | 73.5336 |  |  | x | x | x |  |
| 26 | L.Maavah |  | 1.88534 | 73.23809 |  |  | x | x | x |  |
| 27 | GA.Kolamaafushi |  | 0.83719 | 73.18057 |  |  | x | x | x |  |
| 28 | GA.Villinigili |  | 0.75433 | 73.41282 |  |  | x | x | x |  |
| 29 | Gn.Fuvahmulah |  | -0.29451 | 73.40822 |  |  | x | x | x |  |
| 30 | S.Hulhumedhoo |  | -0.58943 | 73.22074 |  |  | x | x | x |  |

Myanmar

| Sr. No. | Station name/ ID | Station Index | Lat. | Lon. | Alt. (m) | ECMWF | NCRMWF | JMA | CMA | KMA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dawei | 48108 | 14°06′N | 98°13′E | 16.0 | x | x | x | x |  |
| 2 | Hakha | 48030 | 22°39′N | 98°37′E | 1866.0 | x | x | x | x |  |
| 3 | Hpaan | 48099 | 16°45′N | 97°40′E | 9.0 | x | x | x | x |  |
| 4 | Kengtung | 48060 | 21°18′N | 99°37′E | 827.0 | x | x | x | x |  |
| 5 | Lashio | 48035 | 22°56′N | 97°45′E | 747.0 | x | x | x | x |  |
| 6 | Loikaw | 48075 | 19°41′N | 97°13′E | 895.0 | x | x | x | x |  |
| 7 | Phyapon | 48101 | 16°16′N | 95°40′E | 2.0 | x | x | x | x |  |
| 8 | Sittwe | 48062 | 20°08′N | 92°53′E | 4.0 | x | x | x | x |  |
| 9 | Thandwe | 48080 | 18°28′N | 94°21′E | 9.0 | x | x | x | x |  |
| 10 | Yangon | 48097 | 16°46′N | 97°25′E | 14.0 | x | x | x | x |  |
| 11 | Putao | 48001 | 27°20′N | 96°10′E | 409.0 | x | x | x | x |  |
| 12 | Myitkyina | 48008 | 25°22′N | 97°24′E | 145.0 |  | x | x | x |  |
| 13 | Hkamti | 48004 | 26°00′N | 95°42′E | 146.0 |  | x | x | x |  |
| 14 | Homalin | 48010 | 24°52′N | 94°55′E | 130.0 |  | x | x | x |  |
| 15 | Monywa | 48037 | 22°06′N | 95°08′E | 81.0 |  | x | x | x |  |
| 16 | Taunggyi | 48057 | 20°47′N | 97°03′E | 1436.0 |  | x | x | x |  |
| 17 | Mandalay | 48042 | 21°59′N | 96°06′E | 74.0 |  | x | x | x |  |
| 18 | Nyaung Oo | 48048 | 21°12′N | 94°55′E | 61.0 |  | x | x | x |  |
| 19 | Pyinmana | 48074 | 19°43′N | 96°13′E | 101.0 |  | x | x | x |  |
| 20 | Nay Pyi Taw | - | 19°45′N | 96°06′E | 108.0 |  | x | x | x |  |
| 21 | Magway | 48065 | 20°09′N | 94°57′E | 75.0 |  | x | x | x |  |
| 22 | Chauk | 48052 | 20°52′47"N | 94°49′11"E | 81.0 |  | x | x | x |  |
| 23 | Kyaukpyu | 48071 | 29°25′N | 93°33′E | 5.0 |  | x | x | x |  |
| 24 | Taungoo | 48078 | 18°55′N | 96°28′E | 47.0 |  | x | x | x |  |
| 25 | Bago | 48093 | 17°20′N | 96°30′E | 15.0 |  | x | x | x |  |
| 26 | Pyi | 48077 | 18°48′N | 95°13′E | 58.0 |  | x | x | x |  |
| 27 | Hmawbi | 48092 | 17°06′35"N | 96°00′48"E | 12.0 |  | x | x | x |  |
| 28 | Pathein | 48094 | 16°46′N | 94°46′E | 9.0 |  | x | x | x |  |
| 29 | Hinthada | 48087 | 17°40′N | 95°25′E | 25.9 |  | x | x | x |  |
| 30 | Mawlamyine | 48103 | 16°30′N | 97°37′E | 21.03 |  | x | x | x |  |
| 31 | Thaton | 48098 | 16°55′N | 97°22′E | 17.0 |  | x | x | x |  |
| 32 | Yay | 48107 | 15°15′N | 97°52′E | 3.0 |  | x | x | x |  |
| 33 | Myeik | 48110 | 12°26′N | 98°36′E | 36.0 |  | x | x | x |  |
| 34 | Kawthoung | 48112 | 09°58′N | 98°35′E | 46.0 |  | x | x | x |  |

Nepal

| Sr. # | Station name/ ID | Station Index | Lat. | Lon. | Alt. (m) | ECMWF | NRMWF | JMA | CMA | KMA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Birendra Nagar (Surkhet) | 44416 | 28.5878694 | 81.6351611 | 720 | x | x | x | x |  |
| 2 | Chaurikhark | - | 27.7000000 | 86.7166667 | 2619 | x | x | x | x |  |
| 3 | Dadeldhura | 44404 | 29.3000000 | 80.5833333 | 1848 | x | x | x | x |  |
| 4 | Ghorai (Dang) | 44429 | 28.0369444 | 82.4841667 | 634 | x | x | x | x |  |
| 5 | Dhankuta | 44477 | 26.9832194 | 87.3459556 | 1192 | x | x | x | x |  |
| 6 | Dipayal (Doti) | 44406 | 29.2619444 | 80.9369444 | 574 | x | x | x | x |  |
| 7 | Chandra Gadhi | - | 26.5638889 | 88.0615000 | 90 | x | x | x | x |  |
| 8 | Jiri | - | 27.6304472 | 86.2321139 | 1877 |  | x | x | x |  |
| 9 | Kathmandu Airport | 44454 | 27.7038250 | 85.3562472 | 1337 | x | x | x | x |  |
| 10 | Nijgadh | - | 27.1833333 | 85.1666667 | 244 | x | x | x | x |  |
| 11 | Pokhara Airport | 44434 | 28.2001833 | 83.9795222 | 827 | x | x | x | x |  |
| 12 | Gaur | - | 26.7671000 | 85.3130333 | 77 | x | x | x | x |  |
| 13 | Dhangadhi (Atariya) | 44409 | 28.8000000 | 80.5500000 | 187 |  | x | x | x |  |
| 14 | Nepalgunj Airport | 44418 | 28.1005556 | 81.6682472 | 165 |  | x | x | x |  |
| 15 | Jumla | 44424 | 29.2746611 | 82.1795778 | 2363 |  | x | x | x |  |
| 16 | Bhairahawa Airport | 44438 | 27.5068194 | 83.4204472 | 108 |  | x | x | x |  |
| 17 | Simara Airport | 44449 | 27.1641667 | 84.9800000 | 137 |  | x | x | x |  |
| 18 | Okhaldhunga | 44462 | 27.3081208 | 86.5042250 | 1731 |  | x | x | x |  |
| 19 | Taplejung | 44474 | 27.3586111 | 87.6700000 | 1744 |  | x | x | x |  |
| 20 | Biratnagar Airport | 44478 | 26.4839670 | 87.2670060 | 72 |  | x | x | x |  |
| 21 | Janakpur Airport | 44700 | 26.7107500 | 85.9244222 | 76 |  | x | x | x |  |
| 22 | Chainpur (West) | - | 29.5500000 | 81.2166667 | 1304 |  | x | x | x |  |
| 23 | Simikot | - | 29.9715333 | 81.8161111 | 2993 |  | x | x | x |  |
| 24 | Dunai | - | 28.9333333 | 82.9166667 | 2058 |  | x | x | x |  |
| 25 | Jomsom | - | 28.7840111 | 83.7298167 | 2744 |  | x | x | x |  |
| 26 | Baglung | - | 28.2636111 | 83.6000000 | 960 |  | x | x | x |  |
| 27 | Daman | - | 27.6044000 | 85.0928000 | 2265 |  | x | x | x |  |
| 28 | Dhading | - | 27.9125056 | 84.8961333 | 630 |  | x | x | x |  |
| 29 | Nagarkot | - | 27.6933472 | 85.5208583 | 2147 |  | x | x | x |  |
| 30 | Dhunche | - | 28.1099889 | 85.3017611 | 1993 |  | x | x | x |  |

Pakistan

| Sr. # | Station name/ ID | Station Index | Lat. | Lon. | Alt. (m) | ECMWF | UKMO | JMA | CMA | KMA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Badin | 41785 | 24° 38′N | 68° 54′E | 10.0 | x | x | x | x |  |
| 2 | Gilgit | 41516 | 35° 55′N | 74° 20′E | 1459.0 | x | x | x | x |  |
| 3 | Hyderabad | 41764 | 25° 23′N | 68° 25′E | 40.0 | x | x | x | x |  |
| 4 | Islamabad City | 41577 | 33° 42′N | 73° 05′E | 543.0 | x | x | x | x |  |
| 5 | Islamabad Airport | 41571 | 33° 37′N | 73° 06′E | 507.0 | x | x | x | x |  |
| 6 | Karachi Airport | 41780 | 24° 54′N | 67° 08′E | 21.0 | x | x | x | x |  |
| 7 | Lahore City | 41640 | 31° 33′N | 74° 20′E | 213.0 | x | x | x | x |  |
| 8 | Lahore Airport | 41641 | 31° 31′N | 74° 24′E | 215.0 | x | x | x | x |  |
| 9 | Multan | 41675 | 30° 12′N | 71° 26′E | 122.0 | x | x | x | x |  |
| 10 | Peshawar | 41529 | 34° 02′N | 71° 56′E | 329.0 | x | x | x | x |  |
| 11 | Quetta PBO | 41661 | 30° 11′N | 66° 57′E | 1626.0 | x | x | x | x |  |
| 12 | Sargodha | 41594 | 32° 03′N | 72° 40′E | 187.0 | x | x | x | x |  |

Sri Lanka

| Sr. # | Station name/ ID | Station Index | Lat. | Lon. | Alt. (m) | ECMWF | ECMRWF | JMA | CMA | KMA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Anuradhapura | 43421 | 08°20′N | 80°25′E | 93.0 | x | x | x | x |  |
| 2 | Batticaloa | 43436 | 07°43′N | 81°42′E | 2.6 | x | x | x | x |  |
| 3 | Colombo | 43466 | 06°54′N | 79°52′E | 12.0 | x | x | x | x |  |
| 4 | Galle | 43495 | 06°02′N | 80°13′E | 12.5 | x | x | x | x |  |
| 5 | Jaffna | 43404 | 09°41′N | 80°01′E | 9.5 | x | x | x | x |  |
| 6 | Katugastota (suburb of Kandy) | 43444 | 07°20′N | 80°38′E | 477.0 | x | x | x | x |  |
| 7 | Mannar | 43413 | 08°59′N | 79°55′E | 3.6 | x | x | x | x |  |
| 8 | Nuwara Eliya | 43473 | 06°58′N | 80°46′E | 1895.0 | x | x | x | x |  |
| 9 | Ratnapura | 43486 | 06°43′N | 80°23′E | 86.3 | x | x | x | x |  |
| 10 | Trincomalee | 43418 | 08°35′N | 81°15′E | 79.0 | x | x | x | x |  |
| 11 | Puttalam | 43424 | 08°02′N | 79°50′E | 2.13 | x | x | x | x |  |
| 12 | Kurunegala | 43441 | 07°28′N | 80°22′E | 116.0 |  | x | x | x |  |
| 13 | Pottuvil | 43475 | 06°52′N | 81°50′E | 3.6 |  | x | x | x |  |
| 14 | Bandarawela | 43476 | 06°51′N | 80°59′E | 1225.3 |  | x | x | x |  |
| 15 | Badulla | 43479 | 06°59′N | 81°02′E | 707.3 |  | x | x | x |  |
| 16 | Hambantota | 43497 | 06°07′N | 81°08′E | 15.3 |  | x | x | x |  |

Thailand

| Sr. # | Station name/ ID | Station Index | Lat. | Lon. | Alt. (m) | ECMWF | NCMRWF | JMA | CMA | KMA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aranyaprathet | 48462 | 13º 41' 19" | 102º 30' 15" | 47.0 | x | x | x | x |  |
| 2 | Bangkok | 48455 | 13º 43' 36" | 100º 33' 38" | 3.0 | x | x | x | x |  |
| 3 | Chiang Mai | 48327 | 18º 46' 14" | 98º 58' 06" | 313.0 | x | x | x | x |  |
| 4 | Phitsanulok | 48378 | 16º 47' 46" | 100º 16' 33" | 44.0 | x | x | x | x |  |
| 5 | Nakhon Sawan | 48400 | 15º 40' 19" | 100º 17' 57" | 34.0 | x | x | x | x |  |
| 6 | Phuket Airport | 48565 | 08º 08' 42" | 98º 18' 52" | 6.0 | x | x | x | x |  |
| 7 | Prachuap Khirikhun | 48500 | 11º 50' 06" | 99º 48' 37" | 4.0 | x | x | x | x |  |
| 8 | Songkhla | 48568 | 07º 10' 55" | 100º 36' 27" | 5.0 | x | x | x | x |  |
| 9 | Ubonrachathani | 48407 | 15º 15' 00" | 104º 52' 00" | 122.0 | x | x | x | x |  |
| 10 | Udonthani | 48354 | 17º 22' 37" | 102º 48' 34" | 177.0 | x | x | x | x |  |
| 11 | Kanchanaburi | 48450 | 14º 01' 21" | 99º 32' 9" | 27.5 | x | x | x | x |  |
| 12 | Chiang Rai | 48403 | 19º 57' 41" | 99º 52' 53" | 387.8 |  | x | x | x |  |
| 13 | Sukhothai | 48372 | 17º 06' 22" | 99º 48' 00" | 48.3 |  | x | x | x |  |
| 14 | Khonkaen | 48381 | 16º 27' 48" | 102º 49' 00" | 187.0 |  | x | x | x |  |
| 15 | Nakhonratchasima | 48431 | 14º 57' 46" | 102º 04' 36" | 186.6 |  | x | x | x |  |
| 16 | Chumphon | 48517 | 10º 29' 00" | 99º 11' 00" | 4.4 |  | x | x | x |  |

Annex B

The list of Deterministic NWP and Ensemble Products to be made available to IMD

New Delhi by Global Centres

B.1:	Deterministic NWP Products

(All product is provided every 6-hourly out to 72 hours including Analysis)

| Parameters | ECMWF | JMA | NCMRWF | CMA | KMA |
| --- | --- | --- | --- | --- | --- |
| Every 6 hours and 24 hours total accumulated precipitation | YES | YES (6 hrs & 12 hrs) | YES | YES |  |
| 2 meters temperature and dew point temperature | YES (2m T) | YES (2m T) | YES | YES |  |
| 2 meters relative humidity or specific humidity | NO | YES | YES | YES |  |
| 10 meters wind (speed and direction) | YES | YES | YES | YES |  |
| Mean sea level pressure (MSLP) | YES | YES | YES | YES |  |
| Parameters: wind (streamlines and speed/direction), temperature, geopotential height, humidity Levels:1000mb,925mb, 850mb, 700mb, 500mb, 300mb, 200mb, 200mb | YES | YES (except for 1000mb) | YES | YES |  |
| Parameter: vorticity Level: 850mb, 700mb, 500mb, 300mb | YES (500mb & 300mb) | YES (500mb & 300mb) | YES (200mb in place of 300mb) | YES |  |
| Parameter: divergence Level: 500mb, 300mb, 200mb | NO | NO | YES | YES |  |
| Parameter: vertical velocity Level: 850mb, 700mb, 500mb | YES | YES | YES | YES |  |
| Parameter: potential temperature and/or equivalent potential temperature Level: 850mb, 700mb | YES (850hPa) | YES (850hPa) | Yes (850hPa) | YES |  |
| Parameter: Vertical Wind Shear 500-850 hPa, 200-850 hPa | NO | NO | YES (200-850 hPa) | NO |  |
| Parameter: lifted index, K index, total totals index, CAPE, CIN, Showalter index, etc. | CAPE only | K index, CAPE, CIN | YES (except Showalter index) | YES |  |
| SKEW-T logarithmic forecast plots for selected grid points based on NWP output (out to 144 hours, 12-hourly) | NO | NO | YES | NO |  |

B.2: Ensemble NWP Products

| Parameters | ECMWF | JMA | NCMRWF | CMA | KMA |
| --- | --- | --- | --- | --- | --- |
| Probability of 6-hour accumulated precipitation exceeding 50mm and 100mm threshold value | YES (50mm) | YES | YES | YES |  |
| Probability of 24-hour accumulated precipitation exceeding 100mm threshold value | YES | YES | YES | YES |  |
| Probability of 10-meter wind speed exceeding 20kt and 30kt threshold value | YES | YES | YES | YES |  |
| Probability of significant wave height exceeding 2 m, 4 m and 6 m threshold value | YES | YES | YES | NO |  |
| Probability of mean wave period exceeding 10 s and 15 s threshold value | YES | YES | YES | NO |  |
| Ensemble Prediction System meteograms for specified locations (10- day/ 15-day) | YES | YES (11-day) | YES (10-day) | YES |  |
| Spaghetti diagrams for 500mb geopotential height | NO | YES | YES | YES |  |
| Thumbnails of probability of precipitation in excess of threshold of 50mm/6h at 6 hours intervals or more | NO | YES | YES | NO |  |
| ECMWF Extreme Forecast Index and Shift of Tails, and M-Climate for TMean, Tmax, Tmin, wind gust, wind speed, total precipitation, Max significant wave height, total snowfall | YES | NO | NO | NO |  |
| ENS Cumulative Distribution Functions (Forecast and M-Climate) and EFI values (for precipitation | YES | NO | NO | NO |  |
| MJO Index - Extended range forecast | YES | NO | YES | NO |  |
| Tropical cyclone occurrence and genesis probability maps- including extended range forecast | YES | NO | YES | NO |  |
| Tropical cyclone strike probability maps | YES | NO | YES | NO |  |
| Tropical cyclone forecast tracks from ensemble members, including ensemble mean, deterministic and control tracks | YES | NO | YES | NO |  |
| Tropical Cyclone Lagrangian meteograms (ECMWF) | YES | NO | NO | NO |  |

Annex C

The List of Deterministic Global and Regional NWP Products to be available from IMD New Delhi

(All product is provided every 6-hourly out to 72 hours including Analysis)

| Parameters | IMD GFS T1534 | IMD WRF (ARW) | HWRF |
| --- | --- | --- | --- |
| Every 6 hours and 24 hours total accumulated precipitation | YES | YES | YES |
| 2 meters temperature and dew point temperature | YES | YES | YES |
| 2 meters relative humidity or specific humidity | YES | YES | YES |
| 10 meters wind (speed and direction) | YES | YES | YES |
| Mean sea level pressure (MSLP) | YES | YES | YES |
| Parameters: wind (streamlines and speed/direction), temperature, geopotential height, humidity Levels: 1000mb, 925mb, 850mb, 700mb, 500mb, 300mb, 200mb, 200mb | YES | YES | YES |
| Parameter: vorticity Level: 850mb, 700mb, 500mb, 300mb | YES | YES | YES |
| Parameter: divergence Level: 500mb, 300mb, 200mb | YES | YES | YES |
| Parameter: vertical velocity Level: 850mb, 700mb, 500mb | YES | YES | YES |
| Parameter: potential temperature and equivalent potential temperature Level: 850mb, 700mb | YES | YES | YES |
| Parameter: lifted index, K index, total totals index, CAPE, CIN, Showalter index, etc. | YES | YES | YES |
| SKEW-T logarithmic forecast plots for selected grid points based on NWP output (out to 144 hours, 12-hourly) | YES | YES | YES |

Special NWP Products for Cyclone: (a) Genesis Potential Parameter based on GFS T-574,(b) MME based Cyclone Track and (c) Cyclone intensity prediction based on a dynamical statistical HWRF Model.

Wave model products: Indian National Centre for Ocean Information Services (INCOIS) are available in IMD website (cyclone page) through a link to INCOIS website.

Storm surge forecast from RSMC, New Delhi Tropical Cyclone based on IIT-Delhi model and INCOIS, Hyderabad Coastal Inundation Model.

Annex D

Tropical cyclones bulletins and products available from RSMC-TC, New Delhi through GTS, AFTN and IMD website

The information provided by RSMC, New Delhi includes the products and bulletins as mentioned in the following Table 1.

Table 1. Tropical cyclone information, bulletin and product from IMD

| Bulletins/ Products | Mode of dissemination | Frequency and time of issue | Content |
| --- | --- | --- | --- |
| Tropical Weather Outlook | GTS, website | Once a day at 0600 UTC based on 0300 UTC | - Description of convection - Location of low pressure area (one closed isobar with maximum sustained wind (MSW) speed of less than 17 knots) - Large scale environmental features including location of upper tropospheric ridge etc. |
| Special Tropical Weather Outlook | GTS, Website | Twice a day at 0600 and 1500 UTC based on 0300 and 1200 UTC respectively when there is a depression/deep depression (17-33 knots) It is issued more frequently as and when required. | - Current position and intensity, estimated central pressure and maximum sustained surface wind (MSW) - Past movement - Quantitative Forecast track and intensity upto 120 hrs from deep depression stage onwards (+6, +12, +18, +24, +30, +36, +42, +48, +54, +60, +66, +72, 78, +84, +90, +96, +102, +108, +114, +120 hrs). - Description of associated convection, T number based on INSAT-3D/Kalpana, Cloud top temperature, pattern of convection - Sea condition - Significant observational data, if any. - Prognostic and diagnostic features including SST, Ocean heat content, lower level convergence, lower level vorticity, upper level divergence, vertical wind shear, wind shear tendency, phase and amplitude of MJO index, any other synoptic features and NWP model guidance etc. |
| Tropical Cyclone Advisory bulletin | GTS, Website | 8 times a day based on 00, 03, 06, 09, 12, 15, 18 and 21 UTC observation | - Current position and intensity, estimated central pressure and maximum sustained surface wind (MSW) - Past movement - Quantitative Forecast track and intensity upto 120 hrs from deep depression stage onwards (+6, +12, +18, +24, +30, +36, +42, +48, +54, +60, +66, +72, 78, +84, +90, +96, +102, +108, +114, +120 hrs). - Description of associated convection, T number based on INSAT-3D/Kalpana, Cloud top temperature, pattern of convection. - Sea condition - Significant observational data, if any. - Storm surge guidance, as and when necessary - Prognostic and diagnostic features including SST, Ocean heat content, lower level convergence, lower level vorticity, upper level divergence, vertical wind shear, wind shear tendency, phase and amplitude of MJO index, any other synoptic features and NWP model guidance etc. |
| Cone of uncertainty | Web site | 4 times a day based on 00, 06, 12 and 18 UTC from deep depression stage onwards | - Given in graphical form along with track forecast |
| Quadrant wind forecast | GTS, Website | 4 times a day based on 00, 06, 12 and 18 UTC from deep depression stage onwards | - Radius of 28, 34, 50 and 64 knots forecast winds in four quadrants upto 120 hrs (+6, +12, +18, +24, +30, +36, +42, +48, +54, +60, +66, +72, 78, +84, +90, +96, +102, +108, +114, +120 hrs). - The product is available in both text and graphics form |
| Tropical cyclone advisory bulletin for SIGMET | GTS/AFTN | 4 times a day based on 00, 06, 12 and 18 UTC from cyclonic storm (MSW of 34 knots or more) stage onwards | - Current position and intensity, estimated central pressure and maximum sustained surface wind (MSW) - Past movement (direction and speed) - Forecast location and intensity upto 24 hrs (+6, +12, +18, +24 hrs). - In addition, there is advisory graphics in PNG format for transmission. - The TCAC bulletin is also sent to WMO’s, ADRR (Aviation-weather Disaster Risk Reduction) at Hong Kong through ftp. |
| Tropical cyclone warnings for the high seas | INMARSAT safety system, Website | Twice daily, thrice during depression and six times during cyclone | (a) Type of warning and name of the centre (b) Name of the system (c) Date and time of reference in UTC (d) Type of disturbance (depression, cyclonic storm, etc.); (e) Location in terms of latitude and longitude or with reference to well-known landmarks (f) Direction and speed of movement of the disturbance (g) Extent of affected area (h) Wind speed or force and direction in the affected areas (i) Sea and swell condition in affected areas (in qualitative terms) (j) Other important information such as future position of disturbances Items (a), (b), (c), (d), (e), (f), (g) and (h) listed above are always included in the warning bulletins. |
| Satellite bulletin | GTS, Website | 8 times a day based on 00, 03, 06, 09, 12, 15, 18 and 21 UTC observation | - Centre position - Intensity (T /CI number) - Cloud description (area coverage and intensity of convection - Pattern based on Dvorak’s technique - Cloud top temperature - Characteristics of eye, if any - Environmental features based on satellite observation |
| Satellite imagery of cyclone | Website | Every half hourly | - VIS, IR, WV and colour composite imageries - Cyclone specific imageries |
| INSAT-3D Satellite derived products |  | Every three hourly | - Derived products including cloud top temperature, upper tropospheric humidity, sea surface temperature, quantitative precipitation estimate, Outgoing longwave radiation, Cloud motion vectors, water vapour wind vectors etc. - Special products : snow, fog, aerosol, smoke, cloud mask, fire |
| NOAA and MODIS satellite products | Website |  | - The satellite imageries and products based on NOAA and MODIS satellites are available |
| NWP products | Website | Twice dailly based on 00 and 12 UTC | - Model output of GFS(T574L64) (upto 7 days) and WRF model (upto 3 days) - Genesis potential based on IMD GFS Model - Multi-model ensemble (MME) product twice daily (00 UTC, 12 UTC) for prediction of track of cyclone upto 120 hrs - Intensity prediction by SCIP model upto 120 hrs - Probability of rapid intensification - Decay after landfall (+6, +12, +18, +24 hrs). - Track and intensity prediction by HWRF model upto 120 hrs - Track forecast by EPS - Cyclone Strike Probability, based on ensemble technique - INCOIS, Hyderabad storm surge and coastal inundation guidance. - IIT Delhi Storm Surge Model Guidance |
| Preliminary reports | Website | Within a week after the dissipation of the low pressure system | - Salient features, - Life history (genesis, intensification, movement), - Satellite and radar observed features, - Associated adverse weather, - Damage, if any, - Performance of RSMC (statistics of bulletin issued and verification of forecast and warning) |
| RSMC tropical cyclone best track | website | Once a year during March | - Date and time - Centre location - Intensity category - MSW - Estimated central pressure - Pressure drop at the centre - CI number |

Explanatory notes:

- Tropical weather outlook

The tropical weather outlook is prepared once daily by RSMC tropical cyclones, New Delhi throughout the year. It is transmitted on the GTS at 06 UTC every day. The outlook covering the North Indian Ocean indicates possible development of tropical depressions over the sea.

- Special Tropical Weather Outlook

Special Tropical Weather outlook is transmitted on the GTS at 0600 UTC and 1500 UTC when a depression is located over the north Indian Ocean region. The additional bulletin will be issued as and when felt necessary by RSMC, New Delhi.

The special tropical weather outlook issued in association with the depression provides brief descriptions of tropical depressions affecting the area. It will give the location, intensity and movement of the system as well as a general statement of land areas coming under threat. It will also contain description of the convective clouds in satellite imageries and diagnostic & prognostic features of the system. When the depression intensifies into a deep depression, the special tropical weather outlook issued twice a day based on 0300 and 1200 UTC observation will in addition contain the 120 hrs forecast track and intensity of the system in a tabular form. These track and intensity forecasts are issued for (+6, +12, +18, +24, +36, +48, +60, +72, 78, +84, +90, +96, +102, +108, +114, +120 hrs.

- Tropical cyclone advisories

When a tropical low pressure system reaches the cyclonic storm stage, or is shortly expected to reach that intensity, RSMC tropical cyclones, New Delhi will issue tropical cyclone advisories. Advisories are issued at 00, 03, 06, 09, 12, 15, 18 and 21 UTC. The area of responsibility for the issue of tropical cyclone advisories by RSMC Tropical Cyclones, New Delhi covers sea areas of north Indian Ocean between long. 45° E to 100° E. Supplementary advisories may be issued as necessitated by circumstances, e.g., change in intensity or movement.

Tropical cyclone advisories contain the information of tropical cyclone, name of the cyclone, the present location, intensity and movement (present and past twelve hours) of the storm, and its forecast position, movement, intensity, maximum average surface wind speed with highest gust wind speed and sea conditions (in qualitative terms). These track and intensity forecasts are issued for (+6, +12, +18, +24, +36, +48, +60, +72, 78, +84, +90, +96, +102, +108, +114, +120 hrs. It also contains description of the convection as seen in satellite imageries and brief description of the diagnosis and prognosis of the system. The bulletin contains the storm surge guidance based on IIT, Delhi Storm Surge prediction model in case of the cyclone land falling over any member countries. Important information obtained from radar, synoptic, ship observations from the affected areas will also be reported in the advisory bulletin.

Advisories are exchanged under appropriate headings for regional distribution by RTH, New Delhi on the GTS.

- Tropical cyclone warnings for the high seas

The World Meteorological Organization (WMO) in its Manual on Marine Meteorological Services has recommended the issue of weather and sea bulletins for the high seas in six parts. The cyclone warning centres of India issuing forecasts and warnings for the benefit of the ships on the high seas, area covered by these stations in their bulletins, name of the coastal radio stations with their call signs from where the tropical cyclone warnings are broadcast, are given in Table 2.

Table 2. Stations issuing cyclone warnings for ships on the high seas

Station				Area covered

India,  Mumbai			Arabian Sea north of Lat. 5oN and east of Long. 60oE excluding the area north of Lat. 20oN and west of Long. 68oE. The  eastern boundary of the Arabian Sea for which these bulletins are issued by Mumbai is Long. 80oE meridian excluding the Gulf of Mannar.

India, Kolkata			Bay of Bengal north of Lat. 5oN except the area between the coastline on the east and the line drawn through the points 18oN 94.5oE, 18oN 92oE, 13.5oN 92oE, 13.5oN 94oE, 10oN 94oE, 10oN 95oE and 5oN 95oE. The western boundary of the sea area for which bulletins are issued by Kolkata is up to and inclusive of the Gulf of Mannar (i.e., 77.5oE meridian).

India, Chennai			Bay of Bengal bulletins issued by ACWC Kolkata are being broadcast through Navtex, Chennai by Narrow Band Direct Printing ( NBDP )

Under the new Marine Meteorological Broadcast system, GMDSS (Global Marine Distress Safety System) of IMO/WMO, India issues two bulletins at 0900 and 1800 UTC everyday for broadcast through INMARSAT SAFETY SYSTEM. Additional bulletins are broadcast during Cyclone period.

- Warnings and advisories for aviation

In accordance with the International Civil Aviation Organization (ICAO) Annex 3 — Meteorological Service for International Air Navigation/ WMO Technical Regulations [C.3.1], tropical cyclone warnings, required for the international air navigation, are issued by designated meteorological watch offices (MWO) as SIGMET messages * , including an outlook, giving information for up to 24 hours ahead concerning the expected positions and maximum surface wind of the centre of the tropical cyclone. Each MWO provides information for one or more specified Flight Information Regions (FIRs) or Upper Information Regions (UIRs). The boundaries of the FIRs/UIRs are defined in ICAO Air Navigation Plans (ANP) for the Asia (ASIA), Middle East (MID) and Pacific (PAC) Regions.

The content and order of elements in a SIGMET message for tropical cyclone are in accordance with WMO Technical Regulations [C.3.1]. The data type designator to be included in the WMO abbreviated header of such messages shall be T1T 2 = WC (WMO No. 386, Manual on GTS refers).

The designated Tropical Cyclone Advisory Centre (TCAC), New Delhi monitors the development of tropical cyclones in its area of responsibility, in accordance with the ASIA/PAC ANP and issue advisory information concerning the positions of the centre of the cyclone, its direction and speed of movement, central pressure and maximum surface wind near the centre. These advisories are disseminated to the MWOs in the TCAC New Delhi area of responsibility, to be used in the preparation of the OUTLOOK appended to SIGMETs for tropical cyclones. In addition, the tropical cyclone advisories are disseminated to the other TCACs, whose areas of responsibility may be affected, to the World Area Forecast Centers (WAFC) London and Washington and international OPMET data banks and centers operating the satellite distribution systems (SADIS and ISCS).

- Observational data provided through GTS

- All the observational data including SYNOP, AWS, PILOT, TEMP, SHIP, BUOY data are made available through GTS.

- Many of these including current weather observation and upper air data of Indian stations are also available in IMD website (www.imd.gov.in)

Annex E

Warning Hazards and Thresholds Applicable to the RSMC Daily Regional Guidance Products

A representative list of severe weather hazards and the relevant thresholds will be used to prepare guidance products for all areas in SWFDP-South Asia region by the RSMC New Delhi.  This does NOT imply that local, in country, warning systems must use the same thresholds for an NMHS to issue warnings.  Each country has its own thresholds based on good, historical reasons.  However, the guidance forecasts will use a representative threshold for each hazard designed in such a way that it will draw the attention of forecasters of all NMHSs to potential hazards threatening their region.  This will help the NMHS to decide if the threat is real and monitor it for proper advisory or warning actions as determined in their particular countries. During the demonstration phase of SWFDP-South Asia, only two hazards (heavy rain and strong winds) shall be monitored.

The meteorological hazards of concern in this region are those for which NMHSs issue warnings to the public at large.  This approach recognizes the decisions by governments, through their respective NMHSs, to have set threshold criteria for official weather warnings.  At the same time, it is recognized that some other meteorological phenomena could have significant impact on the public, such as heat waves or rapid temperature changes.  There are also some hazardous phenomena for which there is presently no methodology for supporting a Regional Guidance by RSMC New Delhi.

The hazards for the SWFDP that will be monitored by RSMC New Delhi for a lead time up to 5 days and included in the guidance products are listed here with related thresholds.  Conditions associated with tropical cyclones/typhoons (heavy rain, strong wind, high seas) expected to impact land areas will indicate the tropical cyclone association using the forecast and advisories issued by RSMC New Delhi separately.

| HAZARD | THRESHOLD | COMMENTS |
| --- | --- | --- |
| Heavy Rain | ≥ 50 mm in 24 hours ≥ 100 mm in 24 hours (the risk over 200mm/24 should be described in discussion in the Regional Guidance) | The operational country-thresholds may differ widely among participating countries of SWFDP-South Asia. NMHSs may translate the heavy rain into potential flooding in areas likely to be affected by heavy rain depending upon the soil condition, topography and drainage systems in respective areas |
| Strong winds | ≥ 17 knots (over land and Sea) ≥ 34 knots (over Sea) | Affecting oceanic and coastal areas especially. Gusts on land from severe convective systems are not predictable on this time scale effectively |
| High Waves | ≥ 2.5 m | NMHSs may use the information contained in the RSMC Guidance Product to generate impact-based forecasts and risk-based warnings for use by the coastal communities, fisheries, disaster managers etc. at national levels. |
| Storm Surge | ≥ 1m |  |

ANNEX F

Template of Daily Regional Severe Weather Forecast Guidance to be issued by RSMC New Delhi towards the NMCs/NMHSs

F.1	Guidance for Short Range up to 48 Hours (for Day 1 and 2)

The Daily Regional Guidance to be issued by the RSMC New Delhi toward the NMHSs for Short Range Severe Weather Forecasting up to 48 Hours (for Day 1 and Day 2) comprises five parts:

- Part A: Text; depiction of the expected evolution of the weather up to 48 h (for Day 1 and Day 2) and comments about the more representative short range products that are used with reference to figures included in the part B or to charts clearly identified (model, parameter, level, forecast range).

- Part B: Figures; Charts or graphics coming essentially from deterministic models (global or LAM).

- Part C: The assessment of the degree of confidence of the forecast by the forecaster.

- Part D: Two tables (for Day1 and Day 2, respectively), summarizing the risk of severe weather as assessed by the RSMC New Delhi based on its degree of confidence as proposed below. In order to provide more information about the geographical location of the severe event, the following convention can be adopted when filling in the cells: X for the whole country, N for the northern part, S for the southern part, W for the western part and E for the eastern part. C for the central part can also be used if so required. Similarly, NE for the northeastern part and SW for the southwestern part etc.

- Part E: Two geographical maps (Day 1 and Day 2, respectively) including the boundaries of the countries with contours identifying the areas which are likely to be hit by the severe weather event.

An example of table (as mentioned in Part D above) is given  below just for example as it has to be definitively defined by the RSMC New Delhi (number of columns, potential risks etc.)

| Country | Severe Weather type | No risk | Low risk | Medium risk |
| --- | --- | --- | --- | --- |
| Bangladesh | Heavy Precipitation > 50mm/24h | SE |  |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Bhutan | Heavy Precipitation > 50mm/24h |  | X |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| India | Heavy Precipitation > 50mm/24h | C |  |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Maldives | Heavy Precipitation > 50mm/24h |  |  |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Myanmar | Heavy Precipitation > 50mm/24h |  |  | W |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Nepal | Heavy Precipitation > 50mm/24h |  |  | W |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Pakistan | Heavy Precipitation > 50mm/24h |  | NE |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Sri Lanka | Heavy Precipitation > 50mm/24h | SE |  |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Thailand | Heavy Precipitation > 50mm/24h | SW |  |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |

F.2	Guidance for Medium Range (for Day 3, Day 4 and Day 5)

The Daily Regional Guidance to be issued by RSMC New Delhi toward the NMHSs for Medium Range Severe Weather Outlook (for Day 3, Day 4 and Day 5) comprises five parts:

- Part A: Text; depiction of the expected evolution of the weather for Day 3, Day 4 and Day 5 and comments about the more representative medium range products that are used with reference to figures included in the part B or to graphics clearly identified (EPS charts or meteograms).

- Part B: Figures; Charts or graphics coming essentially from Ensemble Prediction Systems (EPS).

- Part C: The assessment of the degree of confidence of the forecast by the forecaster.

- Part D: Three tables (for Day 3, Day 4 and Day 5, respectively), summarizing the probabilities of precipitation and wind higher than a given threshold by the RSMC New Delhi as proposed below. In order to provide more information about the geographical location of the severe event the following convention can be adopted when filling in the cells: X for the whole country, N for the northern part, S for the southern part, W for the western part and E for the eastern part. C for the central part can also be used if so required. Similarly, NE for the northeastern part and SW for the southwestern part etc.

- Part E: Three geographical maps (for Day 3, Day 4 and Day 5, respectively) including the boundaries of the countries with contours identifying the probabilities areas for the occurrence of the weather event.

An example of table (as mentioned in Part D above) is given  below just for example as it has to be definitively defined by the RSMC New Delhi (number of columns, lower and upper limits of probabilities etc.)

| Country | Severe Weather type and threshold value | Low Probability | Medium Probability | High Probability |
| --- | --- | --- | --- | --- |
| Bangladesh | Heavy Precipitation > 50mm/24h | SE |  |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Bhutan | Heavy Precipitation > 50mm/24h |  | X |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| India | Heavy Precipitation > 50mm/24h | C |  |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Maldives | Heavy Precipitation > 50mm/24h |  |  |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Myanmar | Heavy Precipitation > 50mm/24h |  |  | W |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Nepal | Heavy Precipitation > 50mm/24h |  |  | W |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Pakistan | Heavy Precipitation > 50mm/24h |  | NE |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Sri Lanka | Heavy Precipitation > 50mm/24h | SE |  |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |
| Thailand | Heavy Precipitation > 50mm/24h | SW |  |  |
|  | Heavy Precipitation > 100mm/24h |  |  |  |
|  | Strong Winds >17 Knots |  |  |  |
|  | Strong Winds >34 Knots |  |  |  |

Annex G

The Implementation Status of Impact-based Forecast and Warning Services (IBFWS) in SWFDP countries in South Asia

| Member country Vs. IBFWS Training events | IBFWS 2015 | 1st WMO/ KMA IBFWS Workshop, Rep. Korea 7-9 Nov 2017 | 2nd WMO/ KMA IBFWS Workshop, Rep. Korea 19-21 Nov 2018 | SWFDP-BoB Regional Training Workshop on Severe Weather and IBFWS, Sri Lanka 6-8 Dec 2018 | IBFWS Implement. status | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Bangladesh |  |  |  |  |  |  |
| Bhutan |  |  |  |  | No IBFWS in Bhutan yet | It will be discussed with senior officials |
| India |  |  |  |  | IBFWS has been implemented partially | Currently, IBFWS is implemented for tropical cyclone and associated hazards including storm surge and strong winds. For Thunderstorm, IBFWS will be implemented from next Pre-monsoon season in 2019. Color coded warnings are issued for other hazards. |
| Maldives | - In-country workshop |  |  |  | No IBFWS in Maldives yet |  |
| Myanmar | - In-country Pilot Project |  |  |  | No IBFWS in Myanmar yet | Only color-coded warnings are issued. |
| Nepal |  |  |  |  | No IBFWS in Nepal yet | It will be initiated after discussion with senior officials |
| Pakistan |  |  |  |  |  |  |
| Sri Lanka |  |  |  |  | IBFWS has been implemented partially in Sri Lanka | Currently, IBFWS is implemented for tropical cyclone (and associated hazards only e.g. storm surge and strong winds), thunderstorms and heat waves. |
| Thailand |  |  |  |  | No IBFWS in Thailand yet? | A color-coded MetAlarm system is in place. Process to implement IBFWS has been initiated |

Annex H

# Template of Severe Weather Event Evaluation Form

The proposed evaluation form should allow to evaluate the performance of the RSMC Severe Weather Forecasting Guidance and as well as the efficiency of the NMHS warning system.  It must be completed by the NMHS in both of the following cases:

- a severe weather event has been observed; and

- a severe weather event has been forecast.

The evaluation form should document the characteristics of the severe weather event (whether observed or forecast) and allow evaluating the efficiency of the forecasts given by the RSMC Daily Severe Weather Forecasting Guidance as well as the performance of the warnings issued by the NMHS. Therefore it should include the three following sections.

Section A – Identification of the severe weather event:

- NMHS concerned;

- number of the event;

- type of event;

- region affected.

##### Section B – Information about the observed weather event:

- start and end times of the severe weather event;

- maximum observed value of the characteristic parameter;

- assessment about the efficiency of the warning given to the DMCPA;

- information from the end-users (number of interventions, casualties, damages, usefulness of the warning).

##### Section C – Information about the forecast and warning issued from the NMHS:

- lead-time of the warning;

- start and end time of the severe weather event according to the forecaster’s assessment;

- level of risk as indicated in the RSMC Severe Weather Forecasting Daily Guidance;

- probabilities of medium-range in the RSMC Severe Weather Forecasting Daily Guidance;

- usefulness of the various products (RSMC Guidance, various models);

- comments including information on usefulness and applicability of used tools.

How to use this evaluation form to evaluate the performance of warnings?

The common way to evaluate the performance of a warning system is based on the 2 x 2 contingency table matrix including the number of justified warnings (“hits”) “a”, the number of missed severe events “b” and the number of false alarms “c”. The POD index (Probability of Detection) is defined as the ratio of the number of hits by the total number of severe events, i.e., a/(a+b) ; the FAR (False Alarm Ratio) is defined as the ratio of the number of false alarms by the number warnings issued, i.e., c/(a+c).The information contained in the proposed evaluation form enables to computes the performance indicators of the warning issued by the NMHS as long as the assessment of the DMCPA (in section C) is correctly taken into consideration.

A template of an evaluation form is provided in the following pages.  The evaluation form is to be filled by the NMHSs (preferably by a forecaster or manager of the forecasting unit) participating to the SWFDP regional subproject.  This template can be modified with respect to the products selected for preparing the severe weather forecasts and warnings. It is important that the design of the evaluation form be adapted to allow the data and information to be easily gathered and transformed into a tabular form.  Avoid unnecessary and repetitive typing, and as much as possible to encourage and allow reliable creation and maintenance of the dataset that is needed to analyze and evaluate the performance indicators.

Annex I

Summary of Procedure for Verifying Forecasts and Warnings using Contingency Tables by NMCs/NMHSs

1. Verification of Forecasts & Warnings Issued By NMCs/NMHSs.

1.1. MATCHING FORECASTS AND OBSERVATIONS

- Each individual warning defines the predicted event, and should include the threshold (e.g. >50 mm rain), the valid period (e.g. 24 h from 06 to 06 UTC), and the location(s) for which it is valid.

- If a severe event is reported within the time range and within the location range specified by the warning, then a hit is registered. (Fcst=Obs=Yes)

- If more than one severe event is reported, both inside and outside the warning area and/or time range then two events are defined, a missed event and a hit, and each is given a weight of 0.5.

- If no event is reported during the valid period and valid area of the warning, then a false alarm is registered. NMSs should make every effort to determine unambiguously whether or not forecast severe weather occurs within the valid space and time range, so that missing observations are not recorded as negatives. (Fcst=Yes; Obs=No)

- If an event is reported, and there is no valid warning in force, then a missed event is recorded. (Fcst=No; Obs=Yes)

- Any inactive day is recorded as a single correct negative (Fcst=Obs=No)

1.2. SETTING UP THE TABLE

Data can be set up by means of an Excel (or other format) as in the example

below. If there is more than one warning issued on a given day, each warning

is considered and verified as a separate event.

| Date | Event | Fcst to occur? | Observed? |
| --- | --- | --- | --- |
|  | 1 | Yes | Yes |
|  | 2 | No | Yes |
|  | 3 | No | No |
|  | 4 | Yes | No |
|  | 5 | No | No |
|  | 6 | Yes | Yes |
|  | 7 | No | No |
|  | 8 | No | Yes |
|  | 9 | No | No |
|  | Etc. |  |  |

In the data table “1” can be used for “yes” and “0” for no. Once the data table

is constructed, the four boxes of the contingency table can be tallied.

The table should include the marginal sums of forecast and observed events,

and the total events in the sample.

| Event Forecast | Event Observed |  | Marginal Totals |
| --- | --- | --- | --- |
|  | Yes | No |  |
| Yes | Hits a | False Alarms b | Total events Fcst = a+b |
| No | Misses c | Correct Negatives d | Total non-events Fcst = c+d |
| Marginal Totals | Total events observed = a+c | Total non-events observed = b+d | Total sample size = a+b+c+d |

As a minimum, the table should be computed for categorical forecasts. Where probabilistic or “risk” information is forecast, then separate tables can be computed from the same dataset, considering each level of risk as a separate threshold for a categorical prediction.

Different forecast “events” (precipitation >50 mm/24h; wind speed >17 Kt etc.) should

be verified using separate tables. Even if the sample is small, the tables and their statistics can be computed. Tables need not be computed if the aggregated total number of occurrences or warnings issued is fewer than 5. However, tables should be updated from the previous quarter and reported whenever any warnings are issued or any severe events are observed.

The following scores should be computed from the contingency tables:

- Probability of Detection (POD or Hit rate) [POD or Hit rate = a/(a+c)]

- False Alarm Ratio (FAR) [FAR = b/(a+b)]

- Critical Success Index (CSI) or Threat Score (TS) [TS = a/(a+b+c)]

- Frequency Bias (FBI) [FBI = (a+b)/(a+c)]

And, optionally,

- Heidke Skill Score (HSS) [HSS = 2(ad-bc)/{(a+c)(c+d)+(a+b)(b+d)}]

- Extreme Dependency Score (EDS) [EDS = {log p – log H}/{ log p + log H}]

Where p = (a+c)/(a+b+c+d)

& H is Hit rate = a/(a+c)

More information on forecast verification including explanation and equations for all these scores is available from the website:

https://www.met-learning.eu/course/view.php?id=96

1.3. REPORTING

The contingency tables will be useful when submitting Quarterly Progress Report through SWFDP database during demonstration phase. The data period should start when forecast and observation data were first archived, and the tables should be aggregated over one year, updated for inclusion in each quarterly report.

2. Verification of graphical Guidance Products from RSMC New Delhi, using the Hydro Estimator data

The RSMC New Delhi heavy precipitation guidance products can also be verified graphically, and manually, using the Hydro Estimator (HE) data. However, it should be remembered at all times that these data are not true observations, but estimates based on a combination of satellite data and estimated parameters from the NWP model. Their use as “observations” is warranted due to the lack of traditional station observations. Wherever precipitation observations can be obtained, these should also be used to “ground-truth” the satellite-based estimates.

Areas on the forecast maps should be matched to areas on the HE maps following the schematic below. This should be accomplished by overlaying a grid of equal-area rectangles, and counting the number of rectangles which represent false alarms, hits and misses. This process will be easiest if either the forecast maps or the observation maps are remapped to match the other. Correct negatives need not be calculated. Totals of the boxes should be added over all days of the verification, separately for forecast projections of day 1 to 5, to form contingency tables as above, leaving “correct negatives” blank. Then, the following scores should be computed:

- Probability of Detection (Hit rate)

- False Alarm Rate (FAR)

- Critical Success Index (CSI) or Threat Score (TS).

Optionally, correct negatives could be computed as the total number of boxes in the domain (constant) minus the total number covered by severe weather forecasts and/or observations, and a full table computed. Then, following could be computed:

- Frequency Bias (FBI) and

- Heidke Skill Score (HSS),

The usefulness of the probabilistic information can be evaluated by stratifying the forecasts by level of risk, and computing separate tables for “high risk”, “at least moderate risk” (moderate +high), and “at least low risk” (low + moderate+ high), calculating Hit Rate, and False Alarm Rate (=b/(b+d)) and plotting them as demonstrated during the SWFDP training workshops. This is also optional, though would not involve much additional work once the tables are generated. These results should be aggregated over a year and it may also be reported as part of quarterly reports.

Annex J

Key Elements of SWFDP Quarterly Progress Report

(Quarterly Progress Reports are to be submitted by NMCs/NMHSs on-line through SWFDP database https://www.wmo.int/cpdb/login )

- Reporting Period (Start date to end date)

- Severe events (e.g. heavy rainfall, strong winds, high waves, flooding etc.)

- Reporting period highlights (e.g. duration and amount of rainfall, impact of rainfall and/or strong wind and high waves, affected areas, damages (if any), coordination with disaster management offices etc.)

- Clients (e.g. Disaster Management Offices, media, humanitarian organizations etc. New clients can also be added)

- Client feedback (e.g. adequacy and effectiveness of the warning and how it was used etc.)

- Desired products (e.g. NMHS may propose a demand for additional product(s) from global and/or regional centres if already not available etc.)

- Forecast Period and Area (to provide information about area of responsibility of an NMHS and the period for which NMHS issues forecast etc.)

- Dissemination channels (e.g. TV, radio, mobile SMS etc. New channel can also added)

- Observing Systems (e.g. basic synoptic network, AWS network, radar and satellite information receiving stations etc.)

- Workshop (to provide title, duration and summary outcome of the training workshops arranged for the forecasters, emergency managers, media, school officials, general public etc. during the reporting period)

- Product usage (to select various products which are available from participating global and regional centres and are used in making forecasts at national level etc.)

- Local forecasting tools (to provide information about the existing forecasting tools used at the NMHS and any new forecasting tool implemented at the NMHS etc.)

- Resources (to provide information about the budget of NMHS and the number of forecasters and observers working in NMHS etc.)

- Case Studies (to provide title and description of case studies related to the severe event(s) observed during the reporting period, key findings of the study etc.)

- Related projects (to provide information about the on-going and new related projects etc.)

- PROJECT EVALUATION AGAINST SWFDP GOALS

| SWFDP GOAL | COMMENTS ON PROGRESS TOWARDS EACH GOAL | Questions to help you with an answer for each box |
| --- | --- | --- |
| To improve the ability of NMHSs to forecast severe weather events |  | How did the products on the RSMC New Delhi help you make better severe weather forecasts and warnings? |
| To improve the lead time of alerting these events |  | How much earlier do you issue severe weather forecasts & warnings now compared to before? |
| To improve the interaction of NMHSs with Disaster Management and Civil Protection authorities (DMCPAs), the media, and the public, before, during and after severe weather events |  | Comment on any interactions with your disaster agency, media agencies and the public. Please indicate if there hasn't been any interaction since the last repor,. |
| To identify gaps and areas for improvements |  | What are the weaknesses in your forecast system? |
| To improve the skill of products from Global Centres through feedback from NMHSs |  | What weaknesses have you found in the products from RSMC, New Delhi, JMA, NCEP, UKMO, ECMWFetc.? |

- EVALUATION OF PWS COMPONENT

| Users | Question | Answer | Comments |
| --- | --- | --- | --- |
| Public | Any feedback from the public? | Yes or No | If Yes, please give details. |
|  | Any public reaction when the warnings were heard or received? | Yes or No | If Yes, please give details. |
|  | Were there any difficulties in obtaining feedback? | Yes or No | If Yes, please give details. |
| Disaster Management | Any feedback from disaster management authorities about the timeliness and/or usefulness of the warnings | Yes or No | If Yes, please give details. |
|  | Were safety messages and/or call to action statements issued by the disaster management authority in agreement with your forecasts & warnings? | Yes or No | If Yes, please give details. |
| Media | Any feedback from the Media? | Yes or No | If Yes, please give details. |
|  | How did your relationship with the Media work in getting warnings delivered? | Yes or No | If Yes, please give details. |
|  | Were their difficulties in working with the Media? | Yes or No | If Yes, please give details. |

- SUMMARY (general comments, challenges, etc.)

- CASE STUDY (PowerPoint presentation to include guidance products (RSMC and NWP), satellite imagery, warnings issued, impact evidence etc.)

Case studies for each severe weather event DON'T need to be completed at the same time as the rest of this report.

Comment: Case studies don't need to be long. What's important is the learning experience that you gain from actually doing the case study.

- Severe Event Evaluation
(Attach all Severe Weather Event Evaluation Form)

Annex K

# USER ASSESSMENT QUESTIONNAIRE

## K.1 Evaluation Questionnaire for the Public

Q1.	Do you get the warnings and forecasts issued by the National Meteorological Service?

| Yes | No |
| --- | --- |
| □ | □ |

Q2.	Do the warnings and forecasts arrive early enough for you to take any actions?

| Yes | No |
| --- | --- |
| □ | □ |

Q3.	How Do you get the forecasts and warnings? (Can choose more than one)

| Radio | TV |  | Internet | Telephone | Local radio network | Other(s) |
| --- | --- | --- | --- | --- | --- | --- |
| □ | □ |  | □ | □ | □ | □ |

If other(s), please specify:

Q4.	Do you understand the warnings and forecasts?

| Yes | No |
| --- | --- |
| □ | □ |

Q5.	Do you take any action in response to the warnings and forecasts?

| Yes | No |
| --- | --- |
| □ | □ |

If yes, what did you do?

Q6.	The warning was useful to protect your (Can choose more than one)

| family | home | boat | farm | animals | other(s) |
| --- | --- | --- | --- | --- | --- |
| □ | □ | □ | □ | □ | □ |

If other(s), please specify:

Q7.	Are warnings issued by the National Meteorological Service correct?

| Yes | No | More or less |
| --- | --- | --- |
| □ | □ | □ |

Q8.	Are forecasts issued by the National Meteorological Service correct?

| Yes | No | More or less |
| --- | --- | --- |
| □ | □ | □ |

Name: 	   Date:

## K.2 Evaluation Questionnaire for Disaster Management

Q1.	Did you get the warnings for the severe weather events in the period…to….? (Specify)

| Yes | No |
| --- | --- |
| □ | □ |

Q2.	Did the warnings arrive early enough for you to take the necessary actions according to your specified responsibilities?

| Yes | No |
| --- | --- |
| □ | □ |

Q3.	How did you get the warnings? (Can choose more than one)

| Radio | TV | Fax | Internet | Telephone | Local radio network | Other(s) |
| --- | --- | --- | --- | --- | --- | --- |
| □ | □ | □ | □ | □ | □ | □ |

If other(s), please specify:

Q4.	Did you understand the warnings?

| Yes | No |
| --- | --- |
| □ | □ |

Q5.	Did you take any action in response to the warnings?

| Yes | No |
| --- | --- |
| □ | □ |

If yes, what did you do?

Q6.	In your opinion were the warnings correct?

| Yes | No | More or less |
| --- | --- | --- |
| □ | □ | □ |

Q7.	Do you have any suggestions on how to improve the warning process, including dissemination methods, format, language etc.

Post and name: 	   Date:

## K.3 Evaluation Questionnaire for Media

Q1.	Do you get the warnings for the severe weather events and forecasts from the National Meteorological Service?

| Yes | No |
| --- | --- |
| □ | □ |

Q2.	Do the warnings and forecasts arrive early enough for you to take the necessary actions according to your specified responsibilities?

| Yes | No |
| --- | --- |
| □ | □ |

Q3.	How do you get the warnings and forecasts? (Can choose more than one)

| Radio | TV | Fax | Internet | Telephone | Local radio network | Other(s) |
| --- | --- | --- | --- | --- | --- | --- |
| □ | □ | □ | □ | □ | □ | □ |

If other(s), please specify:

Q4.	Do you understand the warnings and forecasts?

| Yes | No |
| --- | --- |
| □ | □ |

Q5.	 Are the language and format clear enough for you?

| Yes | No |
| --- | --- |
| □ | □ |

Q6.	Do you take any action in response to the warnings and forecast you receive?

| Yes | No |
| --- | --- |
| □ | □ |

If yes, what do you do?

Q7.	In your opinion are the warnings and forecasts accurate?

| Yes | No | More or less |
| --- | --- | --- |
| □ | □ | □ |

Q8.	Do you have any suggestions on how to improve the warning and forecast process, including dissemination methods, format, language etc.

Post and name: 	   Date:

Annex L

| Activities | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | Budget (in CHF) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |
| 1. Preparation by the Centres to start pilot demonstration phase from 1 June 2019 |  |  |  |  |  |  |  |  |  |  |  |  | - |
| 2. Pilot Demonstration phase from 1 June 2019 to 31 December 2020 |  |  |  |  |  |  |  |  |  |  |  |  | - |
| 3. SWFDP Regional Training Workshops on Severe Weather and Impact-based Forecasting and Warning Services to be held every year (subject to availability of funds) |  |  |  |  |  |  |  |  |  |  |  |  | 210,000 |
| 3. Second Meeting of RSMT of SWFDP- South Asia to review the subproject progress and update the Regional Subproject Implementation Plan (RSIP) |  |  |  |  |  |  |  |  |  |  |  |  | 40,000 |
| 4. Start a Full Demonstration Phase from 1 January 2021 (subject to availability of products from CMA, JMA and KMA) |  |  |  |  |  |  |  |  |  |  |  |  | - |
| 9. Public weather services (PWS) activities to be implemented on the basis of national needs including to introduce and strengthen impact based forecasts and risk based warnings (e.g. NMHS engagement with users, TV weather, radio, Mobile App. Websites, implementation of Common Alerting Protocol (CAP), impact based forecasts and risk based warnings etc.) (subject to availability of funds) |  |  |  |  |  |  |  |  |  |  |  |  | 150,000 |
| 10. Submission of progress reports by NMHSs and continuous monitoring/ tracking of the subproject (including through RSMT as mentioned above) |  |  |  |  |  |  |  |  |  |  |  |  | - |
| 11. Evaluation report of pilot demonstration phase |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | Sub/total (2019): 100,000 |  |  |  | Sub-total (2020): 150,000 |  |  |  | Sub-total (2021): 150,000 |  |  |  |  |
|  | Total for 3 years (2019-2021) |  |  |  |  |  |  |  |  |  |  |  | 400,000 |

Tentative Work Plan for SWFDP-South Asia  with estimated costs for 2019-2021

(subject to availability of resources)