| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS OPAG DPFS COMMISSION FOR BASIC SYSTEMS NUCLEAR EMERGENCY RESPONSE ACTIVITIES COORDINATION GROUP MELBOURNE, AUSTRALIA, 5-8 MAY 2008 |  | CBS-DPFS/CG-NERA/Doc. 3.3 (25.IV.2008) _______ Agenda item : 3 ENGLISH ONLY |
| --- | --- | --- |

report on follow-up to actions identified at the

WMO nuclear Emergency response activities Coordination Group Vienna meeting (May 2006)

(Submitted by the Chair)

##### Summary and purpose of document

This paper reports on the actions identified at the last meeting of the nERA Coordination Group (Vienna, May 2006) and provides a status report for each one. The objective is to produce a clear picture of what actions are underway or have been completed and to identify the root causes of why some actions have not been taken.

##### Action Proposed

The Meeting is invited to report on / discuss the status of each action; identify which ones should be pursued or dropped and, in light of issues identified at the meeting, recommend new actions to be taken.

1.  INTRODUCTION / BACKGROUND

1.1 At its last meeting in Vienna (May 2006), the WMO nERA Coordination Group identified a set of actions to be undertaken (see section 2). The report of the meeting is available here:

http://www.wmo.int/pages/prog/www/DPFSERA/Reports/CG-NERA_Vienna2006.pdf

1.2 Significant progress and achievements have been made in a number of areas and the Group can be proud of the work accomplished. For example: the implementation of operational backtracking arrangements with CTBTO; the development of RSMC common web pages; quarterly testing between IAEA and ‘’lead’’ RSMCs; the review and updating of the WMO ERA web pages, etc.

1.3 It is also understood that the members of the Group are busy within their respective organizations and that it is not possible to complete all the actions identified at the Vienna meeting for a number of reasons:  technical or communications issues; tasks not defined well enough or too complicated; priority placed on more urgent matters, etc.

1.4 It is important for the Group to identify what actions are underway or have been completed and, as importantly, to identify the root causes of why some actions have not been taken.

1.5 This analysis will help us understand where we stand, what actions might be added or dropped and why etc. Based on this analysis and the discussions at the Melbourne meeting, a new list of actions will be defined.

2. STATUS ON FOLLOW-UP TO VIENNA MEETING ACTIONS

In what follows, the actions identified at the Vienna meeting are listed and a status report given for each one. The paragraphs in parenthesis refer to the report of the meeting.

2.1 ACTION 1: ALL RSMCs and WMO Secretariat (paragraph 4.4)

All RSMCs will maintain the information regarding their respective Centres up-to-date in their mandatory annexes in the WMO Technical Note 778 on Environmental Emergency Response and each RSMC and RTH Offenbach will provide an up-to-date annex by December 2006. The Secretariat will update the Technical Note, including the version posted on the WMO Web-site with the up-to-date revisions.

STATUS: COMPLETED. All RSMCs and RTH Offenbach have updated their information. See http://www.wmo.int/pages/prog/www/DPS/WMOTDNO778/Annex4.html. In addition, considerable work has been done to review and update the WMO ERA web pages. This is discussed in paper 10.1 of the present meeting: http://www.wmo.int/pages/prog/www/DPFSERA/Meetings/CG-NERA_Melbourne2008/Doc10-1.doc

2.2 ACTION 2: ALL RSMCs and WMO Secretariat (paragraph 5.4)

The Joint RSMCs shall conduct a fax test of all the National Operational Contact Points that are listed in the WMO Web-site for their respective regions of responsibility.  Information gathered regarding the validity of the contact information will be compiled and sent by mid-July 2006 to the Secretariat and the Chairman.  Based on this information, the intention is for the Secretariat to address the WMO Members for updates to their operational contact information.

STATUS: ONGOING. Fax test conducted by all in 2006. Follow-up action to be discussed at the meeting.

2.3 ACTION 3: ALL RSMCs (paragraph 5.8)

All RSMCs will send (FTP) their basic products (graphical) to be uploaded to the mirrored Web-sites at Melbourne, Montreal and Washington.  The mirrored Web-site will be expanded to accommodate the posting of the basic products from all 8 RSMCs.  This task should be completed in time for the regular quarterly test of November 2006.  A second step would be, where possible, for every RSMC to implement the expanded mirrored Web-site.

STATUS: ONGOING. This is the subject of paper 5.2 of the present meeting: http://www.wmo.int/pages/prog/www/DPFSERA/Meetings/CG-NERA_Melbourne2008/Doc5-2.doc

2.4 ACTION 4: WMO SECRETARIAT and ALL RSMCs (paragraph 5.11)

It will be necessary to define appropriate file naming conventions consistent with WMO recommended practices or standards to facilitate the exchange, accessibility and management of products.  The Secretariat will investigate if there are existing standards.

STATUS: To be reported on / discussed at the meeting.

2.5 ACTION 5: ALL RSMCs (5.12 and 5.13)

It was agreed that in parallel with the initiative to develop and implement mirrored Web-site, it is desirable that RSMCs also send (FTP) the numeric data form of the basic products in GRIB, GRIB-2, or BUFR to other RSMCs (initially, Melbourne, Montreal and Washington).  This would also allow RSMCs to explore the production of ensemble like products.

STATUS: To be reported on / discussed at the meeting.

2.6 ACTION 6: IAEA and RTH OFFENBACH (paragraph 5.17)

IAEA Incident and Emergency Centre to investigate with RTH Offenbach regarding data exchange in "xml" format.  This way we could eliminate the time delay that the message comes to RTH Offenbach.  Code on the RTH side would have to be developed to parse the relevant information from "xml" to the GTS required format.

STATUS: To be reported on / discussed at the meeting.

2.7 ACTION 7: CHAIRMAN (paragraph 5.18)

The Chair will request the 24/7 operational e-mail addresses from all centres and provide to IAEA IEC.

STATUS: COMPLETED in June 2006.

2.8 ACTION 8: IAEA and RTH OFFENBACH (paragraph 6.5)

The GTS link will be tested at least once per year and IAEA will decide when.  RTH Offenbach will consult with IAEA about the possibility of checking / correcting messages before distribution on the GTS.

STATUS: To be reported on / discussed at the meeting.

2.9 ACTION 9: IAEA (paragraph 6.6)

IAEA will provide a modified IAEA Fax Request Form for inclusion in Appendix II-7 of the Manual on GDPFS (WMO-No.485). The modified form will include instruction to the IAEA operators to send an additional fax copy to RTH Offenbach.

STATUS: COMPLETED. New form included in lasted update to WMO No. 485 – Manual on the GDPFS.

2.10 ACTION 10: ALL RSMCs (paragraph 6.7)

Real-time radionuclide data and real-time radiation monitoring data would be of great value for real-time responses, including modeling, but also for hindcast studies.  It was agreed that each RSMC would investigate the possibility of accessing such monitoring data and report at the next meeting of this Group.

STATUS:  To be reported on / discussed at the meeting.

2.11 ACTION 11: ALL RSMCs (paragraph 9.5. Conditional on receiving the draft document on revised requirements from the NCA Expert Group B.5)

The meeting agreed to review and provide comments to the latest draft of the revised list of requirements for RSMC atmospheric dispersion products that are being developed by the National Competent Authority EG.  Mr. Rojas-Palma agreed to provide the latest draft via e-mail to the members of the Coordination Group.  The Group members are requested to provide comments to the Chair, copied to the Secretariat, preferably before the end of May 2006.

STATUS: Not done. Draft document was not received.

2.12 ACTION 12: IAEA and WMO Secretariat (paragraph 9.11)

The meeting agreed the greatest challenge is to improve the coordination and liaison between NMHSs and the counterpart NCAs. One suggestion was to include in the next mailing (end of 2006) of the IAEA technical operations manual information on the RSMC services and the role of the NMHS Operational Contact Point, and the list of Delegate Authorities for requesting specialized RSMC products. IEC and WMO Secretariat could jointly prepare such an information package for NCAs.

STATUS: To be reported on / discussed at meeting.

2.13 ACTION 13: ALL (paragraph 9.13)

The representative of the IEC noted that the RSMCs seemed to lack a coordinated development process as a group for enhancing products and services to meet requirements without specific users requests.  The Group agreed to improve on its approach to the development and implementation of plans to enhance products within its terms of reference.

STATUS: To be reported on / discussed at meeting.

2.14 ACTION 14: ALL (paragraph 9.14)

The following Terms of Reference were proposed for the CBS Coordination Group on Nuclear ERA for the coming work period:

a) Test and improve the collective ability of all RSMCs, the IAEA, the RTH Offenbach and NMHSs in the ERA to fulfill the operational requirements specified in global and regional arrangements, according to adopted standards and procedures;

b) Implement and explore further improved distribution/access methods for specialized products to NMHS, and the IAEA in collaboration with the IAEA and other relevant organizations;

c) Collate the individual capabilities of RSMCs to produce enhanced products in support of nuclear emergencies;

d) Examine the operational availability of radiological monitoring data;

e) Develop concepts of operational arrangements for atmospheric transport modeling backtracking products;

f) Pursue the implementation of operational arrangements with CTBTO.

STATUS: ONGOING.

2.15 ACTION 15: RSMCs Obninsk, Melbourne, Montreal, Washington and Exceter (paragraph 9.15)

The meeting agreed that under ACTION 14(c), that RSMCs Obninsk, Melbourne, Washington, Montreal would participate in identifying possible enhanced products as well as determine how best to manage the digital exchange of such products, under coordination by Mr. Stewart Wortley of RSMC Exeter.

STATUS: To be reported on / discussed at meeting.

2.16 ACTION 16: ALL RSMCs and RTH OFFENBACH (paragraph 10.2 and 10.3)

The meeting agreed that the RSMCs and RTH Offenbach will produce and share an annual report to cover the calendar year starting with the report for 2006. The report should be submitted to the Chairman of the Coordination Group by the end of February of the following year, for eventual posting on the WMO Web-site for the ERA programme.

The contents of the Annual Report shall include, but not limited to:

RSMCs:

- Introduction

- Operational contact information (RSMC)

- Responses and information on dissemination of products (fax, web-page

access, which products were sent and time delay from point of

notification)

- Exercises and routine tests

- Lessons learned from recent experiences

- Operational issues / challenges

- Summary / status of the operational atmospheric transport and dispersion model(s)

- Plans for the coming year

RTH Offenbach:

- Introduction

- Operational contact information

- Standing operational procedures

- Responses and information on dissemination of products (fax, web-page

access, which products were sent and time delay from point of

notification)

- Programme of exercises, routine tests

- Operational issues / challenges

- Lessons learned from recent experiences

- Plans for the coming year

STATUS: Many reports presented in agenda item 4 papers of the present meeting.

3. RECOMMENDATIONS

The Meeting is invited to report on / discuss the status of each action; identify which ones should be pursued or dropped and, in light of issues identified at the meeting, recommend new actions to be taken.