| WORLD METEOROLOGICAL ORGANIZATION COMMISSION FOR BASIC SYSTEMS OPAG on DPFS expert team on emergency response activites (et-era) College Park, MD, USA, 21-25 October 2013 |  | DPFS/ET-ERA/Doc. 5.1(1), REV. (18.IX.2013) _______ Agenda item : 5.1 ENGLISH ONLY |
| --- | --- | --- |

Review of actions from previous TT-DOP-nNERA meeting 
(Melbourne, Australia, 2012)

(Submitted by the Vice-Chair of the

Expert Team for Emergency Response Activities)

##### Summary and purpose of document

This paper reports on the work done on actions identified at the last meeting of the CBS Task Team on the Development of Operational Procedures for non-Nuclear Emergency Response Activities (TT-DOP-nNERA)

##### Action Proposed

The Meeting is invited to report on / discuss the status of each action; identify which ones should be pursued or dropped and, in light of issues identified at the meeting, recommend new actions to be taken.

Reference:

Melbourne, 2012: Meeting of the CBS Task Team on the Development of Operational Procedures for non-Nuclear Emergency Response Activities (TT-DOP-nNERA), Melbourne, Australia, 5-8 November 2012.

1.  INTRODUCTION AND NEXT STEPS

1.1 At the November 2012 meeting, the WMO Meeting of the CBS Task Team on the Development of Operational Procedures for non-Nuclear Emergency Response Activities (TT-DOP-nNERA), identified actions to be undertaken (c.f. Annex III of Melbourne, 2012).

1.2 This document presents a status report on these actions. Unfortunately the majority of them have not yet been undertaken or only partly completed due, in part, to competing work demands on the ET-ERA co-chairperson for which he offers sincere apologies.

1.3 In reviewing the actions, we have to determine if the actions not undertaken / not completed in the Melbourne 2012 list should be pursued or dropped and why.  Based on this analysis and the discussions at the meeting, a new list of actions for 2014 and 2015 will be defined.

2. STATUS REPORT ON ACTIONS FROM THE MELBOURNE 2012 MEETING OF THE TT-DOP-nNERA

2.1 Area of Requirement:  Development of operational procedures

ACTION 1: Chairperson and Co-Chairperson, WMO Secretariat and ALL RSMCs

Complete the drafting of operational procedures for significant non-nuclear incidents, including the minimum information on the characteristics of the ATM, and circulate it among TT members and other relevant experts, especially those responsible for the existing RSMCs

DUE DATE: January 2013

- ET-ERA Chairperson and Co-chairperson to complete the set of operational procedures

DUE DATE: January 2013

- Secretariat to circulate the draft for comments

DUE DATE: March 2013

- RSMCs to provide feedback

DUE DATE: ASAP

- Secretariat to add the RSMC email addresses on the ERA web page

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.

ACTION 2: Chairperson and Co-Chairperson, WMO Secretariat, RSMCs and Argentina, Ururgay and Brazil

Conduct experiment comprising a simulated request from NMHS to RSMC for assistance during a large chemical fire

DUE DATE: February 2013

- ET-ERA Chairperson to lead development of experiment scenario.

DUE DATE: June/July 2013

- RSMCs, Argentina, Uruguay and Brazil to conduct experiment

STATUS (OCTOBER 2013): Preliminary limited experiment involving NMHS Argentina and RSMC Montreal was held on 1 October 2013.  A report on this experiment is presented in agenda item 5.4.  A full exercise will be held in the coming months.

  - Area of Requirement:  Capacity building and ERA web-page

ACTION 3: WMO Secretariat

Assist NMHSs in the interpretation of ERA-related products and their application by publicizing aspects covered by the WMO-TD. 778

DUE DATE: January 2013

Send out a circular letter to WMO Members and an e-mail to the ERA contact points informing/publicizing the aspects covered by the WMO-TD. 778

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.

ACTION 4: ALL RSMCS

Encourage NMHS capacity building by publicising the WMO-TD. 778 in ERA products

DUE DATE: Ongoing

Include reference (web link) to the WMO-TD. 778 in the dissemination of ERA products issued by RSMCs.

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.

ACTION 5: TT members, RSMCs and WMO Secretariat

Advise the Secretariat on available n-NERA dispersion modelling capabilities from institutions in their RA area that can be ported to NMHSs

DUE DATE: January 2013

TT members, RSMCs to advise; Secretariat to post it on the WMO web site for ERA

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.

ACTION 6: WMO Secretariat

Enable access to web-based training modules

DUE DATE: ASAP

Work with those that have been developing web-based training modules in order to allow access to those web sites which are password protected by NMHSs, and publicize these materials on the website

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.

ACTION 7: Chairperson and Co-Chairperson, TT Members

Review and update the WMO web site for ERA, including updating the glossary

DUE DATE: January 2013

- ET-ERA Chairperson and co-chairperson to coordinate and identify TT members that could contribute and establish timelines;

DUE DATE: July 2013

- TT members to contribute (Mr Anton Muscat, Ms Gwenaëlle Hello, and Mr Jeff McQueen)

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.

ACTION 8: WMO Secretariat and TT members

Promote the non-Nuclear programme via the

DUE DATE: When the operational procedures for non-nuclear ERA are in place

Update the WMO Bulletin article on ERA (January 2006) to further promote the programme

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.

ACTION 9: Jeff McQueen and WMO Secretariat

Enabling dispersion modelling capacity building

DUE DATE: March 2013

Identify those NWP models that could be readily used for operational dispersion modelling

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.

ACTION 10: Jeff McQueen and WMO Secretariat

Capacity building in NMHSs

DUE DATE: Ongoing

Demonstrate transfer of the dispersion modelling capability to candidate NMHSs

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.

2.3  Area of Requirement:  Work with International Organizations

ACTION 11: WMO Secretariat

Engage with relevant international organizations

DUE DATE: Ongoing

Engage with relevant international organizations to promote the usefulness of ERA products and determine requirements

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.

ACTION 12: WMO Secretariat

Enabling capacity building

DUE DATE: Once the operational procedures have been established

Make relevant international organizations aware of the operational procedures for non-nuclear ERA

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.

ACTION 13: WMO Secretariat

Enabling capacity building

DUE DATE: After the exercise

Share the information of the outcomes / report of the exercise, which should include an item on potential implications to other relevant international organizations.

STATUS (OCTOBER 2013): Ongoing. To be discussed at the meeting.