| WORLD METEOROLOGICAL ORGANIZATION __________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION EXPERT TEAM ON REGIONAL INSTRUMENT CENTRES, CALIBRATION AND TRACEABILITY First Session Nairobi, Kenya 23 – 26 September 2013 |  | CIMO/ET-RIC-1/Doc.3 (12.IX.2013) _______ ITEM: 3 Original: ENGLISH |
| --- | --- | --- |

UPDATE ON THE WIGOS DEVELOPMENT AND

WIGOS IMPLEMENTATION PLAN (WIP)

(Submitted by the Secretariat)

##### Summary and purpose of document

The document presents a brief update on the WIGOS implementation at the global and regional levels.

##### Action Proposed

The meeting is invited to consider information presented in the document for the further development of its working plan addressing WIGOS requirements at global and regional levels specified in WIP and R-WIPs for RA I – RA VI.

Annexes:

Annex I: R-WIP-I, Table 2

Annex II: R-WIP-II, Table 2

Annex III: R-WIP-III, Table 2

Annex IV: R-WIP-IV, Table 2

Annex V: R-WIP-V, Table 2

Annex VI: R-WIP-VI, Table 2

References:

1) CIMO/ET-RIC-1/INF.4 (WIP)

2) Regional WIGOS Implementation Plans

STATUS ON THE WIGOS IMPLEMENTATION

EC-65 on WIGOS Implementation

  - The Council (May 2013) adopted the updated version of WIGOS Framework Implementation Plan (WIP) with improved estimation of resource requirements, adjusted target dates for tasks’ completion and identification of risks as requested by EC-64. Effective implementation and operation of WIGOS will depend on sufficient resources and commitments. Available resources will be targeted at ensuring the priority elements of the global WIGOS framework are implemented by Cg-17.

  - The WIGOS framework Implementation Plan (WIP) addresses the necessary activities to establish an operational WIGOS by the end of the period 2012-2015, as per the direction of WMO Congress. To migrate the existing observing systems (GOS, GAW, WMO Hydrological Observing System, incl. WHYCOS, and GCW, including surface-based and space-based components and all WMO contributions to GFCS, GCOS, GOOS, GTOS and GEOSS) into a more integrated single system that is WIGOS, focused effort is required in the following key areas identified and described in the WIP:

(a)	Management of WIGOS implementation;

(b)	Collaboration with WMO and co-sponsored observing systems;

(c)	Design, planning and optimized evolution;

(d)	Integrated Observing System operation and maintenance;

(e)	Integrated Quality Management;

(f)	Standardization, system interoperability and data compatibility;

(g)	The WIGOS Operational Information Resource;

(h)	Data and metadata management, delivery and archival;

(i)	Capacity development;

(j)	Communication and outreach.

  - The WIP also addresses a number of additional activities that would substantially improve the operational capabilities of WIGOS beyond the 2012-2015. During the implementation of WIGOS, the Rolling Review of Requirements (RRR) process, originally developed in formulating the Implementation Plan for the Evolution of the Global Observing Systems (EGOS-IP) will be a major tool for observational gap analysis and observing network design.

  - The Regional WIGOS Implementation Plans (R-WIP) have been developed in all WMO Regions and already adopted by RAs II, IV and VI. R-WIPs take into account regional and subregional needs, requirements and priorities. In this regard, Members’ commitment to, and leadership for WIGOS implementation is essential, including provision of sufficient resources.

  - The WIGOS Quality Management approach is to apply the WMO Quality Management Framework (QMF) to the WIGOS component observing systems (see WMO Technical Regulations (WMO-No. 49), Vol. IV). WIGOS Quality Management will strive for compliance of all components of WIGOS with international standards, such as ISO 9001/9004 and the ISO 17025 standard where appropriate (i.e. with respect to instrument calibration and traceability of data).

  - In addition to the WMO QMF document, further guidance to Members on WIGOS Quality Management will be provided via the standards and best practices described in the Regulatory Materials, such as the WIGOS Manual and Guide. Such guidance, for both mandatory and desirable practices, can be referenced for the application and implementation of quality management in national observing systems. In this context, WIGOS will give attention to:

(a)	The examination of current quality management practices being used by WMO observing programmes;

(b)	The documentation of the quality of observation at all stages of data processing; and

(c)	Ensuring, where possible, traceability to the International System of Units (SI).

ICG-WIGOS and Task Teams

  - In accordance with Resolution 4 (EC-LXIII) and based on the discussion at PTC-2012, the following ICG-WIGOS Task Teams (TT) was established: TT on the WIGOS Implementation Plan (TT-WIP), TT on WIGOS Regulatory Material (TT-WRM) and TT on WIGOS Metadata (TT-WMD). Establishment of a new TT on WIGOS Quality Management (TT-WQM) is under process.

  - TT-WIP-1 (March 2012) finalized the WIGOS framework Implementation Plan (WIP) that was submitted to EC-64 for consideration. TT-WRM-1 (November 2012) agreed on the Draft structure of in WMO Technical Regulations (WMO-No. 49), Vol. I., Part I. WIGOS, and the Action Plan for the developing the WIGOS regulatory material; following the guidance of ICG-WIGOS and EC-65, TT-WRM-2 (June 2013) further continued in the development of the WIGOS regulatory material (WMO-No. 49, Vol. I., Part I. WIGOS as well as the Manual on WIGOS). TT-WMD-1 (March 2013) focused on the standardization of WIGOS component observing system metadata. The final reports of the task team meetings are available at: www.wmo.int/pages/prog/www/WIGOS-WIS/reports.html.

  - The second session of the Inter-Commission Coordination Group on the WMO Integrated Global Observing System (ICG-WIGOS-2) was held at the WMO Secretariat in Geneva, Switzerland, from 18 to 22 March 2013. ICG-WIGOS reviewed the status of the WIGOS Key Activity Areas and agreed on the updated version of the WIGOS Framework Implementation Plan (WIP) that was submitted to EC-65. Further, it reviewed deliberations of its Task Teams, Regional Associations and Technical Commissions relevant to the WIGOS framework Implementation Plan (WIP) and agreed on: (1) The structure of the WIGOS sections to be included in the WMO Technical Regulations and the draft structure of the Manual on WIGOS; (2) The guidance for WIGOS metadata development; (3) The self assessment checklist to assist Members in a national self-assessment of their readiness for WIGOS implementation; (4) The draft of the WIGOS Capacity Development Strategy; (5) The draft of the WIGOS Communications and Outreach Strategy; (6) The way forward for the Regional Associations in developing and executing their Regional Implementation Plans (R-WIPs).

Regional implementation of WIGOS

  - Since December 2011, the WIGOS relevant working bodies of all RAs held their meetings and drafted the Regional WIP for their respective RA. R-WIP for RA II, IV and VI have been already adopted by the session of respective RA. The R-WIP for RA V, III and I will be considered and adopted (in this order) in 2014. All R-WIPs (adopted or draft versions) are available at: http://www.wmo.int/pages/prog/www/wigos/documents.html

  - The Annexes 1-6 to this document contain the Table 2 of the individual R-WIPs, in which the activities directly relevant to ET-RICs are highlighted in yellow; the session is invited to take these activities into account and consider how the Expert Team can contribute to the implementation of WIGOS at the regional level. The activities that are highlighted in turquoise could be taken into account for consideration the draft for expanded activities of RICs.

_________

# Annex I

Table 2	WIGOS Implementation Activities (R-WIP-I)

Depending on the implementation scale, planned activities are specified as follows:

R = Regional activity; SR = Sub-regional activity and N = National activity.

| No | Activity | Deliverables | Timeline | Responsibility | Estimated Costs | Potential Risks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Management of WIGOS Implementation in RA I |
| 1.1 R SR N | Establish the Regional WIGOS Governance structure, including sub-regional responsible bodies, and technical groups for each subregions | RA-I WIGOS Governance structure, incl. WGs established with TOR (see ANNEX 1, Figure 1) | 2012 | RA-I MG |  | Low |
| 1.2 R SR N | Provide an effective RA-I focal points at regional, sub-regional and national levels, to liaise with CBS, CIMO and other relevant TCs, WIGOS-PO on the implementation of WIGOS and EGOS-IP in the Region | National and sub-regional Focal points at all levels are identified with special interest for CBS, CIMO | 2012 | PRs |  | Low |
| 1.3 R SR | Develop and update the Regional WIGOS Implementation Plan for Region I (R-WIP-I), reflecting sub-regional priorities | 1) Up-to-date RA-WIP-I, including: a) actions sheets from all subregions, b) actions specified at WIP for regional level, c) actions specified at EGOS-IP relevant to RA I | 2012-2013 | RA-I TT on WIGOS (TT-WIGOS); RA-I MG; Sub-regional representatives in TT-WIGOS | RB from relevant departments | Low |
| 1.4 R N | Mobilize needed resources for supporting the WIGOS implementation in the Region and all subregions | Appropriate resources are identified and available from Secretariat, subregions, partners, stakeholders and Members for supporting actions | 2012-2015 | RA-I MG; PRs |  | High |
| 1.5 R SR N | Monitor and evaluate (M&E) WIGOS implementation activities | Annual M&E reports; Problems are identified and sorted out timely | 2012-2015 | RA-I WIGOS Governance body defined at 1.1 with the support of WMO Secretariat |  | Low |
| 2. Collaboration with WMO and co-sponsored observing systems |
| 2.1 R SR N | Identify and engage key partner organizations (water, marine, agriculture, environment and research institutes, private sector, etc.) in implementation of WIGOS at regional, sub-regional and national levels | MoUs and Agreements signed with regional, sub-regional and national partner organizations | 2012-2015 | RA-I President with the support of RA-I MG responsible for the MoU/Agreements at the regional and sub-regional levels; PRs responsible for the MoU/Agreements with National Partners, with the support and guidance of RA I MG |  | High |
| 2.2 R SR N | Establish working mechanisms with clear targets (such as data policies, MoUs, agreements) for collaboration in WIGOS implementation in the Region | Established collaboration mechanisms; Increased number and amount of exchanged observations, with the partners at regional, sub-regional and national levels, based on MoUs and agreements. | 2012-15 | RA-I President with the support of RA-I MG responsible for the MoU/Agreements at the regional and sub-regional levels; PRs responsible for the MoU/Agreements with National Partners, with the support and guidance of RA I MG |  | High |
| 3. Design, planning and optimized evolution of WIGOS and its regional, sub-regional and national observing components |
| 3.1 R | Design and plan observing systems in the Region taking into account: a) The technical guidance as represented in the EGOS-IP and other relevant observing systems IP; b) Recommendations by XV-RA-I session (2010); c) Observational Requirements expressed in GFCS-IP; d) Up-to-date users requirements for data, including international river basin authorities | Optimized regional integrated observing system design plan taking into account partners requirements | 2012-2015 | TT- WIGOS |  | High |
| 3.2 R | Develop a design of new RBN, in close collaboration with CBS | Design of a new RBN | 2012-2015 | TT-WIGOS |  | High |
| 3.3 SR | Based on the design of a new RBN, design and plan observing systems in the subregions taking into account their priorities and requirements | Optimized sub-regional observing systems design plans | 2013-2015 | Sub-regional representatives in TT-WIGOS |  | Medium |
| 4. Integrated Observing System Operation and Maintenance |
| 4.1 R | Collect and compile examples of best practices and technical documentation | Availability of technical documents and best practices | 2012-2013 | TT-WIGOS; WMO Secretariat |  | Low |
| 4.2 R SR | Establish a regional/sub-regional repository of guidance and technical documentation | Repository available to Members | 2012-2015 | TT-WIGOS; WMO Secretariat |  | Medium |
| 5. Integrated Quality Management |
| 5.1 R | Examine current quality management practices being used in the Region, including calibration of instruments for surface-based observations | Availability of status report on the current quality of management practices | 2012-2013 | TT-WIGOS; WMO Secretariat |  | Low |
| 5.2 R | Establish mechanisms and systems to improve, monitor and document the quality of observations from the WIGOS Regional observing components at all stages of data processing | Established mechanisms for improved quality of observations at all levels | 2012-2015 | TT-WIGOS; Members; WMO Secretariat |  | High |
| 5.3 R | Ensure, where possible, traceability of observations to the international standards (such as International System of Units (SI)), focusing initially on surface pressure, temperature, precipitation and humidity | Traceable observations | 2012-2015 | Members; RICs; WMO Secretariat |  | High |
| 5.4 R | Progressively achieve compliance of all RICs with international standards | Compliance of RICs | 2012-2015 | Respective Members (RICs) |  | High |
| 5.5 R | Achieve the functionality of RICs and RRCs in all five subregions | RICs and RRCs fulfil their mandates | 2012-2015 | Respective Members |  | High |
| 5.6 R | Enhance support by RICs to Members and encourage Members to work with RICs and RRCs | Established mechanisms for collaboration between RICs, RRCs and Members | 2012-2015 | RICs; Members |  | Medium |
| 5.7 R | Achieve, through collaborative effort of Kenya, Morocco and South Africa full functionality of the RMIC | Operational RMIC | 2012-2015 | South Africa, Kenya and Morocco |  | Medium |
| 5.8 R | Ensure that surface-based sites that are needed for calibration/validation of satellite data are specified | List of surface-based sites for calibration/validation of satellite data | 2012-2015 | TT-WIGOS |  | Medium |
| 6. Standardization, System Interoperability and Data Compatibility |
| 6.1 R | Implement the siting classification throughout the Region | Siting classification implemented | 2012-2015 | Members |  | High |
| 6.2 R SR | Establish mechanisms for monitoring of compliance with WMO standards at regional and sub-regional level | Operational mechanisms for monitoring of compliance with WMO standard; More WMO standards are implemented at the national level | 2012-2015 | TT-WIGOS; WMO Secretariat; Members |  | High |
| 6.3 R SR | Encourage Members to generate and provide metadata (to WIR-OSCAR) | Metadata generated | 2012-2015 | Members; TT-WIGOS; WMO Secretariat |  | High |
| 6.4 N | Achieve migration to TDCF in the Region | Migration completed | 2012-2014 | Members |  | High |
| 7. The WIGOS Operational Information Resource |
| 7.1 R | Develop and maintain a regional metadata database and a web portal to contribute to the WIR-OSCAR | Operational regional/sub regional WIR | 2012-2015 | TT-WIGOS; WMO Secretariat |  | High |
| 7.2 R | Encourage Members to provide and share up-to-date communication and outreach information through the WIR | Up-to-date information available | 2012-2015 | Members; WMO Secretariat |  | Medium |
| 8. Data discovery, delivery and archival |
| 8.1 R N | Encourage Members to be designated as WIS DCPCs or GISCs; Ensure Members to establish WIS NCs | Members designated as DCPCs / GISCs; NCs established | 2012-2015 | Members; WMO Secretariat |  | High |
| 8.2 N | Encourage Members to share data and metadata via WIS, including from institutions other than NHMSs | Enhanced availability of data and products | 2012-2015 | Members; WMO Secretariat |  | High |
| 9. Capacity development |
| 9.1 R SR | Identify the needs for new Regional Centres of Excellence (RICs, RRCs, RMICs, RTCs) | At least one RIC in each Subregion approved by RA I | 2012-2015 | TT-WIGOS; PRs with support of WMO Secretariat |  | Mod |
| 9.2 R SR | Define TORs of these Centres for strengthening the regional capacity on WIGOS | Operational RICs | 2012-2015 | TT-WIGOS; PRs with support of WMO Secretariat |  | Mod |
| 9.3 R N | Prove assistance to Members to establish/enhance institutional mandates and policies that enable effective implementation, operation and management of observing systems by Members | Established/enhanced institutional mandates and policies for effective implementation, operation and management of observing systems by Members | 2012-15 | WMO Secretariat; RA-I MG; PRs |  | Mod |
| 9.5 R N | Prove assistance to Members to fill the existing gaps in the design, operation and maintenance of WIGOS observing systems, including both the infrastructure and human capacities development | Gaps in the WIGOS observing systems of Member countries are identified and filled | 2012-15 | RA-I MG; TT-WIGOS; RA-I WGs; WMO Secretariat Members, in collaboration with regional partners and TCs |  | Mod |
| 10. Communication and outreach |
| 10.1 R SR N | Utilise communication strategies developed by ICG-WIGOS and material provided by WIGOS-PO to raise awareness and commitment to WIGOS in the Region | Effective communication and outreach for WIGOS across the Region by presentations and side events at regional high level events. | 2012-15 | RA-I Vice president; RA-I MG; WMO Secretariat |  | Low |
| 10.2 R SR N | Develop communication and outreach material of RA I with a special focus on policy-makers | Communication and outreach material of RA I is available through appropriate means (WIR, RANET, forums, etc.) | 2013 | WMO Secretariat; Regional Offices; Members |  | Low |
| 10.3 R SR N | Communicate WIGOS benefits using all possibilities, such as COFs, AMCOMET | Workshops & side events at regional, sub-regional and national levels for promoting WIGOS | 2012-15 | RA-I MG; Members with support of WMO Secretariat |  | Low |
| 10.4 R SR N | Convene WIGOS implementation awareness meetings for PRs at sub-regional level | PRs have clear understanding of WIGOS and are aware of their roles in implementation of WIGOS | 2013 | RA-I MG; WMO Secretariat |  | Low |

_______

# Annex II

Table 2	RA II WIGOS IMPLEMENTATION ACTIVITIES (R-WIP-II)

Depending on the implementation scale, planned activities are specified as follows:

R = Regional activity; SR = Sub-regional activity and N = National activity.

| No. | Activity | Deliverables | Timeline | Responsibility | Estimated Costs | Potential Risks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Management of WIGOS Implementation in RA II |
| 1.1 R | Develop and update R-WIP-II | Regional WIGOS Implementation Plan for RA II (R-WIP-II) | Develop in 2012 and update if necessary | Drafted by TT-R-WIP-II, to be adopted by RA II-15 (Dec. 2012) and updated by RA II EG-WIGOS/MG |  | Low (on-going) |
| 1.2 R | Report progress of the RA II R-WIP-II Projects to RA II MG | Progress reports | 2013-2015 every year | Coordinators of Projects |  | Low |
| 1.3 R N | Encourage RA II Members to appoint National Focal Points and submit national reports on progress of EGOS-IP | A list of RA II EGOS-IP National Focal Points | 2013-2015 every year | RA II Members (Project No. I) |  | Mod |
| 2. Collaboration with WMO and co-sponsored observing systems |
| 2.1 SR | Examine data policy and exchange of surface-based remote sensing datasets/ products for NWP use on an offline basis | Exchange of datasets | 2013-2014 | East Asia (China, Japan, Republic of Korea) (Project No. III.1) |  | High |
| 2.2 SR | Examine data policies and exchange observational sand and dust data | Exchange of datasets | 2013 | SDS-WAS Asian Node WG (China, Japan, Republic of Korea) (Project No. V) |  | High |
| 3. Design, planning and optimized evolution of WIGOS and its regional, sub-regional and national observing components |
| 3.1 R | Review the progress of EGOS-IP in RA II based on EGOS national reports submitted by RA II Members | Prioritized actions listed in the EGOS-IP | 2015 | China, Hong Kong, China (Project No. I) |  | Mod |
| 3.2 SR | Design feasible and optimal draft design of integration of surface-based remote sensing observations based on OSE; use the results to update the RRR user requirements database and to fine tune the EGOS-IP and observing system plans. | Draft design of integration of surface-based remote sensing observation based on OSE | 2015 | East Asia (Project No. III.1) |  | High |
| 3.3 SR | Assess enhanced capacity in monitoring and forecasting of sand and dust storms by exchanged datasets; use the results to update the RRR user requirements database and to fine tune the EGOS-IP and observing system plans. | Identified benefits from exchange of sand and dust data on a near real-time basis | 2015 | SDS-WAS Asian Node WG (Project No. V) |  | High |
| 3.4 SR | Develop strategic plan on development of the Southeast Asia radar network. | Draft strategic plan on development of the Southeast Asia radar network | 2015 | Southeast Asia (ASEAN—SCMG: Thailand, Malaysia) (Project No. III.2) |  | Mod |
| 3.5 R | Identify the requirements of NMHSs of developing countries, regarding satellite imagery, data and products, use the results to update the RRR user requirements database and to fine tune the EGOS-IP | Reports on requirements of NMHSs of developing countries, regarding satellite imagery, data and products |  | Japan, Republic of Korea, other satellite operators (Project No. VI) |  | Mod |
| 4. Integrated Observing System Operation and Maintenance |
| 4.1 R | Collect and share standard and best practices documents from RA II Members | Shared best practices on integration of observational systems | 2013-2015 | Republic of Korea (Project No. II) |  | Low |
| 4.2 SR | Develop and share national reports toward operational rainfall estimation/forecasting based on radar data. | Identified technical issues and lessons learned on operation of radar systems among ASEAN countries | 2015 | Southeast Asia (ASEAN—SCMG: Thailand, Malaysia) (Project No. III.2) |  | Mod |
| 5. Integrated Quality Management |
| 5.1 R | Survey and share the status on calibration instruments for surface-based observations in RA II | Reports on status on calibration instruments for surface-based observations in RA II | 2012-13 | China, India, Japan (Project No. IV) |  | Low (on-going) |
| 5.2 R | Monitor data quality by utilizing NWP QC monitoring reports on surface observations | Improved data quality of surface observations | 2012-15 | Japan (Project No. IV) |  | Low (on-going) |
| 5.3 R | Organize intercomparison between regional standards of RICs | Traceability between RICs | 2013-15 | China, Japan (Project No. IV) |  | High |
| 5.4 R | Obtain ISO/IEC 17025 | Enhanced RIC’s capacity | 2013-15 | China, Japan (Project No. IV) |  | Mod |
| 5.5 R | Enhance support by RICs, and encourage Members to work with RICs to ensure traceability to SI | Improved data quality of surface observations | 2013-15 | China, Japan (Project No. IV) |  | Mod |
| 6. Standardization, System Interoperability and Data Compatibility |
| 6.1 R | Survey and share the status on QC/QA procedures and site management for the network of RBCN and RBSN stations | Reports on status on QC/QA procedures and site management in RA II | 2013-15 | Japan (Project No. IV) |  | Mod |
| 6.2 N | Encourage the collection of metadata on observing stations | Collection of metadata on observing stations | 2013-15 | RA II Members |  | High |
| 7. The WIGOS Operational Information Resource |
| 7.1 R | Develop a portal to share EGOS national reports | Portal to share EGOS national reports | 2013-15 | China (Project No. I) |  | Low |
| 7.2 R | Develop a standards and best practices Portal | Standards and best practices Portal | 2013-15 | Republic of Korea (Project No. II) |  | Low |
| 7.3 R | Develop QA/QC Portal | QA/QC Portal | 2013-15 | Japan (Project No. IV) |  | Mod |
| 8. Data discovery, delivery and archival |
| 8.1 R | Encourage RA II Members to be designated as NCs and DCPCs | RA II Members designated as NCs and DCPCs | 2012-15 | RA II EG on WIGOS |  | Mod |
| 8.2 R | Encourage RA II Members to share data via WIS, including from organizations other than NMHSs | New sources of data are available through WIS | 2012-15 | RA II EG on WIGOS |  | Mod |
| 9. Capacity development |
| 9.1 R | Technical Training on QA/QC procedures | Improved QA/QC at RBCN and RBSN stations | 2013-15 | China; India; Japan; Republic of Korea; Hong Kong, China; Kuwait; Russian Fedederation (Project No. IV) |  | High |
| 9.2 R | Hold training workshops on maintenance and calibration of meteorological instruments | Improved capacity in maintenance and calibration of meteorological instruments | 2013 | Japan (Project No. IV) |  | Low (being planned) |
| 9.3 R | Develop training materials on maintenance and calibration of meteorological instruments | Training materials on maintenance and calibration of meteorological instruments | 2013-15 | Japan (Project No. IV) |  | Low (being planned) |
| 9.4 R | Coordinate training activities on utilization of satellite data/products | Improved capacity in utilization of satellite data/products | 2012-15 | Japan, Republic of Korea, other satellite operators (Project No. VI) |  | Low (on-going) |
| 9.5 R | Establishing filed intercomparison campaign for observation techniques | Guidance to operate and maintain observation instruments | 2013-15 | Republic of Korea (Project No. II) |  | Low |
| 10. Communication and outreach |
| 10.1 R | Interlink RA II WIGOS portals and related Websites | Better access to RA II WIGOS-related information and products | 2013-15 | China; Hong Kong, China; India; Japan; Republic of Korea |  | low |
| 10.2 R | Develop RIC Websites | Improved access to information on RICs | 2012-15 | China, Japan (Project No. IV) |  | Low (on-going) |
| 10.3 R | Publish newsletter regularly | Improved access to information on satellite data/products | 2012-15 | Japan, Republic of Korea, other satellite operators (Project No. VI) |  | Low (on-going) |

Project No. IV

| Project Title | RA II WIGOS Project to Enhance the Availability and Quality Management Support for NMHSs in Surface, Climate and Upper-air Observations |
| --- | --- |
| Type | Regional Implementation Project (RA II) |
| Status | Draft Design |
| Overview | The Japan Meteorological Agency (JMA)/World Meteorological Organization (WMO) Workshop on Quality Management in Surface, Climate and Upper-air Observations, held at Tokyo in July 2010 as part of activities of the Pilot Project to Enhance the Availability and Quality Management Support for NMHSs in Surface, Climate and Upper-air Observations (hereafter, Pilot Project), found out that primary factors adversely affecting data quality in RA II are calibration and maintenance of instruments mainly due to lack of traceability of measurements to international standards and calibration facilities. This project will build on outcomes of the workshop. It consists of the following two activities: (i) improvements of data quality of RBCN/RBSN stations; and (ii) enhancement of capabilities of RIC-Tsukuba and RIC-Beijing. All the outcomes of this project will be shared at a Portal to be established by the Coordinator. 1. Improvements of data quality at RBCN/RBSN stations (a) Monitoring Data Quality The Coordinator checks data quality of RA II stations and identifies and requests RA II Members to identify technical issues, based on the following results: Questionnaire on the Surface, Climate, and Upper-air Observations and Quality Management in Regional Association II (Asia) (conducted in July 2010), Questionnaire on meteorological instruments, calibration and training in Regional Association II (Asia) (conducted in January 2012), 6-monthly monitoring reports by the Lead Centre for monitoring the quality of land surface observations in Region II. Survey on status on QA/QC procedures and site managements for the network of RBCN/RBSN stations, and report the results. Based on requests from the Coordinator, the following Members will consider the possibility of technical support if funds are available, and share the summary of the technical missions with RA II Members: CMA, HKO, JMA, and KMA for Southeast Asia, IMD for South Asia, Roshydromet for Central Asia, Kuwait for Middle East. 2. Enhancement of RIC’s Services RICs plan to implement the following action items for further enhancement of their services in capacity building and calibration during the project: Organization of a training workshop to improve understanding of calibration and maintenance of meteorological instruments according to needs of RA II Members to be identified by the “Questionnaire on Meteorological Instruments, Calibration and Training in Regional Association II (Asia)”, Development of training materials on calibration and maintenance of instruments (to be prepared for publication as an Instruments and Methods of Observation Programme (IMOP) technical document), Obtaining the International Standard ISO/IEC 17025 – General requirements for the competence of testing and calibration laboratories – certification for air pressure, temperature, and humidity, Development of RIC’s Websites, Intercomparison between RIC-Tsukuba and RIC-Beijing, Reports on status on calibration instruments for surface-based observations in RA II (to be prepared for publication as an Instruments and Methods of Observation Programme (IMOP) technical document). |
| Aim(s) | This project aims at improvement of data quality at RBCN/RBSN stations and enhancement of services of RA II RICs. |
| Benefits | RA II Members, especially those with technical issues on data quality of observations, will potentially benefit from this project. |
| Role/Involvement of WMO Regional Centres in RA II | Regional Instrument Centres (RICs) Lead Centre for monitoring the quality of land surface observations |
| Key Regional Player | JMA (Coordinator), and Members of Coordination Group Technical Mission: CMA, HKO, JMA, and KMA for Southeast Asia, IMD for South Asia, Roshydromet for Central Asia, Kuwait for Middle East. |
| Capacity development requirements | Workshop on maintenance, field inspection, etc. (basic level), Workshop on traceability, measurement uncertainty, etc. (advanced level). |
| Partners/Participants | RA II Members |
| Funding Source(s) | This project will rely on existing budget allocations at the national level. Additional funding will be needed to dispatch experts to NMHSs in developing countries and/or invite their observational staff to RICs for trainings and calibrations of national standards. |
| Overall Costs | (TBD) |
| Timescale | 2013–2016 |
| Expected Key Deliverables / Key responsible body | Provision of technical support for instrument maintenance and calibration by experts from RICs. Holding a RIC’s training workshop for RA II Members. Development of training materials (to be prepared for publication as an IMOP technical document). Obtaining ISO/IEC 17025 certification. Portal Website to share outcomes of this project. Report on status on QC/QA procedures and site management in RA II. Reports on status on meteorological instruments, calibration and training in Regional Association II. |
| Main risk(s) | Lack of funding for technical missions by RICs, Insufficient communication between the Coordinator, RICs, and RA II Members on their status on maintenance and calibration of instruments to specify needs of technical supports, Lack of responses from RA II Members. |
| Website | RIC’s Website/Portal on QC/QA |
| Summary | Improvement of data quality of RA II Members through enhancement of RIC’s services and capacity |
| Date of the update | 21 November 2012 |
| Contact Person 1 | Mr Yoshihisa KIMATA Senior Coordinator for Observation Networks Administration Division, Observations Department Japan Meteorological Agency (JMA) Japan Tel.: +81 3 3211 6018 Fax: +81 3 3211 7084 Email: kimata@met.kishou.go.jp |
| Contact Person 2 | Mr He Xiaolei Meteorological Observation Center China Meteorological Administration (CMA) China Tel: +86 10 68409767 Fax: +86 10 68400936 E-mail: hxlaoc@cma.gov.cn |

_________

# Annex III

Table 2.	WIGOS implementation activities (R-WIP-III)

Activities in bold are considered the most critical for WIGOS to gain operational acceptance by 2015.

Depending on the implementation scale, planned activities are specified as follows: R = Regional activity and N = National activity.

Key to activity numbers: a, b and c, where a is number of respective sub-section of section 2, b is for a regional (2) or national (3) activity, and c is a sequential number to distinguish activities from one another.

| No. | Activity | Deliverables | Timeline | Responsibility | Estimated Costs | Potential risks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Management of WIGOS implementation in RA III |
| 1.1 R | Devise and keep up to date the WIGOS Regional Implementation Plan | WIGOS Regional Implementation Plan | 2013-2014 | RA III Working Group on Infrastructure and Technological Development (GTIDT) |  | Low (ongoing) |
| 1.2 R | Report progress on implementation to the RA III management group | Annual progress reports | 2013-2015 | RA III GTIDT |  | Low |
| 2. Collaboration with WMO and co-sponsored observing systems |
| 2.1 R | Identify and involve potential partners for regional data collection, clarifying areas of cooperation and governance mechanisms. | Increase the number of observations | 2012-2015 | GTIDT with the support of the RA III Working Groups on Climate and hydrology Services and Water Resources |  | High |
| 2.2 N | Encourage Member countries to identify and involve potential partners for national data collection, clarifying areas of cooperation and governance mechanisms. | Increase the number of observations. | 2012-2015 | Permanent Representatives of the Member countries |  | Medium |
| 2.3 R | Devise mechanisms to integrate observing systems with RA IV | Compatibility of observing systems and data management | 2012-2015 | Presidents of regional associations and Member countries |  | Medium |
| 3. Design, planning and optimized evolution of WIGOS and its regional, subregional and national observing components |
| 3.1 R | Update inventory of national networks, identifying the status and potential for exchange at the regional and international levels | Status report | 2013 | GTIDT observation subgroup, through WIGOS focal points, NMHSs and working groups |  | Medium |
| 3.2 N/R | Develop a consultation mechanism for defining requirements of users in the Region in terms of the twelve WIGOS application areas, using tools (RRR) available on the WMO Website | Table of requirements of the various users or areas | 2013-2015 | GTIDT observation subgroup through NMHSs and working groups |  | Medium |
| 3.3 R | Identify missing information in line with needs of users and design optimal regional network | Status report and proposed network design | 2013-2015 | GTIDT observation subgroup with Member countries |  | Medium |
| 3.4 R | Maintain and update the regional requirements for satellite information | Up-to-date reports on the requirements of each country | 2013-2015 | Specific working group to be set up, with experts from space agencies and NMHSs in Regions III and IV |  | Low |
| 3.5 R | Develop an implementation plan for a regional radar network, taking account of experience in Region IV | Implementation plan | 2013-2015 | RA III Working Group on Infrastructure and Technological Development (GTIDT) |  | Medium |
| 4. Integrated Observing System operation and maintenance |
| 4.1 R | Exchange experience with Members of the Region on best practice for operating and maintaining observing systems | Examples of best practice | 2013-2015 | Regional association, WMO Regional Office with the cooperation of the countries under the leadership of a GTIDT expert |  | Low |
| 5. Integrated quality management |
| 5.1 N/R | Assess and document the current status of meteorological instrument calibration | Status report | 2013-2015 | Regional Instrument Centre with the support of the countries and CIMO focal point in the Region |  | Medium |
| 5.2 N/R | Maintain calibration levels and gradually achieve instrument traceability in accordance with international standards | More countries meeting established standards | 2013-2015 | National Meteorological Services |  | Medium |
| 5.3 N/R | When calibration laboratories are established, efforts should be made to implement a quality management system based on ISO/IEC 17025 | Improve Members' capabilities | 2013-2015 | National Meteorological Services |  | High |
| 6. Standardization, system interoperability and data compatibility |
| 6.1 N/R | Complete the migration to TAC/TDCF coding in accordance with the requirements of the Commission for Basic Systems | Migration complete in the Region | 2013 | Telecommunications subgroup with the National Meteorological Services |  | Low |
| 6.2 N | Encourage countries to provide metadata from the observing station network, based on the standards to be defined by ICG-WIGOS | Availability of metadata | 2013-2015 | Members of RA III |  | Medium |
| 7. WIGOS Operational Information Resource |
| 7.1 R | Encourage Members to provide up-to-date metadata to the WIGOS Information Resource and ensure that it is maintained at all times | Keep up-to-date metadata at the WMO Secretariat | 2013-2015 | RA III Working Group on Infrastructure and Technological Development (GTIDT) and Members |  | Low |
| 8. Data discovery, delivery and archival |
| 8.1 R | Encourage Member countries to exchange data via WIS, including NMHSs and other organizations | New sources of data available through WIS | 2013-2015 | Telecommunications subgroup with the National Meteorological Services |  | Medium |
| 9. Capacity development |
| 9.1 R | Coordinate activities and training for the areas involved in WIGOS/WIS | Enhance the capacity of Member countries through workshops and horizontal cooperation | 2013-2015 | WMO and Member countries |  | Low |
| 9.2 R | Training in methods for quality control, calibration and traceability of meteorological instruments | Enhance the quality of observations | 2013-2015 | WMO and Member countries in coordination with CIMO |  | Low |
| 9.3 R | Coordinate training activities in the use of satellite data and products, especially the new generations | Improve capabilities for using satellite data and products | 2013-2015 | WMO and Member countries in coordination with CBS |  | Low |
| 10. Communication and outreach |
| 10.1 R | Contribute to WIGOS outreach by setting up an RA III Website and help to raise the profile of WIGOS by: (a) a link featured on the Websites of each Meteorological Service; (b) using materials to be provided by the WIGOS Project Office; (c) materials produced in the Region with the support of the WIGOS Project Office. | Raise awareness and visibility of WIGOS in the Region | 2013-2015 | Paraguay Meteorological Service, in cooperation with other countries and the WMO Secretariat |  | Low |
| 10.2 R | Contribute to WIGOS/WIS outreach by running a workshop for all Members of the Region | Raise awareness and visibility of WIGOS/WIS in the Region | 2013 | WMO |  | Low |
| 10.3 R | Promote national meetings to identify potential partners | Effective incorporation of national partners in WIGOS | 2013-2015 | Permanent Representatives of the Member countries |  | Low |

# Annex IV

Table 2	WIGOS Implementation Activities (R-WIP-IV)

Activities in bold are considered the most critical for WIGOS to gain operational acceptance by 2015.

Depending on the implementation scale, planned activities are specified as follows: R = Regional activity and N = National activity.

Key to activity numbers: a.b.c, where a is number of respective sub-section of section 2, b is for a regional (2) or national (3) activity, and c is a sequential number to distinguish activities from one another. ARB = Available Regular Budget. RB = Regular Budget.

| No | Activity | Deliverables | Timeline | Responsibility | Estimated Costs | Potential Risks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Management of WIGOS Implementation in RA IV |
| 1.1 | Regularly update the regional WIGOS Implementation Plan for RA IV (R-WIP) | Regional WIGOS Implementation Plan (RWIP) for RA IV | Developed in 2012 and updated as needed | Maintained by TT-WIGOS approved by MG |  | Low |
| 1.2 | RA IV Members to appoint National Focal Points and submit reports on progress of implementation of national plans | List of RA IV National Focal Points Updated national plans | 2013-2015 once per year | RA IV Members |  | Mod |
| 1.3 | Maintain close links to CBS, CIMO, other relevant TCs, ICG-WIGOS to capture and react to evolving plans. Provide recommendations to the ICG-WIGOS. | Updated R-WIP and contribution to the WIP | continuing | RA IV working groups; RA IV representatives on TCs |  |  |
| 1.4 | Report progress of RA IV R-WIP projects to RA IV MG | Progress reports | 2013-2015 once per year | Coordinators of Projects |  | Low |
| 1.5 | Compile information from Members, other relevant partners and WMO sources as input to existing national observing systems in RA IV. | A report detailing all the current observing systems in the region, including the composition of networks, data outputs and who are the owners/operators. | 2013 | TT-WIGOS assisted by the Secretariat |  | High |
| 1.6 | Task Team to assess the EGOS-IP and other WMO observing system implementation plans, to identify actions relevant to RA IV Members; assign priorities to these actions. | Prioritized list of actions for RA IV Members arising from the EGOS-IP and other IPs. | 2013-14 | TT-WIGOS approved by MG |  | Low |
| 2. Collaboration between observing systems: WMO, co-sponsored and other observing systems |
| 2.2 | Interface with the Inter-Programme Expert team for Observing system Evolution and Design (IPET-OSDE) and other international requirements review activities | Establish the working mechanisms with co-sponsored systems important to RA IV priorities | 2013 and onwards | MG and TT-WIGOS |  |  |
| 2.3 | Interface with EC PORS on Global Crysophere Watch observational components | National and regional observing system designs consider emerging GCW requirements | 2013 and onwards | Relevant Members |  |  |
| 2.4 | Strengthened the collaboration with TCs and develop a feedback mechanism | Meteorological observing systems are compliant with the range of quality standards. | 2013-15 | Members |  | Mod |
| 2.1 | Identify co-sponsored systems of benefit to the Region | A list of co-sponsored systems | 2013 and onwards | TT-WIGOS in coordination with MG |  |  |
| 2.5 | To work with the Secretariat to develop and implement the exchange of information for those co-sponsored of highest priority to the Region | Work with Secretariat to develop strategy for implementation of exchange of data. | 2013 and onwards | Members |  |  |
| 3. Design, planning and optimized evolution of WIGOS and its regional, sub-regional and national observing components |
| 3.1 | Compile the regional observational requirements including from: The Hurricane Committee’s Technical Plan; Marine Programmes including buoys and offshore platforms; Expanded space based observations including NESDIS activities; Expanded agro-met observations including USDA activities; Strategy for the architecture for climate monitoring from space. | Consolidated list of regional observations requirements. | 2013-14 | Members |  |  |
| 3.2 | Validate the user requirements documented by the global RRR process against: Regional user requirements; National user requirements for WMO systems. Use the results to update the RRR user requirements database and to fine tune the EGOS-IP and observing system plans. | Global RRR data updated in accordance with Regional requirements. Appropriate observing system implementation are updated by regional requirements | First quarter of 2014 Last quarter of 2014 | TT-WIGOS |  |  |
| 3.3 | Create an inventory of the existing regional Networks, including a process for its ongoing maintenance. (refer to 1.5) | Inventory and a plan for its periodic update. | 2013 and onwards | Members |  |  |
| 3.4 | Design and plan observing systems in the Region, following: The technical guidance of the TCs as represented in the EGOS-IP and other observation system implementation plans; The Regional priorities adopted by MG (refer to 1.6); Relevant actions identified in the Technical Plan of the Hurricane Committee; The information on silent stations and need for “gap filling” including the restoration of relevant silent stations following the RRR process; and (v) Cross-regional coordination opportunities. | Improved WMO observing system design in Region IV. | 2013 and onwards | Coordination by TT-WIGOS. |  |  |
| 3.5 | Design and execute impact experiments as needed, resources permitting, to provide decision-making support. | Publish reports results from any experiments undertaken and shared with all Members. | As necessary | Relevant Members |  |  |
| 3.6 | Evolve as feasible, existing regional observation networks to meet WIGOS standards. | Regional networks which would evolve to meet WIGOS standards | 2013 and onwards | Members |  |  |
| 3.7 | Define and implement the future regional network in accordance with WIGOS standards. | Definition of the regional WIGOS Network. Workplan for the implementation of the regional WIGOS Network | 2013-14 Within one year after the Definition | TT-WIGOS Adopted by MG |  |  |
| 3.8 | The evolution of the Island component of CARIB-HYCOS through database management and maintenance of the networks. | Maintained database and expanding network. | 2013 and onwards | National recipients and the CIMH |  |  |
| 3.9 | Investigate the need for additional Buoys. | Detailed reports of requirements and/or modifications from Region Members | 2013 and onwards | Member countries in Region IV and Hurricane Committee |  |  |
| 3. 10 | Evolve and implement National observing systems, following the guidance of: National Policy and priorities The technical guidance of the TCs as represented in the EGOS-IP and other observation system implementation plans; The regional priorities; Relevant actions identified in the Technical Plan of the Hurricane Committee; The need for “gap filling” and restoration of relevant silent stations. | Annual National reports of the improving WMO observing systems in Region IV. | 2013 and onwards | Member countries in Region IV. |  |  |
| 4. Integrated Observing System Operation and Maintenance |
| 4.1 | Develop real-time monitoring and reporting capability, to support operations; | A plan be developed for real-time monitoring and reporting implemented Implementation of the plan. | 2014-15 One year after the plan. | Relevant Members and TT-WIGOS to explore |  |  |
| 4.2 | Collect and share best practices from RA IV Members with other Regions | Shared best practices on the integration of observational systems | 2013 and onwards | Members |  |  |
| 4.3 | Develop a process for the identification, implementation and sharing of integrated products for service delivery including rainfall estimation | A process for the sharing of the integrated products | 2015 | TT-WIGOS |  |  |
| 4.4 | Exploit opportunities to benefit from the sharing of experiences, expertise and the pooling of resources across RA III and RA IV | Implementation of joint activities across RA III and RA IV | 2013 and onwards | Members |  |  |
| 5. Integrated Quality Management |
| 5.1 | Obtain ISO/IEC 17025 accreditation for calibration labs | Accredited calibration labs | 2013 and onwards | National and Regional Instrument Centres |  |  |
| 5.2 | Intercomparison standards between RICs | Traceability between RICs | 2013 and onwards | Regional Instrument Centres |  |  |
| 5.3 | Enhance support by RICs, and to encourage Members to work with RICs to ensure traceability of standards | Improved data quality of surface observations | 2013 and onwards | Regional Instrument Centres and Members |  |  |
| 5.4 | Survey and share status on maintenance and instruments calibration for surface-based observations | Reports on status on instruments calibration for surface-based observations | 2013 and onwards | Members |  |  |
| 5.5 | Monitoring data quality to support QA and linked to 4.1 | Develop monitoring capability to support QM | 2013 and onwards | Members |  |  |
| 6. Standardization, System Interoperability and Data Compatibility |
| 6.1 | Implement the WMO Siting Classification Scheme in through: Provision of information and training to Member countries; and Adoption of new procedures by Member countries. | WMO Siting Classification Scheme is implemented in RA IV. | 2013 and onwards | Members |  |  |
| 6.2 | Develop a process to monitor and report on the level of regional compliance with WIGOS standards. | A process is developed to monitor and report on the level of regional compliance with WIGOS standards. | 2013 and onwards | Regional Association |  |  |
| 6.3 | Survey and share status on QC/QA procedures and site management for the network of RBCN and RBSN stations, changes to the site after installation needs to be documented. | Reports on status on QC/QA procedures and site management in RA IV | 2013 and onwards | Members |  |  |
| 6.4 | Request the collection of metadata on all observing stations | Collection of metadata on all observing stations | 2013 and onwards | Members |  |  |
| 6.5 | Review and suggest requirements for new WIGOS standards and/or regional best practices. | Proposals for updating WIGOS standards and/or regional best practices. | 2015 | TT-WIGOS |  |  |
| 6.6 | Radar data integration | Develop specific data collection requirements in support of hurricane analysis and prediction using Caribbean radars; Assess data collection costs for integration of regional radars into near real-time central collection and distribution database’ | 2013 and onwards | TT-WIGOS US |  |  |
| 6.7 | Regional Radar Mosaics | Plans for development of regional or sub-regional mosaics; Implementation of mosaics. | 2013 and onwards | TT-WIGOS and appropriate Members |  |  |
| 7. The WIGOS Operational Information Resource |
| 7.1 | Request, support and encourage Members to provide up-to-date data and metadata to the WIR and ensure its on-going maintenance. | Up-to-date metadata maintained at WMO. | 2013 and onwards | Members |  |  |
| 7.2 | Develop a Regional Information Portal to share: EGOS national reports; Regional standards and best practices; Status QC/QA procedures and site management for the network of RBCN and RBSN stations; share status on maintenance and the instruments calibration for surface-based observations | Information in the Regional Information Portal. | 2013 and onwards | Regional Association |  |  |
| 8. Data discovery, delivery and archival |
| 8.1 | Foster increased exchange of observations data and discovery metadata using WIS in the Region, through awareness raising and provision of guidance for the adoption of WIS standards, including implementation of Data Collection and Production Centres (DCPC) and National Centres (NC) | Increased provision of “discovery metadata” hence accessibility of data through the WIS. | 2013 and onwards | TT-WIGOS |  |  |
| 8.2 | Members to designate NCs and DCPCs | Members designated as NCs and DCPCs | 2013 and onwards | MG |  |  |
| 8.3 | Requests Members to share data via WIS, including data from national organizations other than NMHSs | New sources of data are available through WIS | 2013 and onwards | MG |  |  |
| 8.4 | Maintain catalogue services at each NOAA archival Data Center. Begin assigning persistent identifiers (DOIs) to archived datasets. | A catalogue | 2013 and onwards | United States |  |  |
| 9. Capacity development |
| 9.1 | Creating a regional capacity development plan to include: Radar data analysis and transfer; Improving availability and utilization of AMDAR data; Improving availability and utilization of observation data including metadata; Improving availability and utilization of high resolution radiosonde data; Improving the utilization of satellite data and products; Improving the utilization of marine data and products. | A regional capacity development plan | 2013 and onwards | Members |  |  |
| 9.2 | Review the regional and national technical training requirement to identify gaps and develop training opportunities such as: QA/QC procedures; Maintenance of instruments; National calibration. | A regional training plan for the gaps identified in the review | 2013 and onwards | Members to review, adopted by MG |  |  |
| 10. Communication and outreach |
| 10,1 | Participate in the development of a CBS Socio-economic Impact message | The development of a socio-economic impact message which can be tailored to be used at the National level | 2013 and onwards | Members |  |  |
| 10.2 | Interlink RA IV WIGOS portals and related Websites | Better access to RA IV WIGOS-related information and products | 2013 and onwards | Members |  |  |
| 10.3 | Develop RIC Websites to include content such as: Calibration services provided; Utilization of the services by Members; Purchasing of instruments. | Provide guidance on the content of the RIC’s Websites | 2013 and onwards | RICs in consultation with the MG |  |  |
| 10.4 | Contribute to WIGOS communication and outreach across the Region IV and within Member States to all organizations by: Responding to the role defined in the ICG-WIGOS communication strategy; Utilizing material provided by WIGOS-PO to raise awareness and commitment to WIGOS in Region V. | Effective communication and outreach for WIGOS across Region IV. | 2013 and onwards | Members |  |  |

# Annex V

Table 2 WIGOS Implementation Activities (R-WIP-V)

Activities in bold are considered the most critical for WIGOS to gain operational acceptance by 2015.

Depending on the implementation scale, planned activities are specified as follows: R = Regional activity and N = National activity.

Key to activity numbers: a.b.c, where a is number of respective sub-section of section 2, b is for a regional (2) or national (3) activity, and c is a sequential number to distinguish activities from one another. ARB = Available Regular Budget. RB = Regular Budget.

| No. | Activity | Deliverables | Timeline | Responsibility | Estimated Costs | Potential Risks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Management of WIGOS Implementation in Region V |
| 1.2.1 R | Develop the Regional WIGOS Implementation Plan for Region V (R-WIP-V) | Regional WIGOS Implementation Plan for Region V (R-WIP-V) | 2012-13 | Drafting by WG-Infrastructure (TT-WIGOS), adoption by President RA-V |  | Low |
| 1.2.2 R | Compile information from Member countries, other relevant partners and WMO sources as input to a “stock-take” of existing WMO observing systems in RA-V. | A report detailing all the current WMO observing systems in Region V, including the composition of networks, data outputs and who the owners/operators are. | 2013 | WG-Infrastructure (TT-WIGOS) assisted by Secretariat |  | High |
| 1.2.3 R | Assess the EGOS-IP and other WMO observing system implementation plans to identify actions relevant to RA-V and Member countries; assign priorities to these actions. | Prioritised list of actions for RA-V and for Members arising from the EGOS-IP and other IPs. | 2012-13 | Drafting by WG-Infrastructure (TT-WIGOS), adoption by President RA-V |  | Low |
| 1.2.4 R | Provide an effective RA-V focal point to liaise with CBS about the implementation of EGOS-IP in RA-V. | An effective RA-V focal point for EGOS-IP, who is actively corresponding with CBS. | 2012-15 | RA-V MG, focal point for EGOS-IP |  | Mod |
| 2. Collaboration with WMO and co-sponsored observing systems |
| 2.2.1 R | Identify and engage further potential partners for collaboration in the collection of observations on a Regional scale. Clarify the target area/s for collaboration and the mechanism for resolving governance issues. | A report on existing partnerships on a Regional level, to provide a baseline and reference, | 2012-15 | WG-Infrastructure (TT-WIGOS). |  | Mod |
| 2.3.1 N | Encourage Member countries to identify and engage further potential partners in the collection of observations for WMO programs. Clarify the target area/s for collaboration and the mechanism for resolving governance issues. | Increased number of collaborating partners at a National level and increased collection of observations. | 2012-15 | Encouragement by MG, action by all Member countries in RA-V. |  | Mod |
| 2.2.2 2.3.2 R, N | Collaborate with CIMO to develop a reliable feedback mechanism on the performance of instruments and systems in Region V. Provide feedback regularly. | A status report is provided to RA-V and CIMO on progress of meteorological observing systems against WMO regulations and standards. | 2013 | WG-Infrastructure (TT-Traceability) develop mechanism, Member countries in RA-V provide feedback. |  | Mod |
| 3. Design, planning and optimized evolution of WIGOS component observing systems at regional, sub-regional and national levels |
| 3.2.1 R | Design and plan observing systems in the Region, taking into account: the technical guidance of the technical commissions as represented in the EGOS-IP and other observation system implementation plans; the Regional priorities adopted by President RA-V (see action item 1.2.3); relevant actions identified in the Technical Plan of the Tropical Cyclone Committee for the South Pacific and South-East Indian Ocean; the need for “gap filling” and restoration of silent stations; and (v) cross-regional coordination opportunities. | Improved WMO observing system design in Region-V. | 2012-15 | Coordination by WG-Infrastructure (TT-WIGOS). |  | High |
| 3.3.1 N | Evolve and implement National observing systems, taking into account: the technical guidance of the technical commissions as represented in the EGOS-IP and other observation system implementation plans; the Regional priorities adopted by President RA-V (see action item 1.2.3); relevant actions identified in the Technical Plan of the Tropical Cyclone Committee for the South Pacific and South-East Indian Ocean; the need for “gap filling” and restoration of silent stations. | Improved WMO observing systems in Region-V. | 2012-15 | Member countries in Region V. |  | High |
| 3.2.2 R | Define and describe the Regional WIGOS Network (building on action item 1.2.2) as the collective identity for all WMO observing systems in Region V. | A report to convey the definition and description of the Regional WIGOS Network. | 2014 | WG-Infrastructure (TT-WIGOS). |  | High |
| 3.2.3 R | Validate the user requirements documented by the global RRR process against Regional user requirements; use the results to update the RRR user requirements database and to fine tune the EGOS-IP and observing system plans. | WMO observing systems are responsive to Regional user requirements. | 2013-15 | WG-Infrastructure (TT-WIGOS). |  | Mod |
| 3.3.2 N | Validate the user requirements documented by the global RRR process against National user requirements for WMO systems; use the results to update the RRR user requirements database and to fine tune the EGOS-IP and observing system plans. | WMO observing systems are responsive to National user requirements for WMO systems. | 2013-15 | Member countries in Region V. |  | Mod |
| 4. Integrated Observing System Operation and Maintenance |
| 4.2.1 R | Compile, from Member contributions, a set of examples of integrated operation and maintenance between observing system owners/operators, covering the sharing of experiences, practices and ideas, the sharing of expertise and the pooling of resources for joint activities; noting specifically that: training is an effective way to share knowledge and skills; funding for capacity development is often the trigger which enables increasingly integrated approaches. Promote this report amongst Member countries as a stimulus for thinking broadly about opportunities to benefit from integration. | A report providing examples of integrated approaches to operation and maintenance. | 2013 | WG-Infrastructure (TT-WIGOS). |  | low |
| 4.2.2 R | Capacity development in data communication techniques related to observations collection and reporting | Reference material, case studies and training, leading to enhanced capacities | 2013-15 | WG-Infrastructure (TT- PSC) |  |  |
| 4.2.3 R | Capacity Building in Radar Techniques in Southeast Asia, supported by appropriate technical missions to countries, through: All the ASEAN developing countries will prepare a national report on their arrangements for the operational use of weather radar data; and A sub/cross-region (for the ASEAN developing countries) strategic plan for addressing technical issues and necessary actions identified in the national reports. | Enhanced capacity in monitoring and forecasting of severe weather using radar data. | 2013-15 | Those Member countries involved in the sub-Regional /cross-Regional (with RA-II) ASEAN Sub-Committee on Meteorology and Geophysics |  | Mod |
| 5. Integrated Quality Management |
| 5.2.1 R | Progressively achieve traceability to SI standards of measurements made throughout RA V, focusing initially on surface pressure, temperature, precipitation, humidity, also sea level. | Traceable observations from progressively more components of the Regional WIGOS Network. | 2012-15 | WG-Infrastructure (TT-Traceability), in collaboration with the RICs and Members. |  | Mod |
| 5.2.2 5.3.1 R, N | Develop a self-assessment tool to enable Members to follow CIMO guidelines for observations | Self-assessment tool. | 2014 | WG-Infrastructure (TT-Traceability), with input from Members. |  | High |
| 5.2.3 R | Actively review and respond to the findings of CBS’ periodic data flow monitoring exercises. | An active review process. | 2012-15 | WG-Infrastructure (TT-WIGOS). |  | Low |
| 5.2.4 R | Find new means of continuous monitoring of observations data quality in Region V with the support of Centres of the GDPFS (Global Data Processing and Forecasting System). | Request is made (for the systemic errors in observations from the analysis scheme) and collaboration is established with Chair OPAG-GDPFS on this topic. | 201x | WG-Infrastructure (TT-WIGOS), in collboration with Centres of the GDPFS. |  | Mod |
| 6. Standardization, System Interoperability and Data Compatibility |
| 6.2.1 R | Achieve the migration to Table Driven Code Forms throughout Region V as specified by CBS. | Completed migration to Table Driven Code Forms throughout Region V. | 2014 | WG-Infrastructure (TT-TDCF). |  | Mod |
| 6.2.2 R | Develop a process to monitor and report on what Members currently do in relation to compliance with WIGOS standards. | A process is developed to monitor and report on what Members currently do in relation to compliance with WIGOS standards. | 20xx | WG-Infrastructure (TT-WIGOS). |  | Mod |
| 6.2.3 R | Review and suggest requirements for new WIGOS standards and/or regional best practices. | Proposals for new WIGOS standards and/or regional best practices. | 20xx | WG-Infrastructure (TT-WIGOS). |  | Mod |
| 6.2.4 6.3.1 R,N | Implement the WMO Siting Classification Scheme in RA V, through: Provision of information and training to Member countries, and Adoption of new procedures by Member countries. | WMO Siting Classification Scheme is implemented in RA V. | 201xxx | WG-Infrastructure |  | high |
| 6.2.5 R | Determine capacity of WMO Members in RA-V to maintain and submit to WMO interpretation metadata (as currently required for Vol. A) | Report on the capacity of WMO Members in RA-V to maintain and submit to WMO interpretation metadata (as currently required for Vol.A)… | 2014 | WG-Infrastructure (TT-WIGOS). |  | Mod |
| 7. The WIGOS Operational Information Resource (WIR) |
| 7.2.1 R | Request, support and encourage Members to provide up-to-date metadata to the WIR and ensure its ongoing maintenance. | Up-to-date metadata maintained at WMO. | 201x-(dependent on completion of database) | WG-Infrastructure (TT-WIGOS). |  | Mod |
| 8. Data discovery, delivery and archival |
| 8.2.1 R | Foster increased exchange of observations data and discovery metadata using WIS in the Region, through awareness raising and provision of guidance for the adoption of WIS standards, including implementation of Data Collection and Production Centres (DCPC) and National Centres (NC), in collaboration with GISC Melbourne. | Increased provision of “discovery metadata” hence accessibility of data through the WIS. | 2012-15 | WG-Infrastructure (TT-WIS). |  | Mod |
| 8.2.2 R | Encourage Member countries to share data via the WIS, including from organizations other than NMHSs. | New sources of data are available through the WIS. | 2012-15 | WG-Infrastructure (TT-WIS). |  | Mod |
| 9. Capacity development |
| 9.2.1 R | Assist Member countries to introduce or improve institutional mandates and policies relating to observing systems. | Improved institutional mandates and policies in Member countries relating to observing systems. | 2012-15 | Management Group, supported by TT-WIGOS. |  | Mod |
| 9.2.2 9.3.1 R, N | Assist Member countries to fill gaps (both infrastructure and human capacities) in their WIGOS observing systems, in particular: Assist Fiji to fully implement and sustain their calibration facilities (end of 2013); | Gaps (both infrastructure and human capacities) in the WIGOS observing systems of Member countries are identified and filled. | 2012-15 | WG-Infrastructure (TT-WIGOS, TT-TO), in collaboration with Regional partners and Members. |  | Mod |
| 10. Communication and outreach |
| 10.2.1 R | Contribute to WIGOS communication and outreach across Region V by: responding to the role defined in the ICG-WIGOS communication strategy; utilising material provided by WIGOS-PO to raise awareness and commitment to WIGOS in Region V. | Effective communication and outreach for WIGOS across Region V. | 2012-15 | WG-Infrastructure (TT-WIGOS) and Management Group. |  | Low |
| 10.3.1 N | Contribute to WIGOS communication and outreach within Member Countries by: responding to the role defined in the ICG-WIGOS communication strategy; utilising material provided by WIGOS-PO to raise awareness and commitment to WIGOS in Region V. | Effective communication and outreach for WIGOS within Member countries. | 2012-15 | WMO Member countries in Region V. |  | Low |

# _______________

# Annex VI

Table 2	WIGOS Implementation Activities (R-WIP-VI)

Activities in bold are considered the most critical for WIGOS to gain operational acceptance by 2015.

Depending on the implementation scale, planned activities are specified as follows: R = Regional activity and N = National activity.

Key to activity numbers: a.b.c, where a is number of respective sub-section of section 2, b is for a regional (2) or national (3) activity, and c is a sequential number to distinguish activities from one another. ARB = Available Regular Budget. RB = Regular Budget.

| No | Activity | Deliverables | Timeline | Responsibility | Estimated Costs | Potential Risks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Management of WIGOS Implementation in RA VI |
| 1.2.1 | Regularly update the Regional WIGOS Implementation Plan for RA VI (R-WIP-VI). | R-WIP-VI developed | Developed in 2013 and updated as needed | Maintained by TT-WIGOS approved by WG-TDI & MG |  |  |
| 1.2.2 | Maintain close links to CBS, CIMO, other relevant TCs and ICG-WIGOS to capture and react to evolving plans. Provide recommendations to the ICG-WIGOS. | Updated R-WIP-VI and contribution to the WIP | continuing | RA VI WG-TDI; RA VI representatives on TCs, RA-VI MG |  |  |
| 1.2.3 | Report progress of R-WIP related projects to RA VI MG. | Progress reports | Once per year | Coordinators of Projects: TT-WIGOS |  |  |
| 1.2.4 | Assess the EGOS-IP to identify actions relevant to RA VI and Member countries; assign priorities to these actions. | Prioritized list of actions for RA VI and for Members arising from the EGOS-IP | 2013-14 | Drafting by WG-TDI / TT-WIGOS (TBD) adoption by MG |  |  |
| 1.3.1 | Assist Members to develop their National WIGOS Implementation Plans (N-WIPs). | N-WIPs developed | 2014-15 | Members, TT-WIOGOS WIGOS-PO |  |  |
| 1.3.2 | RA VI Members to appoint National Focal Points (NFP) and submit reports on progress of implementation of N-WIPs. | List of RA VI NFP published; Updated N-WIPs | 2013-15; updates once per year | WIGOS-PO, ROE RA VI Members |  |  |
| 2. Collaboration with WMO and co-sponsored observing systems |
| 2.2.1 | Identify and engage further potential partners for collaboration in the collection of observations on a Regional scale. Clarify the target area(s) for collaboration and the mechanism for resolving governance issues. | Increased number of collaborating partners at a Regional level and increased collection of observations. | 2013-15 | WG-TDI; TT-WIGOS; Regional Office for Europe (ROE) |  |  |
| 2.3.1 | Encourage Member countries to identify and engage further potential partners in the collection of observations for WMO programs. Clarify the target area/s for collaboration and the mechanism for resolving governance issues. | Increased number of collaborating partners at a National level and increased collection of observations. | 2013-15 | Encouragement by the President, with support of MG members, action by Members |  |  |
| 2.3.2 | Collaborate with CIMO to develop a feedback mechanism to CIMO on the performance of instruments and systems in Region VI. Provide feedback regularly. | Meteorological observing systems are widely compliant with WMO regulations and standards. | 2013-15 | WG-TDI; TT-RICs; Members provide feedback. |  |  |
| 3. Design, planning and optimized evolution of WIGOS and its regional, sub-regional and national observing components |
| 3.2.1 | Design and plan observing systems in the Region, taking into account: The network design studies conducted and planned by the EUMETNET Observing Programme, and other relevant studies the technical guidance of the technical commissions as represented in the EGOS-IP and other observation system implementation plans; the need for applying WIGOS QM (see Key implementation activity 5) the need for “gap filling” and restoration of silent stations; and cross-regional coordination opportunities, such as Arctic HYCOS and GCW | Redesigned the Regional Observing Network. | 2015-16 | Coordination by WG-TDI; TT-WIGOS |  |  |
| 3.2.2 | Validate the user requirements documented by the global RRR process against Regional user requirements; use the results to update the WMO RRR user requirements database and to contribute to the update of the EGOS-IP and observing system plans. | WMO observing systems are responsive to Regional user requirements. | 2013-15 | WG-TDI; TT-WIGOS |  |  |
| 3.3.1 | Evolve and implement National observing systems, taking into account: the technical guidance of the technical commissions as represented in the EGOS-IP and other observation system implementation plans; the Regional priorities adopted by MG; the need for applying WIGOS QM (see Key implementation activity 5) the need for “gap filling” and restoration of silent stations. | Improved WMO observing systems in the Region | 2016 onwards | Members |  |  |
| 3.3.2 | Validate the user requirements documented by the global RRR process against National user requirements for WMO systems; use the results to update the WMO RRR user requirements database and to contribute to the update of the EGOS-IP and observing system plans. | WMO observing systems are responsive to National user requirements for WMO systems. | 2013-15 | Members |  |  |
| 3.3.3 | Migrate from the existing RBSN/RBCN into an integrated RBON | RBONs designed and adopted by RAs | 2015 onwards | RAs, Members |  |  |
| 3.3.4 | Define sub-Regional user requirements for observations | Updated RRR database (OSCAR) | 2015 | Members |  |  |
| 4. Observing System Operation and Maintenance |
| 4.2.1 | Develop real-time monitoring and reporting capability to support operations; possibly using existing EUMETNET EUCOS monitoring Portal. | A plan for real-time monitoring and reporting implemented. Implementation of the plan. | 2014-15; Operations one year after the plan. | Relevant Members; EUMETNET and TT-WIGOS |  |  |
| 4.3.1 | Collect and share best practices from Members with other Regions. | Documented best practices of the Region on the WMO website. | 2013 and onwards | Members, ROE |  |  |
| 5. Quality Management |
| 5.2.1 | Implement the real-time quality monitoring of basic surface variables (temperature, pressure, humidity, wind and precipitation) using the existing systems, such as EUMETNET/EUCOS QM Portal. | Extended quality monitoring implemented. | 2015 onwards | WG-TDI and TT-WIGOS in collaboration with ECMWF and other relevant NWP centres |  |  |
| 5.2.2 | Consider implementation of real-time quality monitoring of data from various remote sensing instruments/systems | Decision on implementing of real-time quality monitoring of data from various remote sensing instruments/systems | 2014 | WG-TDI and TT-WIGOS QM |  |  |
| 5.2.3 | Improve collaboration among the RICs and RICs and Members. | Inter-Laboratory Calibration regularly conducted. | 2013-15 | TT-RIC |  |  |
| 5.2.4 | Assist Members to implement required calibration and maintenance practices and procedures. | Survey of current calibration capabilities of Members; Trainings conducted; On-site assistance provided. | 2013-15 | TT-RIC |  |  |
| 5.2.5 | Combine technological knowledge to help Members in the maintenance and calibration of the surface-based remote-sensing systems. | International team of experts set-up to assist Members. | 2014 and onwards | WG-TDI; TT-WIGOS |  |  |
| 5.3.1 | Obtain as far as possible ISO/IEC 17025 accreditation for calibration laboratories. | Increased accredited calibration laboratories of Members. | 2014 and onwards | Members’ national calibration laboratories |  |  |
| 6. Standardization, System Interoperability and Data Compatibility |
| 6.3.1 | Implement the WMO Siting Classification Scheme through: Provision of information and training to Members, Adoption of new procedures by Members, A tool to classify the sites. | WMO Siting Classification Scheme is implemented in the Region. | 2015 | Members |  |  |
| 6.3.2 | Develop a process to monitor and report on the level of regional compliance with WIGOS standards. | A process is developed and implemented; Report on the level of compliance of Members’ with WIGOS related standards is provided. | 2015 and onwards | WG-TDI to develop a process; Members to report |  |  |
| 6.3.3 | Collect the metadata on all observing stations according to a standard to be developed by ICG-WIGOS. | WIGOS Metadata on all observing stations is collected. | 2014 and onwards | Members |  |  |
| 6.3.4 | Radar data integration through the existing mechanism, i.e., OPERA, and based on existing practices adopted by OPERA. | Increased number of radars integrated into the OPERA; Harmonization of sub-regional radar networks based on OPERA practices. | 2015 and onwards | TT on Radar data integration (TBD); Members |  |  |
| 6.3.5 | Wind profiler data integration through the existing mechanism, i.e., WINPROF, and based on existing practices adopted by WINPROF. | Increased number of WP integrated into the WINPROF. | 2015 and onwards | TBD; Members |  |  |
| 7. The WIGOS Operational Information Resource (WIR) |
| 7.3.1 | Request, support and encourage Members to provide up-to-date data and metadata to the WIR and ensure its on-going maintenance. | Up-to-date metadata maintained at WMO. | 2014 and onwards | WG-TDI and TT-WIGOS to request and support; Members to provide metadata |  |  |
| 8. Data discovery, delivery and archival |
| 8.2.1 | Develop a standard for representation and format of hydrological data | A standard for representation and format of hydrological data developed | 2015 | WG-TDI in collaboration with RA VI Hydrological advisor |  |  |
| 8.2.2 | Foster increased exchange of observational data and discovery metadata using WIS in the Region, through awareness raising and provision of guidance for the adoption of WIS standards, including implementation of Data Collection and Production Centres (DCPC) and National Centres (NC). | Increased provision of “discovery metadata” and the accessibility of data through the WIS. | 2014 and onwards | WG-TDI |  |  |
| 8.3.1 | Expedite the implementation of WIS-IP. | Regular monitoring reports are available. | 2013 and onwards | Members; WG-TDI |  |  |
| 8.3.2 | Members to share data via WIS, including data from national organizations other than NMHSs. | New sources of data are available though WIS. | 2013 and onwards | Members; WG-TDI |  |  |

| 9. Capacity development |
| --- |
| 9.2.1 | Assist Member countries to fill gaps (both infrastructure and human capacities) in their WIGOS observing systems. | Gaps in the WIGOS observing systems of Member countries are identified and filled. | 2013-15 | WG-TDI; TT-WIGOS; ROE; WIGOS-PO |  |  |
| 9.2.2 | Creating a regional Capacity Development Plan, addressing identified needs for: radar data analysis and transfer; improving availability and utilization of AMDAR data; improving availability and utilization of high resolution radiosonde data; improving the utilization of marine data; Improved availability of lidar measurements for aerosol and volcanic ash; … | A regional Capacity Development Plan developed and agreed by the MG. | 2014 and onwards | WG-TDI; ROE; WIGOS-PO; Members |  |  |
| 9.3.1 | Review the Regional and National technical training requirement to identify gaps and develop training opportunities such as for: Network design QA/QC procedures; Maintenance of instruments; National calibration | A regional training plan to fill the gaps is developed and agreed by the MG | 2013 and onwards | Members to propose; WG-TDI in collaboration with ROE, RA6-MG and ETR Division |  |  |
| 9.3.2 | Assist Members in using WIR Tools for the design and management of national WIGOS networks. | Initial steps taken to improve design on national networks | 2015 | WG-TDI in collaboration with ICG-WIGOS WMO Members |  |  |
| 9.3.3 | Assist Members in implementing WIGOS metadata | Tools and procedures available to assist Members in providing the WIGOS metadata | 2014 | WMO Secretariat, WG-TDI and Members |  |  |
| 10. Communication and outreach |
| 10.2.1 | Contribute to WIGOS communication and outreach across the Region by: Responding to the role defined in the ICG-WIGOS communication strategy; Utilizing material provided by WIGOS-PO to raise awareness and commitment to WIGOS in the Region. | Effective communication and outreach for WIGOS across the Region. | 2013-15 | WG-TDI; TT-WIGOS; WIGOS-PO |  |  |
| 10.3.1 | Contribute to WIGOS communication and outreach within Member Countries by: Responding to the role defined in the ICG-WIGOS communication strategy; Utilizing material provided by WIGOS-PO and Members to raise awareness and commitment to WIGOS in the Member Countries. | Effective communication and outreach for WIGOS within Member countries. | 2013-15 | Members, PWS |  |  |

_________

# Footnotes

www.wmo.int/pages/prog/www/wigos/documents.html

See the Final Report at: www.wmo.int/pages/prog/www/WIGOS-WIS/reports.html

It is expected that mandate of TT-WIGOS will be extended by RA-I MG in October 2012 until the end of 2015;

Linkage with implementation of GFCS

See Section 2.3, p. 8

Agreement of the TT-WIGOS is needed on this issue: to specify it in general or with a specific focus on the most critical variables, such as listed here

See 2.5, p. 9

Specialized education, training activities and improvement of necessary observing infrastructure should be reflected in the regional, sub-regional and national WIGOS implementation plans, especially for NMHSs of LDCs, LLDCs and SIDS. Hence, capacity building is not to be limited to scientific and technological concerns, but also to strategic and management consideration including human resources development, resource mobilization and communications and outreach activities.