| WORLD METEOROLOGICAL ORGANIZATION |
| --- |
| COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION OPAG-CAPACITY BUILDING CIMO EXPERT TEAM ON REGIONAL INSTRUMENT CENTRES, QUALITY MANAGEMENT SYSTEMS AND COMMERCIAL INSTRUMENTS INITIATIVES Reduced Session GENEVA (SWITZERLAND), 4-7 APRIL 2006 |  | CIMO/OPAG-CB/ /ET-RICs/Doc. 3 (8.III.2006) _________ ITEM: 3 Original: ENGLISH ONLY |

# WORK PLAN

(Submitted by the Secretariat)

______________________________________________________________

Summary and purpose of  document

This document summarizes the plan of tasks, actions and deliverables of the Expert Team

Action proposed

The Expert Team is invited to review the Work Plan and adjust the deadlines accordingly.

Draft WORK PLAN

Expert Team on RICs, Quality Management Systems and Commercial Instruments Initiatives

(2003-2006)

| No. | Task description | Person responsible | Action | Deadline | Deliverables | Deadline |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Boost activities of RICs to maximize their effectiveness in collaboration with RAs: |  |  |  |  |  |
| 1 a) | Strengthen further the services of RICs, particularly those located in developing countries, such as calibration practices and reporting | Heng ZHOU & Wenhua LU | Analyze Questionnaire No.4 on RICs Conduct survey on RICs by Questionnaire No.5 Develop Plan of evaluation visits to RICs Develop recommendation on required improvements and on the ways to strengthen RICs | Dec.03 Oct.05 Mar.04 Dec.04 | Report on RICs Analyzed results of survey on RICs Plan of evaluation visits Recommendations on the: Improvements required, Ways to strengthen RICs | Feb.04 Dec.05 Feb.04 Feb.05 |
| 1 b) | Explore the possibility of strengthening cooperation among RICs by the establishment of a mutual relationship between RICs in the developed and the developing countries | Heng ZHOU & Nicolaas G. SWART | Explore the possibility of strengthening cooperation among RICs Investigate possibilities of establishment of a mutual relationship between RICs in the developed and the developing countries | Dec.04 Feb.05 | Recommendations on cooperation methods, e.g. mentoring, training of trainers, attachments Draft proposals for a mutual relationship between RICs | Jan.05 May.05 |
| 1 c) | Improve the guidance for RICs, review their terms of reference and develop an appropriate procedure to assist in evaluation of RICs | Kenneth L. RANCOURT | Review TOR of RICs Develop criteria for evaluation of RICs Prepare Manual on RICs’ activities | Feb.04 Mar.04 Dec.04 | Reviewed TOR Report on developed evaluation criteria IOM Report on Manual on RICs’ activities | Mar.04 May.04 Feb.05 |
| 1 d) | Conduct periodic visits to RICs, by CIMO's representative or regional authority, to provide needed training/briefings and validating the compliance to the stated terms of reference. Evaluate existing RICs | Heng ZHOU & Kenneth L. RANCOURT | Conduct visits to RICs Evaluate existing RICs against agreed criteria | Dec.05 Dec.05 | Visits of RICs completed IOM Report on Results of the evaluation of RICs | Dec.05 Feb.05 |
| 2 | Provide advice on Quality Management Systems procedures for instruments and methods of observation (based on the CIMO Guide) and implement links with relevant international organizations active in this area |  |  |  |  |  |
| 2 a) | Develop performance measures to demonstrate continuous improvement in the quality of observations | Bruce FORGAN | Develop basic procedures for quality management of observations, instrument maintenance, calibration and operational practices | Sep.04 | IOM Report on Basic procedures for quality management of observations, instrument maintenance, calibration and operational practices | Nov.04 |
| 2 b) | Contribute to the review and update of WMO Technical Regulations, Guides and other material related to Quality Management and standardization of observations | Bruce FORGAN | 1. Prepare proposal for relevant updates of CIMO Guide Prepare proposals for update of WMO Technical Regulations and Guides | Nov.04 Dec.05 | CIMO Guide updated Proposals submitted to CIMO-XIV | Jan.05 May.06 |
| 3 | Review and suggest methods to develop the IMOP capacities of developing countries, in collaboration with HMEI |  |  |  |  |  |
| 3 a) | Encourage development, fabrication of instruments and operation of low-cost, good quality meteorological and hydrological observing systems | Heng ZHOU & Samuel A. ADERINTO | Review the requirements for observation equipment in developing countries Explore the possibilities of enhancing equipment development in developing countries Study the possibilities for joint procurement mechanisms for consumables and equipment to assist in achieving a reduction in the cost of instrument operation | Dec.04 Dec.04 Dec.04 | IOM Report on Requirements for observation equipment in developing countries Proposals for enhancing equipment development in developing countries Proposals for joint procurement mechanisms for consumables and equipment | Mar.05 Feb.05 Feb.05 |
| 3 b) | Consider possible means to minimize the impact on the cost of the continuous improvements of instruments | Bruce FORGAN | Study the impacts Suggest means to minimize impacts | Mar.04 May.04 | IOM Report on Means to minimize the impact on the cost of the continuous improvements of instruments | Jun.04 |