Workplan of the Expert Team on Operational Metrology (2014-2018)
(Version: 05.09.2017)

| No. | Task description | Person responsible and subteam | Action | Deliverable | Deadline for deliv. | Priority | Status [%] | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Estimation of calibration uncertainty – traceability to SI | D.Groselj, A.Mounir, T.Holfelder, N.Mander | 1. Review document on computation of calibration uncertainties 2. Develop workshop on uncertainty calculations 3. Carry-out workshop | 1. IOM report on calibration uncertainties 2a. Concept for Workshop 2b. Training units and associated presentations prepared. 3. Workshop carried out | 1. Approved for publication 2a. Dec 2016 (Drago) 2b. June 2017 General Uncertainties (Francoise, Drago) Temperature (Drago, Michael) Humidity (Aziz / Drago) Pressure (Tilman / Holger) Solar Radiation (DWD?, Krunoslav) Precipitation (Drago, contact LC in Italy, Francoise, Neil) Wind (Tilman / Holger) 3. Spring 2018 | M | 100% 25% 0% | CIMO-XV para 6.3 CIMO-16, Doc. 6, para 6.9 Workshop should also address how to establish calibration certificates Workshop could be done on-site, or possibly remotely (including RICs). |
| 2. | RIC inter-laboratory intercomparisons (demonstrating capabilities in achieving declared RIC calibration and measurement capabilities (CMCs)) | RA-VI: D.Groselj, F.Montariol, RA-II & V: K.Nakashima, F.Barcenas, RA-I: A.Mounir, RA-IV & III: D.Walker, D.Prescod | 1. Set-up intercomparison kit for temperature, humidity and pressure (at least one, but preferably all 3 parameters) 2. Schedule intercomparisons with other RICs of Regions 3. Publish intercomparison report 4. Develop procedure for conducting and evaluating inter-laboratory comparison (based on general principles published in ISO standard for comparison between many laboratories) | 1-3. (IOM) Reports on intercomparisons & Presentations at CIMO-2016 (23.-27. Sept., Madrid) 4a.Document describing procedure 4b. Update of CIMO Guide, incorporating procedure. | 1. July 2015 2. Dec. 2015 3. Mar. 2017 4a. July 2017 4b. December 2018 | M | 1. 100% RAVI 100% RAII&V 100% RAI 10% RAIV&III 2. 100% RA VI 100% RA II&V 100% RA I 0% RAI V&III 3. 100% RA VI 0% RA II&V 0% RA I 0% RAI V&III | CIMO-XV para 6.3 CIMO-16, Doc. 6, para 6.9 ET-RIC meeting report, § 3.5, 7.3 and 8.8 Protocol METEOMET should be used as input |
| 3. | Strengthening RICs and supporting their communication with Members and with respective RA | K.Nakashima, D.Groselj, A.Mounir, T.Holfelder, D.Prescod | 1. Contact RICs without standard websites and support them in developing the information needed for their websites 2. Review outcomes of RIC evaluations and support those which have problems in performing such evaluations 3. On request, provide support for the evaluation of RICs 4. Prepare a template for report of RICs to the RA | 1. Standard websites for all RICs (WMO will connect annual reports) 2. Evaluation of all RICs 3. Report on RIC audits 4. Template for RIC reporting | 1. Dec 2016 2. June 2017 3. September 2017 4. December 2016 | H | 1. 0% 2. 50% 3. 0% 4. 100% | CIMO-XV para 6.3 (WMO will collect annual reports) |
| 4. | Towards calibration of ceilometer, visibilimeter and present weather sensor | N.Mander, F.Montariol, D.Groselj, J.Lin Jitze van der Meulen | 1. Identify and review existing guidance material on calibration procedure for ceilometer, visibilimeter and present weather sensor 2. Synthesize information obtained into general guidance material 3. Establish first draft of technical procedures | 1. Guidance material identified 2. General guidance established on the achievement of the traceability of these instruments 3. Technical procedures drafted based on the identified materials, | 1. Dec 2016 2. July 2017 3. December 2017 | M | 30% | Outcome from A.1 and A.2 and CIMO TB and TL centers Action 2 will require guidance on their traceability provided by the dedicated expert bodies Note: Outcomes of volcanic ash/aerosol intercomparison may help in progressing this task. Get in contact with Jitze van der Meulen (Alexander Haefele?) |
| 5. | Implementation of the strategy for improving traceability of basic measurements (such as p, T, h) to SI | N.Mander, D.Groselj, A.Mounir, K.Nakashima, F.Barcenas, J.Lin, D.Prescod | 1. Develop outreach flyer (for decision makers) on importance of measurement traceability and how to achieve it. 2. Finalize calibration/traceability strategy 3. Ensure inclusion of the strategy in the CIMO Guide 4. Develop guidance material on how to implement traceability (for ex. use of field inspection kit) | 1. Outreach flyer 2. Document with calibration strategy 3. Relevant CIMO Guide chapters updated 4a. Document showing best practice in each NMHS 4b. Document with guidance material published as IOM report or Annex to CIMO Guide | 1. April 2015 2. Dec. 2016 3. July 2017 4a. September 2017 4b. March 2018 | H | 1. 100% 2. 100% 3. 100% (WMO) 4a. 0% 4b. 0% | CIMO-16, Doc. 6, §6.8 Perspective is for a strategy for ensuring world-wide traceability of measurements to SI. Strategy is approved by the CIMO MG Update of chapters is going to be done by WMO |
| 6 & 8 | Guidance for transition from mercury-based instruments to alternative technologies (due to Impact of Minamata convention) and addressing issues with obsolete or unserviceable instruments | A.Mounir, N.Mander, D.Groselj, T.Holfelder, D.Prescod, P. Copping, K.Nakashima J. Lin F.Barcenas | 1. Develop outreach flyer (for decision makers) on impact of Minamata convention 2. Collect expertise and information from Members having successfully transitioned away from mercury-based (particularly obsolete) instruments and to collaborate with HMEI in identifying alternative instruments 3. Develop road-map/guidance for transition of instruments containing mercury to alternative devices.Develop guidance on how to select, maintain and calibrate modern instruments replacing outdated (including mercury-based) instruments. | 1. Outreach flyer 2a. List of relevant publications, and links provided on IMOP website 2b. Document (possibly IOM Report) proposing alternatives 3. Guidance document and/or updates of relevant CIMO Guide chapters | 1. March 2015 2a. Dec 2016 2b. April 2017 3 July 2017 | H | 1. 100% 2a. 100% 2b. 50% 3. 50% |  |
| 7 | Assess status and need for regional standard barometer and update CIMO Guide and relevant WMO resolutions accordingly | A.Mounir, K.Nakashima, F.Montariol, D.Prescod, F.Barcenas | 1. Collect the needs for regional standards barometers in RAs | 1. Report to CIMO on the status and need for regional standard barometers | 1. Dec. 2015 | M | 100% |  |
| 9 | CIMO Guide update | Temperature: T.Holfelder (+DWD), M. de Podesta D.Groselj, F.Montariol, K.Nakashima Pressure: Van der Muelen Humidity: N.Mander, M. de Podesta S. Bell D.Groselj | 1. Fully revise and update CIMO Guide chapter on temperature and pressure | 1. Updated CIMO Guide chapter | 1. November 2017 (final version) | H | 50% | check chapter I of CIMO guide Chapter I and chapters for temperature, pressure and humidity have been updated and proceeded to the MG in April 2016 |
| 10 | Precipitation | N. Mander, A.Mounir, D.Groselj, D.Walker | 1. Review the CIMO Guide chapter on precipitation 2. Review documentation on practices on laboratory precipitation calibration 3. Liaise with CEN on the development of standard | 1. Propose updates of the CIMO guide | 1. November 2017 | L | 1. 0% | Liaise with A.1 and A.2 |