| WORLD METEOROLOGICAL ORGANIZATION _____________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION CIMO MANAGEMENT GROUP First session Los Angeles/CA., USA, 13-15 February 2003 |  | Distr.: RESTRICTED CIMO/MG-1/Doc. 3.1 _________ (13.I.2003) ITEM: 3.1 ENGLISH only |
| --- | --- | --- |

Status and plan for update of the CIMO Guide

(Submitted by the Secretariat)

Summary and purpose of document This document provides an overview of work done on the update of the CIMO Guide and a plan to finalize new edition of the Guide. .

#### Action proposed

The meeting is invited to review the work done on the update of the CIMO Guide and decide on further steps to finalize new edition of the CIMO Guide.

Status of update of the CIMO Guide

- CIMO-XII agreed that a continuous review and update of the Guide is needed due to the rapid development of technology and observing practices. It invited the Secretary-General to support this by providing the necessary recourses.

- In order to keep the Guide under review and develop updates, the Commission requested its president to consider establishing a task team within the Advisory Working Group (AWG). AWG considered this task as an important one to be done by all members of AWG and requested Mr Dombrowsky to act as focal point for updating the CIMO Guide.

- Mr Dombrowsky reported during the AWG Meeting in January 2002 that in the Circular 
Letter #3 (March 2001) of the President of CIMO, sent to all members, a request was made for updates and comments.  Unfortunately, no proposals for amendment were received in response to this letter.  However, extensive comments were collected from experts through the efforts of the chairpersons of the working groups and the assigned Advisory Working Group focal point.  The comments were then provided to the WMO Secretariat.  Revisions were suggested in 20 of the 32 chapters of the Guide.  Also two new chapters on  “Urban observations” and “Road Meteorological Measurements” were proposed. Some proposals for a revision were accompanied by a revised text and some only requested that a particular text has to be revised. Many of the comments involved technical corrections or clarifications.  There were also instances where the instruments described are obsolete, or new technology has become available.

- Mr Pannett (New Zealand) was contracted in 2002 by Secretariat to review comments and suggestions on updates relevant to Part I of the Guide received from AWG. He revised Chapters 1 “General”, Ch.2 “Measurement of temperature”, Ch.3 “ Measurement of pressure”, Ch.5 “Measurement of surface wind” and   Ch.6 “Measurement of precipitation” of Part I and a new Chapter 12 “Road meteorological measurements” of Part II of the Guide.  Those draft revisions were sent, as suggested by AWG, to Mr Dombrowsky and chairmen of the Working Groups for further action.

- The CBS-XII invited other technical Commissions, through its president, to arrange for the harmonization of relevant manuals, guides, and regulations with the sixth edition of the Guide.  During the AWG meeting, January 2002, Mr Van der Meulen also reported the need for updating the cross references in some other WMO Guides and Manuals, such as International Meteorological Tables (WMO-No.188, TP.93), which is out of print and to which CIMO Guide refers to, and Technical Regulations (WMO-No.49), where there is a need to bring in line its Attachment B (Operational desirable and currently attainable accuracy of measurements or observations) with CIMO Guide Annex 1/B (Accuracy requirements and achievable accuracy). No concrete results have been achieved in this regard so far, except of suggestions made by CBS ET on AWS (Geneva, 2-6 September 2002).

- The status table on CIMO Guide updates is in the Annex 1.

Further actions and plan for update of the CIMO Guide

- CIMO-XIII in discussing the CIMO Guide suggested some actions and concrete proposals relevant to the update of the Guide:

- Inform PRs of the importance of the CIMO Guide for providing definitive guidance and as an indispensable training resource, and to encourage them to make available their experts and to afford them time and due recognition in this important work (responsible: President of CIMO).

- Request the presidents of the technical commissions to consider updates of Manuals and Guides to achieve consistency of Manuals and Guides, under the auspices of other technical commissions, with the CIMO Guide (responsible: President of CIMO).

- Publish the 7th edition of the CIMO Guide and make arrangements for the production of an electronic version of the Guide (responsible: WMO Secretariat).

- Publish in CIMO Guide Measuring range and uncertainty requirements for rainfall intensity (RI) measurements (responsible: OPAG-SURFACE).

- Review the table on Operational Accuracy Requirements and Typical Instrument Performance. Request the other technical commissions to provide assistance in reviewing the requirements (responsible: OPAG-SURFACE).

- Include within Chapter I/7 of the CIMO Guide “Alternate Method” of Dr B. Forgan (1996) for calibrating pyranometers (responsible: OPAG-SURFACE).

- Discourage the use of the old Schott-glass filter pyrheliometer methods in the next edition of the CIMO Guide (responsible: OPAG-SURFACE).

- Monitor the efforts of the CAS Scientific Steering Committee on UV Measurements and use the relevant reports, when available, as the basis for updating Chapter 7, "Measurement of radiation", of Part I of the CIMO Guide (responsible: OPAG-SURFACE).

- Include in the CIMO Guide, as far as possible, relevant recommendations confirmed by the Executive Council (responsible: WMO Secretariat).

- It should be noted that updating the CIMO Guide is an ongoing activity, however for the sake of meeting a fixed publication date of the 7th edition there is a need to freeze amendments at some point. Therefore, it is proposed that the 7th edition of the Guide will contain only those amendments for which a “text” is supplied by the end of March 2003. WMO Secretariat will send a reminder to those reviewers who suggested an update but have not yet supplied a proposed text.

- All available proposals for revisions will be reviewed and edited by Mr Pannett upon the schedule presented in Annex 1. All queries, that will inevitably come up during the editing work, will be channeled to the relevant OPAG’s co-chairpersons who themselves or through recognized expert would provide authorized answers to Mr Pannett.

- “Final Edit” will be subjected to a final approval according to Annex 1, fairly in advance before it is provided to the Expert Team on the Development Guidance and Training Materials (ET/DGTM) to allow for redrawing the necessary figures.  (Original figures are only available as bit map files and cannot be edited. They may or may not be suitable for insertion 'as is' in the MS Word text. If an amendment is required, they need to be redrawn from scratch.)

- ET/DGTM will discuss (ET meeting in 4 quarter 2004) the approved final editor’s version and decide on the procedure the 7th edition of the Guide will be published. It is expected that a new edition be first published on the CIMO/IMOP Web-site. A period of about 6 months may be allowed for comments from a wide-range of users. Their comments should be analyzed and incorporated in the 7th edition by the decision of the ET/DGTM in a timely manner so that the 7th edition of the Guide is published in both an electronic and a hard copy version during 1st quarter 2006.

ANNEX 1

| Ch./ Part |  | PROPOSALS FOR UPDATES | DRAFT EDIT | QUERIES SOLVED BY | FINAL EDIT | APPROVAL OF FINAL EDIT |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Responsible | Date |  | Responsible | Date | Responsible | Date |
| P.I | MEASUREMENT OF METEOROLOGICAL VARIABLES |  |  |  |  |  |  |  |  |
| 1 | General | Yes | R. Pannett | Aug 02 | J. Van der Meulen | R. Pannett | Mar 03 | J. Van der Meulen | May 03 |
| 2 | Measurement of temperature | Yes | R. Pannett | Aug 02 | J. Van der Meulen | R. Pannett | Mar 03 | J. Van der Meulen | May 03 |
| 3 | Measurement of atmospheric pressure | Yes | R. Pannett | Aug 02 | J. Van der Meulen | R. Pannett | Mar 03 | J. Van der Meulen | May 03 |
| 4 | Measurement of humidity | No |  |  |  |  |  |  |  |
| 5 | Measurement of surface wind | Yes | R. Pannett | Aug 02 | J. Van der Meulen | R. Pannett | Mar 03 | J. Van der Meulen | May 03 |
| 6 | Measurement of precipitation | Yes | R. Pannett | Aug 02 | J. Van der Meulen | R. Pannett | Mar 03 | J. Van der Meulen | May 03 |
| 7 | Measurement of radiation | No |  |  |  |  |  |  |  |
| 8 | Measurement of sunshine duration | Yes; (no text) | R. Pannett | Apr 03 | C. Richter | R. Pannett | Jul 03 | C. Richter | Sept 03 |
| 9 | Measurement of visibility | Yes; (no text) | R. Pannett | Apr 03 | C. Richter | R. Pannett | Jul 03 | C. Richter | Oct 03 |
| 10 | Measurement of evaporation | Yes; (no text) | R. Pannett | Apr 03 | C. Richter | R. Pannett | Jul 03 | C. Richter | Nov 03 |
| 11 | Measurement of soil moisture | No |  |  |  |  |  |  |  |
| 12 | Measurement of upper air pressure, temperature, humidity | Yes | R. Pannett | Feb 03 | J. Nash | R. Pannett | Apr 03 | J. Nash | June 03 |
| 13 | Measurement of upper wind | Yes; (no text for GPS) | R. Pannett | Mar 03 | J. Nash | R. Pannett | May 03 | J. Nash | Aug 03 |
| 14 | Observation of present and past weather; state of the ground | Yes; (no text) | R. Pannett | Apr 03 | J. Van der Meulen | R. Pannett | Jul 03 | J. Van der Meulen | Sept 03 |
| 15 | Observation of clouds | Yes; (no text) | R. Pannett | July 03 | J. Van der Meulen | R. Pannett | Oct 03 | J. Van der Meulen | Jan 04 |
| 16 | Measurement of ozone | No |  |  |  |  |  |  |  |
| 17 | Measurement of atmospheric composition | Yes | R. Pannett | Feb 03 | C. Richter | R. Pannett | Apr 03 | C. Richter | July 03 |

| Ch./ Part |  | PROPOSALS FOR UPDATES | DRAFT EDIT | QUERIES SOLVED BY | FINAL EDIT | APPROVAL OF FINAL EDIT |
| --- | --- | --- | --- | --- | --- | --- |
| P.II | OBSERVING SYSTEMS |  |  |  |  |  |  |  |  |
| 1 | Measurements at automatic weather stations | Yes | R. Pannett | Jul 03 | J. Van der Meulen | R. Pannett | Oct 03 | J. Van der Meulen | Jan 04 |
| 2 | Measurements and observations at aeronautical meteorological stations | Yes | R. Pannett | Jul 03 | J. Van der Meulen | R. Pannett | Oct 03 | J. Van der Meulen | Feb 04 |
| 3 | Aircraft observations | Yes | R. Pannett | Jul 03 | R. Dombrowsky | R. Pannett | Oct 03 | R. Dombrowsky | Jan 04 |
| 4 | Marine observations | No |  |  |  |  |  |  |  |
| 5 | Special profiling techniques for the boundary layer and the troposphere | No |  |  |  |  |  |  |  |
| 6 | Rocket measurements in the stratosphere and mesosphere | No |  |  |  |  |  |  |  |
| 7 | Locating the sources of atmospherics | No |  |  |  |  |  |  |  |
| 8 | Satellite observations | No |  |  |  |  |  |  |  |
| 9 | Radar measurements | Yes | R. Pannett | Jul 03 | R. Dombrowsky | R. Pannett | Oct 03 | R. Dombrowsky | Jan 04 |
| 10 | Balloon techniques | Yes | R. Pannett | Feb 03 | R. Dombrowsky | R. Pannett | Apr 03 | R. Dombrowsky | June 03 |
| 11 | Urban observations | New chapter by R.D.Vashistha (needs further review by Prof. T. Oke) | R. Pannett | Jul 03 | C. Richter | R. Pannett | Oct 03 | C. Richter | Jan 04 |
| 12 | Road meteorological measurements | New chapter by T. Ladent | R. Pannett | Aug 02 | J. Van der Meulen | R. Pannett | Mar 03 | J. Van der Meulen | May 03 |
| P.III | QUALITY ASSURANCE AND MANAGEMENT OF OBSERVING SYSTEMS |  |  |  |  |  |  |  |  |
| 1 | Sampling meteorological variables | Yes | R. Pannett | Feb 03 | R. Canterford | R. Pannett | Apr 03 | R. Canterford | June 03 |
| 2 | Data reduction | No |  |  |  |  |  |  |  |
| 3 | Quality management | No |  |  |  |  |  |  |  |
| 4 | Training of instrument specialists | No |  |  |  |  |  |  |  |
| 5 | Testing, calibration and intercomparison | Yes | R. Pannett | Oct 03 | R. Canterford | R. Pannett | Dec 03 | R. Canterford | Feb 04 |