| WORLD METEOROLOGICAL ORGANIZATION _____________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION CIMO MANAGEMENT GROUP First session Los Angeles/CA., USA, 13-15 February 2003 |  | Distr.: RESTRICTED CIMO/MG-1/Doc. 3.2 REV.1 _________ (22.I.2003) ITEM: 3.2 ENGLISH only |
| --- | --- | --- |

Status and plan for IMOP Reports

(Submitted by the Secretariat)

Summary and purpose of document This document provides an overview of work done on the IMOP Reports and a future Plan.

#### Action proposed

The meeting is invited to review the work done on the IMOP Reports and to decide on the future Plan.

Status of preparation of IOM Reports

- The only CIMO-XII related IOM Report already published is the IOM-72 “Papers and Poster Presented at the WMO TECO-2002”. All others were at various levels of development and needed to be finalized and checked (see Appendix B).

- All IOM Reports will be available on the CIMO/IMOP website and will be grouped together into one or 2 CDs. Only the IOM reports on intercomparisons will be printed.

Future Plan

- It is suggested to concentrate on the IOM Reports that are CIMO-XII related and publish them all before the end of 2004 according the Plan in Appendix B.

- A proposal for CIMO-XIII related IOM reports together with responsible OPAG, format and date of publication is in Appendix B.  The names of authors depend on the decision on the leadership of individual ETs, however some may be produced by OPAG co-chairpersons.

| No. | IOM Report | Author | Status | OPAG's Final Approval | Format/ Location | Publication scheduled |
| --- | --- | --- | --- | --- | --- | --- |
|  | CIMO-XII related |  |  |  |  |  |
|  | Evaluation of the AWS Algorithm Questionnaire | M. Gifford | Draft provided in March 2002. | Co-chairs, Surface | Website CD | June 2003 |
|  | The Vision of Road Managers and Meteorologists on Road Meteorological Measurements | J. Terprstra & T. Ladent | Draft provided in March 2002. | Co-chairs, Surface | Website CD | July 2003 |
|  | GPS Radiosonde Comparison – Brazil | R. Silveira et al. | Preliminary Report provided in January 2003 | Co-chairs, Upper-Air | Website Printed CD | Oct 2003 |
|  | 7th Edition of Instrument Development Inquiry | T. Prager & J. van der Meulen | In preparation | Co-chairs, Surface | Website CD | Oct 2003 |
|  | Radiosonde Relative Humidity Sensors Intercomparisons – Russia/USA 1995-1997 | Schmidlin et al. | In preparation | Co-chairs, Upper-Air | Website Printed CD | Nov 2003 |
|  | Summary of the first five WMO Radiosonde Comparisons | J. Nash | In preparation | Co-chairs, Upper-Air | Website Printed CD | Nov 2003 |
|  | Compatibility of Radiosonde Geopotential Measurements | J. Elms | In preparation | Co-chairs, Upper-Air | Website CD | Dec 2003 |
|  | Operational Aspects of Wind Profilers | J. Dibbern | Draft provided in April 2002, but based only on COST-76 Final Report | Co-chairs, Upper-Air | Website CD | 3rd quarter 2004 |
|  | CIMO-XIII related |  |  |  |  |  |
|  | Papers and Posters - TECO-2004 |  | - | WMO Secretariat | Website CD | 4th quarter 2004 |
|  | Guidance material on developing GPS water vapour networks |  | - | Co-chairs, Upper-Air | Website CD | 2005 |
|  | Guidance on the State-of-the-art of Instruments and Automated Surface Observing Systems |  | - | Co-chairs, Surface | Website CD | 2005 |

|  | Existing data processing algorithms for radiosondes |  | - | Co-chairs, Upper-Air | Website CD | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Intercomparison of rainfall intensity gauges |  | - | Co-chairs, Surface | Website Printed CD | 2006 |
|  | Intercomparison of thermometer screens/shields |  | - | Co-chairs, Surface | Website Printed CD | 2006 |
|  | Intercomparison of hygrometers |  | - | Co-chairs, Surface | Website Printed CD | 2006 |
|  | Recommendations for a standard automated ozone observational site |  | - | Co-chairs, Surface | Website CD | 2006 |
|  | WMO radiosonde intercomparison of various types of aerological measurement systems |  | - | Co-chairs, Upper-Air | Website Printed CD | 2006 |
|  | WMO intercomparison of remote and in situ U/A sounding systems |  | - | Co-chairs, Upper-Air | Website Printed CD | 2006 |
|  | Procedures for the publication of results of WMO Radiosonde Inter-comparisons |  | - | Co-chairs, Upper-Air | Website CD | 2006 |
|  | 8th Edition of Instrument Development Inquiry |  |  | Co-chairs, Surface | Website CD | 2006 |