| WORLD METEOROLOGICAL ORGANIZATION __________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION CIMO MANAGEMENT GROUP Eleventh Session Payerne, Switzerland 10 – 14 March 2014 |  | CIMO/MG-11/Doc. 2.4(2) (10.III.2014) _______ ITEM: 2.4 Original: ENGLISH |
| --- | --- | --- |

OPAG CAPACITY BUILDING

REPORT ON PROGRESS, RECOMMENDATIONS AND FUTURE ACTIVITIES OF CIMO GUIDE EDITORIAL BOARD

(Submitted by Volker KURZ)

Summary and purpose of document This document provides information on the work done by the CIMO Guide Editorial Board since CIMO-XV.

Action proposed

The Meeting is invited to review and comment on this report.

________________

Appendices:	I	Updated Workplan

II	Background Information

III	Draft Workplan for 2014-18

REPORT ON PROGRESS, RECOMMENDATIONS AND FUTURE ACTIVITIES OF CIMO GUIDE EDITORIAL BOARD

- INTRODUCTION

  - Since its inauguration in 2010, the CIMO Guide Editorial Board has met twice in Geneva. Reports of those meetings are available from the appropriate WMO web page. In addition, especially during the last months several virual meetings using WebEx were organized. Those video conferences shined as a very valuable and efficient tool for organizig work of a distributed team. Even more, those meetings are very economical not only with respect to travelling expenses but also with respect to the time to be contributed by the members.

  - In addition to the originally appointed members, Aki Lilja joined the Editorial Board as an additional HMEI representative.

- ACHIEVEMENTS WITH RESPECT TO WORKPLANS

2.1	Since CIMO-XV, a number of updates and/or fully revised chapters were developed and reviewed by CIMO Expert Teams. Significant contributions to this effort were also provided by experts from the Commission for Basic Systems (CBS), the Commission for Atmospheric Science (CAS), and the Joint Commission for Oceanography and Marine Meteorology (JCOMM). All these proposals were reviewed in detail by the CIMO Guide Editorial Board and compiled into the Preliminary 2014 Edition. The Preliminary 2014 Edition of the CIMO Guide is now available for consideration by members ßhas been posted on the Instruments and Methods of Observation website, under the heading 'CIMO Guide - Preliminary 2014 Edition', at: http://www.wmo.int/pages/prog/www/IMOP/IMOP-home.html. As could be expected for a new edition, many chapters were updated, Editorial Board member Krunoslav Premec was successfully keeping contact to the heads of other ETs. The most spectacular change is the introduction of a new part on Space-based Observations between the current Part II and Part III.

2.2	After thorough discussions not only within the Editorial Board, but also with the relevant teams responsible for the development of WIGOS regulatory material, it was decided to pick up the suggestion of the CIMO Management Group not to introduce a separate CIMO Manual but to contribute material to the Manual on WIGOS directly.

2.3	Another prominent task was to extract appropriate material to be included in the new Manual on WIGOS. This was achieved by the participance of the chief editor in IPET-WIFI an TT-WRM. The result was not only a conttibution to the WIGOS regulatory material but also a proposal for the procedure to link material to both WIGOS Manual and CIMO Guide.

2.4	The International Cloud Atlas also emerged into a very important task. A task team was established headed by Editorial Board Member Steve Cohn.

2.5	A universal search tool did not materialize yet. It is postponed in favour of the decision concerning the deployment of a more general and modern editing and publishing tool.

2.6	WIGOS TT-WRM unanimously agreed to use the terms “space-based” and “surface-based” (and not “ground-based” and “ satellite-based”). The Editorial Board decided to follow this convention throughout the CIMO Guide as well.

2.7	Material taken from the CIMO Guide and promoted to be part of the Manual on WIGOS will be put into appendices there. So this material can be referenced from both Manual on WIGOS and CIMO Guide.

2.8	Guidelines for the drafting / updating of CIMO Guide chapters were developed and published on the web.

- PROBLEMS ENCOUNTERED, RISKS IDENTIFIED

  - …

- SPECIFIC REPORTS REQUESTED BY MG

[Fill-in only if specific reports had been requested by CIMO-MG]

  - …

- RECOMMENDATIONS

[Include here recommendations that require actions or decisions from CIMO-16]

  - The following recommendations are submitted by ET/TL… to CIMO-XVI

- ….;

- TOPICS FOR FUTURE WORK PLAN AND EXPECTED ASSOCIATED DELIVERABLES

[include draft workplan 2014-18 in Annex III]

6.1		It is felt that Part II, Ch 5 (Special Profiling Techniques for the Boundary Layer and the Troposphere) needs some update. A volunteer for this task is already identified. However, it was not clear for which Team this would fall into its area of responsibility. Perhaps closest would be the ET on New Technologies or the ET on Operational Remote Sensing. It would possibly best fit within the terms of reference of B2. However, if other experts want to contribute to the update that should be welcome too. Sonthe.Management Groupnis askednhere for help and advice.

6.2		A draft recommendation to be considered by CIMO MG concerning the use of SI Units and editorial practices to be used in their context for the CIMO Guide and possibly other WMO publications was developed, see Appendix II.

_________________

APPENDIX I: Updated workplan (2010-2014)

| No. | Task description | Person responsible | Action | Deliverable | Deadline for deliv. | Status [%] | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Guidelines for the drafting/ updating of CIMO Guide chapters | All (in collab. with Secretariat) 3. S. Cohn | Develop general guidance for authors / reviewers of CIMO Guide chapters in view of ensuring homogeneous presentation of material throughout the Guide Review and document procedure for approval of modifications to the CIMO Guide For technical review For formal approval process of new version Update to guidelines providing guidance to author on how to indicate preferred methods to be used | 1. Document with guidelines for posting on website 2. Document with procedure (for posting on website) a. on technical review b. on approval process | 2011 2011 2012 (MG-10) 2014 | 100 % 100 % | CIMO-XV, para 7.8 |
| 2. | Collect and review (small) modifications proposed by Members | K. Premec | Collect proposals of revision received from Members and maintain list of outstanding issues Consult with relevant ET Chairs/experts on appropriateness of proposals Develop updates for relevant chapters | List of proposals (received by whom and when) and their status /decisions taken (when and by whom were they approved or rejected) Revised chapters | On-going | 100 % | ETs to be prompted every year. ET and external contributors of a chapter (other TC) should be prompted before each new edition/update |
| 3. | Review of fully revised chapters and chapters revised by ETs | V. Kurz S. Cohn K. Premec | Review newly revised chapters on their compliance with the guidelines / homogeneity with rest of guide Liaise with authors on need for amendments In collaboration with relevant expert teams, identify areas to be up-dated, revised or completely rewritten | Revised chapters for consideration by Members Authors contacted List of chapters/sections to be rewritten, incl. recommendations on topics to adress | As needed As needed 2011 | 100 % | CIMO-XV, para 7.8 |
| 4. | Contribution to the development of the Manual on WIGOS | V. Kurz (find out what is requested, then plan further) | Follow-up and contribute to the development of the Manual on WIGOS as required Liaise with CIMO ET on required contributions Compile ET contributions for submission to WIGOS, if appropriate | Document with CIMO contribution to Manual on WIGOS | Upon request | 100 % | CIMO-XV, para 7.8 |
| 5. | Development of CIMO Manual | V. Kurz (discuss with MG what is required and when, then plan further) | Develop a strategy for the development of the CIMO Manual (incl. position on appropriateness to develop CIMO Manual in context of development of Manual on WIGOS) Consider the possibility of upgrading non controversial parts of the CIMO Guide to the level of common ISO/WMO standards Propose expert to review CIMO Guide and identify non-controversial parts/guidelines that would be appropriate to be published as standard practices (WIGOS Manual and possibly ISO-WMO standard), in collab. with relevant CIMO ETs | 1. Statement on strategy for consideration by MG | 2011 Spring 2012 Mid 2012 | 100% 100% 100% | CIMO-XV, para 7.7 No separate CIMO Manual, but contribution to Manual on WIGOS Siting classification should be submitted as common ISO/WMO standard V. Kurz will contact ETs and ask for their proposals. |
| 6. | Contribute to the implementation of WIGOS and provide relevant advice and support to the CIMO-MG | V. Kurz | Address relevant items of WIGOS Implementation Strategy approved by Cg-XVI and subsequent WIGOS IP Prepare information for MG-10 | TBD after Cg-XVI | Oct.2012 | 100% | Contributing to the development of the WIGOS Manual S. Cohn contributing to the update of the Cloud Atlas (CA) and chairing the TT-CA |

| Lower priority |
| --- |
| 7. | Coherency between Manual on WIGOS, CIMO Manual, CIMO Guide and relevant ISO standards |  | Review proposals of ETs for ISO/WMO standards and advise ETs |  | Upon request | 100% | CIMO-XV, para 7.8 |

APPENDIX II: Background information

1.	Analysing different practices found in the Guide to Meteorological Instruments and Methods of Observation, and in some other WMO publications, concerning the use of quantities, units and symbols, as well as editorial practices, CIMO Guide Editorial Board is of the opinion that uniform, world-wide accepted, practice should be applied throughout all WMO publications (Technical Regulations, Guides, Manuals, Reports…).

Therefore, CIMO Guide Editorial Board would like to propose following recommendations to be considered by CIMO Management Group:

- General principles concerning the use of quantities, units and symbols, throughout all WMO publications, should be in accordance with the International System of Units (SI), published and regularly updated by the International Bureau of Weights and Measures (BIPM, 2006), the Quantities and Units, defined by International Organization for Standardization (ISO, 2009) and the Symbols, Units, Nomenclature and Fundamental Constants in Physics, described by International Union of Pure and Applied Physics (IUPAP, 1987). Variables not defined as an international symbol by the above mentioned documents, but commonly used in meteorology should be used as stated in the International Meteorological Tables, published by World Meteorological Organization (WMO, 1966).

- WMO Style Guide should be updated in accordance with the Recommendation 1 and applied as general editorial practice for the future editions of all WMO publications.

References:

Bureau International des Poids et Mesures (International Bureau of Weights and Measures), 2006: The International System of Units (SI). BIPM, Sèvres/Paris.

International Organization for Standardization, 2009: Quantities and Units ‐ Part	1: General. (ISO 80000-1:2009), Geneva.

International Union of Pure and Applied Physics, 1987: Symbols,	Units,	Nomenclature	and Fundamental Constants in Physics. SUNAMCO Document IUPAP-25 (E.R. Cohen and P. Giacomo), reprinted from Physica 146A, pp. 1–68.

National Institute of Standards and Technology, 2008: Guide for the Use	of the	International System of Units (SI) (A. Thompson and B.N. Taylor). (NIST Special Publication No. 811), Gaithersburg, United States.

World Meteorological Organization, 1966: International Meteorological Tables (S. Letestu, ed.) (1973 amendment) (WMO-No. 188. TP.94), Geneva.

________________

APPENDIX III: Draft workplan (2014-2018)
(Note: do not fill in colum Person Responsible)

| No. | Task description | Person responsible | Action | Deliverable | Deadline for deliv. | Status [%] | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Update Part II, Ch 5 (Special Profiling Techniques for the Boundary Layer and the Troposphere) |  | Contact appropriate ET Contact volunteer | Updated version |  |  |  |
| 2. |  |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |  |
| 6. |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| 8. |  |  |  |  |  |  |  |
| 9. |  |  |  |  |  |  |  |
| 10. |  |  |  |  |  |  |  |