| WORLD METEOROLOGICAL ORGANIZATION __________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION CIMO MANAGEMENT GROUP Thirteenth Session Offenbach, Germany 7 – 9 December 2014 |  | CIMO/MG-13/Doc. 3.2(2) (27.XI.2014) _______ ITEM: 3.2 Original: ENGLISH |
| --- | --- | --- |

WORK PLAN OF THE CIMO EXPERT TEAM ON NEW REMOTE SENSING TECHNOLOGIES (ET-NRST)

(Submitted by E. Buyukbas and L. Cucurull)

Summary and purpose of document This document provides information on the proposed Work Plan for ET-NRST

Action proposed

The Meeting is invited to note the structure and content of the draft Work Plan, and to approve the Workplan.

________________

Appendix:	Draft Workplan of ET-NRST

WORK PLAN OF THE CIMO EXPERT TEAM ON NEW REMOTE SENSING TECHNOLOGIES (ET-NRST)

- INTRODUCTION

The proposed Work Plan for ET-NRST is contained in the Appendix for the consideration and approval of the CIMO Management Group. The Expert Team currently lacks the expertise to perform the last task in the Work Plan, which concerns remotely sensed measurements of snow depth. Further efforts will be made by the expert team to identify and recruit an additional expert for this task. The session is invited to propose suitable experts for this task.

_________________

APPENDIX: Workplan of ET-NRST (2014-2018)
CIMO-16 5.14, 5.15, 5.16

| No. | Task description | Person responsible | Action | Deliverable | Deadline for deliv. | Status [%] | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Feasibility study for intercomparison of techniques for aerosol / volcanic ash detection. | Apituley Donovan Ristori | Conduct a feasibility study for an intercomparison on various techniques for aerosol/ volcanic ash detection Report to CIMO MG on the findings of the study Prepare a plan for such an intercomparison if feasible | 1. Report on feasibility study. 2. Plan for intercomparison | 12/2015 TBD |  | CIMO-16 § 5.24 In liaison with ET-II May need to involve seismologists community Will there a need for ‘portability’ of the intercomparison? |
| 2. | Passive microwave profilers | Chan Cucurull | Further develop draft guidance material on operational use of passive microwave profilers (with emphasis on PBL performance) Review relevant CIMO Guide chapter and develop update if appropriate | 1. IOM Report on MW Profilers 2. Updated CIMO Guide Chapter | 12/2015 12/2016 |  | CIMO-16 Doc. 5, §5.18 Note existing draft doc available from WMO secretariat |
| 3. | Lidar Standards | Apituley Chan | Provide WMO input to ISO TC146/SC5 development of a joint WMO/ISO standard on Doppler wind lidar. Provide advice to CIMO MG on the merit of development of joint WMO/ISO standards. Collaborate with ISO TC146/SC5 working group on maintenance of ISO lidar standards. | WMO/ISO standard on Doppler wind lidar | 1. 06/2015 2. Ongoing 3. Ongoing |  | CIMO-16 Doc 4, §4.6 CIMO-16 Doc 5, §5.22 CIMO-16 Doc 8, 8.3 |

| 4. | Monitor, evaluate and report on development and implementation of new remote-sensing technologies and their operational application (excluding weather radars, radar wind profilers and lightning detection systems) | a. Tulley b. Cucurull de Haan Tulley c. Apituley Ristori Sakai d. Sakai Apituley Roininen e. de Haan Cucurull Apituley Chan f. Donovan g. Ristori Apituley Tulley Roininen Donovan h. Cucurull All | Review, evaluate and report on development and implementation of various new remote-sensing technologies and their potential/readiness for operational application, including path to operational use and traceability to SI, for: MWR, GNSS Raman WV lidar DIAL lidar Doppler wind LIDAR cloud radars aerosol&volcanic ash detection other (incl. simple, cheap technology) | Updated reports on performance, implementation and operational use of various systems. IOM or other report(s) on new RS technologies (e.g. Operational use of LIDARs) Relevant CIMO Guide updates (as required) | 1.1 12/2015 1.2 06/2017 2. As req 3. As req |  | CIMO-16 4.17, §5.15, 5.16, 5.17, 5.18, 5.19, 5.20, 5.21, 5.22, 7(5).3, 7(5).4 Note 1: Ensure due consideration of new technologies which are cheap and simple to operate and maintain. Note 2: Take into account reports from previous intersessional period. Note 3: Liaise with GRUAN on WV Lidars, etc. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5. | Monitoring of assigned CIMO Testbeds (Lindenberg, Hohenpeissenberg, Payerne) | De Haan (Berger, Plass-Duelmer, Ruffieux) | Monitor and review outcomes of assigned CIMO Testbeds and Lead Centres (with focus on performance of new surface-based RS technologies) Assess need to, and develop if required, up-dates for relevant parts of CIMO Guide. | Document summarizing main outcomes of testbeds relevant to ET Terms of Reference Revised CIMO Guide Chapters | Ongoing |  | CIMO-16 Doc. 5, §5.11 |
| 6. | Uncertainty and traceability to SI of remotely sensed atmospheric vertical profiles. | De Haan Cucurull | Identify one technology (from 4 above, e.g. GNSS) for which SI traceability and quantification of uncertainty is tractable, and develop guidance material on this. | Document or IOM Report on uncertainty and traceability of remotely sensed vertical profiles. |  |  | Note existing draft document at http://www.wmo.int/pages/prog/www/IMOP/meetings/RS-NT/ET-NTTB-1/Doc%209_Traceability.doc CIMO-16 Doc. 5 §5.25,5.26 |
| 7. | Remote sensing of snow depth | TBA | Study the latest results of different research groups in Canada, Europe, Russia and Japan concerning the space born and aircraft remote measurements of the snow pack Prepare guidance material for Members | Document with draft guidance on remote sensing of snow depth. |  |  |  |