| WORLD METEOROLOGICAL ORGANIZATION __________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION CIMO MANAGEMENT GROUP Thirteenth Session Offenbach, Germany 7 – 9 December 2014 |  | CIMO/MG-13/Doc. 3.3(4) (21.XI.2014) _______ ITEM: 3.3 Original: ENGLISH |
| --- | --- | --- |

WORK PLAN OF THE CIMO TASK TEAM ON THE CLOUD ATLAS (TT-ICA)

(Submitted by M. Garcia and S. Cohn)

Summary and purpose of document This document provides information on the proposed Work Plan for TT-ICA

Action proposed

The Meeting is invited to note the structure and content of the draft Work Plan, and to approve the Workplan.

________________

Appendix:	Draft Workplan of TT-ICA

WORK PLAN OF THE CIMO TASK TEAM ON THE CLOUD ATLAS (TT-ICA)

- INTRODUCTION

The proposed Work Plan for TT-ICA is contained in the Appendix for the consideration and approval of the CIMO Management Group. Responsible persons and delivery dates for the final three tasks of the Work Plan have not yet been proposed because they will be dependent on the availability of financial resources for these tasks.

_________________

APPENDIX: Workplan of TT-ICA (2014-2018)

| No. | Task description | Person responsible | Action | Deliverable | Deadline for deliv. | Status [%] | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Establish sub-groups as required (text experts, image experts, decision aid) and prepare detailed plan of action | All, Cohn, Bruhn | 1. Develop project plan 2. Continuous review. | 1. Detailed Project Plan 2. Refinement of plan. | 1.Sep 2014, then 2. ongoing | 100 50 | CIMO-16 4.35-36 |
| 2. | Identify needs for new/ replacement imagery and metadata. Generate a list of images and metadata required | Image Expert Sub-Group: Bruhn (lead), Anderson, Trice (may need others) | 1. Review imagery 2. Prepare list of required images and metadata | 1. List of the needs for new/replacements imagery and metadata | 1. Oct 2014 2. Oct 2014 | 100 50 |  |
| 3. | Draft the new Glossary | Text Expert Sub-Group - Glossary: Lovell (lead Glossary), Rae, Cohn (eg NSSL liaison), others | Prepare List Add definitions | List Glossary of terms | 1. 80% Dec 2014 2. 100% Apr 2015 | 70 0 |  |
| 4. | Review, revise and update text | Text Expert Sub-Group: Rae (lead), Anderson, Lovell, Cohn, need others | 1. Review Revise/update | 2. Completed text | 1. Oct 2014 2. 80% Mar 2015 | 100 10 |  |
| 5. | Acquire and sort candidate imagery | Secretariat, Tam, Trice | 1. Build and test web portal 2. Request submissions 3. Sort Images/Metadata | 1. Test portal ready for testing. 2. Live portal built, debugged. 3. Letter to PRs etc 4. Full set of candidate images and metadata online | 1. Dec 2014 2. Feb 2015 3. Feb 2015 4. 50% Apr 2015 | 0 0 |  |
| 6. | Select Imagery | Image Expert Sub-Group | 1. Select images for ICA 2. Assemble associated metadata 3. Compose descriptions/captions 4. Get second opinion on imagery and metadata | 1. Imagery Set 2. Associated metadata 3. Complete information in place for each image | 1. Sep 2015 2. Nov 2015 3. Nov 2015 4. Nov 2015 | 0 |  |
| 7. | Create an updated Cloud Coding Decision Aid and develop a simplified Cloud Classification Decision Aid (limited to identifying genera) for Volume I | Decision Aid Sub-Group: Thurig-Jenzer (lead), Rae, Campos, Lovell | 1. Develop Decision/Coding Aid 2. Develop simplified Indentification Aid | 1. Updated Cloud Coding Decision Aid and Cloud 2. Classification Decision Aid | 1. 80% Dec 2014 2. 80% Feb 2015 | 80 10 |  |
| 8. | Design all aspects of the web-based ICA, including the Image Template, all desired functionality, the final formats needed (e.g. various printable subsets), and search requirements | Trice (lead), Tam | 1. Do it. 2. Confirm compliance with WMO website design requirements | 1. Website design. | 1. Sep 2015 | 20 |  |
| 9. | Build the website | Tam (lead), Trice | 1. Do it 2. Quantify the cost of operating/maintain the website once operational. | 2. Fully functional (offline, empty) website | 1. Nov 2015 | 0 |  |
| 10. | Prepare all text, images and metadata for web format and populate the website | Secretariat |  | 1. ICA assembled (not yet operational) | 31 Dec 2015 | 0 |  |
| 11. | Complete web site functionality | TBD |  | 1. Fully functional website | TBD |  |  |
| 12. | Final proof-read, error correction, and approval | TBD |  | 1. Errors/bugs removed | TBD |  |  |
| 13. | Publication | TBD |  | ICA published on web ICA hard copy available | TBD |  |  |