| WORLD METEOROLOGICAL ORGANIZATION __________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION CIMO MANAGEMENT GROUP Thirteenth Session Offenbach, Germany 7 – 9 December 2014 |  | CIMO/MG-13/Doc. 3.3(5) (27.XI.2014) _______ ITEM: 3.3 Original: ENGLISH |
| --- | --- | --- |

WORK PLAN OF THE CIMO TASK TEAM ON THE COMPETENCIES (TT-Comp)

(Submitted by R. Merrouchi and B. Shandu)

Summary and purpose of document This document provides information on the proposed Work Plan for TT-Comp

Action proposed

The Meeting is invited to note the structure and content of the draft Work Plan, and to approve the Workplan.

________________

Appendix:	Draft Workplan of TT-Comp

WORK PLAN OF THE CIMO TASK TEAM ON THE COMPETENCIES (TT-Comp)

- INTRODUCTION

The proposed Work Plan for TT-Comp is contained in the Appendix for the consideration and approval of the CIMO Management Group.

_________________

APPENDIX: Workplan of TT-Comp (2014-2018)

| No. | Task description | Person responsible | Action | Deliverable | Deadline for deliv. | Status [%] | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Competency sets required for observations and instrumentation | All | Review existing relevant material and examples (e.g. competencies developedby other TCs and work done by former ET-RIC) Liaise with EC Panel of Experts on Education and Training to follow WMO overall approach to this topic. Derive overall competency sets required to cover all functions related to instrumentation and observations | Documentation List List of competency sets. | 10 Nov 2014 13 Nov 2014 | 100% 100% | CIMO-XV, para 6.20 CIMO-16 6.19, 7(6).3 |
| 2. | Competencies for meteorological observations. | All | Develop competencies for meteorological observations. | 1. Document with required competencies for consideration of CIMO MG. | 26 Nov 2014 | 90% |  |
| 3 | Competencies for instrumentation | All: Shandu Chen Chan Angulu Harper Atilan | Develop draft competencies for observational instrumentation. HLCs 1,5 HLCs 3,4 HLCs 2 Finalise | Document with required competencies for consideration of CIMO MG. | Teleconf Feb 2015 | 30% |  |
| 4 | Competencies for instrument calibration | Harper All | Review and revise draft competencies for instrument calibration developed by ET-RIC. Finalise | Document with required competencies for consideration of CIMO MG. | Teleconf Feb 2015 | 70% |  |
| 5 | Competencies for observing network and programme management | Chen Shandu Angulu Chan Atilan Harper | Develop draft competencies for meteorological observations. a Network Management b Planning c Procurement and Installation | Document with required competencies for consideration of CIMO MG. | Teleconf Sep 2015 | 5% |  |
| 6 | WMO Regulatory and/or Guidance Material | All | Recommend to CIMO MG on where output should appear. Arrange for inclusion of competencies in CIMO Guide and/or WMO regulatory documentation | Recommendation to CIMO MG on regulatory status of competencies. Update of relevant CIMO Guide chapter or regulatory material | 1. Dec 2015 | 0% |  |