| WORLD METEOROLOGICAL ORGANIZATION __________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION CIMO MANAGEMENT GROUP Fifth Session GENEVA, SWITZERLAND, 28-30 JANUARY 2008 |  | CIMO/MG-5/Doc. 2.2(3) ADD.1 (25.I.2008) ______ ITEM: 2.2 Original: ENGLISH ONLY |
| --- | --- | --- |

## Progress Report of OPAG Capacity Building Co-Rapporteurs on
Training Activities and Training Materials

(Submitted by the ERCAN BÜYÜKBAŞ and B.Y. LEE)

Summary and Purpose of Document This document provides the activity report of the OPAG Capacity Building Co-Rapporteurs on Training Activities and Training Materials.

## ACTION PROPOSED

The MG is invited to consider the activities of the co-rapporteurs and provide further recommendations and endorsement.

TSMS					WMO					         HKO

WORLD METEOROLOGICAL ORGANIZATION

(WMO)

COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATIONS

(CIMO)

OPAG ON CAPACITY BUILDING (OPAG-CB/C.2)

TRAINING ACTIVITIES AND TRAINING MATERIALS (R-TA&TM)

PROGRESS REPORT OF CO-RAPPORTEURS

1 DECEMBER 2007

ERCAN BÜYÜKBAŞ						B.Y. LEE

CO-RAPPORTEUR 						CO-RAPPORTEUR

TURKISH STATE METEOROLOGICAL SERVICE		HONG KONG OBSERVATORY

Progress Report as of 1st December, 2007 on

# Training Activities and Training Material

This is to report the progress of the tasks carried by the Rapporteurs within the scope of the work plan as of 1st December 2007.

- ASSIGNMENT

We, Mr. B.Y. LEE and Mr. E. BUYUKBAS, have been assigned as the co-rapporteurs on Training Activities and Training Material by CIMO Management Group during the session of CIMO XIV held in Geneva from 7 to 14 December 2006.

- WORK PLAN

The Work Plan covering 2007-2010 was prepared in accordance with the Terms of Reference of the Rapporteurs, and submitted to the Co-Chair of OPAG-CB, Mr. M. Nbou, and WMO Secretariat as requested in March 2007. After the approval of the Work Plan, the following activities were carried out.

- ACTIVITIES

In line with the work plan prepared and the goals to be achieved, training courses were organized and training documents were prepared. Some of the activities successfully carried out are as follows:

- A training course on weather radars was conducted with the participation of 10 trainees from 10 countries in Alanya premises of RTC-Turkey from 18 to 22 June 2007. The report of the course was prepared and submitted to Mr. M. Nbou and WMO secretariat.

- Training document on weather radars has been reviewed and updated. This document will be submitted to WMO secretariat after final review and modifications by the end of this year.

- Training document on Automated Weather Observing Systems has been reviewed and updated. This document will be submitted to WMO secretariat after final review and modifications by the end of this year.

- A training document on upper air observing systems has been prepared. This document was submitted for review to Mr. John Nash, Mr. M. Nbou, Mr. B. Y. Lee and WMO secretariat. It was reviewed and updated based on the comments and recommendations of them. This document is planned to be submitted to the WMO secretariat by the end of this year.

- A general training course on meteorology including instruments and observing systems was give to 17 trainees from Palestinian Meteorology Office in Ankara premises of RTC-Turkey from 6-30 November 2007.

- National training courses on observing systems were organized in Turkey for own staff of TSMS and trainees from other agencies.

- A training course on automatic weather stations was conducted in Hong Kong, China, for 9 meteorological personnel from 9 countries from 26 to 30 November 2007.  Details can be found at: http://www.weather.gov.hk/wxinfo/news/2007/pre1129e.htm.  A majority of the participants (90%) found the course ‘very good’ or ‘excellent’.

- OTHERS

Some activities were planned but not realized due to some reasons. These are:

- A training course on automated weather observing systems was planned to be conducted in September 2007. But it had to be cancelled and postponed to 2008 due to the insufficient application (only Argentina and Uzbekistan).

- A training course on upper observing systems was planned to be conducted in the last week of November 2007. But it had to be cancelled and postponed to 2008 due to the insufficient application (only Romania).

- FUTURE PLAN

- Senegal Meteorology Administration asked a training course on the maintenance of weather radars. It will be tried to arrange a special training course on weather radars for Senegal in 2008.

- The work plan will be updated for 2008-2010 and be followed accordingly.

This report was prepared by us. 1st December, 2007

Ercan BÜYÜKBAŞ					B.Y. LEE

Co-Rapporteur						Co-Rapporteur

Turkish State Meteorological Service			Hong Kong Observatory

___________________