| WORLD METEOROLOGICAL ORGANIZATION __________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION CIMO MANAGEMENT GROUP Seventh Session Geneva, Switzerland 15 - 19 February 2010 |  | CIMO/MG-7/Doc. 4.4(1) (8.II.2010) _______ ITEM: 4.4 Original: ENGLISH |
| --- | --- | --- |

OTHER PERTINENT ISSUES

Status of IOM Reports

(Submitted by the Secretariat)

Summary and purpose of document This document provides the status of the Instruments and Observing Methods Reports since CIMO-XIV.

Action proposed

The MG is invited to note the status of IOM Reports and to assist Secretariat in finalizing those due to publish before CIMO-XV.

________________

STATUS OF IOM REPORTS

- IOM reports that were finalized since CIMO-XIV were published on the CIMO website only, with the exception of the proceedings from TECO-2008, which were published on CD as well and distributed to all WMO Members. It is proposed to prepare a CD for the distribution of those IOM reports that were published on the website and for any other IOM report that will be ready for publication before CIMO-XV session.

- To that effect, OPAG and ET-Chairs should liaise with authors to ensure that the reports will be ready in time for review by the relevant ET members and approval by the ET-Chair. Such reports should be forwarded to the Secretariat at the latest early July 2010 to ensure their timely publication on CD prior to CIMO-XV.

- The following table provides the status of the Instruments and Observing Methods Reports since CIMO-XIV.

| No | IOM No. TD No. | IOM Report | Author | Status |
| --- | --- | --- | --- | --- |
|  |  | Already published |  |  |
|  | IOM 99 (TD 1504) | WMO Field Intercomparison of Rainfall Intensity Gauges (10.4 MB) Vigna di Valle, Italy, October 2007 - April 2009 | E. Vuerich, C. Monesi, L. Lanza, L. Stagi (all Italy), E. Lanzinger (Germany) | Published on website only |
|  | IOM 98 (TD 1501) | Sub-Regional Pyranometer Intercomparison of the RA VI members from South-Eastern Europe Split, Croatia, 22 July to 6 August 2007 | K. Premec (Croatia) | Published on website only |
|  | IOM 97 (TD 1494) | Second WMO Regional Pyrheliometer Comparison of RA II Tokyo, 22 January to 2 February 2007 | H. Sasaki (Japan) | Published on website only |
|  | IOM 96 (TD 1462) | Papers and Posters presented at the WMO Technical Conference on Instruments and Methods of Observation, St. Petersburg, Russian Federation, 27-29 November 2008 |  | CD-ROM and website |
|  | IOM 95 (TD 1433) | Global criteria for tracing the improvements of radiosondes over the last decades | P. Jeannet (Switzerland), C. Bower (USA), B. Calpini (Switzerland) | Published on website only |
|  |  | Under finalization |  |  |
|  |  | CIMO Survey on Lightning Detection Systems | M. Dahoui | Planned in mid 2010 Report ready, approved by ET-RSUATT, needing minor grammatical revision Needed: - President approval, - Foreword |
|  |  | Guidance on instrumentation for calibration laboratories, including RICs | D. Groselj | Planned in mid 2010 Report ready, Needed: - ET chair and president approval, - Foreword |
|  |  | Evaluation of the survey on Solid Precipitation | R. Nitu | Under finalization, draft expected in spring 2010 |
|  |  | Tentative |  |  |
|  |  | Report on the combined intercomparison of thermometer screens/shields in conjunction with humidity measuring instruments, Ghardaia, Algeria | TBD | In preparation, draft expected in March 2010 |
|  |  | Guidelines and procedures for the transition from manual to Automatic Weather Stations | M. Molyneux | Due date according to ET-ST&MT workplan: July 2010 |
|  |  | IOM report on skill factor requirements | J. van den Meulen | Due date according to ET-ST&MT workplan: July 2010 |
|  |  | Instrument Development Inquiry | J. van den Meulen | Due date according to ET-ST&MT workplan: July 2010 |
|  |  | Joint COST/WMO Publication of COST 727 Action | A. Heimo | Due date according to ET-ST&MT workplan: July 2010 |
|  |  | Training course on radiation measurements, Presentations and Syllabus | W. Finsterla & B. Forgan | Sept.-Oct. 2010 |
|  |  | Correction of wind measurements | J. van den Meulen |  |

_________________