| WORLD METEOROLOGICAL ORGANIZATION __________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION CIMO MANAGEMENT GROUP Ninth Session Geneva, Switzerland 5 - 8 April 2011 |  | CIMO/MG-9/Doc. 4.3(1) (16.III.2011) _______ ITEM: 4.3 Original: ENGLISH |
| --- | --- | --- |

OPAG CAPACITY BUILDING

Workplan for the Expert Team on Regional Instrument Centers, Calibration and Traceability

(Submitted by J. Duvernoy)

Summary and purpose of document This document provides the proposed workplan for the CIMO Expert Team on Regional Instrument Centers, Calibration and Traceability developed by J. Duvernoy.

Action proposed

The Meeting is invited to review the draft work and make any necessary changes taking into account CIMO priorities before approving it.

________________

WORKPLAN

C1: CIMO Expert Team on Regional Instrument Centers, Calibration and Traceability

(2011-2014)

| No. | Task description | Person responsible | Action | Deliverable | Deadline for deliv. | Status | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Template for RIC websites (capabilities, contacts, etc) | K. Nakashima D. Groselj R. Merrouchi All ET-Members | Develop list of information a RIC website should contain Develop template to report RIC capabilities on WMO website Fill template for own RIC Contact RIC without websites | List with minimum information that a RIC website should contain Template to report capabilities to WMO Secretariat (WMO website) Provide filled template for own RIC | 09/2011 09/2011 12/2011 2012 |  | CIMO-XV, para 6.3 + Spanish-speaking expert |
| 2. | Estimation of calibration uncertainty – traceability to SI | J. Duvernoy D. Groselj J. Gorman | Review available material Compile set of examples of computation of calibration uncertainties (ex. extracted from own RIC procedures and made anonymous, or extracted from bibliography) Develop guidance document on how to use the examples, ensure traceability and make calibration certificates Carry-out workshop on uncertainty calculations (possibly in conjunction with TECO 2010) | List of available documents (also for WMO website update) Set of examples Guidance document (IOM report) Workshop | 2012 2012 Jan. 2014 TBD, upon request |  | CIMO-XV, para 6.13 (In collab. with Theme Leader Training Material & Training Activities) |
| 3. | Strategy to ensure traceability of measurements to SI units | J. Gorman R. Merrouchi | Develop Strategy Develop relevant guidance and outreach material | Document with strategy Brochure, IOM report and or update of CIMO Guide | Sept. 2011 2013 |  | CIMO-XV, para 6.2 |
| 4. | RIC Evaluations | J. Duvernoy W. Burnett TBD, as required | Contact all RICs of Region, encourage and support them in assessing their capabilities, carrying out evaluations (using evaluation scheme) and communicating with Members On request, provide Support to evaluation of RICs | All RICs capabilities and contact points published on CIMO website Report to MG (ev. TECO paper) on RIC capabilities & evaluation results Report on RIC audit | 2012 2012 (next MG-Mtg, TECO-2012) |  | CIMO-XV, para 6.3 |
| 5. | RIC intercomparisons | HE Xiaolei (RA-II&V) D. Groselj (RA-VI) R. Merrouchi (RA-I) W. Burnett (RA-III&IV) | Set-up intercomparison kit for temperature, humidity and pressure (at least one, but preferably all 3 parameters) Schedule intercomparisons with other RICs of Regions Publish intercomparison report | Intercomparison kit Schedule of intercomp. Report on intercomparison results / problems encountered | 2011 2012 Jan. 2014 |  | CIMO-XV, para 6.5 Each person is responsible for comparison inside one or two RA |
| 6. | Alternatives for dangerous and obsolete instruments | Amudha B. J. Gorman J. Ngamini HE Xiaolei | Approach Members on their needs regarding replacement of dangerous (mercury) and obsolete instruments (barographs, thermographs) Collaborate with manufacturers (HMEI) to identify possible alternative instruments Provide advice to Members on alternatives | Personal approach or questionnaire to chosen countries Document on member needs/problems Contact to HMEI taken Document reporting on possible alternatives | 2011 2012 2012 Jan. 2014 |  | ET-RIC-2, para. 4.5 |

| 7. | Improvement of CIMO Guide | J. Duvernoy J. Gorman | Review relevant parts of CIMO Guide (Part I, Chap. 2, 3.10, 4.9) Make proposals for updates, if needed | Proposals for update of CIMO Guide (Part I, Chap. 2, 3.10, 4.9) | Nov. 2011 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 8. | Competencies for personal performing observations, maintenance and calibration of instruments | J. Gorman D. Groselj (In collab. with TL-C3) K. Nakashima | Review existing relevant material and examples (ex. competencies developed by CAeM) Finalize update of training notes developed for RA-II training workshop Develop competencies for meteorological observations, calibration and maintenance of instruments Arrange for inclusion of competencies in CIMO Guide Identify need for and develop relevant training material, if appropriate | Document with required competencies for consideration of CIMO MG IOM Report Update of relevant CIMO Guide chapter IOM report with training material | April 2012 June 2011 For later |  | CIMO-XV, para 6.20 |

The first name (in bold) is the main responsible for the specific action. Others assist him (her), for instance when the action is separated by Region.